## Summary
BSEIDC, PATNA
Progress report for the construction of Higher Secondary School (Sanctioned Year 2012-13) | [20 empty] | Date:-31.12.2014
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna (East) | 4 | 5 | 543.08 | 3 | 4 | 430.17 |  | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 4 | 0 | 188.92 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E., BSEIDC, Div.-Patna (West) | 3 | 3 | 327.59 | 3 | 3 | 327.59 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 11 | 23 | 2503.01 | 10 | 20 | 2162.07 |  | 0 | 6 | 1 | 2 | 4 | 2 | 2 | 0 | 3 | 17 | 0 | 363.67 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Bhagalpur | 2 | 6 | 619.0781 | 2 | 6 | 619.0781 |  | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 2 | 4 | 0 | 193.81 |  | 0
5 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 7 | 15 | 1722.77 | 3 | 4 | 462.69 |  | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 0 | 76.28 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 2 | 2 | 243.76 | 2 | 2 | 243.76 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 8 | 18 | 2229.61 | 8 | 18 | 2229.61 |  | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 0 | 5 | 13 | 0 | 284.23 |  | 0
8 | TIRHUT (EAST) | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 28 | 58 | 3999.61 | 19 | 39 | 3999.61 |  | 0 | 10 | 3 | 2 | 4 | 2 | 2 | 0 | 16 | 23 | 0 | 519.46 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha, (8544126916), E.E. BSEIDC, Div.- Tirhut (West) | 7 | 19 | 475.19 | 5 | 13 | 236.67 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 12 | 1 | 0 | 43.39 |  | 0
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 5 | 7 | 818.6 | 3 | 5 | 589.7 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0
11 | SARAN | Uday Kumar Das, (9431821558) EE BSEIDC, Div.- Saran | 33 | 70 | 7983.3 | 32 | 69 | 7983.3 |  | 4 | 3 | 12 | 9 | 15 | 2 | 8 | 1 | 15 | 54 | 0 | 1707.97 |  | 0
Total (HSS) |  |  | 110 | 226 | 21465.5981 | 90 | 183 | 19284.2481 | 0 | 6 | 26 | 19 | 16 | 29 | 9 | 16 | 3 | 59 | 124 | 0 | 3377.73 |  | 0

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- PATNA (EAST) - Patna, Nalanda & Bhojpur | [21 empty] | Date:-31.12.2014
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Aggrement No & date | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | HSS-1 | Patna | Patna Sadar | 1 | Mahant Hanuman Saran Higher Secondary School, Rajapur, Mainpura | KRISHNA KUMAR-9934252394 | 9934252394 |  | 110.55 |  | 15 Months | [8 empty] | 1 |  | 61.39
2 | HSS-2 | Patna | Bakhtiyaarpur | 1 | Sri Sunder Devi Higher Secondary School, Rupas Mahaji, | BHAWANI BUILDCON AND PROJECT PVT LTD 9835287922 | 9835287922 |  | 107.75 |  | 1 Year | [5 empty] | 1 |  |  |  |  | 35.78
3 | HSS-5 | Nalanda | Nalanda | 1 | High School G.M.K, Islampur | M/S K.D. Company 9431497838 (01.06.2012) | 9431497838 |  | 211.87 |  | 1 Year | [6 empty] | 1 |  |  |  | 91.75
|  |  | Nalanda | 2 | High School, Khudaganj | [12 empty] | 1
4 | H.S.S- 88 | iVuk | uxj | 1 | vk;Z dU;k mPp fo¦ky;] u;k Vksyk | Retender |  |  | 112.91
| Total No. of Schools |  |  | 5 |  |  |  |  | 543.08 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 188.92

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- PATNA (WEST) - Buxar, Rohtas & Kaimur | [21 empty] | Date:-31.12.2014
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Aggrement No & date | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | HSS-3 | Buxar | Chausa | 1 | High School, Chausa | MS ANANYA CONSTRUCTION -9334745882 | 9334745882 |  | 107.79 |  | 1 Year | 1 | [10 empty] | Land not available
2 | HSS-4 | Buxar | Buxar | 1 | Girl's High School, Chaugain | Mahnar Infratech Pvt.Ltd -9334383960 | 9334383960 |  | 107.79 |  | 1 Year | 1 | [10 empty] | Land not available
3 | H.S.S-106 | cDlj | MqejkaWo | 1 | eŒmŒckfydk mPp fo¦ky;] Mqejk¡o | JITENDRA KUMAR SINGH, BUXAR | 9939871932 |  | 112.01 |  |  | 1
| Total No. of Schools |  |  | 3 |  |  |  |  | 327.59 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Magadh
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- MAGADH | [24 empty] | Date:-31.12.2014
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block |  | S.N. | Name of School | Name of Agency | Agency Address and Mobile No | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[15 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[19 empty] | LL | RL | LL | RL
1 | HSS-6 | Jehanabad | Modanganj | 1 | 1 | High School, Okari | Ramjee Prasad 9334489874 |  |  |  | 113.09 | [8 empty] | 1 |  |  |  |  | 25.94
2 | HSS-7 | Gaya |  | 1 | 1 | Zila School, Gaya | Sanjeet kumar 9304368289 |  |  |  | 341.27 |  |  |  | 1 | [9 empty] | 11.36
|  |  |  | 2 | 2 | Gandhi High School, Sewtar | [13 empty] | 1
3 | HSS-8 | Nawada |  | 1 | 1 | High School, Chakwai | Retender |  |  |  | 340.94
|  |  |  | 2 | 2 | High School, kutri
|  |  |  | 3 | 3 | Project Girl's High School, Pakaribarawan
4 | HSS-9 | Nawada |  | 1 | 1 | Inter School, Meskaur | Pankaj Kumar 933445721 |  |  |  | 341.2 | [7 empty] | 1 | [5 empty] | 36.17
|  |  |  | 2 | 2 | High School, Medhukuri | [11 empty] | 1
|  |  |  | 3 | 3 | High School, Biju Bigha | [10 empty] | 1
5 | HSS-10 | Nawada |  | 1 | 1 | Inter School, Narhat | Baijnath Nirman India Pvt. Ltd., Vill- Dihuri, P.O- Malwan, P.S- Khudwan, Distt.- Aurangabad, Bihar. 9939911835 (08/06/2012) |  |  |  | 341.74 | [5 empty] | 1 | [7 empty] | 69.64
|  |  |  | 2 | 2 | Inter School, Laund | [12 empty] | 1
|  |  |  | 3 | 3 | High School, Narpur Pakaria | [10 empty] | 1
6 | HSS-11 | Nawada |  | 4 | 1 | High School, Targir | Shri Chandra Mouleshwar |  |  |  | 343.6 | [10 empty] | 1 |  |  | 104.58
|  |  |  | 1 | 2 | Project Girl's High School, Akbarpur | [10 empty] | 1
|  |  |  | 2 | 3 | High School, Shahpur | [13 empty] | 1
7 | HSS-12 | Arwal | karpi | 1 | 1 | High School, Kinjar | Kaushlendra kumar 8409113501 |  |  |  | 342.14 | [10 empty] | 1 |  |  | 45.47
|  |  |  | 2 | 2 | High School, Sahar Telpa | [14 empty] | 1
|  |  |  | 3 | 3 | High School, Anandpur | [10 empty] | 1
8 | HSS-13 | Aurangabad |  | 1 | 1 | High School, Dumri | Ramesh kumar Singh | [12 empty] | 1 |  |  |  |  | 26.3
9 | HSS-14 | Aurangabad |  | 1 | 1 | High School, Pathraur Dewhara | Nilesh kumar 8294888140 | [13 empty] | 1 |  |  |  | 44.21
10 | HSS-97 | Gaya |  | NA | 1 | High School, Mali Ramgarh | Kamlesh Kumar, Teka Bigha |  |  |  | 121.3 |  |  |  | 1
11 | HSS-98 | Gaya |  | NA | 1 | High School, Sudhari | Mitlesh Kumar, Nawada |  |  |  | 217.73 | [5 empty] | 1
|  | Gaya |  | NA | 2 | Project Kanya High School, Govindpur | [8 empty] | 1
Total No. of Schools |  |  |  |  | 23 | [5 empty] | 2503.01 |  |  |  | 3 | 0 | 6 | 1 | 2 | 4 | 2 | 2 | 0 | 0 | 363.67

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- BHAGALPUR | [22 empty] | Date:-31.12.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-15 | Banka | Baunsi | 1 | LND HS Baunsi | Bricks Liner |  |  | 316.8006 | 316.8006 |  | 15 Months | 1 | [9 empty] | 79.55
|  | Banka | Rajoun | 2 | Pro.GHS Dhoni | [12 empty] | 1
|  | Banka | Chandan | 3 | Pro.GHS Chandan | [14 empty] | 1
2 | HSS-16 | Banka | Katoriya | 1 | ASS.HS Kharhara | Binod Kr. Singh |  |  | 302.2775 | 302.2775 | 20.02.14 | 15 Months | [8 empty] | 1 |  | 114.26
|  | Banka |  | 2 | Govt.HS Katoriya | [14 empty] | 1 |  |  |  | FF LL-20/10/2014
|  | Banka |  | 3 | Pro.GHS Katoriya | [7 empty] | 1
Total No. of Schools |  |  |  | 6 |  |  |  |  | 619.0781 |  |  |  | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 193.81

## Munger
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- MUNGER | [21 empty] | Date:-31.12.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-17 | Jamui |  | 1 | Government High School, Lathlath | BRAJESH KUMAR SINGH-9939622814 |  |  | 118.3 | [6 empty] | 1 | [6 empty] | 39.43
2 | HSS-18 | Munger |  | 1 | Baijnath Girl's High School, Munger | RAJENDRA PRASAD YADAV-7765903650 |  |  | 233.4 | [6 empty] | 1
|  |  |  | 2 | N.C Ghosh Girl's High School, Jamalpur | [7 empty] | 1 | [10 empty] | Land Problem
3 | HSS-19 | Munger |  | 1 | High School, Sardha | Retender |  |  | 235.02
|  |  |  | 2 | Adarsh High School, Ghorgha
4 | HSS-20 | Khagaria |  | 1 | Shiv Maha High School, Chautham | Retender |  |  | 362.73
|  |  |  | 2 | Deep Nara Ram Krishna High School, Vasua Koyla
|  |  |  | 3 | C. S High School, Mandar
5 | H.S.S- 96 |  | ijcŸkk | 1 | Jh d`".k mPp fo¦ky;] u;kxk¡o | Retender |  |  | 113.72
6 | H.S.S-105 | csxwljk; | fogV | 1 | ohŒ,lŒ,lŒ dkSysft,V] csxwljk; | MS DAYARAM SINGH, BEGUSARAI, 9801031299 |  |  | 110.99 | [8 empty] | 1 |  |  |  |  | 36.85
7 | H.S.S-107 | y[khljk; | cMfg;k | 1 | jketkudh jke/ku flag dU;k mŒfoŒ] oMfg;k | Retender |  |  | 548.61
|  |  | pkUu | 2 | vkjŒyky pkuu mPp fo¦ky;] yk[kkspd
|  |  | y[khljk; | 3 | mPp fo¦ky; iqjkuh cktkj] y[khljk;
|  |  | lq;Zx<+k | 4 | ?kkslSB mPp fo¦ky;] ihjhcktkj
|  |  |  | 5 | mPp fo¦ky; ujksRreiqj] dtjk
Total No. of Schools |  |  |  | 15 |  |  |  |  | 1722.77 |  |  |  | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 76.28

## Kosi
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- KOSI | [21 empty] | Date:-31.12.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-29 | Madhepura |  | 1 | B. L. (+2) School, Murliganj | SUBHASH KUMAR SUBHASH Patna,993421227 |  |  | 126.27 |  |  |  | 1
2 | HSS-94 | Madhepura |  | 1 | Shivnandan Prasad Mandal High School , Madhepura | FLEXICON ENGINEERS AND PLANNER PRIVATE LIMITED,9709888878 |  |  | 117.49 |  |  |  | 1
Total No. of Schools |  |  |  | 2 |  |  |  |  | 243.76 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Purnea
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- PURNEA | [21 empty] | Date:-31.12.2014
Name & contact no. of EE :-Manoj Kumar Pandey (9661818750) , AE :- Madan Mohan (9431413291), JE :- Uttam Kr. (9973563185)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-21 | Purnia |  | 1 | Rajkiya Girl's High School, Purnia | BIRENDRA KUMAR SINGH, KATIHAR,9473440405 |  |  | 121.99 |  |  |  | 1
2 | HSS-22 | Katihar |  | 1 | Gyanda High School, Roshna, Pranpur | Umakant Singh-9431096239 |  |  | 245.32 | [10 empty] | 1 |  |  | 102.44
|  |  |  | 2 | Project Girl's High School, Bastaul, Pranpur | [14 empty] | 1
3 | HSS-23 | Katihar |  | 1 | Project Girl's High School, Korha | ASHOK KUMAR-9431096238 |  |  | 243.74 |  |  |  |  | 1 | [8 empty] | 29.63
|  |  |  | 2 | Project Girl's High School, Falka | [13 empty] | 1
4 | HSS-24 | Katihar |  | 1 | Project Girl's High School, Kumhri, Kadwan | Umakant Singh-9431096239 |  |  | 374.01 | [7 empty] | 1 | [5 empty] | 87.34
|  |  |  | 2 | Project Girl's High School, Barsoi | [12 empty] | 1
|  |  |  | 3 | Project Girl's High School, Ajamnagar | [12 empty] | 1
5 | HSS-25 | Katihar |  | 1 | High School, Abadpur | BIRENDRA KUMAR SINGH, KATIHAR,9473440405 |  |  | 374.71 | [5 empty] | 1
|  |  |  | 2 | A.L. High School, Sonali | [9 empty] | 1
|  |  |  | 3 | High School, Salmari | [7 empty] | 1
6 | HSS-26 | Katihar |  | 1 | Jageshwer High School, Grubazar | BIRENDRA KUMAR SINGH, KATIHAR,9473440405 |  |  | 369.92 | [6 empty] | 1 | [6 empty] | 20.5
|  |  |  | 2 | High School, B. Balrampur | [7 empty] | 1
|  |  |  | 3 | Shiv Na. Sarvoday High School, Bareta | [7 empty] | 1
7 | HSS-27 | Kishanganj |  | 1 | N. A. High School, Bishanpur | MD SHAFIQUE ALAM-9431259842 |  |  | 249.96 |  |  |  |  | 1 | [8 empty] | 21.36
|  |  |  | 2 | Girl's High School, Kishanganj | [11 empty] | 1
8 | HSS-28 | Kishanganj |  | 1 | High School, Bishanpur | MD SHAFIQUE ALAM-9431259842 |  |  | 249.96 | [7 empty] | 1 | [5 empty] | 22.96
|  |  |  | 2 | National High School, Kishanganj | [7 empty] | 1 | [10 empty] | insufficient land
Total No. of Schools |  |  |  | 18 |  |  |  |  | 2229.61 |  |  |  | 5 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 0 | 0 | 284.23

## Tirhut (East)
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- TIRHUT (EAST) - Vaishali, Muzaffarpur & Sitamarhi | [22 empty] | Date:-31.12.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-30 | Muzaffarpur |  | 1 | B. B. Collagiate, Muzaffarpur | Amit Kumar Shahi -9835280982 |  |  | 121.21 | [7 empty] | 1 | [5 empty] | 31.94
2 | HSS-31 | Vaishali |  | 1 | Government High School, Goraul | Anil Kumar-9931044826 |  |  | 244.07 | [8 empty] | 1 |  |  |  |  | 77.38
|  |  |  | 2 | Government High School, Sarsai Fatehpur | [12 empty] | 1
3 | HSS-32 | Sitamarhi |  | 1 | Kamla Girl's High School, Dumra | RAJEEV KUMAR. DUMRA, SITAMARHI,9199022302 |  |  | 371.18 |  |  |  | 1
|  |  |  | 2 | Lakshmi High School, Sitamarhi | [9 empty] | 1
|  |  |  | 3 | M.R.D. Girl's High School,Sitamarhi | [7 empty] | 1
4 | HSS-33 | Sitamarhi |  | 1 | S. R. High School, Bariyarpur | M/S Galaxce-9431067656 |  |  | 254.86 |  |  |  | 1 | [10 empty] | Tree
|  |  |  | 2 | High School, Parsauni Chowk | [7 empty] | 1 | [10 empty] | Tree
5 | HSS-34 | Sitamarhi |  | 1 | High School, Bairgania | Rajesh Kumar-9931490405 |  |  | 253.77 |  |  |  | 1
|  |  |  | 2 | Jauharimal High School, Bairgania | [9 empty] | 1
6 | HSS-35 | Sitamarhi |  | 1 | Praject Girl's High School, Sasaula Sabha | Rabindra Singh |  |  | 376.52 | [9 empty] | 1 |  |  |  | 192.47
|  |  |  | 2 | Saryu High School, Sursand | [11 empty] | 1
|  |  |  | 3 | V. R Sahi Girl's High School, Sursand | [14 empty] | 1
7 | HSS-36 | Sitamarhi |  | 1 | Shree Gandhi High School, Parihar | Retender |  |  | 378.45
|  |  |  | 2 | High School, Koiriya Pipra
|  |  |  | 3 | Praject Girl's High School, Gorhari
8 | HSS-37 | Sitamarhi |  | 1 | Project Girl's High School, Siwaipatti | Retender |  |  | 373.5
|  |  |  | 2 | Shree Sutha High School, Balha
|  |  |  | 3 | High School, Bajpatti
9 | HSS-38 | Sitamarhi |  | 1 | High School, Dumri | Manohar Kumar, AT+P.O.- Dumari Kala, P.S.- Mejorganj, Distt.- Sitamarhi, Bihar. |  |  | 252.09 | [8 empty] | 1 |  |  |  |  | 150.94
|  |  |  | 2 | Ra. Gu. High School, Kanhauli Bhandser | [14 empty] | 1
10 | HSS-39 | Sitamarhi |  | 1 | High School, Sonbarsa | Retender |  |  | 376.99
|  |  |  | 2 | Project Girl's High School, Bhutahi
|  |  |  | 3 | Ja. High School, Bhutahi
11 | HSS-40 | Sitamarhi |  | 1 | Project Girl's High School, Majhaulia State | RAJEEV KUMAR.; DUMRA, SITAMARHI,9199022302 |  |  | 248.41 |  |  |  | 1 | [10 empty] | water logging
|  |  |  | 2 | Project Girl's High School, Manik Chowk | [7 empty] | 1 | [10 empty] | water logging
12 | HSS-41 | Sitamarhi |  | 1 | AA. High School, Madhaul | Rajesh Kumar-9931490405 |  |  | 248.02 | [5 empty] | 1
|  |  |  | 2 | M. High School, Tilaktajpur | [9 empty] | 1
13 | HSS-42 | Sitamarhi |  | 1 | High School, Bela Shanti Kutir | ABHAY KUMAR SINGH,BRAHMAUL SIRSI NANPUR SITAMARHI |  |  | 250.11 | [5 empty] | 1
|  |  |  | 2 | Project Girl's High School, Bahela Jahidpur | [9 empty] | 1
14 | HSS-43 | Sitamarhi |  | 1 | High School, Choraut | Malti Singh-9931123641 |  |  | 250.43 | [9 empty] | 1 |  |  |  | 34.65
|  |  |  | 2 | L. M. High School, Pupri | [7 empty] | 1
15 | H.S.S- 70 | lhrke<+h | lksucjlk | 1 | mPp fo¦ky;] flagokfguh | SHARDA CONSTRUCTION,PATNA , 9709400379 | [6 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] t;uxj | [7 empty] | 1
16 | H.S.S- 71 | lhrke<+h | cFkukgk | 1 | mPp fo¦ky;] cFkukgk | DOLPHIN CONTRACTORS AND ENGINEERS PVT LTD, DANAPUR CANTT, PATNA. 9835464364 | [9 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] iqjufg;k | [10 empty] | 1
|  |  |  | 3 | mPp fo¦ky;] ;ksxokukcktkj | [10 empty] | 1
17 | H.S.S- 72 | lhrke<+h | ifjgkj | 1 | mPp fo¦ky;] Hkhlok cktkj | Retender
|  |  |  | 2 | mPp fo¦ky;] [kSjok fo".kqiqj
18 | H.S.S- 73 | lhrke<+h | :Uuh lSniqj | 1 | mPp fo¦ky;] eksjlaM+ | Retender
|  |  |  | 2 | mPp fo¦ky;] fo".kqiqj oklqnso
19 | H.S.S- 74 | lhrke<+h | csylaM | 1 | mPp fo¦ky;] pankSyh | Retender
|  |  |  | 2 | mPp fo¦ky;] csylaM+
20 | H.S.S- 75 | lhrke<+h | ukuiqj | 1 | mPp fo¦ky;] jk;iqj | Retender
|  |  |  | 2 | mPp fo¦ky;] tkuhiqj
21 | H.S.S- 76 | lhrke<+h | cks[kM+k | 1 | mPp fo¦ky;] [kM+dk | SANJAY KUMAR, LAHERIASARAI, DARBHANGA, 8521954601 | [8 empty] | 1
22 | H.S.S- 77 | lhrke<+h | cktiÍh | 1 | mPp fo¦ky;] okpksiÍh ujgk | Retender
23 | H.S.S- 78 | lhrke<+h | estjxat | 1 | mPp fo¦ky;] estjxat | MANOHAR KUMAR, MEJORGANJ, DIST.- SITAMARHI, 9430218256 | [6 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] eM+ik fljiky | MANOHAR KUMAR, MEJORGANJ, DIST. - SITAMARHI,9430218256 | [6 empty] | 1
24 | H.S.S- 79 | lhrke<+h | lqIih | 1 | mPp fo¦ky;] lqIih | Retender
25 | H.S.S- 80 | lhrke<+h | jhxk | 1 | mPp fo¦ky;] oHkuxkok¡ | PRINCE INFRA TECH PRIVATE LIMITED, PATLIPUTRA, 9431017667 / 9304812067 | [8 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] jsoklh | [9 empty] | 1
|  |  |  | 3 | mPp fo¦ky;] lgcktiqj [kjlku | [7 empty] | 1
26 | H.S.S- 81 | lhrke<+h | lqjlaM | 1 | deynkl ckfydk mPp fo¦ky;] lqjlM | PRAVEEN KUMAR,,DUMRA SITAMARHI,9430973025 | [6 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] j/kkmj | [7 empty] | 1
|  |  |  | 3 | mPp fo¦ky;] ekus'oj LFkku | [7 empty] | 1
27 | H.S.S- 82 | lhrke<+h | pksjkSr | 1 | mPp fo¦ky;] cjjh csgVk | MALTI INFRASTRUCTURE PRIVATE LIMITED, Phulwarisarif, Patna-801505, 9471238807 | [8 empty] | 1
28 | H.S.S- 83 | eqt¶Qjiqj | eq'kgjh | 1 | mPp fo¦ky;] tekykckn | HARI SHANKAR PRASAD, MINAPUR DIST MUZAFFARPUR, 9939363702 | [11 empty] | 1 |  |  |  |  | 32.08
Total No. of Schools |  |  |  | 58 |  |  |  |  | 3999.61 |  |  |  | 16 | 0 | 10 | 3 | 2 | 4 | 2 | 2 | 0 | 0 | 519.46

## Tirhut (West)
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- TIRHUT (WEST) - East Champaran, West Champaran & Shivhar | [22 empty] | Date:-31.12.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | H.S.S- 95 | iŒ pEikj.k | fldVk | 1 | vkn'kZ mPp fo¦ky;] nq[khNkij | Retender |  |  | 238.52
|  |  |  | 2 | igokjh ;kno mPp fo¦ky;] txUukFkiqj
2 | H.S.S- 99 | iqohZ pEikj.k | ?kksM+klkgu | 1 | mPp fo¦ky;] Hkssyok lfdZy | Ravi Shekhar |  |  | 236.67 |  |  |  | 1
|  |  |  | 2 | mPp fo¦ky;] ?kksM+klkgu | [7 empty] | 1
3 | H.S.S- 100 | iqohZ pEikj.k | <+kdk | 1 | dU;k mPp fo¦ky;] djeok | Retender
|  |  |  | 2 | vyila[;d mPp fo¦ky;] [kSjok
|  |  | idMhn;ky | 3 | mPp fo¦ky;] pSrk
|  |  |  | 4 | mPp fo¦ky;] cM+dkxk¡o
4 | H.S.S- 101 | iqohZ pEikj.k | dksVok | 1 | mPp fo¦ky;] ePNjxk¡ok | KESHAV KUMAR KESHRI, EAST CHAMPARAN, 7779830772 | [6 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] Hkqifriqj | [7 empty] | 1
5 | H.S.S- 102 | iqohZ pEikj.k | dY;k.kiqj | 1 | mPp fo¦ky;] rsuqvk | RADHA DEVI,- EAST CHAMPARAN, BIHAR.,9471886673 | [6 empty] | 1
|  |  | pfd;k | 2 | chŒ,yŒ,lŒihŒ mPp fo¦ky;] pfd;k | [7 empty] | 1
|  |  | esglh | 3 | mPp fo¦ky;] ckykdksBh | [7 empty] | 1
6 | H.S.S- 103 | iqohZ pEikj.k | fpjS;k | 1 | txUukFk mPp fo¦ky;]fpjS;k | PRINCE INFRA TECH PRIVATE LIMITED, PATNA, 9431017667 / 9304812067 | [6 empty] | 1
|  |  |  | 2 | mPp fo¦ky;] fljkSuk | [7 empty] | 1
|  |  | e/kqcu | 3 | mPp fo¦ky;] e/kqcu | [7 empty] | 1
7 | H.S.S- 104 | iqohZ pEikj.k | vjsjkt | 1 | mPp fo¦ky;] eykgh | ALOK KUMAR., EAST CHAMPARAN,9631044077 | [11 empty] | 1 |  |  |  |  | 43.39
|  |  |  | 2 | ikoZrh dU;k mPp fo¦ky;] vjsjkt | [7 empty] | 1
|  |  | rqjdkSfy;k | 3 | mPp fo¦ky;] rqjdkSfy;k | [7 empty] | 1
Total No. of Schools |  |  |  | 19 |  |  |  |  | 475.19 |  |  |  | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43.39

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- DARBHANGA | [22 empty] | Date:-31.12.2014
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of LOA | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-44 | Darbhanga |  | 1 | High School, Mahinam Pohaddi | MADHAV CONSTRUCTION,DARBHANGA,9835288951, 9234460951 |  |  | 124.13 | [5 empty] | 1
2 | H.S.S- 91 | leLrhiqj | fo¦kifr uxj | 1 | fo¦kifr uxj mPp fo¦ky; em ckftriqj | MS REETA RANJAN,KUDHANI, MUZAFFARPUR,9162406190 |  |  | 114.99 | [5 empty] | 1
3 | H.S.S- 92 | leLrhiqj | foHkwfriqj | 1 | mPp fo¦ky;] pdgcho foHkwfriqj | Retnder |  |  | 113.99
4 | H.S.S- 93 | leLrhiqj | f'kokthuxj | 1 | xk¡/kh Lekjd nkŒ mPp fo¦ky;] oYyhiqj | Retnder |  |  | 114.91
5 | H.S.S-108 | njHkaxk |  | 1 | mPp fo¦ky;] uoknk | DEVENDRA AND DEVENDRA INFRASTRUCTURE PRIVATE LIMITED,PATNA.,9304417600 |  |  | 350.58 | [5 empty] | 1
|  |  | fojkSy | 2 | mPp fo¦ky;] cank] fcjkSy | [9 empty] | 1
|  |  | csuhiqj | 3 | mPp fo¦ky;] csgsM+k ouhiqj | [9 empty] | 1
Total No. of Schools |  |  |  | 7 |  |  |  |  | 818.6 |  |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Saran
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
Name of Division :- SARAN | [21 empty] | Date:-31.12.2014
Name & contact no. of EE :- Uday Kumar Das (9431821558), AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | HSS-45 | Siwan |  | 1 | High School, Ander | Arbind Singh-9801721172 | 360.99 |  | 360.99 |  |  |  | 1
|  |  |  | 2 | M. S. High School Cum Inter Collage, Husainganj | [7 empty] | 1
|  |  |  | 3 | Kishan Majdur High School, Tari | [7 empty] | 1
2 | HSS-46 | Siwan |  | 1 | Islamia High School, Siwan | Bighnahanta Construction pvt ltd. 68 Chanakyapuri, Raja Bazar B.V. College patna-14 | 239.71 |  | 239.71 |  |  |  | 1
|  |  |  | 2 | Smt. Rajvansi Devi Girl's High School, Siwan | [7 empty] | 1
3 | HSS-47 | Siwan |  | 1 | Town High School, Mairwa | Arbind Singh-9801721172 | 241.84 |  | 241.84 |  |  |  | 1 | [10 empty] | Land Problem
|  |  |  | 2 | High School, Nikatikala Raghunath | [7 empty] | 1
4 | HSS-48 | Siwan |  | 1 | Janta High School, Musaipur | Asiana Contractor Pvt. Ltd.-9431088485 | 241.53 |  | 241.53 | [8 empty] | 1 |  |  |  |  | 87.07
|  |  |  | 2 | Indira Singh High School, Hilser | [14 empty] | 1
5 | HSS-49 | Saran |  | 1 | Shiv Dulari High School, Sonepur | M/S Shiva Const.- 9431662461 | 354.49 |  | 354.49 |  |  |  | 1 | [9 empty] | 22.36 | tree
|  |  |  | 2 | Gogal Singh High School, Naya Gaoun, Sonepur | [10 empty] | 1 | [7 empty] | tree
|  |  |  | 3 | K. P. S. High School, Gangajal, Sonepur | [7 empty] | 1 | [10 empty] | tree
6 | HSS-50 | Saran |  | 1 | S. P. S. High School, Sonepur | M/S Shiva Const.- 9431662461 | 357.67 |  | 357.67 |  |  |  | 1
|  |  |  | 2 | High School, Chanwa | [7 empty] | 1
|  |  |  | 3 | Sishu Sangh High School, Sonepur | [7 empty] | 1
7 | HSS-51 | Saran |  | 1 | Durga High School, Sahpur, Sutihar | Asiana Contractor Pvt. Ltd.-9431088485 | 239.96 |  | 239.96 | [7 empty] | 1 | [5 empty] | 23.32
|  |  |  | 2 | Sarvoday High School, Bhagwanpur | [7 empty] | 1
8 | HSS-52 | Saran |  | 1 | Raghuveer Singh High School, Mahdalichak | Ashutosh kumar vill+ po-Bithauli Bhagwanpur Vashali | 243.01 |  | 243.01 | [7 empty] | 1 | [5 empty] | 22.44
|  |  |  | 2 | High School, Atersan | [7 empty] | 1
9 | HSS-51(A) | Saran |  | 1 | High School, Parsagarh | Shivam Const.-9973398595 | 243.32 |  | 243.32 | [6 empty] | 1 | [6 empty] | 44.13
|  |  |  | 2 | Alakh Narain Singh High School, Ekma | [11 empty] | 1
10 | HSS-52(A) | Saran |  | 1 | Zila School, Chapra | Asiana Contractor Pvt. Ltd.-9431088485 | 238.2 |  | 238.2 | [7 empty] | 1 | [5 empty] | 85.03
|  |  |  | 2 | Dr. Ram Bihari Singh High School, Vishnupura | [14 empty] | 1
11 | HSS-53 |  |  | 1 | Medauri Devi High School, Mahammadpur | Asiana Contractor Pvt. Ltd.-9431088485 | 238.12 |  | 238.12 | [7 empty] | 1 | [5 empty] | 59.04
|  |  |  | 2 | Rana Pratap High School, Rampur Kala | [10 empty] | 1
12 | HSS-54 | Gopalganj |  | 1 | High School, Kalyanpur | Sai Highway And Builder Pvt.Ltd.-9771455967 | 369.8 |  | 369.8 | [6 empty] | 1 | [6 empty] | 45.78
|  |  |  | 2 | High School, Vijaypur | [11 empty] | 1
|  |  |  | 3 | High School, Koreya | [8 empty] | 1
13 | HSS-55 | Gopalganj |  | 1 | High School, Gaura | Sona Engicon Pvt.Ltd.-9431008581 | 369.1 |  | 369.1 | [8 empty] | 1 |  |  |  |  | 84.32
|  |  |  | 2 | High School, Bagahi | [12 empty] | 1
|  |  |  | 3 | High School, Belhikhas | [12 empty] | 1
14 | HSS-56 | Gopalganj |  | 1 | High School, Sashamusa | Ramajee mishra & co sirisia sasamusa gopalganj | 245.04 |  | 245.04 | [8 empty] | 1 |  |  |  |  | 23.56
|  |  |  | 2 | High School, Ratanpura | [9 empty] | 1
15 | HSS-57 | Gopalganj |  | 1 | Sahu Jain Girl's High School, Mirganj | Anand Mishra-9931648331 | 244.47 |  | 244.47 | [7 empty] | 1 | [5 empty] | 72.11
|  |  |  | 2 | High School, Jamunaha Bazar | [14 empty] | 1
16 | HSS-58 | Gopalganj |  | 1 | Sahu Jain High School, Mirganj | Akhileshwar Kumar Singh-9431264865 | 244.8 |  | 244.8 | [8 empty] | 1 |  |  |  |  | 39.88
|  |  |  | 2 | Ialamia Urdu Academy, Mirganj | [10 empty] | 1
17 | HSS-59 | Gopalganj |  | 1 | High School, Sadaua | M/S Co hesive Infrastructure Developer Pvt.Ltd-9431212019 | 365.56 |  | 365.56 | [10 empty] | 1 |  |  | 102.65
|  |  |  | 2 | High School , Haluaar, Pipra | [8 empty] | 1
|  |  |  | 3 | High School, Devapur | [11 empty] | 1
18 | HSS-60 | Gopalganj |  | 1 | High School, Dharamparsa | Sona Engicon | 244.24 |  | 244.24 | [9 empty] | 1 |  |  |  | 126.29
|  |  |  | 2 | High School , Madhopur | [14 empty] | 1
19 | HSS-61 | Gopalganj |  | 1 | High School, Uchkagaon | Sai Highway And Builder Pvt.Ltd.-9771455967 | 244.72 |  | 244.72 | [8 empty] | 1 |  |  |  |  | 39.31
|  |  |  | 2 | Maya Chota High School, Uchkagaon | [10 empty] | 1
20 | HSS-62 | Gopalganj |  | 1 | High School, Sankhe Ramdas | M/S Shaeb singh | 245.98 |  | 245.98 | [5 empty] | 1 | [7 empty] | 52.93
|  |  |  | 2 | High School, Dahibhatta | [10 empty] | 1
21 | HSS-63 | Gopalganj |  | 1 | High School, Ganeshsthan, Manjha | Kumar Manash Const. Pvt.Ltd.-9801582832 | 365.86 |  | 365.86 | [6 empty] | 1 | [6 empty] | 86.69
|  |  |  | 2 | High School , Koiladeva | [10 empty] | 1
|  |  |  | 3 | High School, Kusaundhi | [12 empty] | 1
22 | HSS-64 | Gopalganj |  | 1 | High School, Sahpur, Sindhwalia | Asiana Contractor Pvt. Ltd.-9431088485 | 244.48 |  | 244.48 | [10 empty] | 1 |  |  | 127.69
|  |  |  | 2 | High School, Sher | [14 empty] | 1
23 | HSS-65 | Gopalganj |  | 1 | High School, Larauli | Asiana Contractor Pvt. Ltd.-9431088485 | 243.59 |  | 243.59 | [6 empty] | 1 | [6 empty] | 59.31
|  |  |  | 2 | High School, Shirsha | [12 empty] | 1
24 | HSS-66 | Gopalganj |  | 1 | High School, Nechua Jalalpur | M/S Shri Krishna Const.Pvt.Ltd.- | 247.04 |  | 247.04 | [8 empty] | 1 |  |  |  |  | 69.54
|  |  |  | 2 | High School, Baliwan Sagar | [10 empty] | 1
25 | HSS-67 | Gopalganj |  | 1 | High School, Bishunpur Yadavpur | Rand S Const.Pvt.Ltd.-9234272194 | 244.24 |  | 244.24 | [11 empty] | 1 |  | 130.61
|  |  |  | 2 | M. S. Urdu High School, Gopalganj | [12 empty] | 1
26 | HSS-68 | Gopalganj |  | 1 | High School, Sonhula | Akhileshwar Kr. Singh-9431264865 | 36718000 |  | 367.18 | [7 empty] | 1 | [5 empty] | 67.85
|  |  |  | 2 | High School, Bathuwa Bazar | [13 empty] | 1
|  |  |  | 3 | High School, Ramchandpur | [8 empty] | 1 | [9 empty] | Land Problem
27 | HSS-69 | Gopalganj |  | 1 | D. A. V. High School, Gopalganj | Asiana Contractor Pvt. Ltd.-9431088485 | 244.72 |  | 244.72 | [8 empty] | 1 |  |  |  |  | 115.07
|  |  |  | 2 | D. G. High School, Dumaria | [14 empty] | 1
28 | HSS-84 | SIWAN |  | 1 | D.A.V.High school Siwan | Brajesh kumar vill- Dhanuanti Tola ,po- Dhanuanti math Siwan | 112.98 |  | 112.99 | [6 empty] | 1 | [6 empty] | 25.59
29 | HSS-85 | SIWAN |  | 1 | High school Basantpur | Asiana Contractor Pvt. Ltd.-9431088485 | 113.53 |  | 113.54 | [8 empty] | 1 |  |  |  |  | 37.08
30 | HSS-86 | Siwan |  | 1 | High School Hadsar Dhanauti | Retender |  |  | 113.4
31 | HSS-87 | SIWAN |  | 1 | High school Rajpur | Pankaj kumar vill- Benaut, po-Srawan, distt-Chhapra | 113.71 |  | 113.71 | [8 empty] | 1 |  |  |  |  | 36.47
32 | H.S.S- 89 | lkj.k | fjfoyxat | 1 | jked`".k mPp fo¦ky;] flefj;k] fjfoyxat | EKLAVYA INFRA CONSULTECH PVT. LTD, CHAPRA SARAN,9430010264 | [8 empty] | 1 | [7 empty] | 21.85
|  |  |  | 2 | jktdh; ckfydk mPp ek/;fed fo¦ky;] Nijk | [12 empty] | 1
33 | H.S.S- 90 | lkj.k | lnj | 1 | rkilh flag mPp fo¦ky;] fpjkan | SHOBH NATH PRASAD, CHAPRA (SARAN),9431692381 | [6 empty] | 1
|  |  |  | 2 | vkuan mPp fo¦ky;] jkeiqj izrkiiqj nfj;kiqj | [8 empty] | 1
Total No. of Schools |  |  |  | 70 |  |  |  |  | 7983.3 |  |  |  | 15 | 4 | 3 | 12 | 9 | 15 | 2 | 8 | 1 | 0 | 1707.97