## Summary
BSEIDC, PATNA
Progress report for the construction of SSS (Sanctioned Year 2012-13) | [20 empty] | Date:-28.02.2015
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna | 29 | 54 | 4803.64 | 27 | 52 | 4803.64 |  | 0 | 9 | 6 | 10 | 3 | 8 | 1 | 0 | 15 | 37 | 0 | 1010.97 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E. BSEIDC, Div.- Patna (West) | 40 | 68 | 7140.95 | 37 | 62 | 6721.94 |  | 1 | 13 | 2 | 1 | 10 | 5 | 8 | 14 | 8 | 54 | 0 | 1829.91 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 67 | 116 | 10086.25 | 61 | 110 | 8951.64 |  | 2 | 14 | 13 | 7 | 25 | 3 | 22 | 0 | 24 | 86 | 0 | 2272.87 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Bhagalpur | 24 | 55 | 5261.89 | 15 | 40 | 3675.68 |  | 2 | 4 | 4 | 4 | 5 | 5 | 5 | 1 | 9 | 30 | 1 | 1125.58 |  | 0
5 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 64 | 122 | 12887.97 | 43 | 87 | 8656.75 |  | 2 | 17 | 11 | 2 | 9 | 3 | 5 | 4 | 32 | 53 | 2 | 1993.37 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 44 | 90 | 10173.64 | 39 | 85 | 6437.58 |  | 3 | 7 | 14 | 9 | 8 | 6 | 12 | 2 | 24 | 61 | 0 | 2130.52 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnea | 49 | 82 | 19701.03 | 32 | 63 | 6531.59 |  | 9 | 6 | 6 | 4 | 3 | 1 | 4 | 0 | 30 | 33 | 0 | 522.53 |  | 0
8 | TIRHUT (EAST) | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 56 | 114 | 12306.83 | 37 | 87 | 8719.52 |  | 5 | 12 | 6 | 7 | 14 | 3 | 10 | 5 | 25 | 62 | 0 | 1721.577 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha, (8544126916) EE, BSEIDC, Div.- Tirhut (West) | 51 | 103 | 11423.81 | 43 | 94 | 11201.98 |  | 1 | 6 | 7 | 11 | 9 | 15 | 6 | 3 | 36 | 58 | 0 | 2018.95 |  | 0
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 65 | 115 | 11094.84 | 43 | 61 | 4913.77 |  | 3 | 4 | 4 | 2 | 9 | 5 | 5 | 3 | 26 | 35 | 0 | 1316.4 |  | 0
11 | SARAN | Uday Kumar Das, (9431821558), EE BSEIDC, Div.- Saran | 38 | 74 | 8127.08 | 36 | 71 | 7685.29 |  | 6 | 4 | 11 | 5 | 18 | 0 | 5 | 4 | 18 | 53 | 0 | 1588.77 |  | 0
Total (SSS) |  |  | 527 | 993 | 113007.93 | 413 | 812 | 78299.38 | 0 | 34 | 96 | 84 | 62 | 113 | 54 | 83 | 36 | 247 | 562 | 3 | 17531.447 |  | 0

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- PATNA (EAST) - Patna, Nalanda & Bhojpur | [22 empty] | Date:-28.02.2015
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-98 | iVuk | fcgVk | 1 | e/; fo¦ky;] jk?kksiqj] fcgVk] iVuk | Jai Mata di Construction |  |  | 105.51 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 42.1
2 | SSS-99 | iVuk | nkukiqj | 1 | mRØfer e/; fo¦ky;] cfj;kjiqj | Jai Mata di Construction |  |  | 106.32 |  |  | 15 Months | 1
3 | SSS-100 | ukyUnk | bLykeiqj | 1 | e/; fo¦ky;] dksfcy | Baba Hans Construction Pvt. Ltd. | Canal Road, Patna Mob# 9430407767 |  | 208.37 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 65.2
|  |  |  | 2 | e/; fo¦ky;] pkSjek | [11 empty] | 1
4 | SSS-101 | ukyUnk | fcgkj | 1 | mRØfer e/; fo¦ky;] gosyh | Pinku Kumari | Nalanda, Bihar |  | 104.25 |  |  | 15 Months |  |  | 1
5 | SSS-102 | ukyUnk | fcgkj'kjhQ | 1 | mRØfer e/; fo¦ky;] gjxk¡o | Krishandeo prasad | Mumurabad, Nalanda |  | 314.06 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 15.06
|  |  |  | 2 | mRØfer e/; fo¦ky;] ldjkSy | [7 empty] | 1 | [10 empty] | Land not available
|  |  |  | 3 | mRØfer e/; fo¦ky;] ijkSgk | [9 empty] | 1
6 | SSS-103 | ukyUnk | fgylk | 1 | e/; fo¦ky;] diflvkou | Prem Kumar Sinha | Maheshpur, Nalanda |  | 209.37 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 41.59
7 | SSS-104 | ukyUnk | flyko | 1 | mnwZ e/; fo¦ky;] lkscbZr | Raj Kumar Singh Raja Construction Pvt. Ltd. | Patna-25 |  | 520.78 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 40.51 | Up to GL
|  |  |  | 2 | e/; fo¦ky;] pk¡nh ekWm | [10 empty] | 1 | [7 empty] | Tie beam
|  |  |  | 3 | e/; fo¦ky;] dqy | [11 empty] | 1 | [6 empty] | G.L.
|  |  |  | 4 | mRØfer e/; fo¦ky;] ikadh | [7 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] t;fd'kqu fcxgk | [9 empty] | 1 | [8 empty] | E/W (water logged)
8 | SSS-105 | ukyUnk | fxfj;d | 1 | e/; fo¦ky;] vkneiqj | M/S Rama Construction | Aunta, Patna |  | 208.16 |  |  | 15 Months | 1 | [9 empty] | 44.18 | Land not available
|  |  |  | 2 | e/; fo¦ky;] pkSjlqvk | [13 empty] | 1
9 | SSS-106 | ukyUnk | gjukSr | 1 | e/; fo¦ky;] usgqlk | Prem Kumar Sinha | Nalanda |  | 105.36 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 44.79
10 | SSS-107 | ukyUnk | ijoyiqj | 1 | m0vk0e/; fo¦ky;] ebZ | Pappu Singh | Bihar Sharif, Patna |  | 104.52 |  |  | 15 Months | 1 | [10 empty] | Land not available
11 | SSS-108 | ukyUnk | jgqbZ | 1 | e/; fo¦ky;] eksM+kryko | Vikash Kumar Singh | Patna-26 |  | 210.57 |  |  | 15 Months | 1 | [9 empty] | 37.34 | Land not available
|  |  |  | 2 | e/; fo¦ky;] dFkkSyh | [14 empty] | 1 |  |  |  | Water Logged
12 | SSS-109 | ukyUnk | ljesjk | 1 | e/; fo¦ky;] dkthpd | Budha Infrastructure Pvt. Ltd | Patna |  | 210.42 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 74.92 | Water Logged
|  |  |  | 2 | e/; fo¦ky;] eykou | [12 empty] | 1 | [5 empty] | Water Logged
13 | SSS-120 | ukyUnk | uwjljk; | 1 | e/; fo¦ky;] eeqjknkckn | M/S Uma Shankar & Company | Naya Gaon, Patna |  | 209.96 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 31.06 | G.L. (way not available)
|  |  |  | 2 | e/; fo¦ky;] ljnkjfoxgk | [12 empty] | 1 | [5 empty] | 11000 v wire (BFS)
14 | SSS-121 | ukyUnk | vLFkkok¡ | 1 | mnZw e/; fo¦ky;] mxkou | Budha Infrastructure Pvt. Ltd. | Hanuman Nagar, Patna |  | 521.31 |  |  | 15 Months | 1 | [9 empty] | 117.22
|  |  |  | 2 | mRØfer e/; fo¦ky;] vksb;kc | [13 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] [ksryiqjk | [13 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] tkuk | [7 empty] | 1 | [10 empty] | Land problem
|  |  |  | 5 | e/; fo¦ky;] vkSUMk | [10 empty] | 1
15 | SSS-122 | Hkkstiqj | cM+gjk | 1 | e/; fo¦ky;] uFkeyiqj | Bhawani Buidcon & Project Pvt. Ltd. | C/o Sanjay Kumar Singh, Patna |  | 103.58 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 40.17
16 | SSS-123 | Hkkstiqj | fcfg;kW | 1 | mRØfer e/; fo¦ky;] ohjiqj | Sudarshan Mahato | Jagdishpur, Ara |  | 208.81 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 60.91
|  |  |  | 2 | çk;ksfxd e/; fo¦ky;] fcfg;kW | [7 empty] | 1 | [10 empty] | Required old building demolision
17 | SSS-124 | Hkkstiqj | ihjks | 1 | mRØfer e/; fo¦ky;] ,;kj | Manoj Kumar | Bhojpur |  | 210.14 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 16.52 | B/W upto PL
|  |  |  | 2 | e/; fo¦ky;] ygjkckn | [9 empty] | 1 | [8 empty] | E/W in progress
18 | SSS-125 | Hkkstiqj | lans'k | 1 | e/; fo¦ky;] ppkj | M/S Kalaratri Associates | Nawada, Bhojpur |  | 104.91 |  |  | 15 Months |  |  | 1 | [7 empty] | 18.76 | E/W in progress
19 | SSS-126 | Hkkstiqj | lkgiqj | 1 | e/; fo¦ky;] ygax Mqefj;k | M/S Kalaratri Associates | Nawada, Bhojpur |  | 104.55 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 43.77
20 | SSS-127 | Hkkstiqj | mnoUruxj | 1 | mRØfer e/; fo¦ky;] [kyhlk | Ashok Kumar | Jokta, Bhojpur |  | 309.13 |  |  | 15 Months | 1 | [9 empty] | 61.59 | Work stop by DEO
|  |  |  | 2 | mRØfer e/; fo¦ky;] ckeikWyh | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky; ohjeiqj | [10 empty] | 1 | [7 empty] | Foundation PCC
21 | SSS-128 | Hkkstiqj | rjkjh | 1 | e/; fo¦ky;] pank | Sadhu Saran Singh | Pawar,Ara |  | 208.58 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 60.67 | Tie beam work in prog.
|  |  |  | 2 | e/; fo¦ky;] csjbZ | [9 empty] | 1 | [8 empty] | Tie Beam
22 | SSS-129 | Hkkstiqj | txnh'kiqj | 1 | mRØfer e/; fo¦ky;] nkWok | Sudarshan Mahto | ,Jagdishpur,Ara |  | 209.45 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 74.06
|  |  |  | 2 | mRØfer e/; fo¦ky;] cSjgh | [10 empty] | 1 | [7 empty] | RCC in foundation
23 | SSS-130 | Hkkstiqj | vkjk | 1 | e/; fo¦ky;] [ktqfj;kW | Janardan Yadav | ,Agarsanda,Bhojpur |  | 205.53 |  |  | 15 Months |  |  | 1 | [7 empty] | 62.58 | RCC in foundation
|  |  |  | 2 | mRØfer e/; fo¦ky;] y{e.kiqj | [11 empty] | 1
24 | SSS-415 | iVuk | ikyhxat | 1 | e/; fo¦ky;] /kks[kjk | Retender |  |  | 107.4
25 | SSS-451 | ukyank | bLykeiqj | 1 | e/; fo¦ky;] ekSyukpd | M/S DAYANAND PRASAD SINHA &CO. JANTA PATH |  |  | 104.18 | [5 empty] | 1 | [7 empty] | 17.97
26 | S.S.S-374 | iVuk | ikyhxat | 1 | e/; fo¦ky;] esjk[kkuiqjk | MS VATSHYAN CONSTRUCTION 9546109122 |  |  | 328.93 |  |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] lsgjk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dY;k.kiqj | [9 empty] | 1
27 | S.S.S-375 | iVuk | /ku:vk | 1 | e/; fo¦ky;] vatuh xksfoUniqj | Retender |  |  | 110.58
28 | S.S.S-376 | iVuk | fcgVk | 1 | e/; fo¦ky;] fgjkeuiqj idM+hundred | NEER GAGAN CONSTRUCTION 9308641711 |  |  | 220.28 |  |  |  | 1
|  |  | Qqyokjh 'kjhQ | 2 | mPp ek/;fed fo¦ky;] xksuiqjk ¼funs'kd] ek/;fed f'k{kk ds Kkikad&11@;ksŒ&02&03@2012&123] fnukad&29-01-2014 esa fn, x, vkns'kkuqlkj xzke iapk;Rs.&xksuiqjk ds csfld Ldwy ds tehu ij Hkou fuekZ.k gksxkA½ | [7 empty] | 1
29 | S.S.S-377 | iVuk | iquiqu | 1 | mRØfer e/; fo¦ky;] jkt?kkV uoknk | KAMESHWAR PRASAD SINGH, 9386235888 |  |  | 110.42 |  |  |  | 1
| Total No. of Schools |  |  | 54 |  |  |  |  | 4803.64 |  |  |  | 15 | 0 | 9 | 6 | 10 | 3 | 8 | 1 | 0 | 0 | 1010.97

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- PATNA (WEST) - Buxar, Rohtas & Kaimur (Bhabhua) | [22 empty] | Date:-28.02.2015
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-131 | jksgrkl | djxgj | 1 | e/; fo¦ky;] efu;kjh | Krishna Ganeshpur, PO- Mamrejpur, PS- chenari, Rohtas |  |  | 208.93 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 18.69 | BFS (water logged)
|  |  |  | 2 | mRØfer e/; fo¦ky;] :iSBk | [9 empty] | 1 | [8 empty] | Way not available
2 | SSS-132 | jksgrkl | dkspl | 1 | mRdzfer e/; fo¦ky;] ygsjh | Vikash Kumar | Koilwar,Ara |  | 209.97 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] dq:lk | [9 empty] | 1
3 | SSS-133 | jksgrkl | f'kolkxj | 1 | e/; fo¦ky;] eqgEeniqj | M/S Shree Jogmaya Infrastructure Co. Pvt. Ltd. | ,Sasaram,Bihar |  | 414.24 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 179.27 | Dispute
|  |  |  | 2 | mRdzfer e/; fo¦ky;] xksrgj | [15 empty] | 1 |  |  | R/C
|  |  |  | 3 | mRdzfer e/; fo¦ky;] lsejh | [7 empty] | 1 | [10 empty] | Dispute
|  |  |  | 4 | e/; fo¦ky;] FkuqvkW | [15 empty] | 1 |  |  | Shuttering & Steel Binding
4 | SSS-134 | jksgrkl | fMgjh | 1 | mRdzfer e/; fo¦ky;] HkMdqfM;k | Uday Nath Dubey,Pahari Tola,Ranchi |  |  | 206.54 |  |  | 15 Months |  |  | 1 | [8 empty] | E/W
|  |  |  | 2 | e/; fo¦ky;] nqxkZiqj | [7 empty] | 1 | [10 empty] | Land problem
5 | SSS-135 (A) | jksgrkl | fnukjk | 1 | e/; fo¦ky;] osyoS;k | Sidheshwar Singh,Rohtas,Bihar |  |  | 419.01 |  |  | 15 Months |  | 1
6 | SSS-135 (B) |  |  | 1 | e/; fo¦ky;] cjk<hdyk | Kanchan Cons. | [6 empty] | 1
7 | SSS-135 (C) |  |  | 1 | e/; fo¦ky;] esnuhiqj | Tender Process
8 | SSS-135 (D) |  |  | 1 | mRdzfer e/; fo¦ky;] [kylkiqj | Suraj Traders | [6 empty] | 1
9 | SSS-136 | jksgrkl | frykSFkq | 1 | e/; fo¦ky;] lsogh | Anil Ray,Rohtas |  |  | 103.43 |  |  | 15 Months | [8 empty] | 1 |  | 55.4 | Shuttering
10 | SSS-137 | jksgrkl | frykSFkw | 1 | e/; fo¦ky;] Hknks[kjk | Chandra Bhushan Roy,Kaimur |  |  | 103.43 |  |  | 15 Months | 1 | [10 empty] | Low Land about 12'-0"
11 | SSS-138 | jksgrkl | Lkklkjke | 1 | mRdzfer e/; fo¦ky;] nouiqj | M/S Shree Jogmaya Infrastrunture Co. Pvt. Ltd,Sasaram.Bihar |  |  | 308.31 |  |  | 15 Months | [8 empty] | 1 |  | 201 | R/C
|  |  |  | 2 | e/; fo¦ky;] nfjxkao | [15 empty] | 1 |  |  | Shuttering
|  |  |  | 3 | e/; fo¦ky;] xksVik | [15 empty] | 1 |  |  | Shuttering
12 | SSS-139 | jksgrkl | lklkjke | 1 | e/; fo¦ky;] HkSlgha | M/S A.K.Construction,Rohtas, Bihar |  |  | 309.4 |  |  | 15 Months | [8 empty] | 1 |  | 163.81
|  |  |  | 2 | e/; fo¦ky;] ukSxkbZ | [12 empty] | 1 | [5 empty] | PCC
|  |  |  | 3 | e/; fo¦ky;] ifr;k< | [15 empty] | 1
13 | SSS-140 | jksgrkl | psukjh | 1 | e/; fo¦ky;] HkqMdqfM;k | Krishna,Ganeshpur,Rohtas |  |  | 209.19 |  |  | 15 Months |  |  | 1 | [7 empty] | 28.95 | Earth Excavation
|  |  |  | 2 | mRdzfer e/; fo¦ky;] x.ks'kiqj | [13 empty] | 1
14 | SSS-141 | jksgrkl | uks[kk | 1 | e/; fo¦ky;] ef<;kW | Maa Pragati ConstructionCo-Ramanand Singh,Rohtas |  |  | 103.58 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 30.83
15 | SSS-142 | jksgrkl | ukSgêk | 1 | mRØfer e/; fo¦ky;] HkoukFkiqj | M/S Manoj Singh,Rohtas |  |  | 106.15 |  |  | 15 Months | [7 empty] | 1 |  |  | 28.51 | Tie Beam
16 | SSS-143 | jksgrkl | vdks<+hxksyk | 1 | mRdzfer e/; fo¦ky;] lyS;k | Sidheshwar Singh,Rohtas,Bihar |  |  | 205.83 |  |  | 15 Months | [8 empty] | 1 |  | 175.01 | Shuttering
|  |  |  | 2 | e/; fo¦ky;] dkSik | [15 empty] | 1
17 | SSS-144 | cDlj | bVk<+h | 1 | e/; fo¦ky;] fc>kSjk | Buxar Construction |  |  | 211.32 |  |  | 15 Months |  |  | 1 | [7 empty] | 33.31
|  |  |  | 2 | e/; fo¦ky;] cSjh | [12 empty] | 1
18 | SSS-145 | cDlj | cDlj | 1 | e/; fo¦ky;] cksDlk | Bablu Kumar Singh Ram Jee chak,Patna |  |  | 210.92 |  |  | 15 Months | [8 empty] | 1 |  | 129.28
|  |  |  | 2 | e/; fo¦ky;] tklks | [15 empty] | 1
19 | SSS-146 | cDlj | czãiqj | 1 | g0m0 e/; fo¦ky;] j?kqukFkiqj | Sharda Construction,sri Kung,Patna |  |  | 212.63 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 20.53
|  |  |  | 2 | e/; fo¦ky;] cjk<+h | [9 empty] | 1
20 | SSS-147 | cDlj | flejh | 1 | d0 e/; fo¦ky;] nqYygiqj | Ranjan kumar Singh,Civil Lines,buxer,Bihar |  |  | 317.85 |  |  | 15 Months | [7 empty] | 1 |  |  | 172.68
|  |  |  | 2 | e/; fo¦ky;] NksVdk flaguiqjk | [14 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ,dkSuk | [14 empty] | 1
21 | SSS-148 | cDlj | jktiqj | 1 | e/; fo¦ky;] eaxjko | M/S Darshita Buildres and Developers pvt. Ltd,Kaimur,Bhabua |  |  | 106.38 |  |  | 15 Months | [7 empty] | 1 |  |  | 45.17
22 | SSS-149 | cDlj | pkSlk | 1 | e/; fo¦ky;] iouh | Krishna pratap Singh,Ramgarh,kaimur-9801133880 |  |  | 317.65 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 134.36
|  |  |  | 2 | e/; fo¦ky;] lxjk | [13 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] pqUuh | [14 empty] | 1
23 | SSS-150 | cDlj | ukokuxj | 1 | e/; fo¦ky;] Hknkj | M/S Aditya Construction,Govindpur,Buxer |  |  | 211.67 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] xksfoUniqj | [9 empty] | 1
24 | SSS-151 | dSewj | eksgfu;ka | 1 | mRØfer e/; fo¦ky;] nknj | M/S Ashtbhuja Construction,Kanchanapur,rohtas |  |  | 315.37 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 62 | Sill level
|  |  |  | 2 | e/; fo¦ky;] Hkj[kj | [7 empty] | 1 | [10 empty] | Land Not available
|  |  |  | 3 | mRØfer e/; fo¦ky;] vesB | [12 empty] | 1
25 | SSS-152 | dSewj | HkHkqvk | 1 | e/; fo¦ky;] Hksdkl | Nav Nirman Construction,bhabhua,Kaimur |  |  | 104.49 |  |  | 15 Months | [7 empty] | 1 |  |  | 39.54
26 | SSS-153 | dSewj | Hkxokuiqj | 1 | mRØfer e/; fo¦ky;] dlsj | Ajay kumar Singh,Bhabua,Kaimur |  |  | 210.11 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 87.94
|  |  |  | 2 | mRØfer e/; fo¦ky;] fla/kh | [15 empty] | 1
27 | SSS-154 | dSewj | nwxkZorh | 1 | mRØfer e/; fo¦ky;] xksjkj | Baba vishwannath construction,Nowan,Kaimur |  |  | 106.08 |  |  | 15 Months | [7 empty] | 1 |  |  | 52.5
28 | SSS-155 | dSewj | pkWan | 1 | e/; fo¦ky;] Hkjkjh | M/S Gupta dham Construction,Kaimur,bhabhua |  |  | 106.27 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 43.15
29 | SSS-156 | dSewj | pSuiqj | 1 | e/; fo¦ky;] c<kSuk | M/S Gupta dham Construction,Kaimur,bhabhua |  |  | 105.13 |  |  | 15 Months | [8 empty] | 1 |  | 56.85
30 | SSS-157 | dSewj | v/kkSjk | 1 | mRØfer e/; fo¦ky;] pQuk | Ajay Kumar Singh , Bhabua,Kaimur |  |  | 216.41 |  |  | 15 Months |  |  | 1 | [7 empty] | 39.8 | Land Problem
|  |  |  | 2 | mRØfer e/; fo¦ky;] U;w | [12 empty] | 1
31 | SSS-391 | dSewj | v/kkSjk | 1 | mRØfer jktdh; e/; fo¦ky;] cnokadyk | TENDER PROCESS |  |  | 432.8
|  |  |  | 2 | mRØfer jktdh; e/; fo¦ky;] cgsM+k
|  |  |  | 3 | mRØfer jktdh; e/; fo¦ky;] dUgukj
|  |  |  | 4 | e/; fo¦yk;] ngkj
32 | SSS-392 | dSewj | jkeiqj | 1 | e/; fo¦ky;] veho | AJAY KUMAR SINGH |  |  | 105.07 |  |  |  | 1
33 | SSS-393 | dSewj | Hkxokuiqj | 1 | e/; fo¦ky;] tSrqiqjdyk | NAV NIRMAN CONSTRUCTION,9507456472 |  |  | 105.05 | [5 empty] | 1
34 | SSS-394 | dSewj | eksguh;k¡ | 1 | e/; fo¦ky;] dFkst | RISHABH KUMAR MISHRA |  |  | 105.12 | [7 empty] | 1 | [5 empty] | 10.25
35 | SSS-395 | dSewj | uqvk¡o | 1 | e/; fo¦ky;] dksVk | TENDER PROCESS |  |  | 105.06
36 | SSS-396 | dSewj | jkex<+ | 1 | e/; fo¦ky;] uksukj | DARSHITA BUILDER AND DEVELOPERS PVT LTD,09801134120 |  |  | 105.14 | [5 empty] | 1
37 | SSS-397 | dSewj | pSuiqj | 1 | mRØfer e/; fo¦ky;] Mqekjdksu | SHARDA SECURITY AND ALLIED SERVICES,9708277777 |  |  | 105.13 | [8 empty] | 1 |  |  |  |  | 21.08
38 | SSS-429 | jksgrkl | foØexat | 1 | e/; fo¦ky;] uksugj | MANOJ KUMAR SINGH,8804224510 |  |  | 208.95 | [6 empty] | 1
|  |  |  | 2 | e/; fo¦ky;] mn; fMgjh | [9 empty] | 1
39 | SSS-430 | jksgrkl | jksgrkl | 1 | mRØfer e/; fo¦ky;] VqEck | MAA MUNDESHWARI CONSTRUCTION,9430895576 |  |  | 103.74 | [6 empty] | 1
40 | SSS-431 | jksgrkl | psukjh | 1 | mRØfer e/; fo¦ky;] fi;kdyk | MANOJ KUMAR SINGH,8804224510 |  |  | 104.6 | [5 empty] | 1
| Total No. of Schools |  |  | 68 |  |  |  |  | 7140.95 |  |  |  | 8 | 1 | 13 | 2 | 1 | 10 | 5 | 8 | 14 | 0 | 1829.91

## Magadh
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- MAGADH | [24 empty] | Date:-28.02.2015
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block |  | S.N. | Name of School | Name of Agency | Agency Address and Mobile No | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[15 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[19 empty] | LL | RL | LL | RL
1 | SSS-254 | x;k | bekexat |  | 1 | e/; fo¦ky;] oa'kh | Mata Di Construction | C/o- Rina Devi, faya |  |  | 418.32 |  |  | 15 Months | 1
[5 empty] | 2 | e/; fo¦ky;] fojkt | [8 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] f>dfV;kdyk | [8 empty] | 1
[5 empty] | 4 | e/; fo¦ky;] olsrk | [10 empty] | 1
2 | SSS-255 | x;k | cFkkuh |  | 1 | mnwZ e/; fo¦ky;] oaMh | Roy Engineers | Danapur |  |  | 103.96 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 11.45
3 | SSS-256 | x;k | ckads ctkj |  | 1 | e/; fo¦ky;] jkS'kuxat | Sanju kuamri | Gaya |  |  | 102.68 |  |  | 15 Months | [7 empty] | 1 |  |  | 60.77
4 | SSS-257 | x;k | ckds ctkj |  | 1 | e/; fo¦ky;] yqVqvk | Koela Construction, Gaya |  |  |  | 206.22 |  |  | 15 Months | 1 | [9 empty] | 22.08
[5 empty] | 2 | e/; fo¦ky;] eksus;k | [13 empty] | 1
5 | SSS-258 | x;k | ckjkpV~Vh |  | 1 | e/; fo¦ky;] fnofu;ka | MS Azad Construction, Gaya |  |  |  | 208.04 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 59.93
[5 empty] | 2 | e/; fo¦ky;] uokMhg | [12 empty] | 1
6 | SSS-259 | x;k | cks/kx;k |  | 1 | e/; fo¦ky;] teM+h | M/s om Shakti Construction | Gaya |  |  | 408.89 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 142.82
[5 empty] | 2 | e/; fo¦ky;] ijfj;k | [15 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] ekspkfje | [15 empty] | 1
[5 empty] | 4 | e/; fo¦ky;] 'ksjokjk | [13 empty] | 1
7 | SSS-260 | x;k | cthjxat |  | 1 | e/; fo¦ky;] fo'kquiqj | M/s Sidhnath Construction | Gaya |  |  | 103.37 |  |  | 15 Months |  |  | 1
8 | SSS-261 | x;k | eksguiqj |  | 1 | e/; fo¦ky;] tsBqvkMkgk | Keol Construction |  |  |  | 206.84 |  |  | 15 Months |  |  | 1 | [7 empty] | 6.74
[5 empty] | 2 | e/; fo¦ky;] [kqMqvk | [10 empty] | 1
9 | SSS-262 | x;k | ekuiqj |  | 1 | e/; fo¦ky;] xsjs | Satish Kusum Raj | Patna |  |  | 205.11 |  |  | 15 Months | [7 empty] | 1 |  |  | 86.64
[5 empty] | 2 | e/; fo¦ky;] Hkksjs | [15 empty] | 1
10 | SSS-263 | x;k | f[ktjljk; |  | 1 | e/; fo¦ky;] lfj;k | Ranjan Kumar Gajraj Singh |  |  |  | 102.85 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 16.52
11 | SSS-264 | x;k | 'ks[k?kkVh |  | 1 | e/; fo¦ky;] mfpjek | Narendra Yadav | Gaya |  |  | 307.28 |  |  | 15 Months | [7 empty] | 1 |  |  | 72.19
[5 empty] | 2 | e/; fo¦ky;] eksguiqj | [8 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] dpkSM+h | [13 empty] | 1
12 | SSS-265 (A) | x;k | Mqefj;k |  | 1 | e/; fo¦ky;] cjgk | Retender |  |  |  | 209.37 |  |  | 15 Months
13 | SSS-265 (B) |  |  |  | 1 | e/; fo¦ky;] gsljk jkeiqj | Sunil Kumar | [7 empty] | 1
14 | SSS-266 | x;k | Qrsgiqj |  | 1 | e/; fo¦ky;] lyS;kdyk | Ms Sidhnath Construction |  |  |  | 103.36 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 17.7
15 | SSS-267 | x;k | uxj |  | 1 | xzke&dsokyh] Fkkuk laŒ&197 | Satish Kusum Raj | Patna |  |  | 307.3 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 72.55
[5 empty] | 2 | e/; fo¦ky;] dksjeka | [13 empty] | 1
[5 empty] | 3 | xzke&/kqosZ Fkkuk laŒ&177 | [12 empty] | 1
16 | SSS-268 | x;k | vkel |  | 1 | e/; fo¦ky;] ';kedyk | Jai Kumar | Gaya |  |  | 204.74 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 39.7
[5 empty] | 2 | e/; fo¦ky;] fuek cq)kSy | [13 empty] | 1
17 | SSS-269 | x;k | Vsdkjh |  | 1 | e/; fo¦ky;] cych?kk | Ram Pukar Singh |  |  |  | 102.78 |  |  | 15 Months | 1
18 | SSS-270 | x;k | VudqIik |  | 1 | e/; fo¦ky;] ukSokx<+ | M/s Sidhnath Consdtruction | Gaya |  |  | 206.78 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 70.86
[5 empty] | 2 | e/; fo¦ky;] HksVkSjk | [13 empty] | 1
19 | SSS-271 (A) | x;k | xq:vk |  | 1 | e/; fo¦ky;] 'ksjiqj | M/S Sheel Cons. |  |  |  | 409.65 |  |  | 15 Months | 1
20 | SSS-271 (B) |  |  |  | 1 | e/; fo¦ky;] ukSfMgk | Tender Process
21 | SSS-271 (C) |  |  |  | 1 | e/; fo¦ky;] fojfgek | Tender Process
22 | SSS-271 (D) |  |  |  | 1 | e/; fo¦ky;] dkt | Sharwan Kumar Singh | [9 empty] | 1
23 | SSS-272 | uoknk | esLdkSj |  | 1 | mRØfer e/; fo¦ky;] iokbZ | M/s Om Shakti Construction | Anil Kumar |  |  | 203.7 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 51.32
[5 empty] | 2 | mRØfer e/; fo¦ky;] vdfj | [13 empty] | 1
24 | SSS-273 | uoknk | fglqvk |  | 1 | mRØfer e/; fo¦ky;] ,dukj | Arvind Kumar |  |  |  | 101.62 |  |  | 15 Months |  |  |  | 1
25 | SSS-274 | uoknk | fljnyk |  | 1 | mRØfer e/; fo¦ky;] dksyfMgk | MD. Rais Khan | Nawada |  |  | 309.53 |  |  | 15 Months |  |  | 1 | [7 empty] | 35.57
[5 empty] | 2 | e/; fo¦ky;] [kuiqjk | [15 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] vdEck | [8 empty] | 1
26 | SSS-275 | uoknk | idjhcjkok¡ |  | 1 | e/; fo¦ky;] ds'kkSjh | Gopal Kumar |  |  |  | 101.8 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 22.5
27 | SSS-276 | uoknk | jksg |  | 1 | e/; fo¦ky;] dqat | Arvind Kumar |  |  |  | 102.21 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 12.78
28 | SSS-277 (A) | uoknk | jtkSyh |  | 1 | mRØfer e/; fo¦ky;] /kkeqpd | Nawin Kumar |  |  |  | 206.72 |  |  | 15 Months | 1
29 | SSS-277 (B) |  |  |  | 1 | e/; fo¦ky;] pijk | Dhirendra prasad,Nalanda | [7 empty] | 1
30 | SSS-279 | uoknk | ujgV |  | 1 | mRØfer e/; fo¦ky;] cjcŸkk | Ramesh Kumar | Patna |  |  | 203.81 |  |  | 15 Months |  |  | 1 | [7 empty] | 16.05
[5 empty] | 2 | mRØfer e/; fo¦ky;] nkbZfcxgk | [13 empty] | 1
31 | SSS-280 | uoknk | uoknk |  | 1 | mRØfer e/; fo¦ky;] ifN;k Mhg | M/S Shiv Shakti Construction | Nawada |  |  | 101.67 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 20.82
32 | SSS-281 | uoknk | vdcjiqj |  | 1 | mRØfer e/; fo¦ky;] Qjgk | Dhirendra prasad | Nalanda |  |  | 513.18 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 176.92
[5 empty] | 2 | mRØfer e/; fo¦ky;] rsyHknzks | [14 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] Hkusy | [13 empty] | 1
[5 empty] | 4 | mRØfer e/; fo¦ky;] Qqyek | [13 empty] | 1
[5 empty] | 5 | mRØfer e/; fo¦ky;] ifl;k | [15 empty] | 1
33 | SSS-282 | uoknk | xksfoUniqj |  | 1 | mRØfer e/; fo¦ky;] rsrfj;k | Arbind Prasad | Sheikhpura |  |  | 208.27 |  |  | 15 Months |  |  | 1 | [7 empty] | 19.95
[5 empty] | 2 | e/; fo¦ky;] cq/kokM+k | [11 empty] | 1
34 | SSS-283 | vjoy | djih |  | 1 | e/; fo¦ky;] [ktqjh | Kaushalendra Kumar |  |  |  | 204.41 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 34.3
[5 empty] | 2 | e/; fo¦ky;] v/kkjpd | [11 empty] | 1
35 | SSS-284 | vjoy | dysj |  | 1 | e/; fo¦ky; mljh | Raj kumar Singh raja ConstructionPvt Ltd | Patna |  |  | 205.66 |  |  | 15 Months |  | 1
[5 empty] | 2 | e/; fo¦ky; ofynkn | [10 empty] | 1
36 | SSS-285 | vjoy | dqFkkZ |  | 1 | mRØfer e/; fo¦ky;] dSFkksyksnhiqj | Kaushlendra Kumar | Jehanabad |  |  | 101.87 |  |  | 15 Months | 1
37 | SSS-286 | vjoy | lksuHknz oa'kh lw;Ziqj |  | 1 | e/; fo¦ky;] iksfUny | Kaushalendra Kumar |  |  |  | 102.28 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 16.05
38 | SSS-287 | vjoy | vjoy |  | 1 | e/; fo¦ky; jkeiqj pkSje | M/s Maa KamaKhya |  |  |  | 101.96 |  |  | 15 Months | [7 empty] | 1 |  |  | 18.43
39 | SSS-288 | vkSjaxkckn | ck:.k |  | 1 | e/; fo¦ky;] dnks[kjh | Arvind Kumar Singh |  |  |  | 205.43 |  |  | 15 Months |  |  |  | 1
[5 empty] | 2 | e/; fo¦ky;] fiBuqvk |  | New area, Aurangabad | [8 empty] | 1
40 | SSS-289 | vkSjaxkckn | dqVqEck |  | 1 | e/; fo¦ky;] pkS[kMk | Maa Sharda Construction |  |  |  | 725.98 |  |  | 15 Months | [7 empty] | 1 |  |  | 378.48
[5 empty] | 2 | e/; fo¦ky;] fd'kquiqj | [15 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] cStkfcxgk | [15 empty] | 1
[5 empty] | 4 | e/; fo¦ky;] cSjko | [15 empty] | 1
[5 empty] | 5 | e/; fo¦ky;] ?ksmjk | [15 empty] | 1
[5 empty] | 6 | e/; fo¦ky;] iksyk xksjMhgk | [15 empty] | 1
[5 empty] | 7 | e/; fo¦ky;] ihijk cxkgh | [15 empty] | 1
41 | SSS-290 (A) | vkSjaxkckn | jQhxat |  | 1 | e/; fo¦ky;] ljkod | Tender Process |  |  |  | 206.09 |  |  | 15 Months
42 | SSS-290 (B) |  |  |  | 1 | e/; fo¦ky;] i[kukSj | M/s Hari Om Construction, Aurangabad | Bhabua-9973920426 | [6 empty] | 1
43 | SSS-291 | vkSjaxkckn | nso |  | 1 | e/; fo¦ky;] ukjk;.kiqj | M/s Darshita Builders & Developers Pvt Ltd. | Aurangabad |  |  | 102.77 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 33.47
44 | SSS-292 | vkSjaxkckn | nso |  | 1 | e/; fo¦ky;] cjaMk jkeiqj | M/s Hari Om Construction |  |  |  | 309.39 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 149.04
[5 empty] | 2 | e/; fo¦ky;] dVS;k | [14 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] csyk | [15 empty] | 1
45 | SSS-293 | vkSjaxkckn | uchuxj |  | 1 | e/; fo¦ky;] jkeuxj | Satyendra Kumar Consyruction,Patna |  |  |  | 417.45 |  |  | 15 Months |  |  | 1 | [7 empty] | 79.81
[5 empty] | 2 | e/; fo¦ky;] e>hvko | [13 empty] | 1
[5 empty] | 3 | e/; fo¦ky;] dadsj | [15 empty] | 1
[5 empty] | 4 | e/; fo¦ky;] csykbZ | [11 empty] | 1 | [7 empty] | Land Dispute
46 | SSS-294 | vkSjaxkckn | vkSjaxkckn |  | 1 | e/; fo¦ky;] cHkUMh | M/S Raj Construction, Aurangabad |  |  |  | 102.34 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 46.31
47 | SSS-295 | vkSjaxkckn | xksg |  | 1 | e/; fo¦ky;] ?kkVks | MS Om Enterprises |  |  |  | 204.57 |  |  | 15 Months | 1
[5 empty] | 2 | e/; fo¦ky;] 'ks[kiqjk | [9 empty] | 1
48 | SSS-296 | vkSjaxkckn |  |  | 1 | e/; fo¦ky;] rqjrk | Bhole Shankar Construction pvt Ltd,aurangabad |  |  |  | 104.08 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 25.12
49 | SSS-297 | tgkukckn | dkdks |  | 1 | mRØfer e/; fo¦ky;] nso/kjk | M/S Uma Shankar & Co,Patna-7 |  |  |  | 204.22 |  |  | 15 Months | [7 empty] | 1 |  |  | 63.07
[5 empty] | 2 | mRØfer e/; fo¦ky;] mÙkjlsjFkq | [8 empty] | 1 | [10 empty] | Land not available
50 | SSS-298 | tgkukckn | e[knqeiqj |  | 1 | mRØfer e/; fo¦ky;] mnwZ eykBh | M/s shree krishna Engineering Works,Jehanabad |  |  |  | 102.6 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 9.58
51 | SSS-299 | tgkukckn | eksnuxat |  | 1 | e/; fo¦ky;] oSuk | Rajesh Kumar |  | ,C/o shiva Hardware,Patna |  | 101.83 |  |  | 15 Months |  |  | 1
52 | SSS-300 | tgkukckn | gqyklxat |  | 1 | e/; fo¦ky;] dsmj | Maa Sherawali Construction , Patna |  |  |  | 102.47 |  |  | 15 Months |  |  |  |  | 1
53 | SSS-301 | tgkukckn | jruh |  | 1 | e/; fo¦ky;] ?kstu | Kaushlendra Kumar |  |  |  | 408.76 |  |  | 15 Months | [7 empty] | 1 |  |  | 170.24
[5 empty] | 2 | mRØfer e/; fo¦ky;] iaMkSy | [15 empty] | 1
[5 empty] | 3 | mRØfer e/; fo¦ky;] tgk¡xhjiqj | [15 empty] | 1
[5 empty] | 4 | mRØfer e/; fo¦ky;] c<srk | [10 empty] | 1
54 | SSS-302 | tgkukckn | tgkukckn |  | 1 | mRØfer e/; fo¦ky;] /kqfj;k | M/s Shree Krishna Engineering |  |  |  | 102.04 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 27.35
55 | SSS-452 | ukoknk | jtkSyh | 1 | 1 | e/; fo¦ky;] fljSyk | Mahnar Infratech Pvt. Ltd,9771410513 |  |  |  | 105-28 | [6 empty] | 1 | [6 empty] | 15.92
56 | SSS-453 | ukoknk | fljnyk | 1 | 1 | e/; fo¦ky;] pkScs | SUJAY BHAN SINGH,9473297677 |  |  |  | 106.4 |  |  |  | 1
57 | SSS-454 | ukoknk | dksvkdksy | 1 | 1 | e/; fo¦ky;] /keku | MS ANANYA CONSTRUCTION,9334745882 |  |  |  | 210.56 | [6 empty] | 1 | [6 empty] | 30.65
|  |  |  | 2 | 2 | mRØfer e/; fo¦ky;] dkyqvkckj | [11 empty] | 1
58 | SSS-457 | vkSjaxkckn | gliqjk | 1 | 1 | e/; fo¦ky;] vfg;kiqj | DARSHITA BUILDER AND DEVELOPERS PVT LTD,09801134120 |  |  |  | 103.05 |  |  |  | 1
59 | SSS-458 | vkSjaxkckn | jQhxat | 1 | 1 | e/; fo¦ky;] flMqyh njxkg | MS GUPTA DHAM CONSTRUCTION, 9661648500 |  |  |  | 206.09 |  |  |  | 1 | [9 empty] | 29.85
|  |  |  | 2 | 2 | e/; fo¦ky;] yksgjk | [11 empty] | 1
60 | SSS-459 | vkSjaxkckn | uohxat | 1 | 1 | e/; fo¦ky;] Fksxks | SHAMSHER KUMAR |  |  |  | 208.72 |  |  |  | 1
|  |  | uohxat | 2 | 2 | e/; fo¦ky;] daMh | [8 empty] | 1
61 | SSS-460 | vkSjaxkckn | nso | 1 | 1 | e/; fo¦ky; nykjs | TRADEWELL CONSTRUCTION PVT LTD,9801181475 |  |  |  | 102.8 |  |  |  | 1
62 | SSS-461 | vkSjaxkckn | enuiqj | 1 | 1 | e/; fo¦ky;] Nkyhnksgj | Tender Process |  |  |  | 102.71
63 | SSS-462 | vkSjaxkckn | xksg | 1 | 1 | e/; fo¦ky;] egnhuiqj | Tender Process |  |  |  | 102.74
64 | SSS-463 | x;k | gfFk;kok¡ | 1 | 1 | e/; fo¦ky;] egdkj | KAUSHLENDRA KUMAR,8409113501 |  |  |  | 104.4 |  |  |  | 1 | [9 empty] | 64.79
65 | SSS-464 | x;k | xq:vk | 1 | 1 | e/; fo¦ky;] ljS;kVkM+ | SANJAY KUMAR SINGH, 9973456006 |  |  |  | 102.41 | [7 empty] | 1 | [5 empty] | 21.53
66 | SSS-465 | x;k | bekexat | 1 | 1 | e/; fo¦ky; cgsM+k pkSHkkj | SANJU KUMARI, 9430676434 |  |  |  | 209.14 |  |  |  | 1
|  |  |  | 2 | 2 | e/; fo¦ky;] njHkaxk | [8 empty] | 1
67 | S.S.S-356 | vkSjaxkckn | xksg | 1 | 1 | e/; fo¦ky;] cUns;k | MS OM ENTERPRISESMS |  |  |  | 215.6 | [7 empty] | 1 | [5 empty] | 23.02
|  |  |  | 2 | 2 | e/; fo¦ky;] csuh dSFkh | [10 empty] | 1
| Total No. of Schools |  |  |  | 116 | [5 empty] | 10086.25 |  |  |  | 24 | 2 | 14 | 13 | 7 | 25 | 3 | 22 | 0 | 0 | 2272.87

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- BHAGALPUR | [22 empty] | Date:-28.02.2015
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-230 | Hkkxyiqj | [kjhd | 1 | e/; fo¦ky;] vykyiqj | Tender Process |  |  | 209.89 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cxMh
2 | SSS-231 | Hkkxyiqj | bLekbZyiqj | 1 | e/; fo¦ky;] jkeuxj | Tender Process |  |  | 210.17 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eksrh Vksyk
3 | SSS-232 | Hkkxyiqj | dgyxkao | 1 | e/; fo¦ky;] dVksfj;k | Daya Nand singh, 3-lp-2, Barari |  |  | 103.88 |  |  | 15 Months | [7 empty] | 1 |  |  | 65.78
4 | SSS-233 | Hkkxyiqj | fcgiqj | 1 | e/; fo¦ky;] vkSfy;kokn | M/S Sai Highway & Builders pvt ltd, Patna |  |  | 106.37 |  |  | 15 Months | [7 empty] | 1 |  |  | 45.97
5 | SSS-234 | Hkkxyiqj | ihjiSarh | 1 | e/; fo¦ky;] clariqj | Baba bateshwar Construction Pvt.Ltd,Bhagalpur |  |  | 415.75 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 163.49
|  |  |  | 2 | e/; fo¦ky;] nmok | [7 empty] | 1 | [10 empty] | Water loging
|  |  |  | 3 | e/; fo¦ky;] Kkuorh Viqvk | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] ij'kqjkeiqj | [13 empty] | 1
6 | SSS-235 | Hkkxyiqj | jaxjk pkSd | 1 | e/; fo¦ky;] Hkokuhiqj Vksyk | Tender Process |  |  | 211.53 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cfu;k
7 | SSS-236 | Hkkxyiqj | 'kkgdqaM | 1 | e/; fo¦ky;] oklqnsoiqj | Kuhu Construction |  |  | 317.04 |  |  | 15 Months | [7 empty] | 1 |  |  | 193.22
|  |  |  | 2 | e/; fo¦ky;] iap:[kh | [14 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] HkaMkjou | [14 empty] | 1
8 | SSS-237 | Hkkxyiqj | lckSj | 1 | e/; fo¦ky;] cStukFkiqj | Shyam Sundar Yadav,Banka |  |  | 104.44 |  |  | 15 Months |  |  |  | 1
9 | SSS-238 | Hkkxyiqj | lUgkSyk | 1 | e/; fo¦ky;] rsykaS/kk | Tender Process |  |  | 104.06 |  |  | 15 Months
10 | SSS-239 | Hkkxyiqj | ukFkuxj | 1 | e/; fo¦ky;] fo'kuiqj | Tender Process |  |  | 104.28 |  |  | 15 Months
11 | SSS-240 | Hkkxyiqj | ukjk;.kiqj | 1 | e/; fo¦ky;] jk;iqj | Sudhir Prasad, Jamui |  |  | 319.01 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 22.6
|  |  |  | 2 | e/; fo¦ky;] Hkokuhiqj | [7 empty] | 1 | [10 empty] | No Drawing
|  |  |  | 3 | dU;k e/; fo¦ky;] eFkqjkiqj | [8 empty] | 1
12 | SSS-241 | Hkkxyiqj | uoxfN;k | 1 | e/; fo¦ky;] txriqj | Dharmendra Kumar Choudhary, Bhagalpur |  |  | 210.53 |  |  | 15 Months |  |  | 1 | [7 empty] | 74.97
|  |  |  | 2 | e/; fo¦ky;] [kSjiqj | [11 empty] | 1
13 | SSS-242 | Hkkxyiqj | xksikyiqj | 1 | e/; fo¦ky;] edUniqj | M/S Daya Ram Singh, Begusarai |  |  | 105.23 |  |  | 15 Months | [9 empty] | 1 | 98.56
14 | SSS-243 | Hkkxyiqj | xksikyiqj | 1 | e/; fo¦ky;] ipxfN;k | Karnawati Builders Pvt. Ltd, Samastipur |  |  | 208.09 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] fMegk | [7 empty] | 1
15 | SSS-244 | Hkkxyiqj | xksjkMhg | 1 | e/; fo¦ky;] fo'kuiqj ftPNksa | Lalan Kumar Radha Rani Sinha road, Bhagalpur |  |  | 626.7 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 224.05
|  |  |  | 2 | e/; fo¦ky;] lksuwMhg | [13 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] eksguiqj | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] xaxkdjgfj;k | [13 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] eqDrkiqj | [12 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] dk'khy | [11 empty] | 1
16 | SSS-245 | Hkkxyiqj | /kkSjS;k | 1 | e/; fo¦ky;] vLlh edSrk | CHITRAGUPTA CONSTRUCTION PVT LTD,9431258544, 9931823577 |  |  | 312.61 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] pUnkMhg | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] eFkqjkiqj | [10 empty] | 1
17 | SSS-246 | ckadk | ckadk | 1 | izksŒ e/; fo¦ky;] vejiqj | Amarpur Construction Co. Pvt. Ltd, Banka |  |  | 105.34 |  |  | 15 Months | [8 empty] | 1 |  | 65.16
18 | SSS-247 | ckadk | ckjkgkV | 1 | izksŒ e/; fo¦ky;] egqvk | Bricks Liner Infrastructure |  |  | 104.91 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 64.2
19 | SSS-248 | ckadk | ckSalh | 1 | izksŒ e/; fo¦ky;] cHkuxkek | Dilendra Prasad Singh, jamui |  |  | 209.98 |  |  | 15 Months |  | 1 | [8 empty] | 32.3
|  |  |  | 2 | izksŒ e/; fo¦ky;] >ifu;ka | [12 empty] | 1
20 | SSS-249 | ckadk | csygj | 1 | e/; fo¦ky;] Jhuxj | Rajesh kumar Singh,Jamui |  |  | 108.09 |  |  |  | 1
21 | SSS-250 | ckadk | dVksfj;k | 1 | e/; fo¦ky;] bukjkoj.k | Dilendra Prasad Singh, jamui |  |  | 215.33 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 25.16
|  |  |  | 2 | izksŒ e/; fo¦ky;] Nkrkdq:e | [11 empty] | 1
22 | SSS-251 | ckadk | jtkSu | 1 | izksŒ e/; fo¦ky;] vyhiqj /kfu;ka | Tender Process |  |  | 209 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] y'kdjh
23 | SSS-252 | ckadk | QqYyhMwej | 1 | e/; fo¦ky;] dksfM+;k bukjkoj.k | M/s Satya Narayan singh, deoghar |  |  | 429.27 |  |  | 15 Months | 1
|  |  |  | 2 | izksŒ e/; fo¦ky;] /kkok dU;k | [7 empty] | 1
|  |  |  | 3 | izksŒ e/; fo¦ky;] lkniqj | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] /kudqfM+;k | [7 empty] | 1
24 | SSS-253 | ckadk | vejiqj | 1 | izksŒ e/; fo¦ky;] eSuek | M/s Tribhuwan prasad Singh & Co,Jamui |  |  | 210.39 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 50.12
|  |  |  | 2 | xjhciqj mjnq | M/s Tribhuwan prasad Singh & Co,Jamui | [5 empty] | 15 Months |  |  | 1
25 | SSS-384 | ck¡dk | pkUnu | 1 | mRØfer e/; fo¦ky; Qqygjk | RETENDER |  |  | 217.16
|  |  |  | 2 | e/; fo¦ky;] Hkksjk cktkj
26 | SSS-385 | ck¡dk | csygj | 1 | mRØfer e/; fo¦ky;] Vsaxjk | RETENDER |  |  | 216.18
|  |  |  | 2 | mRØfer e/; fo¦ky;] csyk fctgjk
27 | SSS-410 | Hkkxyiqj | ihjiSrh | 1 | mRØfer e/; fo¦ky;] ckcqiqj | RETENDER |  |  | 103.94
| Total No. of Schools |  |  | 55 |  |  |  |  | 5261.89 |  |  |  | 9 | 2 | 4 | 4 | 4 | 5 | 5 | 5 | 1 | 1 | 1125.58

## Munger
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- MUNGER | [21 empty] | Date:-28.02.2015
Name & contact no. of EE :-Surendra Kumar (9939599803), Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-158 (A) | eqaxsj | gŒ [kM+xiqj | 1 | e/; fo¦ky;] lenk gfFk;k | Bricks Liner Infra. |  |  | 420.22 |  |  | 15 Months | 1
2 | SSS-158 (B) |  |  | 1 | e/; fo¦ky;] yMqbZ | M/S Tribhuwan Prasad Singh,Jamui | [8 empty] | 1
3 | SSS-158 (C) |  |  | 1 | e/; fo¦ky;] dUnuh | Tender Process
4 | SSS-158 (D) |  |  | 1 | e/; fo¦ky;] vxzg.k | Tender Process
5 | SSS-159 | eqaxsj | laxzkeiqj | 1 | e/; fo¦ky;] pUnfu;ka | Rajesh kumar Singh Sikandara,Jamui |  |  | 106.58 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 37.16
6 | SSS-160 | eqaxsj | rkjkiqj | 1 | e/; fo¦ky;] fcgek | Rajendra Kumar |  |  | 316.55 |  |  | 15 Months |  |  | 1 | [7 empty] | 43.08
|  |  |  | 2 | e/; fo¦ky;] jkeiqj | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] [kqfV;k | [9 empty] | 1
7 | SSS-161 | eqaxsj | tekyiqj | 1 | e/; fo¦ky;] ckspkgh | Puja Kumari |  |  | 104.22 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 20.39
8 | SSS-162 | eqaxsj | vljxat | 1 | e/; fo¦ky;] eklqexat | Rajesh kumar Singh Sikandara,Jamui |  |  | 105.1 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 13.67
9 | SSS-163 | eqaxsj | VsfV;kcEcj | 1 | e/; fo¦ky;] Hkquk | Puja Kumari, Munger |  |  | 211.8 |  |  | 15 Months | [10 empty] | 17.42
|  |  |  | 2 | e/; fo¦ky;] /kkSjh | [7 empty] | 1
10 | SSS-164 | 'ks[kiqjk | vfj;kjh | 1 | mRØfer e/; fo¦ky;] djdh | Anil Kumar Singh |  |  | 311.86 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 168.64
|  |  |  | 2 | mRØfer e/; fo¦ky;] csyNh | [13 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] o:.kk | [12 empty] | 1
11 | SSS-165 | 'ks[kiqjk | psojk | 1 | e/; fo¦ky;] Nfr;kjk | Anil Kumar Singh,Sheikhpura |  |  | 104.2 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 19.15
12 | SSS-166 | 'ks[kiqjk | 'ks[kiqjk | 1 | e/; fo¦ky;] cSfj;k ch?kk | Ashok Kumar ,Sheikhpura |  |  | 103.69 |  |  | 15 Months |  |  | 1 | [7 empty] | 9.06
13 | SSS-167 | osxwljk; | [kksnkoUriqqj | 1 | mRØfer e/; fo¦ky;] elqjkt | M/S Balram Kumar |  |  | 214.48 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 172.11
|  |  |  | 2 | mRØfer e/; fo¦ky;] eq'kgjh | [10 empty] | 1
14 | SSS-168 | csxwljk; | c[kjh | 1 | e/; fo¦ky;] c[kjh | M/S BalramKumar |  |  | 214.48 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 188.73
|  |  |  | 2 | e/; fo¦ky;] pDdjehM] unSy | [15 empty] | 1
15 | SSS-169 | csxwljk; | cjkSuh | 1 | e/; fo¦ky;] fetkZiqj pkWn | Budha infrastructure Pvt. Ltd. |  |  | 520.63 |  |  | 15 Months | 1 | [9 empty] | 116.92 | No Land
|  |  |  | 2 | e/; fo¦ky;] Hkouxkek | [9 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] pdh;k iquokZl | [7 empty] | 1 | [10 empty] | Local Problem
|  |  |  | 4 | mRØfer e/; fo¦ky;] vlqjkjh | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ds'kos | [7 empty] | 1 | [10 empty] | No Land
16 | SSS-170 | osxwljk; | cjkSuh | 1 | e/; fo¦ky;] iijkSj | M/s Daya Ram singh |  |  | 103.94 |  |  | 15 Months | [9 empty] | 1 | 97.62
17 | SSS-171 | osxwljk; | csxwljk; | 1 | mRØfer e/; fo¦ky;] dqlekSr | Saheb Singh Construction |  |  | 104.7 |  |  | 15 Months | 1 | [10 empty] | Land Problem
18 | SSS-172 | osxwljk; | efVgkuh | 1 | e/; fo¦ky;] nfj;kiqj | M/S Daya Ram Singh, Begusarai |  |  | 210.48 |  |  | 15 Months | [8 empty] | 1 |  | 176.26
|  |  |  | 2 | e/; fo¦ky;] xksnjxkek | [16 empty] | 1
19 | SSS-173 | osxwljk; | Hkxokuiqj | 1 | e/; fo¦ky;] rktiqj | M/S Brij Deo Singh, Begusarai |  |  | 104.62 |  |  | 15 Months | [7 empty] | 1 |  |  | 45.65
20 | SSS-174 | osxwljk; | lkgsciqj deky | 1 | e/; fo¦ky;] lkniqj | M/S Imperial Foundation Pvt.Ltd. Kankarbag |  |  | 534.25 |  |  | 15 Months | 1 | [9 empty] | 214.41 | Land Problem
|  |  |  | 2 | e/; fo¦ky;] jgqvk | [15 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jlyiqj | [7 empty] | 1 | [10 empty] | Land Problem
|  |  |  | 4 | e/; fo¦ky;] nhgk | [14 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] j?kqukFkiqj | [9 empty] | 1 | [8 empty] | Land Problem
21 | SSS-175 | osxwljk; | MaMkjh | 1 | e/; fo¦ky; eksgCck* | Ms. Arpana Construction Begusarai |  |  | 323.47 |  |  | 15 Months |  |  | 1 | [7 empty] | 33.34 | School name change with Ref.No. 1815 NIT-45 (Retender)
|  |  |  | 2 | e/; fo¦ky;] jktksiqj | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fllkSuh | [12 empty] | 1
22 | SSS-176 | osxwljk; | rs?kM+k | 1 | e/; fo¦ky;] vdkgk jkeiqj | M/S Chandra Shekhar Singh & Co.Bihat,Begusarai |  |  | 312.97 |  |  | 15 Months | [8 empty] | 1 |  | 88.11
|  |  |  | 2 | mRØfer e/; fo¦ky;] vks>k Vksy | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fi<+kSyh | [7 empty] | 1 | [10 empty] | Land Problem
23 | SSS-177 (A) | osxwljk; | ukodksBh | 1 | mRØfer e/; fo¦ky;] pdeqt¶Qj | Ganga Yamuna Cons. |  |  | 209.47 |  |  | 15 Months |  |  | 1
24 | SSS-177 (B) |  |  | 1 | dU;k e/; fo¦ky;] igljk | Tender Process
25 | SSS-178 | osxwljk; | x<+iqjk | 1 | e/; fo¦ky;] eNjkgk] jtkSj | M/Raja Enterprises & Co.,Begusarai |  |  | 320.87 |  |  | 15 Months |  | 1 | [8 empty] | 131.23
|  |  |  | 2 | mRØfer e/; fo¦ky;] dksfj;ek | [12 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] çk.kiqj fgUnh | [14 empty] | 1
26 | SSS-179 | y[khljk; | cM+fg;k | 1 | e/; fo¦ky;] izrkiiqj | Ravi Bhushan Singh, Alawaalpur |  |  | 206.21 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] y{ehiqj] lgtkniqj | [7 empty] | 1
27 | SSS-180 | y[khljk; | lw;Zx<+k dtjk f'k{kkapy | 1 | e/; fo¦ky;] ?kks?kh cfj;kjiqj | M/S Tribhuwan Prasad Singh, Jamui |  |  | 311.03 |  |  | 15 Months |  |  | 1 | [7 empty] | 65.91
|  |  |  | 2 | e/; fo¦ky;] uodkMhg mjSu | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dtjk | [13 empty] | 1
28 | SSS-181 (A) | y[khljk; | pkuu | 1 | mRØfer e/; fo¦ky;] fr;kpd | Stanely Engineering |  |  | 206.35 |  |  | 15 Months | 1
29 | SSS-181 (B) |  |  | 1 | e/; fo¦ky;] Hkkanj | Tender Process
30 | SSS-182 | y[khljk; | pkuu | 1 | e/; fo¦ky;] cUuw cxhpk | Dilendra Prasad Singh, Jamui |  |  | 206.92 |  |  | 15 Months | 1 | [9 empty] | 13.06
|  |  |  | 2 | mRØfer e/; fo¦ky;] clqvkpd | [10 empty] | 1
31 | SSS-183 | y[khljk; | y[khljk; | 1 | mRØfer e/; fo¦ky;] [kxkSj | Rama Construction |  |  | 102.53 |  |  | 15 Months | [7 empty] | 1 |  |  | 45.46
32 | SSS-184 | teqbZ | [kSjk | 1 | e/; fo¦ky;] :ikosy | M/S Satyanarayan Singh, Deoghar |  |  | 417.75 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] /kjeiqj | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] fVfg;kfnukjh | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] dSM+kdknks | [9 empty] | 1
33 | SSS-185 | teqbZ | >k>k | 1 | e/; fo¦ky;] iSjxkgk | Rajesh Kumar Singh, Jamui |  |  | 317.07 |  |  | 15 Months |  | 1 | [8 empty] | 36.19
|  |  |  | 2 | mRØfer e/; fo¦ky;] lqUnjh VkaM | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ps;u | [10 empty] | 1
34 | SSS-186 | teqbZ | cjgV | 1 | e/; fo¦ky;] yk[ks; | Sudhir Prasad,Jamui |  |  | 208.66 |  |  | 15 Months | 1 | [9 empty] | 14.77
|  |  |  | 2 | e/; fo¦ky;] iaps'ojh | [9 empty] | 1
35 | SSS-187 | teqbZ | fldUnjk | 1 | e/; fo¦ky;] lcych?kk | Dilendra Prasad Singh, jamui |  |  | 208.47 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 55.64
|  |  |  | 2 | e/; fo¦ky;]uodkMhg | [12 empty] | 1
36 | SSS-188 | teqbZ | pdkbZ | 1 | e/; fo¦ky;] /keukMhg | M/S Satyanarayan Singh, Deoghar |  |  | 873.92 |  |  | 15 Months |  |  | 1 | [7 empty] | 48.99
|  |  |  | 2 | e/; fo¦ky;] flejk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] njok | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] ejgh clcqfV;k | [10 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ikaMsMhg | [10 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] Bk<+h | [7 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] ek/kksiqj | [7 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] flefj;k | [10 empty] | 1
37 | SSS-189 | teqbZ | teqbZ | 1 | e/; fo¦ky;] izrkiiqj | M/S tribhuwan Prasad Singh,Jamui |  |  | 103.51 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 28.15
38 | SSS-190 | teqbZ | y{ehiqj | 1 | mRØfer e/; fo¦ky;] flaf?k;k | Mukesh Kumar |  |  | 104.9 |  |  | 15 Months |  |  | 1
39 | SSS-191 | [kxfM+;k | csynkSj | 1 | e/; fo¦ky;] cksfcy Qqyofj;k | Retender |  |  | 435.3 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] ekyh
|  |  |  | 3 | e/; fo¦ky;] ldjksgj
|  |  |  | 4 | e/; fo¦ky;] ipkSr
40 | SSS-192 | [kxfM+;k | ekulh | 1 | e/; fo¦ky;] veuh | Krishna Kumar Singh, khagaria |  |  | 106.17 |  |  | 15 Months | [7 empty] | 1 |  |  | 35.23
41 | SSS-193 | [kxfM+;k | pkSFke | 1 | e/; fo¦ky;] jksfg;kj | Puja kumari,Munger |  |  | 106.85 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 29.53
42 | SSS-379 | [kxfM+;k | ekulh | 1 | e/; fo¦ky; vjs;k | Retender |  |  | 106.17
43 | SSS-380 | [kxfM+;k | ijoÙkk | 1 | e/; fo¦ky; cUnsgjk | Retender |  |  | 319.7
|  |  |  | 2 | e/; fo¦ky; dcSyk
|  |  |  | 3 | e/; fo¦ky;] [khjk Mhg
44 | SSS-381 | [kxfM+;k | xksxjh | 1 | e/; fo¦ky; jkeiqj | Retender |  |  | 530.85
|  |  |  | 2 | e/; fo¦ky; cM+h iSdkr
|  |  |  | 3 | e/; fo¦ky; enkjiqj
|  |  |  | 4 | e/; fo¦ky; u'dhiqj
|  |  |  | 5 | e/; fo¦ky; nsoBk
45 | SSS-382 | [kxfM+;k | pkSFke | 1 | e/; fo¦ky; /kuNkj cqPpk | Retender |  |  | 106.85
46 | SSS-383 | [kxfM+;k | [kxfM+;k | 1 | e/; fo¦ky; dkf'keiqj | Retender |  |  | 108.82
47 | SSS-386 | csxwljk; | ukodkVh | 1 | e/; fo¦ky;] vdgk jfjvkSuk | M/S AASTHA AND SAUMYA CONSTRUCTION,9570856865 |  |  | 104.74 | [5 empty] | 1
48 | SSS-387 | csxwljk; | [kksnkoUriqj | 1 | mnwZ e/; foZ¦ky;] rq:Yykgiqj | M/S AASTHA AND SAUMYA CONSTRUCTION,9570856865 |  |  | 107.24 |  |  |  | 1
49 | SSS-388 | csxwljk; | NkSMkgh | 1 | e/; fo¦ky;] xhjhMhg | Retender |  |  | 104.7
50 | SSS-400 | eqaxsj | tekyiqj | 1 | e/; fo¦ky;] bUnz:[k | Retender |  |  | 104.22
51 | SSS-401 | eqaxsj | eqaxsj lnj | 1 | e/; fo¦ky;] pjkSu | Retender |  |  | 104.25
52 | SSS-402 | eqaxsj | BsVh;k cEcj | 1 | e/; fo¦ky;] eksguiqj | Retender |  |  | 105.9
53 | SSS-403 | eqaxsj | /kjgjk | 1 | dU;k e/; fo¦ky;] f'kodqaM | Retender |  |  | 105.23
54 | SSS-445 | teqÃ | teqÃ | 1 | e/; fo¦ky;] cqdkj | SUDESH KUMAR AND CO CONST PVT LTD |  |  | 310.53 |  |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] lksuis | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] uohuxj | [7 empty] | 1
55 | SSS-446 | teqÃ | cjgV | 1 | e/; fo¦ky;] xqxqyMhg | BRAJESH KUMAR SINGH |  |  | 208.66 |  |  |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] nsopd | [7 empty] | 1
56 | SSS-447 | teqÃ | [kSjk | 1 | e/; fo¦ky;] pkuuokj | Retender |  |  | 208.86
|  |  |  | 2 | e/; fo¦ky;] Á/kkupd
57 | SSS-448 | teqÃ | lksuks | 1 | e/; fo¦ky;] cfV;k | JAY KISHOR SINGH |  |  | 211.2 |  |  |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] jtkSy | [7 empty] | 1
58 | SSS-449 | teqÃ | >k>k | 1 | e/; fo¦ky;] fleqyryk | Retender |  |  | 317.07
|  |  |  | 2 | e/; fo¦ky;] ckftyk
|  |  |  | 3 | e/; fo¦ky;] cq/kh[kj
59 | SSS-450 | teqÃ | pdkÃ | 1 | e/; fo¦ky;] cksub | Retender |  |  | 214.24
|  |  |  | 2 | e/; fo¦ky;] csUnzk
60 | SSS-467 | y[khljk; | pkuu | 1 | mRØfer e/; fo¦ky;] dqanj | Retender |  |  | 103.53
61 | SSS-468 | y[khljk; | lw;Zx<+k | 1 | e/; fo¦ky;] jlqyiqj | Retender |  |  | 207.34 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] dfueksg
62 | SSS-469 | 'ks[kiqjk | 'ks[kksiqj | 1 | e/; fo¦ky;] i{kh | MS Dayanand Prasad Sinha and Co |  |  | 103.68 |  |  | 15 Months | 1
63 | S.S.S-358 | 'ks[kiqjk | 'ks[kiqjk | 1 | e/; fo¦ky;] iSu | GOPAL KUMAR 9234334864 |  |  | 110.35 |  |  | 15 Months | 1 | [9 empty] | 27.49
64 | S.S.S-378 | y[khljk; | fiifj;k | 1 | mRØfer e/; fo¦ky;] fiifj;k fn;kjk ¼fo¦ky; ds LokfeRo esa 50 fMlfey ijrh Hkwfe gksus ds 'krZ ds lkFk½ | Retender |  |  | 109.62 |  |  | 15 Months | 1
| Total No. of Schools |  |  | 122 |  |  |  |  | 12887.97 |  |  |  | 32 | 2 | 17 | 11 | 2 | 9 | 3 | 5 | 4 | 2 | 1993.37
School name change with Ref.No. 1815 NIT-45 (Retender) *
mRØfer e/; fo¦ky;] u;k Vksyk] dY;k.kiqj @ e/; fo¦ky; eksgCck*

## Kosi
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- KOSI | [21 empty] | Date:-28.02.2015
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-303 | lgjlk | cuek bVgjh | 1 | e/; fo¦ky;] ikjlcUuh | M/S ALAM CONSTRUCTION |  |  | 109.52 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 18.28
2 | SSS-304 | lgjlk | dgjk | 1 | e/; fo¦ky;] lqfyaUnkckn | Jiwan Laxmi Construction Pvt Ltd, Patna |  |  | 110.01 |  |  | 15 Months | [8 empty] | 1 |  | 73.11
3 | SSS-305 | lgjlk | efg"kh | 1 | e/; fo¦ky;] dUnkgk | M/S ALAM CONSTRUCTION |  |  | 441.01 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 56.85
|  |  |  | 2 | e/; fo¦ky;] Fkuokj | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] rsygj | [8 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] eaxjkSuh | [9 empty] | 1
4 | SSS-306 | lgjlk | flejh | 1 | e/; fo¦ky;] osyokjk | Archana Contractors Pvt Ltd, Patna |  |  | 110.44 |  |  | 15 Months | [7 empty] | 1 |  |  | 73.03
5 | SSS-307 | lgjlk | flejh c[fr;kjiqj | 1 | e/; fo¦ky;] dFkMqej | Samrat Construction |  |  | 109.38 |  |  | 15 Months | 1
6 | SSS-308 | lgjlk | irj?kV | 1 | e/; fo¦ky;] fd'kuiqj | M/S ALAM CONSTRUCTION |  |  | 220.38 | [8 empty] | 1 |  |  |  |  | 50.46
|  |  |  | 2 | e/; fo¦ky;] iLrij | [6 empty] | 15 Months | [5 empty] | 1
7 | SSS-309 | lgjlk | lksuo"kkZ | 1 | e/; fo¦ky;] xksnjke | M/S Alam Construction, Madhepura |  |  | 438.57 |  |  | 15 Months | 1 | [9 empty] | 50.93
|  |  |  | 2 | e/; fo¦ky;] dksik | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] [ktqjkgk | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] vkjlh | [10 empty] | 1
8 | SSS-310 | lgjlk | lrj dVS;k | 1 | e/; fo¦ky;] fcgjk | Ashok Kumar |  |  | 110.56 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 76.99
9 | SSS-311 | lgjlk | ly[kqvk | 1 | e/; fo¦ky;] vyuh | M/s Krishna Construction,Saharsa |  |  | 220.7 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 107.08
|  |  |  | 2 | e/; fo¦ky;] [kkspjnsok | [14 empty] | 1
10 | SSS-312 | lgjlk | uogêk | 1 | dU;k e/; fo¦ky;] dkfleiqj | Bholi Nath Roy |  |  | 111.2 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 18.42
11 | SSS-313 | lqikSy | clariqj | 1 | e/; fo¦ky; cuSyhiÍh | Satendra Kumar Construction Pvt. Ltd., Patna |  |  | 920.32 |  |  | 15 Months |  | 1 | [8 empty] | 88.41
|  |  |  | 2 | e/; fo¦ky;] lenk | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fueZyh | [11 empty] | 1
|  |  |  | 4 | e/; fo¦ky; <k<k | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky; gn;uxj | [8 empty] | 1
|  |  |  | 6 | e/; fo¦ky; iVsjok | [10 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] ijlk mnwZ | [9 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] fo'kuiqj pkS/kjh | [11 empty] | 1
12 | SSS-314 | lqikSy | çrkixat | 1 | e/; fo¦ky;] Vsdquk | M/S Sri Krishna Construction.Co.,C/Osudhila Swami Sdan,Gopalgang |  |  | 113.98 |  |  | 15 Months | [7 empty] | 1 |  |  | 71.92
13 | SSS-315 (A) | lqikSy | f=os.khxat | 1 | e/; fo¦ky;] xksugk | Akash Kumar khaijpura |  |  | 563.29 |  |  | 15 Months | 1
14 | SSS-315 (B) |  |  | 1 | e/; fo¦ky; ijlkgh gkV | Madan Kumar Singh, Supaul/95721030516 | [6 empty] | 1
15 | SSS-315 (C) |  |  | 1 | e/; fo¦ky;] ik.Ms;iÍh | Akash Kumar Khajpura Post BV | [6 empty] | 1
16 | SSS-315 (D) |  |  | 1 | e/; fo¦ky;] fejtkok | Akash Kumar khaijpura | [6 empty] | 1
17 | SSS-315 (E) |  |  | 1 | e/; fo¦ky;] ekSu | Koshitech Devloper India Pvt.Ltd | [6 empty] | 1
18 | SSS-316 | lqikSy | fd'kuiqj | 1 | e/; fo¦ky;] deyngk | Dhiraj Kumar agarwal,Supaul |  |  | 113.01 |  |  | 15 Months | 1
19 | SSS-317 | lqikSy | fiijk | 1 | e/; fo¦ky;] clqyh | Madan Kumar Singh,Supaul |  |  | 112.37 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 60.72
20 | SSS-318 | lqikSy | jk?kksiqj | 1 | e/; fo¦ky;] jkeiqjdyk | M/s Durga Pratap Singh,Kidwaipuri,Patna |  |  | 698.88 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 247.76
|  |  |  | 2 | e/; fo¦ky; dkfj;kiÍh nsohiqj | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky; gqykl | [14 empty] | 1
|  |  |  | 4 | e/; fo¦ky; ckSjkgk] fgUnh | [7 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] eksfriqj | [13 empty] | 1
|  |  |  | 6 | jkeukFk e/; fo¦ky;] xkSliqj | [13 empty] | 1
21 | SSS-319 | lqikSy | ljk;x<+ | 1 | e/; fo¦ky;] fiijk[kqnZ | Kailash Prasad ydav,Supaul |  |  | 227.07 |  |  | 15 Months |  |  | 1 | [7 empty] | 59.87
|  |  |  | 2 | e/; fo¦ky;] >Yyk Mqejh | [11 empty] | 1
22 | SSS-320 | lqikSy | ljk;x<+&HkifV;kgh | 1 | e/; fo¦ky;] ykyxat | Dhiraj Kumar agarwal,Supaul |  |  | 113.92 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 57.48
23 | SSS-321 | lqikSy | lqikSy | 1 | e/; fo¦ky;] cSjks | Ashok Kumar,Saharsa |  |  | 333.66 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 197.66
|  |  |  | 2 | dU;k e/; fo¦ky;] ckM+k | [14 empty] | 1
|  |  |  | 3 | eqjyh euksgj e/; fo¦ky; cjSy | [14 empty] | 1
24 | SSS-322 | lqikSy | Nkrkiqj | 1 | e/; fo¦ky;] jrulkj | Satendra Kumar Construction Pvt. Ltd. |  |  | 567.02 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 51.56
|  |  |  | 2 | e/; fo¦ky;] dVgh | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fxfj/kjiÍh | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] egnhiqj | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] 'ks[kVksyk y{ehfu;ka | [7 empty] | 1
25 | SSS-323 | e/ksiqjk | dqekj[kaM | 1 | e/; fo¦ky;] csykjh | M/S Alam Construction, Madhepura |  |  | 683.22 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 163.39 | EXCAVATION WORK IN PROGRESS
|  |  |  | 2 | e/; fo¦ky;] j?kqfu;k | [11 empty] | 1 | [6 empty] | EXCAVATION WORK STOPPED DUE TO WATER LOGGING
|  |  |  | 3 | e/; fo¦ky; jhrk | [11 empty] | 1 | [6 empty] | TIE BEAM LEVEL WORK IN PROGRESS
|  |  |  | 4 | mRØfer e/; fo¦ky;] [kWwVgk jtsS | [11 empty] | 1 | [6 empty] | EXCAVATION WORK STOPPED DUE TO WATER LOGGING
|  |  |  | 5 | mRØfer e/; fo¦ky;] bljk;u xksB | [10 empty] | 1 | [7 empty] | NOT STARTED
|  |  |  | 6 | mRØfer e/; fo¦ky;] lqUnjuxj ¼v0tk0½ | [10 empty] | 1 | [7 empty] | EXCAVATION WORK IN PROGRESS
26 | SSS-324 | e/ksiqjk | eqjyhxat | 1 | e/; fo¦ky; frudksuek | Saliesh Kumar SIngh |  |  | 221.29 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfe.r e/; fo¦ky;] jtuh fefYyd | [7 empty] | 1
27 | SSS-325 | e/ksiqjk | eqjyhxat | 1 | e/; fo¦ky;] jruiÍh] Hksykgh | M/S alam Construction works & Company, Madhepura |  |  | 332.8 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 137.16
|  |  |  | 2 | e/; fo¦ky;] thrkiqj | [15 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fnX?kh | [12 empty] | 1
28 | SSS-326 (A) | e/ksiqjk | fcgkjhxat | 1 | e/; fo¦ky;] dBkSfr;k | Flexicon Engineers And Planner Private Limited |  |  | 332.51 |  |  | 15 Months | 1
29 | SSS-326 (B) |  |  | 1 | e/; fo¦ky;] y{ehiqj | Tender Process
30 | SSS-326 (C) |  |  | 1 | mRØfer e/; fo¦ky;] jkexat | Tender Process
31 | SSS-327 | e/ksiqjk | flags'oj | 1 | e/; fo¦ky;] rjgk MaMkjh | M/S alam Construction works & Company, Madhepura |  |  | 443.36 |  |  | 15 Months | [7 empty] | 1 |  |  | 244.46
|  |  |  | 2 | e/; fo¦ky;] lcSyk | [14 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] ekuiqj | [14 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] iVksjh | [14 empty] | 1
32 | SSS-328 | e/ksiqjk | mnkfd'kquxat | 1 | dchj xaxk e/; fo¦ky;] chM+hj.kiky | Chandan Kumar Singh |  |  | 221.2 |  |  | 15 Months |  |  | 1 | [7 empty] | 59.69
|  |  |  | 2 | e/; fo¦ky;] eatkSjk | [14 empty] | 1
33 | SSS-329 | e/ksiqjk | vkyeuxj | 1 | e/; fo¦ky;] fo"kiÍh | Avaneesh Enterprises, Ghaziabad |  |  | 334.29 |  |  | 15 Months | [7 empty] | 1 |  |  | 121.55
|  |  |  | 2 | e/; fo¦ky;] gfjgjiqj ctjkgk | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] difl;k | [10 empty] | 1
34 | SSS-330 | e/ksiqjk | XokyikM+k | 1 | e/; fo¦ky;] 'kkgiqj | Shailesh Kumar Singh, Madhepura |  |  | 332.41 |  |  | 15 Months | 1 | [9 empty] | 22.14
|  |  |  | 2 | e/; fo¦ky;] VsekHksyk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] [kks[klh ckM+k] jkexat | [9 empty] | 1
35 | SSS-399 | e/ksiqjk | eqjyhxat | 1 | e/; fo¦ky;] o``nkou | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED,9431685933 |  |  | 221.29 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] ijekuUniqj | [7 empty] | 1
36 | SSS-439 | lqikSy | lqikSy | 1 | e/; fo¦ky;] yksdgk | MS ALAM CONSTRUCTION WORKS AND COMPANY,9472103786 9199574775 |  |  | 222.44 |  |  | 15 Months | 1
|  |  |  | 2 | ckfydk e/; fo¦ky;] lqikSy | [7 empty] | 1
37 | SSS-440 | lqikSy | fd'kuiqj | 1 | e/; fo¦ky;] czgecqyksd nqfc;kgh | DHIRAJ KUMAR AGRAWAL,9771645678 |  |  | 113.09 |  |  | 15 Months | 1
38 | S.S.S-359 | lqikSy | fueZyh | 1 | e/; fo¦ky;] csyk Vksyk] nkseqgku | TRISHUL CONSTRUCTIONS,8252940655 |  |  | 123.37 |  |  | 15 Months | 1
39 | S.S.S-360 | lqikSy | lqikSy | 1 | e/; fo¦ky;] eYguh | Baba Hans Construction Pvt Ltd 9430407767 |  |  | 238.15 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 21.6
|  |  |  | 2 | e/; fo¦ky;] clfoV~Vh | [7 empty] | 1
40 | S.S.S-361(A) | lqikSy | ljk;x<+ | 1 | e/; fo¦ky;] cSlk | Retender |  |  | 242.88 |  |  | 15 Months
41 | S.S.S-361(B) |  |  | 1 | e/; fo¦ky;] eqjyh | Retender
42 | S.S.S-362(A) | lqikSy | ejkSuk | 1 | e/; fo¦ky;] ejkSuk | Retender |  |  | 245.5 |  |  | 15 Months
43 | S.S.S-362(B) |  |  | 1 | e/; fo¦ky;] ljkstk csyk | GULAB DEVI,9472390207 | [6 empty] | 1
44 | S.S.S-363 | lqikSy | fd'kuiqj | 1 | e/; fo¦ky;] rqykiV~Vh | MADHAV CONSTRUCTION |  |  | 120.55 |  |  | 15 Months | 1
| Total No. of Schools |  |  | 90 |  |  |  |  | 10173.64 |  |  |  | 24 | 3 | 7 | 14 | 9 | 8 | 6 | 12 | 2 | 0 | 2130.52

## Purnea
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- PURNEA | [21 empty] | Date:-28.02.2015
Name & contact no. of EE :-Manoj Kumar Pandey (9661818750) , AE :- Madan Mohan (9431413291), JE :- Uttam Kr. (9973563185)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-73 | iwf.kZ;k¡ | /kenkgk | 1 | ukScr yky eŒfoŒ dqdjkSu&2 | M/S SATYANARAYAN SINGH 9431190410 |  |  | 325.36 |  |  | 15 Months | 1 | [10 empty] | contractor has not initiated the work due to his illness, as informed by telephonic communication.
|  |  |  | 2 | e/; fo¦ky;] jaxiqjk | [7 empty] | 1
|  |  |  | 3 | vkŒ e/; fo¦ky;] uhjiqj | [7 empty] | 1
2 | SSS-74 | iwf.kZ;k¡ | chŒ dksBh | 1 | e/; fo¦ky;] xfgyLFkku | BIRENDRA KUMAR SINGH 9473440405 |  |  | 766.44 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 36.65
|  |  |  | 2 | e/; fo¦ky;] fpduh iVjkgk | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] xqykcVksy eYyMhgk | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] Hkrlkjk | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] lq[klsuk | [10 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] fuifu;k¡ | [7 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] lglkSy | [7 empty] | 1
3 | SSS-75 | iwf.kZ;k¡ | cueu[kh | 1 | e/; fo¦ky;] xaxSyh | M/S SATYANARAYAN SINGH 9431190410 |  |  | 764.93 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] ft;uxaat e/; | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dk>h | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] gfjiqjeknh | [7 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] nsoksÙkj | [7 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] cksjkgh | [7 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] jkeiqj fryd iwoZ | [7 empty] | 1
4 | SSS-76 | iwf.kZ;k¡ | iwf.kZ;k¡ iwoZ | 1 | e/; fo¦ky;] ykyxat | BIRENDRA KUMAR SINGH 9473440405 |  |  | 107.55 |  |  | 15 Months | 1
5 | SSS-77 | iwf.kZ;k¡ | Jhuxj | 1 | vkŒ e/; fo¦ky;] glSyh [kqWÎh | Hari Mohan Bishwas Hasanganj Katihar-9955713757 |  |  | 108.53 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 44.47
6 | SSS-78 | vjfj;k | dqlkZdkaVk | 1 | mRØfer e/; fo¦ky;] fcduh | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 225.1 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 45.82
|  |  |  | 2 | mRØfer e/; fo¦ky;] gksfj;k | [12 empty] | 1
7 | SSS-79 | vjfj;k | fldVh | 1 | e/; fo¦ky;] Msfu;k | M/S R.P Construction Rahikatoal Araria-9431412396 |  |  | 112.71 |  |  | 15 Months |  |  |  | 1
8 | SSS-80 | vjfj;k | Hkjxkek | 1 | mRØfer e/; fo¦ky;] fljfl;k dyk | Hari Mohan VishwasHasnganj Katihar-9955713757 |  |  | 111.5 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 32.29
9 | SSS-81 (A) | vjfj;k | iyklh | 1 | e/; fo¦ky;] neZxat | Retender |  |  | 337.4 |  |  | 15 Months
10 | SSS-81 (B) |  |  | 1 | e/; fo¦ky; Qqyljk | Retender
11 | SSS-81 (C) |  |  | 1 | e/; fo¦ky;] Mkyk | Suraj Traders | [6 empty] | 1
12 | SSS-82 | vjfj;k | jkuhxat | 1 | e/; fo¦ky;] ykyiqj egqvk | M/S R.P Construction Rahikatoal Araria-9431412396 |  |  | 328.47 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 39.48
|  |  |  | 2 | e/; fo¦ky;] cM+gkjk | [12 empty] | 1
|  |  |  | 3 | dU;k e/; fo¦ky;] iksfB;k | [8 empty] | 1
13 | SSS-84 | vjfj;k | jkuhxat | 1 | e/; fo¦ky;] ekStgk | Hari Mohan Bishwas Hasanganj Katihar-9955713757 |  |  | 221.27 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 21.06
|  |  |  | 2 | e/; fo¦ky;] e/kqyrk | [9 empty] | 1
14 | SSS-85 | vjfj;k | Qkjfclxat | 1 | mRØfer e/; fo¦ky; xkSfj;k | M/S R.P Construction Rahikatoal Araria-9431412396 |  |  | 559.2 |  |  | 15 Months |  |  | 1 | [7 empty] | 42.71 | Obstruction (tree)
|  |  |  | 2 | e/; fo¦ky;] ijokgk gfjtu | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] clxM+k jkeiqj | [9 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] ckjk | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] HkkxijHkkgk | [10 empty] | 1
15 | SSS-86 | vjfj;k | tksdhgkV | 1 | e/; fo¦ky;] nkseksguk 2 | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 109.56 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 11.03
16 | SSS-87 (A) | vjfj;k | ujirxat | 1 | e/; fo¦ky;] lkgscxat | Retender |  |  | 451.24 |  |  | 15 Months
17 | SSS-87 (B) |  |  | 1 | e/; fo¦ky;] MqejcUuk | Shailendra Kumar | [6 empty] | 1
18 | SSS-87 (C) |  |  | 1 | e/; fo¦ky;] x<+xkek | Retender
19 | SSS-87 (D) |  |  | 1 | e/; fo¦ky;] Hkokuhiqj | Shailendra Kumar | [6 empty] | 1
20 | SSS-88 (A) | vjfj;k | vjfj;k | 1 | e/; fo¦ky;] csyokr | Retender |  |  | 332.98 |  |  | 15 Months
21 | SSS-88 (B) |  |  | 1 | e/; fo¦ky;] dqfl;kjxkao | Suraj Traders | [7 empty] | 1
22 | SSS-88 (C) |  |  | 1 | mRØfer e/; fo¦ky;] frjgqrfcêk | Retender
23 | SSS-89 | dfVgkj | leSyh | 1 | e/; fo¦ky;] Nksgkj | Ashok Kumar Goushala- Katihar-9431096238 |  |  | 214.7 |  |  | 15 Months | 1 | [9 empty] | 50.15 | Land not avialable
|  |  |  | 2 | e/; fo¦ky;] eygfj;k | [14 empty] | 1
24 | SSS-90 | dfVgkj | dqlSyk | 1 | e/; fo¦ky;] dVfj;k | BIRENDRA KUMAR SINGH 9473440405 |  |  | 214.68 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 33.54
|  |  |  | 2 | e/; fo¦ky;] tjykgh | [11 empty] | 1
25 | SSS-91 | dfVgkj | MaM[kksjk | 1 | e/; fo¦ky;] usigk | Pankaj Kumar Singh Gami Tola Katihar, Bihar-9431229327 |  |  | 216.75 |  |  | 15 Months | [7 empty] | 1 |  |  | 100.51
|  |  |  | 2 | e/; fo¦ky;] fVdSyh | [14 empty] | 1
26 | SSS-92 | fd'kuxat | Bkdqjxat | 1 | mRØfer e/; fo¦ky;] yks/kk | Birendra Kumar Singh |  |  | 339.89 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky;] csgqynaxh | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] iapxkNh | [8 empty] | 1
27 | SSS-93 | fd'kuxat | cgknwjxat | 1 | mRØfer e/; fo¦ky;] ykSpk | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 222.58 |  |  | 15 Months | 1 | [10 empty] | Land Not aviable
|  |  |  | 2 | mRØfer e/; fo¦ky;] eaMyVksyk Mksgj | [7 empty] | 1 | [10 empty] | Land Not aviable
28 | SSS-94 | fd'kuxat | dkspk/kkeu | 1 | mRØfer e/; fo¦ky;] ckykuxj | Sirajur Rahman Churipatti Road Kishanganj Bihar-9470866777 |  |  | 111.36 |  |  | 15 Months |  |  | 1 | [7 empty] | 16.66
29 | SSS-95 | fd'kuxat | fd'kuxat | 1 | e/; fo¦ky;] iuhlky | Sirajur Rahman Churipatti Road Kishanganj Bihar-9470866777 |  |  | 110.65 |  |  | 15 Months | [7 empty] | 1 |  |  | 48.16
30 | SSS-96 | fd'kuxat | iksfB;k | 1 | e/; fo¦ky;] tkyqpkSd | BIRENDRA KUMAR SINGH 9473440405 |  |  | 337.85 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] lksukiqj | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] csyxkNh ohjiqj | [8 empty] | 1
31 | SSS-97 | fd'kuxat | Vs<+kxkN | 1 | mRØfer e/; fo¦ky;] vkfnoklh Vksyk Hkksjgk | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 230.08 |  |  | 15 Months | 1 | [10 empty] | LOA not available
|  |  |  | 2 | e/; fo¦ky;] Hkkstiqj] cyok | [7 empty] | 1 | [10 empty] | LOA not available
32 | SSS-389 | dfVgkj | dks<+k | 1 | e/; fo¦ky; f'ko yky Vksyk pkWih | Retender |  |  | 108.38
33 | SSS-390 | dfVgkj | Qydk | 1 | ckfydk e/; fo¦ky;] iksfB;k | Retender |  |  | 107.52
34 | SSS-404 | fd'kuxat | fd'kuxat | 1 | e/; fo¦ky;] gyeyk | Retender |  |  | 110.65
35 | SSS-405 | fd'kuxat | dkspk/kkeu | 1 | mRØfer e/; fo¦ky;] lkgiqj | BHOLI NATH ROY,7352520025 |  |  | 111.36 |  |  |  | 1
36 | SSS-406 | fd'kuxat | Vs<+kxkN | 1 | e/; fo¦ky;] >udh eqlgjh iqohZ | Retender |  |  | 115.03
37 | SSS-407 | fd'kuxat | iksfFkok | 1 | e/; fo¦ky;] Mkeyckjh | MD ANZAR ALAM,9431445928 |  |  | 112.62 |  |  |  | 1
38 | SSS-408 | fd'kuxat | cgknqjxat | 1 | e/; fo¦ky;] HkkVkckjh | MD ANZAR ALAM,9431445928 |  |  | 112.82 |  |  |  | 1
39 | SSS-416 | iwf.Zk;k¡ | dlck | 1 | e/; fo¦ky;] lq/kqosyh | Retender |  |  | 325.35
|  |  |  | 2 | e/; fo¦ky;] ft;uxat] xqjgh
|  |  |  | 3 | e/; fo¦ky;] deyiqj] vejk] ykxu
40 | SSS-417 | iwf.Zk;k¡ | tykyx<+ | 1 | e/; fo¦ky;] lksjlksuh fctqfy;k | Retender |  |  | 108.45
41 | SSS-418 | iwf.Zk;k¡ | ok;lh | 1 | e/; fo¦ky;] e<+ok | Retender |  |  | 108.48
42 | SSS-419 | iwf.Zk;k¡ | Mx:vk | 1 | e/; fo¦ky;] egyckjh | Retender |  |  | 108.5
43 | SSS-420 | iwf.Zk;k¡ | iwf.kZ;k¡ ¼iwohZ½ | 1 | e/; fo¦ky;] csyok | Retender |  |  | 107.55
44 | SSS-421 | iwf.Zk;k¡ | Hkokuhiqj | 1 | e/; fo¦ky;] lksunhi | Retender |  |  | 109.27
45 | SSS-455 | vjfj;k | jkuhxat | 1 | mRØfer e/; fo¦ky;] Hkokuhuxj | Retender |  |  | 11064
46 | SSS-456 | vjfj;k | tksdhgkV | 1 | mRØfer e/; fo¦ky;] ckjk bLrkecjkj | MD ARFIN,9006212706 |  |  | 109.56 |  |  |  |  | 1
47 | S.S.S-357(A) | iwf.kZ;k | /kenkgk | 1 | e/; fo¦ky;] la>k?kkV | RATNESH KUMAR RATNA,9334271195 |  |  | 346.07 |  |  |  | 1
48 | S.S.S-357(B) |  |  | 1 | e/; fo¦ky;] ehjxat | MS ALAM CONSTRUCTION WORKS & COMPANY, 9199574775 | [6 empty] | 1
49 | S.S.S-357(C) |  |  | 1 | e/; fo¦ky;] xaxkjke] nexkM+k | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | [6 empty] | 1
| Total No. of Schools |  |  | 82 |  |  |  |  | 19701.03 |  |  |  | 30 | 9 | 6 | 6 | 4 | 3 | 1 | 4 | 0 | 0 | 522.53

## Tirhut (East)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- TIRHUT (EAST) - Vaishali, Muzaffarpur & Sitamarhi | [22 empty] | Date:-28.02.2015
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-35 | lhrke<+h | :uh lSniqj | 1 | e/; fo¦ky;] egs'kk 1 | Akhilesh Kumar Chaudhary Sitamarhi-9431415700 |  |  | 217.84 |  |  | 15 Months | [8 empty] | 1 |  | 175.24
|  |  |  | 2 | e/; fo¦ky;] oxkgh | [12 empty] | 1
2 | SSS-36 (A) | lhrke<+h | cFkukgk | 1 | e/; fo¦ky;] gjcsy | Sharda Construction Patna-9431829462 |  |  | 442.74 |  |  | 15 Months | 1
3 | SSS-36 (B) |  |  | 1 | e/; fo¦ky;] jukSyh | Sharda Construction Patna-9431829462 | [6 empty] | 1
4 | SSS-36 (C) |  |  | 1 | e/; fo¦ky;] ;equk cjgh | Retender
5 | SSS-36 (D) |  |  | 1 | e/; fo¦ky;] gjiqj cygk | Retender
6 | SSS-37 | lhrke<+h | cktiÍh | 1 | e/; fo¦ky;] clsiqj | Rajesh Kumar Sitamarhi-9931490405 |  |  | 109.69 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 21.99
7 | SSS-38 (A) | lhrke<+h | csylaM | 1 | e/; fo¦ky;] Mqejk | Retender |  |  | 327.74 |  |  | 15 Months
8 | SSS-38 (B) |  |  | 1 | e/; fo¦ky;] nekeh eB | Sadafal cons. Pvt. Ltd. | [6 empty] | 1
9 | SSS-38 (C) |  |  | 1 | e/; fo¦ky;] e/kdkSy | Retender
10 | SSS-39 | lhrke<+h | ijlkSuh | 1 | e/; fo¦ky;] /kuxsj | Amresh Kumar Dumra Sitamarhi-9525120333 |  |  | 109.09 |  |  | 15 Months | [8 empty] | 1 |  | 84.54
11 | SSS-40 (A) | lhrke<+h | jhxk | 1 | e/; fo¦ky;] cqykdhiqj | Saroj Kumar |  |  | 439.01 |  |  | 15 Months |  |  | 1
12 | SSS-40 (B) |  |  | 1 | e/; fo¦ky;] mljfg;k | Retender
13 | SSS-40 (C) |  |  | 1 | e/; fo¦ky;] nks?kjk | Retender
14 | SSS-40 (D) |  |  | 1 | e/; fo¦ky;] ikSlk | Retender
15 | SSS-41 | lhrke<+h | lksuo"kkZ | 1 | e/; fo¦ky;] clgh;k fgUnh | Sharda Construction Patna-9431829462 |  |  | 221.66 |  |  | 15 Months | [7 empty] | 1 |  |  | 105.16
|  |  |  | 2 | e/; fo¦ky;] ejik dpkSj | [14 empty] | 1
16 | SSS-42 | lhrke<+h | lqjlaM | 1 | e/; fo¦ky;] dksfj;kgh | M/S Sheel Construction Sheohar Bihar-9473034622 |  |  | 221.32 |  |  | 15 Months | 1 | [9 empty] | 73.08
|  |  |  | 2 | e/; fo¦ky;] c[kjh | [14 empty] | 1
17 | SSS-43 | eqt¶Qjiqj | canjk | 1 | mRØfer e/; fo¦ky;] ?kksljkek dksBh | MS Jayshankar Kumar, Samastipur |  |  | 437.38 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] cuxgh | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jruefu;k | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] caxjk | [8 empty] | 1
18 | SSS-44 | eqt¶Qjiqj | ckspgkW | 1 | e/; fo¦ky;] /kjHkjk | Ashok Kumar Singh Muzaffarpur-8521110001 |  |  | 107.95 |  |  | 15 Months |  |  | 1
19 | SSS-45 | eqt¶Qjiqj | ckspkgkW | 1 | e/; fo¦ky;] okftriqj | Ravi Jalan Patna City-9546109122 |  |  | 216.48 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 34.82
|  |  |  | 2 | e/; fo¦ky;] vrgj | [7 empty] | 1
20 | SSS-46 | eqt¶Qjiqj | dkWVh | 1 | e/; fo¦ky;] cjfj;k | Retender |  |  | 538.14 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eqLrQkiqj
|  |  |  | 3 | mRØfer e/; fo¦ky;] e/kqcu
|  |  |  | 4 | e/; fo¦ky;] diyiqjk
|  |  |  | 5 | e/; fo¦ky;] ';keiqj Hkkstk
21 | SSS-47 | eqt¶Qjiqj | dkWVh | 1 | mRØfer e/; fo¦ky;] dksfB;kiqj | Maa Tara Construction |  |  | 214.97 |  |  | 15 Months |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] jruiqjk | [9 empty] | 1
22 | SSS-48 | eqt¶Qjiqj | dq<+uh | 1 | e/; fo¦ky;] caxjk | M/S Sanjay Construction Mahendru Patna-9431877189 |  |  | 1071.95 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 350.89
|  |  |  | 2 | e/; fo¦ky;] rsfy;k | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] djepUn jkeiqj cyjk | [13 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] Qrsgiqj | [12 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] p<+qvk | [9 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] fd'kquiqj] e/kqcu | [14 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] vej[k | [14 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] efjpk | [15 empty] | 1
|  |  |  | 9 | e/; fo¦ky;] flykSV | [15 empty] | 1
|  |  |  | 10 | e/; fo¦ky;] eksfjfuLd mnwZ | [8 empty] | 1
23 | SSS-49 | eqt¶Qjiqj | ehukiqj | 1 | e/; fo¦ky;] ed'kqniqj | Minni Devi Siwan 9162643061 |  |  | 431.81 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 107.67
|  |  |  | 2 | e/; fo¦ky;] [kfjdk | [13 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dksngfj;k | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] flok;iÍh | [12 empty] | 1
24 | SSS-50 | eqt¶Qjiqj | eksrhiqj | 1 | e/; fo¦ky;] eksjlaMh | Devendra Kumar-Motipur Muzaffarpur-9473156515 |  |  | 322.17 |  |  | 15 Months | [7 empty] | 1 |  |  | 87.45
|  |  |  | 2 | e/; fo¦ky;] vatukdksV | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] /kqeuxj | [12 empty] | 1
25 | SSS-51 | eqt¶Qjiqj | eMou | 1 | mRØfer e/; fo¦ky;] xolkjk | Ravi Shekhar 8002497100 |  |  | 212.61 |  |  | 15 Months | 1 | [9 empty] | 65.94
|  |  |  | 2 | mRØfer e/; fo¦ky;] cFkuk jke | [15 empty] | 1
26 | SSS-52 | eqt¶Qjiqj | eqjkSy | 1 | e/; fo¦ky;] cyqvk | Deam Eathcon Pvt. Ltd. 9431115629 |  |  | 432.38 |  |  | 15 Months |  |  | 1 | [7 empty] | 18.397
|  |  |  | 2 | e/; fo¦ky;] fVVjk fo'kquiqj | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] eq'kgjk ykSru | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] fo¦k>kai | [7 empty] | 1
27 | SSS-53 | eqt¶Qjiqj | eq'kgjh | 1 | e/; fo¦ky;] idM+h LekbZy | Deam Eathcon Pvt. Ltd. 9431115629 |  |  | 426.65 |  |  | 15 Months |  |  | 1 | [7 empty] | 35.52
|  |  |  | 2 | e/; fo¦ky;] [kcjk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] izgykniqj | [12 empty] | 1
|  |  |  | 4 | mRØŒ e/; fo¦ky;] eqlgjh QkeZ | [7 empty] | 1
28 | SSS-54 (A) | eqt¶Qjiqj | ik: | 1 | e/; fo¦ky;] jkepUnziqj | Retender |  |  | 321.71 |  |  | 15 Months
29 | SSS-54 (B) |  |  | 1 | e/; fo¦ky;] lygiqj | Retender
30 | SSS-54 (C) |  |  | 1 | e/; fo¦ky;] l[kgjk | M/S Rana Cons. | [6 empty] | 1
31 | SSS-55 | eqt¶Qjiqj | ldjk | 1 | e/; fo¦ky;] y{ehiqj | Mahesh Kumar Minapur Muzaffarpur-9931805726 |  |  | 107.99 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 20.48
32 | SSS-56 (A) | eqt¶Qjiqj | ldjk | 1 | mRØfer e/; fo¦ky;] egenkiqj cuokjh | Retender |  |  | 975.54 |  |  | 15 Months
33 | SSS-56 (B) |  |  | 1 | e/; fo¦ky;] eFkqjkiqj] xksoZ/kuiqj | Retender
34 | SSS-56 (C) |  |  | 1 | e/; fo¦ky;] xfu;kjh | Retender
35 | SSS-56 (D) |  |  | 1 | e/; fo¦ky;] eglh | Retender
36 | SSS-56 (E) |  |  | 1 | e/; fo¦ky;] flejh | Pramod Kumar | [6 empty] | 1
37 | SSS-56 (F) |  |  | 1 | e/; fo¦ky;] gfjiqj d`".k | Retender
38 | SSS-56 (G) |  |  | 1 | mRØfer e/; fo¦ky;] jfgeiqj jldk mnwZ | Retender
39 | SSS-56 (H) |  |  | 1 | e/; fo¦ky;] ljeLriqj | Retender
40 | SSS-56 (I) |  |  | 1 | e/; fo¦ky;] ipMgh | Retender
41 | SSS-57 | eqt¶Qjiqj | ljS;k | 1 | mRØfer e/; fo¦ky;] oklqnso | Hari Shankar Prasad |  |  | 427.74 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 143.36
|  |  |  | 2 | mRØfer e/; fo¦ky;] fo".kqiqj clSFkk | [14 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] xkSjhxkok | [14 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] /kqch;kgh jked`".k | [12 empty] | 1
42 | SSS-58 | eqt¶Qjiqj | vkSjkb | 1 | e/; fo¦ky;] vkSjkb fgUnh | Retender |  |  | 542.43 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] 'kaHkqrk
|  |  |  | 3 | e/; fo¦ky;] HkjFkqvk
|  |  |  | 4 | e/; fo¦ky;] HknbZ
|  |  |  | 5 | e/; fo¦ky;] veukSj
43 | SSS-59 | eqt¶Qjiqj | xk;?kkV | 1 | e/; fo¦ky; cq'kgjk eu | Keshav Kumar Keshri Bihar-7779830772 |  |  | 106.52 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 12.79
44 | SSS-62 | oS'kkyh | egqvk | 1 | mRØfer e/; fo¦ky;] ijekuaniqj | Prem Pratap Ray 9852833505 |  |  | 531.77 |  |  | 15 Months |  | 1 | [8 empty] | 51.57
|  |  |  | 2 | mRØfer e/; fo¦ky;] 'kkgiqj pdqEej | [9 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] gjiqj xaxkjke | [7 empty] | 1
|  |  |  | 4 | jktdh; e/; fo¦ky;] pdmej | [11 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] idM+h | [11 empty] | 1
45 | SSS-63 | oS'kkyh | egukj | 1 | e/; fo¦ky; etfyliqj | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 |  |  | 107.28 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 30.73
46 | SSS-64 | oS'kkyh | ikrsiqj | 1 | e/; fo¦ky;] ckftriqj] drkZj | Hitech Construction and Developers Pvt. Ltd. 9470836333 |  |  | 432.88 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 53.67
|  |  |  | 2 | mRØfer e/; fo¦ky;] eksgEeniqj tqEeu | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] igkM+iqj | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] cfyxkWo | [11 empty] | 1
47 | SSS-65 | oS'kkyh | ikrsiqj | 1 | e/; fo¦ky;] cyk<+ | Hitech Construction and Developers Pvt. Ltd. 9470836333 |  |  | 432.59 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 29.95
|  |  |  | 2 | mRØfer e/; fo¦ky;] ekSng pkrqj | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ikrsiqj | [9 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] iLrkjk | [9 empty] | 1
48 | SSS-66 | oS'kkyh | iVs<+h csylj | 1 | mRØfer e/; fo¦ky;] csylj gkV | Dilip Kumar Patepur Vaishali-8521072115 |  |  | 106.78 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 42.63
49 | SSS-67 | oS'kkyh | jk?kksiqj | 1 | pdflaxkj e/; fo¦ky; | M/S Sanjay Construction Musllahpur Hat Mahendru Patna-9431877189 |  |  | 214.77 |  |  | 15 Months | 1
|  |  |  | 2 | pkWniqjk e/; fo¦ky; | [7 empty] | 1
50 | SSS-68 | oS'kkyh | jktkikdj | 1 | mRØfer e/; fo¦ky;] xkSliqj | Er. A.P. Construction Pvt.Ltd. Hajipur Vaishali-9431450146 |  |  | 212.57 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky; cu?kkM+k | [7 empty] | 1
51 | SSS-69 | oS'kkyh | nsljh | 1 | mRØŒ e/; fo¦kŒ] eejstiqj dU;k | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 |  |  | 213.2 |  |  | 15 Months |  |  | 1 | [7 empty] | 38.95
|  |  |  | 2 | e/; fo¦ky;] mQjkSy | [14 empty] | 1
52 | SSS-70 | oS'kkyh | oS'kkyh | 1 | e/; fo¦ky;] trdkSyh | M/S Satyendra Kumar & Co. Construction Pvt.Ltd Exhibition Road Patna-9308003925 |  |  | 638.72 |  |  | 15 Months | [7 empty] | 1 |  |  | 136.75
|  |  |  | 2 | e/; fo¦ky;] cjfV;k e>kSyh | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky; pdvYgnkn ifjlj | [11 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] gqlSuiqj | [10 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] [ktqvrk | [12 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] nkmnuxj ifjlj | [7 empty] | 1
53 | SSS-71 | oS'kkyh | tUnkgk | 1 | mRØfer e/; fo¦ky;] lksgjFkh | Ravindra Prasad Sharma jorpura Samastipur-9006504477 |  |  | 107.39 |  |  | 15 Months | 1
54 | SSS-72 | oS'kkyh | ykyxat | 1 | mRØfer e/; fo¦ky;] txksMhg gfjtu | Er.A.P. Construction Pvt.Ltd. Hajipur Vaishali-9431450146 |  |  | 106.07 |  |  | 15 Months | 1
55 | SSS-437 | lhrke<+h | बाजपट्टी | 1 | jktdh; e/; fo¦ky;] fuekgh | BIRENDRA KUMAR SINGH |  |  | 109.7 |  |  |  | 1
56 | SSS-438 | lhrke<+h | Mqejk | 1 | e/; fo¦ky;] rkjknsoh] jathriqj | MUKESH KUMAR |  |  | 109.6 |  |  |  | 1
Total No. of Schools |  |  |  | 114 |  |  |  |  | 12306.83 |  |  |  | 25 | 5 | 12 | 6 | 7 | 14 | 3 | 10 | 5 | 0 | 1721.577

## Tirhut (West)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- TIRHUT (WEST) - East Champaran, West Champaran & Shivhar | [22 empty] | Date:-28.02.2015
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-1 | iwohZ paikj.k | pfd;k | 1 | mRØfer e/; fo¦ky;] [kSjh teqfu;k | Pristine Engicon Pvt. Ltd., Ranchi |  |  | 328.4 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] cSfj;k | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jkedj.k idM+h | [7 empty] | 1
2 | SSS-2 | iwohZ paikj.k | rqjdkSfy;k | 1 | e/; fo¦ky;] liêh | M/S Sushil kumar Gayatri Nagar, Motihari-9430494360 |  |  | 218.19 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 44.68
|  |  |  | 2 | mŒe/; fo¦kŒ Hkxr Vksyk] eksgCcr Nijk | [11 empty] | 1
3 | SSS-3 | iwohZ paikj.k | dksVok | 1 | e/; fo¦ky;] jketh Vksyk | Munna Kumar Singh East Champaran Bihar-9097820489 |  |  | 326.11 |  |  | 15 Months | [8 empty] | 1 |  | 204.51
|  |  |  | 2 | e/; fo¦ky;] iêh] ¼egkRek½ | [15 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] djfj;k tkxhj | [15 empty] | 1
4 | SSS-4 | iwohZ paikj.k | idMh+n;ky | 1 | e/; fo¦ky;] jktsiqj] uoknk | Ravi Bhusan Singh, Alawalpur patna-9431083150 |  |  | 218.7 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] /kukSth | [10 empty] | 1
5 | SSS-5 | iwohZ paikj.k | jkex<+ok | 1 | e/; fo¦ky;] eqjyk | Virendra Kumar Chaudhari, East Champaran Bihar- |  |  | 111.41 |  |  | 15 Months | 1
6 | SSS-6 | iwohZ paikj.k | gjlhnh | 1 | e/; fo¦ky;] mTtSu yksfg;kj | Smt.Radha Devi,East Champaran, Bihar-9471886673 |  |  | 109.83 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 16.9
7 | SSS-7 | iwohZ paikj.k | fiijkdksBh | 1 | mRØfer e/; fo¦ky;] gfFk;kgh | Sanjay Kumar Jha, East Champaran-9934244750 |  |  | 105.25 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 51.7
8 | SSS-8 | iwohZ paikj.k | lqxkSyh | 1 | mRØfer e/; fo¦ky;] ';keiqj | Munna Kumar Singh -East Champaran-9097820489 |  |  | 109.98 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 24.34
9 | SSS-9 | iwohZ paikj.k | esglh | 1 | e/; fo¦ky;] e>kSfy;k | Keshav Kumar Keshri East Champaran-7779830772 |  |  | 109.1 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 39.55
10 | SSS-10 | iwohZ paikj.k | fpjS;k | 1 | e/; fo¦ky;] gjkt?kkV | Sanjay Kumar Jha East Chaparan-9934244750 |  |  | 110.03 |  |  | 15 Months | [7 empty] | 1 |  |  | 67.38
11 | SSS-11 | iwohZ paikj.k | eksfrgkjh | 1 | mRØfer e/; fo¦ky;] ePNgkW | Keshav Kumar Keshri East Champaran-7779830772 |  |  | 108.82 |  |  | 15 Months | [7 empty] | 1 |  |  | 64.86
12 | SSS-12 | iwohZ paikj.k | vjsjkt | 1 | e/; fo¦ky;] jeflfj;k¡ | KUNAL KISHOR MISHRA DUMRA KOTWA EAST CHAMPARAN |  |  | 219.01 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 45.02
|  |  |  | 2 | e/; fo¦ky;] >[kjk | [11 empty] | 1
13 | SSS-13 | iwohZ paikj.k | <+kdk | 1 | e/; fo¦ky;] rsygkjk dyk | R.S.Construction Telharakala.East Champaran |  |  | 110.53 |  |  | 15 Months |  |  | 1
14 | SSS-14 | iwohZ paikj.k | vnkiqj | 1 | mRØfer e/; fo¦ky;] cjok | Vijay Kumar Singh Persouni East Champaran-9471296790 |  |  | 335.31 |  |  | 15 Months | 1 | [9 empty] | 37.41
|  |  |  | 2 | mRØfer e/; fo¦ky;] y{ehiqj | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Hkokuhiqj cktkj | [13 empty] | 1
15 | SSS-15 | iwohZ paikj.k | igkjiqj | 1 | e/; fo¦ky;] jk;djfj;k | Alok Kumar Sangrampur East Champaran-9631044077 |  |  | 109.85 |  |  | 15 Months | [7 empty] | 1 |  |  | 66.11
16 | SSS-16 | iwohZ paikj.k | Qsugjk | 1 | e/; fo¦ky;] fo'kquiqj clar | Vijay Kumar Singh Persouni, East Champaran-9471296790 |  |  | 329.08 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 105.76
|  |  |  | 2 | e/; fo¦ky; Vsolk | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ijlkSuh dksBh | [13 empty] | 1
17 | SSS-17 | iwohZ paikj.k | jDlkSy | 1 | e/; fo¦ky;] tksfd;kjh | Vijay Kumar Singh Persouni, East Champaran-9471296790 |  |  | 112.06 |  |  | 15 Months | [7 empty] | 1 |  |  | 44.05
18 | SSS-18 | iwohZ paikj.k | catfj;k | 1 | mRØfer e/; fo¦ky; xkSfj;k | DESHBANDHU KUMAR SINGH 7739855654 |  |  | 219.2 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] vtxjok fgUnh | [7 empty] | 1
19 | SSS-19 | iwohZ paikj.k | dY;k.kiqj | 1 | e/; fo¦ky;] j?kqukFkiqj | Kiran Devi East Champaran Biha-9006524444 |  |  | 109.21 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 64.29
20 | SSS-20 | if'pe paikj.k | cxgk II | 1 | e/; fo¦ky;] egqvk | M/S C.S.Construction Gaytri Nagar,Motihari-9473290979 |  |  | 1014.79 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 369.41
|  |  |  | 2 | e/; fo¦ky;] cksjoy | [13 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky; csyok p[kuh | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] ukSruok | [13 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] fl/kko | [13 empty] | 1
|  |  |  | 6 | mRØfer e/; fo¦ky;] feJkSSyh | [14 empty] | 1
|  |  |  | 7 | mRØfer e/; fo¦ky; jeofy;k | [13 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] egqvkj | [13 empty] | 1
|  |  |  | 9 | mRØfer e/; fo¦ky; ePNjxkoka] | [10 empty] | 1
21 | SSS-21 | if'pe paikj.k | jkeuxj | 1 | mRØfer e/; fo¦ky; tqM+k idM+h | Sabir Husain West Champaran Bihar-9430023820,9661948918 |  |  | 787.01 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 312.73
|  |  |  | 2 | mRØfer e/; fo¦ky; Mqejh | [13 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] f'koiqj dkWyuh | [13 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] chŒ,eŒlhŒ Qqydksy | [13 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] Hkkoy | [13 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] eqM+sjk | [12 empty] | 1
|  |  |  | 7 | e/; fo¦ky; cM+xks | [12 empty] | 1
22 | SSS-22 | if'pe paikj.k | ea>kSfy;k | 1 | mRØfer e/; fo¦ky; cSBfu;k | M/S M.K. Enterprises, Sansaraiya W.Champaran-9431212686 |  |  | 447.52 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 156.57
|  |  |  | 2 | e/; fo¦ky;] efB;k o`r cSBfu;k | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] ijlk ckcw Vksyk | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] lsuqvfj;k | [14 empty] | 1
23 | SSS-23 | if'pe paikj.k | ujdfV;kxat | 1 | e/; fo¦ky;] euok ijlh | Sisley Construction Basantpur, W. Champaran |  |  | 446.42 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] cuofj;k | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jktiqj enku | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky; pxkSuk | [7 empty] | 1
24 | SSS-24 | if'pe paikj.k | fHkrgk | 1 | e/; fo¦ky;] fcugh | MS Maa Bindyavashani Construction 9801696390 |  |  | 226.23 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] [kSjok | [7 empty] | 1
25 | SSS-25 | if'pe paikj.k | xkSukgk | 1 | e/; fo¦ky;] gkSnk Mqejk | Sisley Construction Basantpur, W. Champaran |  |  | 562.82 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] fHkfrgjok | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] MjkSy | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] c[kjh | [7 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] /kekSjk | [7 empty] | 1
26 | SSS-26 | if'pe paikj.k | ;ksxkiÍh | 1 | mRØfer e/; fo¦ky;] cklksiÍh | Retender |  |  | 221.83 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] nqf/kvok
27 | SSS-27 | if'pe paikj.k | puifV;k | 1 | mRØfer e/; fo¦ky;] dksokgk | Shatrughan PrasadBettiah, W. Champaran-9431204259 |  |  | 551.94 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 108.89
|  |  |  | 2 | mRØfer e/; fo¦ky;] ghjk ikdM+ | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] HkjifV;k | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky; lcs;k dkyk | [12 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] eksgNh lqXxk | [13 empty] | 1
28 | SSS-28 | if'pe paikj.k | cSfj;k | 1 | mŒe/; fo¦ky;] r/kokuUniqj y[kuh cktkj | Ravi Bhushan Singh-Patna,Bihar-9431083150 |  |  | 330.94 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky; Kkuhth dk VksYkk | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky; cyqvk jeiqjok | [7 empty] | 1
29 | SSS-29 | if'pe paikj.k | cxgk I | 1 | e/; fo¦ky;] pUnzgkW | Brijesh Kumar |  |  | 112.43 |  |  | 15 Months | 1
30 | SSS-30 | if'pe paikj.k | ukSru | 1 | mRØfer e/; fo¦ky; fl;kjgh | Prem Pratap Ray 9852833505 |  |  | 549.94 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 78.61
|  |  |  | 2 | vkn'kZ e/; fo¦ky;] eMqvkgkW | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Mcfj;k | [9 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] f'kojktiqj | [8 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] y{ehiqj nqcksfy;k | [11 empty] | 1
31 | SSS-31 | if'pe paikj.k | csfr;k | 1 | e/; fo¦ky;] flaXkkNkij | Sanjay Kumar Mishra West Champaran-9546215798 |  |  | 220.35 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 39.33
|  |  |  | 2 | e/; fo¦ky;] 'ks[kkSuk | [12 empty] | 1
32 | SSS-32 | if'pe paikj.k | fldVk | 1 | e/; fo¦ky;] flfjfl;k | Asiana Contract Pvt.Ltd.Gopalganj-9431088485 |  |  | 112.28 |  |  | 15 Months | 1
33 | SSS-33 | if'pe paikj.k | e/kqcuh | 1 | e/; fo¦ky;] /kugk | BED BRAT PANDEY VILL-SONKHAR,P.O.+P.S.-RAMNAGAR,DIST.-WEST CHAMPARAN |  |  | 230.29 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] rudwgk | [7 empty] | 1
34 | SSS-34 | if'pe paikj.k | ykSfj;k | 1 | e/; fo¦ky;] cudVok | Radhey Krishna Construction |  |  | 111.53 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 23.48
35 | S.S.S-60 (A) | f'kogj | rfj;kuh | 1 | e/; fo¦ky;] vkSjk | Retender |  |  | 437.67 |  |  | 15 Months
36 | S.S.S-60 (B) |  |  | 1 | e/; fo¦ky;] eqlgjh | Retender
37 | S.S.S-60 (C) |  |  | 1 | e/; fo¦ky;] NrkSuh | Retender
38 | S.S.S-60 (D) |  |  | 1 | e/; fo¦ky;] exqjkgk | Sadafal Construction | [6 empty] | 1
39 | S.S.S-61 | f'kogj | f'kogj | 1 | e/; fo¦ky;] lqanjiqj [kjkSuk | Sushil Kumar Brindavan Sheohar-9905176583 |  |  | 110.75 |  |  | 15 Months | 1
40 | SSS-409 | f'kogj | f'kogj | 1 | e/; fo¦ky; dVljh | Retender |  |  | 110.75 |  |  | 15 Months
41 | SSS-411 | if'pe pEikj.k | cxgk &1 | 1 | e/; fo¦ky;] cjxk¡o | Retender |  |  | 112.75 |  |  | 15 Months
42 | SSS-412 | if'pe pEikj.k | cxgk &2 | 1 | mRØfer e/; fo¦ky;] Hksjhgjh dkWyksuh | RAVI SHEKHAR 8002497100 |  |  | 225.5 |  |  | 15 Months | 1
|  |  | cxgk &2 | 2 | mRØfer e/; fo¦ky;] ip:[kk | [7 empty] | 1
43 | SSS-413 | if'pe pEikj.k | ujdfV;kxat | 1 | e/; fo¦ky;] vtqvk lqxkSyh | RAVI SHEKHAR 8002497100 |  |  | 111.6 |  |  | 15 Months | 1
44 | SSS-414 | if'pe pEikj.k | ykSfj;k | 1 | mRØfer e/; fo¦ky;] ejfg;k | MS RADHEY KRISHNA CONSTRUCTION |  |  | 111.53 |  |  | 15 Months |  |  | 1
45 | SSS-422 | iwohZ pEikj.k | jkex<+ok | 1 | mRØfer e/; fo¦ky;] f=os.kh | VANSHAJ CONSTRUCTION |  |  | 111.41 |  |  | 15 Months |  |  |  | 1
46 | SSS-423 | iwohZ pEikj.k | eksfrgkjh | 1 | jktdh; e/; fo¦ky;] dVgk | Retender |  |  | 108.82 |  |  | 15 Months
47 | SSS-424 | iwohZ pEikj.k | laxzkeiqj | 1 | mRØfer e/; fo¦ky;] bUnzxkNh uohu | SANTOSH PRASAD YADAV |  |  | 108.84 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 53.37
48 | SSS-425 | iwohZ pEikj.k | dksVok | 1 | mRØfer e/; fo¦ky;] VdVdkiqj | VARUN KUMAR |  |  | 108.7 |  |  | 15 Months | 1
49 | SSS-426 | iwohZ pEikj.k | e/kqcu | 1 | jktdh; e/; fo¦ky;] catfj;k | Retender |  |  | 108.74 |  |  | 15 Months
50 | SSS-427 | iwohZ pEikj.k | <+kdk | 1 | mRØfer e/; fo¦ky;] Qqyofj;k | BHAWANI BUILDCON AND PROJECT PVT LTD |  |  | 221.06 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] ipidM+h | [7 empty] | 1
51 | SSS-428 | iwohZ pEikj.k | ?kksM+klkgu | 1 | e/; fo¦ky;] iqjufg;k | BHAWANI BUILDCON AND PROJECT PVT LTD |  |  | 109.3 |  |  | 15 Months | 1
| Total No. of Schools |  |  | 103 |  |  |  |  | 11423.81 |  |  |  | 36 | 1 | 6 | 7 | 11 | 9 | 15 | 6 | 3 | 0 | 2018.95

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- DARBHANGA | [22 empty] | Date:-28.02.2015
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of LOA | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-194 | njHkaxk |  | 1 | e/; fo¦ky;] ?ku';keiqj | Ajay Kumar Pathak |  |  | 111.07 |  |  | 15 Months | 1
2 | SSS-195 (A) | njHkaxk | dq0LFkku | 1 | mRØfer e/; fo¦ky;] mljh | Retender |  |  | 661 |  |  | 15 Months
3 | SSS-195 (B) |  |  | 1 | e/; fo¦ky;] gjkSyh | Retender
4 | SSS-195 (C) |  |  | 1 | e/; fo¦ky;] vkSjkgh | Amar Nath Jha | [6 empty] | 1
5 | SSS-195 (D) |  |  | 1 | e/; fo¦ky;] gfjuxj | Amar Nath Jha | [6 empty] | 1
6 | SSS-195 (E) |  |  | 1 | e/; fo¦ky;] ?kksjnkSj | Amar Nath Jha | [6 empty] | 1
7 | SSS-195 (F) |  |  | 1 | e/; fo¦ky;] cjxkWo | Retender
8 | SSS-196 (A) | njHkaxk | fcjkSy | 1 | e/; fo¦ky;] f'kouxj | Vikash Anand Mahila |  |  | 438.19 |  |  | 15 Months | 1
9 | SSS-196 (B) |  |  | 1 | e/; fo¦ky;] vEckfctqfy;k | Avinash Kumar | [6 empty] | 1
10 | SSS-196 (C) |  |  | 1 | e/; fo¦ky;] yngks | Avinash Kumar | [6 empty] | 1
11 | SSS-196 (D) |  |  | 1 | e/; fo¦ky;] lkgks | Avinash Kumar | [6 empty] | 1
12 | SSS-197 | njHkaxk | guqekuuxj | 1 | mRØfer e/; fo¦ky;] jkeiqj | Madhav Construction, Darbhanga |  |  | 109.1 |  | 20-2-14 | 15 Months | [5 empty] | 1 |  |  |  |  | 35.82
13 | SSS-198 | e/kqcuh | ?kks?kjMhgk | 1 | e/; fo¦ky;] fpduk | Retender |  |  | 340.65 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] dsoVuk
|  |  |  | 3 | mRØefr e/; fo¦ky;] clqvkjk
14 | SSS-199 | e/kqcuh | [kqVkSuk | 1 | e/; fo¦ky;] ugjh | Retender |  |  | 339.68 |  |  | 15 Months | [10 empty] | 15.81
|  |  |  | 2 | e/; fo¦ky;] va/kkjou
|  |  |  | 3 | e/; fo¦ky;] fldfV;kgh
15 | SSS-200 | e/kqcuh | [ktkSyh | 1 | mRØfer e/; fo¦ky;] dqlekj | Retender |  |  | 557.96 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] dlek ejkj
|  |  |  | 3 | mRØfer e/; fo¦ky;] Nijk<+h
|  |  |  | 4 | e/; fo¦ky;] jlhniqj
|  |  |  | 5 | mRØfer e/; fo¦ky;] bujok iwjc
16 | SSS-201 | e/kqcuh | >a>kjiqj | 1 | e/; fo¦ky;] flejk | Kailash Prasad Yadav, Supaul |  |  | 332.21 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky;] flM+[kfj;k | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] vM+fj;k laxzke | [8 empty] | 1
17 | SSS-202 | e/kqcuh | ckcwcjgh | 1 | e/; fo¦ky;] dqYgfM+;k | Avaneesh Enterprises, 111-k-35/3A. Gaziabad |  |  | 337.09 |  | 20-2-14 | 15 Months |  |  |  | 1 | [6 empty] | 66.69
|  |  |  | 2 | e/; fo¦ky;] fodze'ksj | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] cyku'ksjiqjc | [10 empty] | 1
18 | SSS-203 | e/kqcuh | cklksiÍh | 1 | mRØfer e/; fo¦ky;] dkSvkgk | Retender |  |  | 565.95 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] pUnu dlsjk
|  |  |  | 3 | e/; fo¦ky;] xkSluxj
|  |  |  | 4 | mRØfer e/; fo¦ky;] egFkkSaj
|  |  |  | 5 | e/; fo¦ky;] ?kksM+cadh
19 | SSS-204 | e/kqcuh | csuhiêh | 1 | e/; fo¦ky;] tjSy | Subodh kumar , Madhubani |  |  | 106.38 |  | 20-2-14 | 15 Months | [7 empty] | 1 |  |  | 82.22
20 | SSS-205 | e/kqcuh | e/kokiqj | 1 | e/; fo¦ky;] iks[kjkSuh | Retender |  |  | 452.14 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] fcgkjh
|  |  |  | 3 | mRØfer e/; fo¦ky;] vkSjk
|  |  |  | 4 | mRØfer e/; fo¦ky;] dsjck
21 | SSS-206 | e/kqcuh | e/ksiqj | 1 | mRØfer e/; fo¦ky;] cdqvk | Retender |  |  | 449.51 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] }ky[k
|  |  |  | 3 | e/; fo¦ky;] Vsaxjkgk
|  |  |  | 4 | mRØfer e/; fo¦ky;] ijcyiqj
22 | SSS-207 | e/kqcuh | gjyk[kh | 1 | mRØfer e/; fo¦ky;] jkeiqj | M/S Subodh kumar Singh, Saran |  |  | 113.49 |  | 20-2-14 | 15 Months | [8 empty] | 1 |  | 84.89
23 | SSS-208 | e/kqcuh | iaMkSy | 1 | e/; fo¦ky;] HkkSj | Rajesh Kumar, C/o shiva Hardware |  |  | 334.39 |  | 20-2-14 | 15 Months | [5 empty] | 1 |  |  |  |  | 109.6
|  |  |  | 2 | e/; fo¦ky;] uogFk | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Hkokuhiqj | [12 empty] | 1
24 | SSS-209 | e/kqcuh | jfgdk | 1 | mRØfer e/; fo¦ky;] ekM+j | Retender |  |  | 444.88 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cfy;k
|  |  |  | 3 | e/; fo¦ky;] btjk
|  |  |  | 4 | mRØfer e/; fo¦ky;] uhek
25 | SSS-210 (A) | e/kqcuh | jktuxj | 1 | mRØfer e/; fo¦ky;] jgh iwjc | Bhawani Shankar Cons. |  |  | 666.63 |  |  | 15 Months | 1
26 | SSS-210 (B) |  |  | 1 | e/; fo¦ky;] lqxkSuk iks[kj v0tk0 | Retender
27 | SSS-210 (C) |  |  | 1 | e/; fo¦ky;] flejh | Retender
28 | SSS-210 (D) |  |  | 1 | mRØfer e/; fo¦ky;] cM+gkjk | Retender
29 | SSS-210 (E) |  |  | 1 | e/; fo¦ky;] tgjeksgjk | Retender
30 | SSS-210 (F) |  |  | 1 | mRØfer e/; fo¦ky;] jk/kksiqj | Retender
31 | SSS-211 (A) | e/kqcuh | Qqyijkl | 1 | e/; fo¦ky;] vekStk | Kiraye Baba Cons |  |  | 339.7 |  |  | 15 Months | 1
32 | SSS-211 (B) |  |  | 1 | e/; fo¦ky;] egFkkSj [kqnZ | Retender
33 | SSS-211 (C) |  |  | 1 | e/; fo¦ky;] fltkSfy;k] xksB | Bhawani Shankar Cons. | [6 empty] | 1
34 | SSS-212 | e/kqcuh | t;uxj | 1 | e/; fo¦ky;] dqok<+ | Rajesh Kumar, C/o Shiva Hardware, Patna |  |  | 112.92 |  | 20-2-14 | 15 Months | [6 empty] | 1 |  |  |  | 38.87
35 | SSS-213 | e/kqcuh | va/kjkBk<+h | 1 | e/; fo¦ky;] enuiêh | Kailash Prasad Yadav Constructions Pvt Ltd,SUPAUL |  |  | 112.25 |  |  | 15 Months |  |  |  | 1
36 | SSS-214 | e/kqcuh | ykSdgh | 1 | e/; fo¦ky;] HkjQksM+h | Retender |  |  | 802.14 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] ujsUnziqj
|  |  |  | 3 | mRØfer e/; fo¦ky;] dfj;kSr
|  |  |  | 4 | mRØfer e/; fo¦ky;] ujgh
|  |  |  | 5 | e/; fo¦ky;] csygh dpujok
|  |  |  | 6 | mRØfer e/; fo¦ky;] dqjhou
|  |  |  | 7 | mRØfer e/; fo¦ky;] Fk:vkjh
37 | SSS-215 | e/kqcuh | ynfu;k¡ | 1 | e/; fo¦ky;] ,dgjh | Retender |  |  | 459.22 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] Hkxorhiqj
|  |  |  | 3 | e/; fo¦ky;] dqej[kr
|  |  |  | 4 | e/; fo¦ky;] fla/ki ijlkgh
38 | SSS-216 | leLrhiqj | [kkuiqj | 1 | mRØfer e/; fo¦ky;] elhuk | Ray & Raj engineering Pvt.Ltd, Samastipur |  |  | 324.64 |  | 20-2-14 | 15 Months | [6 empty] | 1 |  |  |  | 90.05
|  |  |  | 2 | mRØfer e/; fo¦ky;] cFkukgk | [7 empty] | 1 | [10 empty] | LOW LAND MORE THAN 10 FEET
|  |  |  | 3 | e/; fo¦ky;] Hkkuiqj | [10 empty] | c | c | 1
39 | SSS-217 | leLrhiqj | dY;k.kiqj | 1 | mRØfer e/; fo¦ky;] /kksyh;kgh | Anil Kumar, Vaishali |  |  | 107.25 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 35.52
40 | SSS-218 | leLrhiqj | eksjok | 1 | e/; fo¦ky; /keZiqj cans | M/S Maruti Enterprises,Hajipur |  |  | 107.63 |  | 2014-03-03 | 15 Months | [6 empty] | 1 |  |  |  | 52.13
41 | SSS-219 | leLrhiqj | f'kokthuxj | 1 | mRØfer e/; fo¦ky;] tUnkgk | M/S Maruti Enterprises,Hajipur |  |  | 108.17 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 58.99
42 | SSS-220 | leLrhiqj | flaf?k;k | 1 | mRØfer e/; fo¦ky;] ijgV | Prakash Kumar, Muzaffarpur |  |  | 218.21 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] uhjiqj Hkjfj;k | [7 empty] | 1
43 | SSS-221 | leLrhiqj | fo¦kifruxj | 1 | vkn'kZ jktdh; e/; fo¦ky;] dkaWpk | Vinod Kumar Singh, Samastipur |  |  | 214.36 |  | 20-2-14 | 15 Months | [5 empty] | 1 |  |  |  |  | 119.23
|  |  |  | 2 | mRØfer e/; fo¦ky;] lksBxkek | [14 empty] | 1
44 | SSS-222 | leLrhiqj | foHkqrhiqj | 1 | e/; fo¦ky;] dY;k.kiqj | Chandra Prakash, 305, Patna |  |  | 107.54 |  | 2014-03-03 | 15 Months | 1 | [10 empty] | LOW LAND MORE THAN 10 FEET DEEP IN HALF PORTION AND ENCROCHMENT IN HALF PORTION
45 | SSS-223 | leLrhiqj | gluiqj | 1 | mRØfer e/; fo¦ky;] nso?kk | Bablu Kumar Singh, Patna |  |  | 217.56 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] gluiqj | [9 empty] | 1
46 | SSS-224 | leLrhiqj | jksljk | 1 | mRØfer e/; fo¦ky;] xksfoUniqj | Smt. Rita Devi, Hanuman Nagar |  |  | 107.71 |  | 3.3.14 | 15 Months | 1 | [10 empty] | land dispute
47 | SSS-225 (A) | leLrhiqj | jksljk | 1 | mRØfer e/; fo¦ky;] egqyh | Rita Devi |  |  | 430.84 |  |  | 15 Months | 1
48 | SSS-225 (B) |  |  | 1 | e/; fo¦ky;] iapxkek | Rita Devi | [6 empty] | 1
49 | SSS-225 (C) |  |  | 1 | mRØfer e/; fo¦ky;] HkVksVj | Retender
50 | SSS-225 (D) |  |  | 1 | mRØfer e/; fo¦ky;] ihV/kknksHkh | Retender
51 | SSS-226 | leLrhiqj | leLrhiqj | 1 | e/; fo¦ky;] 'kaHkqiêh | Sudhakant enterprises Pvt. Ltd. Samastipur |  |  | 428.15 |  | 20-2-14 | 15 Months | [7 empty] | 1 |  |  | 143.92
|  |  |  | 2 | mRØfer e/; fo¦ky;] ckftriqj | [14 empty] | 1
|  |  |  | 3 | e/; fo¦ky; /kwjy[k | [7 empty] | 1 | [10 empty] | ENCROCHEMENT
|  |  |  | 4 | mRØfer e/; fo¦ky;] flykSV | [7 empty] | 1 | [10 empty] | Land not Avilab.
52 | SSS-227 | leLrhiqj | ljk;jatu | 1 | mRØfer e/; fo¦ky;] jlyiqj | Vinod kumar Singh, Samastipur |  |  | 321.51 |  |  | 15 Months | [7 empty] | 1 |  |  | 212.65
|  |  |  | 2 | jktdh; e/; fo¦ky;] vf[r;kjiqj | [15 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] ukSvkpd | [15 empty] | 1
53 | SSS-228 | leLrhiqj | mft;kjiqj | 1 | mRØfer e/; fo¦ky;] ijksfj;k | Arvind Kumar Singh, Samastipur |  |  | 107.54 |  |  | 15 Months | 1 | [10 empty] | PRIVATE LAND REGISTRATION REQUIRED
54 | SSS-229 | leLrhiqj | okfj"kuxj | 1 | mRØfer e/; fo¦ky;] gtiqjok | Satyendra Kumar Construction, Patna-800001 |  |  | 107.18 |  | 2014-03-03 | 15 Months | [5 empty] | 1 |  |  |  |  | 35.42 | MODEL/BUILDING TO BE DISMANTED
55 | SSS-355 | e/kqcuh |  | 1 | e/; fo¦ky;] nhi | MAA VASUNDHARA CONSTRUCTION, 9006650591 |  |  | 119.47 |  |  |  | 1
56 | SSS-398 | e/kqcuh | Qqyijkl | 1 | e/; fo¦ky;] lqfj;kgh | DADIALA ENTERPRISES,9835998444 | 115.5 | 136.71 | 113.23 | NIT 10/2014-15,DATED-27-5-14 | 04.07-2014 |  | 1
57 | SSS-432 | leLrhiqj | ljk;jatu | 1 | e/; fo¦ky;] fe;kjh | SUDHAKANT ENTERPRISES PVT LTD,9431208455 | 115.5 | 256.9 | 214.08 | [9 empty] | 1 |  |  |  | 53.27
|  |  |  | 2 | e/; fo¦ky;] eqlkiqj |  | 115.5 | [9 empty] | 1
58 | SSS-433 | leLrhiqj | fo¦kifruxj | 1 | e/; fo¦ky;] 'ksjiqj | RENU DEVI,8540807915 | 115.5 | 128.87 | 107.18 | [8 empty] | 1 |  |  |  |  | 36.13
59 | SSS-434 | leLrhiqj | uks[kk | 1 | e/; fo¦ky;] xqukÃ] clgh | vipin kumar sahni,9931468694 | 115.5 | 129.61 | 106.94 |  |  |  | 1 | [9 empty] | 21.5
60 | SSS-435 | leLrhiqj | foHkqfriqj | 1 | jktdh; e/; fo¦ky;] csylaMh] rkjk | Retender | 115.5 | 386.97 | 322.62
|  |  |  | 2 | e/; fo¦ky;] [kEgkj |  | 115.5
|  |  |  | 3 | jktdh; e/; fo¦ky;] ekukjk; Vksyk |  | 115.5
61 | SSS-436 | leLrhiqj | nyflag ljk; | 1 | jktdh; e/; fo¦ky;] dejkm | Retender | 115.5 | 128.77 | 107.2
62 | SSS-441 | njHkaxk | e.khxkNh | 1 | mRØfer e/; fo¦ky;] VVqvkj | SANJAY KUMAR, 8521954601 | 115.5 | 115.5 | 111.08 |  |  |  | 1
63 | SSS-442 | njHkaxk | fcjkSy | 1 | mRØfer e/; fo¦ky;] fcjkSy vdcjiqj | CITY CREATION, 9386742763 | 115.5 | 115.5 | 219.1 | [7 empty] | 1 | [5 empty] | 23.69
|  |  |  | 2 | mRØfer e/; fo¦ky;] lksuiqj i?kkjh |  | 115.5 | 115.5 | [6 empty] | 1
64 | SSS-443 | njHkaxk | ?ku';keiqj | 1 | mRØfer e/; fo¦ky;] t;nsoiV~~Vh | CITY CREATION, 9386742763 | 115.5 | 115.5 | 111.06 | [5 empty] | 1
65 | SSS-444 | njHkaxk | tkys | 1 | e/; fo¦ky;] eqjSBk | SANJAY KUMAR, 8521954601 | 115.5 | 115.5 | 111.08 | [5 empty] | 1
| Total No. of Schools |  |  | 115 |  |  |  |  | 11094.84 |  |  |  | 26 | 3 | 4 | 4 | 2 | 9 | 5 | 5 | 3 | 0 | 1316.4

## Saran
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- SARAN | [21 empty] | Date:-28.02.2015
Name & contact no. of EE :- Uday Kumar Das (9431821558), AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-331 | lkj.k | tykyiqj | 1 | e/; fo¦ky;] dksBs;kW | Ms Jagdamba buildcon pvt ltd jai prakash nagar Ara |  |  | 213.66 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 59.65
|  |  |  | 2 | e/; fo¦ky;] vuoy | [11 empty] | 1
2 | SSS-332 | lkj.k | Nijk lnj | 1 | e/; fo¦ky;] clk<+h | Shiv Shankar Singh Construction pvt. Ltd |  |  | 536.83 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 118.57
|  |  |  | 2 | mRØfer e/; fo¦ky;] me/kk | [12 empty] | 1
|  |  |  | 3 | dU;k e/; fo¦ky;] 'ksjiqj | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] mn;iqjk | [10 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] cyou Vksyk | [9 empty] | 1
3 | SSS-333 | lkj.k | rjS;k | 1 | e/; fo¦ky;] gjiqj Qfjnu | Bajrangi Singh,chapra |  |  | 213.37 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 94.55
|  |  |  | 2 | e/; fo¦ky;] ljS;k clar | [10 empty] | 1
4 | SSS-334 | lkj.k | ,dek | 1 | mRØfer e/; fo¦ky;] xkSliqj | Shivasati Cons truction pvt ltd. Patliputra colony patna |  |  | 216.2 |  |  | 15 Months |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] ukSru | [8 empty] | 1
5 | SSS-335 | lkj.k | cfu;kiqj | 1 | mRØfer e/; fo¦ky;] djgh | Satrughan singh |  |  | 214.98 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 37.93
|  |  |  | 2 | mRØfer e/; fo¦ky;] fiiM+k | [8 empty] | 1
6 | SSS-336 | lkj.k | blqvkiqj | 1 | e/; fo¦ky;] fllokW | M/s Sethi Construction, Chapra |  |  | 106.73 |  |  | 15 Months |  |  |  |  | 1
7 | SSS-337 | lkj.k | ijlk | 1 | e/; fo¦ky;] HksYnh | M/s Gaurav Construction, Muzaffarpur |  |  | 105.27 |  |  | 15 Months |  |  |  | 1
8 | SSS-338 | lkj.k | e<+kSjk | 1 | e/; fo¦ky;] eqckjdiqj | Jitendra Kumar singh Gosi Amnour,Saran |  |  | 106.12 |  |  | 15 Months | 1
9 | SSS-339 | lkj.k | Eklj[k | 1 | e/; fo¦ky;] xaMkeu | Er. A p Construction Pvt Ltd,Gopalgang |  |  | 107.11 |  |  | 15 Months | [7 empty] | 1 |  |  | 54.71
10 | SSS-340 | lhoku | ip:[kh | 1 | mRØfer e/; fo¦ky;] MVokW | M/s shailcon Construction, Gopalgang |  |  | 106.51 |  |  | 15 Months | [8 empty] | 1 |  | 71.6
11 | SSS-341 | xksikyxat | dVs;k | 1 | e/; fo¦ky;] /kjgjk esyk | M/s Shailon Construction, Gopalgang |  |  | 330.68 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 124.68
|  |  |  | 2 | mRØfer e/; fo¦ky;] idM+h Mhg | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jlkSrh | [12 empty] | 1
12 | SSS-342 | xksikyxat | ek>kW | 1 | e/; fo¦ky;] rsfy;k ckW/k | Pawan Construction |  |  | 216.53 |  |  | 15 Months | 1 | [9 empty] | 62.35
|  |  |  | 2 | mRØfer e/; fo¦ky;] e/kq ljs;k | [14 empty] | 1
13 | SSS-343 | xksikyxat | cjkSyh | 1 | mRØfer e/; fo¦ky;] lksucjlk | Savitri technorats pvt ltd kaithwalia ward no. 7 gopalganj |  |  | 215.99 |  |  | 15 Months |  | 1 | [8 empty] | 48.95
|  |  |  | 2 | e/; fo¦ky;] dY;k.kiqj | [14 empty] | 1
14 | SSS-344 | xksikyxat | cjkSyh | 1 | mRØfer e/; fo¦ky;] osylM | Asiana Contractor Pvt. Ltd.-9431088485 |  |  | 432.83 |  |  | 15 Months | 1 | [9 empty] | 77.41
|  |  |  | 2 | mRØfer e/; fo¦ky;] [ktqfj;k ckyd | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ekMuiqj | [14 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] usmjh | [10 empty] | 1
15 | SSS-345 | xksikyxat | Hkksjs | 1 | e/; fo¦ky;] dqlgkW | Anand Mishra, Gopalgang |  |  | 665.15 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 145.45
|  |  |  | 2 | mRØfer e/; fo¦ky;] egjknsmj | [9 empty] | 1 | [8 empty] | land problem
|  |  |  | 3 | e/; fo¦ky;] ftxuk nwcs | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] fllbZ | [12 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ykehpkSj | [12 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] oudVk tkxhjnkjh | [12 empty] | 1
16 | SSS-346 | xksikyxat | fl/kofy;k | 1 | mRØfer e/; fo¦ky;] oq/klh | NORTH BIHAR CONSTRUCTION |  |  | 325.86 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 129.15
|  |  |  | 2 | mRØfer e/; fo¦ky;] cqfp;k | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] >>okW | [11 empty] | 1
17 | SSS-347 | xksikyxat | oSdq.Biqj | 1 | mRØfer e/; fo¦ky;] calrNkijk | Hariom construction vill-khaira po-jaihindtendua distt- Aurangabad |  |  | 216.78 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 22.98
|  |  |  | 2 | mRØfer e/; fo¦ky;] eMok | [7 empty] | 1
18 | SSS-348 | xksikyxat | dqpk;dksV | 1 | mRØfer e/; fo¦ky;] HkkstNkij | Anand mishra, Gopalgang |  |  | 328.8 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 179.46
|  |  |  | 2 | e/; fo¦ky;] fo'kEHkjiqj | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] o`rHkkeh Vksyk | [15 empty] | 1
19 | SSS-349 | xksikyxat | xksikyxat | 1 | mRØfer e/; fo¦ky;] ekfudiqj dU;k | Sona Engicon Pvt Ltd, Gopalganj |  |  | 216.24 |  |  | 15 Months | [8 empty] | 1 |  | 127.01
|  |  |  | 2 | mRØfer e/; fo¦ky;] [kSjfV;k jke uxj | [12 empty] | 1
20 | SSS-350 | xksikyxat | gFkqvk | 1 | e/; fo¦ky;] lsejko | Shiv Shankar Singh Construction pvt. Ltd |  |  | 216.22 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 23.07
|  |  |  | 2 | e/; fo¦ky;] pSuiqj | [7 empty] | 1
21 | SSS-351 | xksikyxat | Qqyofj;k | 1 | mRØfer e/; fo¦ky;] exgkW | Kumar manash Construction, Gopalganj |  |  | 326.91 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 98.95
|  |  |  | 2 | e/; fo¦ky;] ekMhiqj | [14 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] laxzkeiqj xksiky | [7 empty] | 1 | [10 empty] | no land
22 | SSS-352 | xksikyxat | mpdkxkWo | 1 | mRØfer e/; fo¦ky;] eqMk edlwniqj | M/s Pawan Construction, Uchakagawn |  |  | 109.2 |  |  | 15 Months | [8 empty] | 1 |  | 89.01
23 | SSS-353 | xksikyxat | iapnsojh | 1 | mRØfer e/; fo¦ky;] fiijgh | Anand mishra |  |  | 109.69 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 23.29
24 | SSS-354 | xksikyxat | fot;hiqj | 1 | e/; fo¦ky;] lqvjgkW gadkjiqj | Ashok construction vill+po- Chhitwana, Gopalganj |  |  | 110.4 |  |  | 15 Months |  |  |  | 1
25 | SSS-466 | xksikyxat | cSdq.Biqj ¼cjkSyh½ | 1 | mRØfer e/; fo¦ky;] cyjk | RETENDER |  |  | 215.98 |  |  | 15 Months
|  |  | cSdq.Biqj | 2 | e/; fo¦ky;] eqatk c[kjh
26 | S.S.S-364 | floku | njkSyh | 1 | mRØfer e/; fo¦ky;] d`".kkikyh | ASIANA CONSTRACT PVT LTD 9431088485 |  |  | 459 |  |  | 15 Months | 1 | [9 empty] | 37.27
|  |  |  | 2 | e/; fo¦ky;] pdjh | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] gjukVkaM | [10 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] Vmoka ijfl;ka | [7 empty] | 1
27 | S.S.S-365(A) | floku | njkSank | 1 | mRØfer e/; fo¦ky;]cSnkiqj | ASIANA CONSTRACT PVT LTD,9431081485 |  |  | 225.81 |  |  | 15 Months | 1
28 | S.S.S-365(B) |  |  | 1 | e/; fo¦ky;] idofy;k | Retender
29 | S.S.S-366 | floku | egkjktxat | 1 | e/; fo¦ky;] ek/kksijq | MS SHAILENDRA SHEKHAR MISHRA 9471004272 |  |  | 113.31 |  |  | 15 Months | 1
30 | S.S.S-367 | floku | Hkkxokuiqj gkV | 1 | mRØfer e/; fo¦ky;] ljk; iMkSyh | ASIANA CONSTRACT PVT LTD 9431088485 |  |  | 340.54 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky;] tqvkQj | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;][kfM+;k Vksyk | [9 empty] | 1
31 | S.S.S-368 | floku | xqBuh | 1 | e/; fo¦ky;] cdqykjh | AMIT KUMAR CHATURVEDI 7562033432 |  |  | 229.26 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 24.92
|  |  |  | 2 | e/; fo¦ky;] rkyh | [7 empty] | 1
32 | S.S.S-369(A) | floku | j?kqukFkiqj | 1 | e/; fo¦ky;] fn?koyh;k | SUBHASH KUMAR SUBHASH,9934211227 |  |  | 227.51 |  |  | 15 Months | 1
33 | S.S.S-369(B) |  |  | 1 | e/; fo¦ky;] uoknk | SIENN SECURITY PRIVATE LIMITED,9708011111 | [6 empty] | 1
34 | S.S.S-370(A) | floku | fllou | 1 | e/; fo¦ky;] iM+jh | DURGA PRATAP SINGH,7781003700 |  |  | 226.93 |  |  | 15 Months |  |  |  | 1
35 | S.S.S-370(B) |  |  | 1 | e/; fo¦ky;] Hkkxj | DURGA PRATAP SINGH,7781003700 | [6 empty] | 1
36 | S.S.S-371 | floku | thjknsbZ | 1 | e/; fo¦ky;] latyiqj | RENU DEVI 9771455967 |  |  | 113.65 |  |  | 15 Months | 1
37 | S.S.S-372 | floku | xksjs;kdksBh | 1 | mRØfer e/; fo¦ky;] e>ofy;k | ASIANA CONSTRACT PVT LTD 9431088485 |  |  | 114.22 |  |  | 15 Months |  |  |  | 1
38 | S.S.S-373 | floku | ip:[kh | 1 | e/; fo¦ky;] orZofy;k | MD RAFIQUE,8292149970 |  |  | 112.81 |  |  | 15 Months | 1
| Total No. of Schools |  |  | 74 |  |  |  |  | 8127.08 |  |  |  | 18 | 6 | 4 | 11 | 5 | 18 | 0 | 5 | 4 | 0 | 1588.77