## Summary
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School) | [19 empty] | Date:-31.05.2015
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[12 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna (East) | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E., BSEIDC, Div.-Patna (West) | 5 | 15 | 1788.99 | 2 | 8 | 1788.99 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 7 | 0 | 0 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 16 | 36 | 0 | 11 | 17 | 0 | 0 | 1 | 0 | 1 | 3 | 0 | 0 | 0 | 12 | 5 | 0 | 0 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) , E.E. BSEIDC, Div.-Bhagalpur | 17 | 28 | 0 | 6 | 14 | 0 | 0 | 1 | 0 | 4 | 4 | 0 | 0 | 1 | 4 | 10 | 0 | 0 |  | 0
5 | MUNGER | Surendra Kumar (9939599803), E.E. BSEIDC, Div.-Munger | 27 | 51 | 0 | 13 | 20 | 0 | 0 | 7 | 2 | 2 | 6 | 0 | 0 | 0 | 3 | 17 | 0 | 0 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 21 | 24 | 0 | 14 | 16 | 0 | 0 | 1 | 3 | 1 | 1 | 1 | 1 | 0 | 8 | 8 | 0 | 0 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 52 | 81 | 0 | 42 | 67 | 0 | 5 | 13 | 10 | 6 | 11 | 0 | 2 | 2 | 18 | 49 | 0 | 0 |  | 0
8 | TIRHUT (EAST) | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 12 | 19 | 0 | 6 | 8 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 5 | 3 | 0 | 0 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha, (8544126916), E.E. BSEIDC, Div.- Tirhut (West) | 26 | 38 | 0 | 22 | 29 | 0 | 3 | 5 | 1 | 4 | 4 | 5 | 0 | 0 | 7 | 22 | 0 | 0 |  | 0
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 25 | 31 | 0 | 15 | 19 | 0 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 2 | 7 | 12 | 0 | 0 |  | 0
11 | SARAN | Uday Kumar Das, (9431821558) EE BSEIDC, Div.- Saran | 2 | 10 | 0 | 2 | 10 | 0 | 2 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 4 | 6 | 0 | 0 |  | 0
Total (SSSM) |  |  | 208 | 356 | 1788.99 | 133 | 208 | 1788.99 | 12 | 33 | 21 | 23 | 30 | 8 | 6 | 6 | 69 | 139 | 0 | 0 |  | 0

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- PATNA (EAST) - Patna, Nalanda & Bhojpur | [21 empty] | Date:-31.05.2015
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Aggrement No & date | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | USSS-26 | ukyUnk |  | 1 | Middle School, Basuan | Tender Process
|  |  |  | 2 | Middle School, Malikpur
|  |  |  | 3 | Middle School, Mohaddinpur
|  |  |  | 4 | Middle School, Jagdishpur Tayari
|  |  |  | 5 | Middle School, Puraini
|  |  |  | 6 | Middle School, Lodipur
2 | USSS-27 | iVuk |  | 1 | Middle School, Diwra | Tender Process
|  |  |  | 2 | Middle School, Samstichak
|  |  |  | 3 | Middle School, Pirbarhouna
|  |  |  | 4 | Middle School, Gangachak
3 | USSS-28 | iVuk |  | 1 | Middle School, Karai | Tender Process
4 | USSS-29 | Hkkstiqj |  | 1 | Govt. Middle School, Kudariya Parshurampur | Tender Process
|  |  |  | 2 | Upgraded Middle School, Paiga
|  |  |  | 3 | Upgraded Middle School, Barouli
|  |  |  | 4 | Middle School, Barka Dumra
|  |  |  | 5 | Upgraded Middle School, Dadiyabag
|  |  |  | 6 | Upgraded Middle School, Bhoparpur
5 | USSS-30 | Hkkstiqj |  | 1 | Middle School, Sara | Tender Process
|  |  |  | 2 | Middle School, Bhakura
|  |  |  | 3 | Middle School, Dhanpura
|  |  |  | 4 | Middle School, Perhap
|  |  |  | 5 | Middle School, Nonuar
|  |  |  | 6 | Middle School, Purhara
Total Number of Schools |  |  |  | 23 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of USSS
Name of Division :- PATNA (WEST) - Buxar, Rohtas & Kaimur | [21 empty] | Date:-30.04.2015
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Aggrement No & date | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | USSS-31 | बक्‍सर | ब्रहम्‍पुर | 1 | Middle School, Bhadwar | Tender Process |  |  | 339.23
|  |  | ब्रहम्‍पुर | 2 | Girl Middle School, Akrasi |  | 9334745882
2 | USSS-32 | भभुआ कैमूर | चैनपुर | 1 | Middle School, Dhardihan | KRISHNA | 9334383960 |  | 558 | [5 empty] | 1
|  |  | चॉंद | 2 | Upgraded Middle School, Chouri |  | 9939871932 |  |  |  |  | 1 | [10 empty] | Encrochment
|  |  | भगवानपुर | 3 | Middle School, Dadar | [13 empty] | 1 |  |  |  | Sill level of FF
|  |  | रामपुर | 4 | Middle School, Lohandi | [8 empty] | 1
|  |  | मोहनियॉं | 5 | Middle School, Badhani | [9 empty] | 1
3 | USSS-33 | रोहतास | दावत | 1 | Middle School, Parmdiha | Tender Process |  |  | 334.61
|  |  | नोखा | 2 | Middle School, Hathini
|  |  | काराकाट | 3 | Middle School, Itdhiyan
4 | USSS-34 | रोहतास | अकोढ़ीगोला | 1 | Middle School, Gobardhanpur | SHALINI SINGH |  |  | 331.16 |  |  |  |  | 1
|  |  | डिहरी | 2 | Middle School, Tandwa | [10 empty] | 1
|  |  | काराकाट | 3 | Middle School, Danwar | [10 empty] | 1
5 | USSS-35 | रोहतास | करहगर | 1 | Upgraded Middle School, Rehari | Tender Process |  |  | 225.99
|  |  | रोहतास | 2 | Middle School, Majhiyawan
| Total No. of Schools |  |  | 15 |  |  |  |  | 1788.99 |  |  | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0

## Magadh
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- MAGADH | [24 empty] | Date:-31.05.2015
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block |  | S.N. | Name of School | Name of Agency | Agency Address and Mobile No | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[15 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[19 empty] | LL | RL | LL | RL
1 | USSS-36 | tgkukckn |  | 1 | 1 | Middle School, Ahiyasa | Tender Process
|  |  |  | 2 | 2 | Middle School,Sewnon
|  |  |  | 3 | 3 | Middle School, Dewra
2 | USSS-37 | vkSjaaxkckn |  | 1 | 1 | Middle School, Kusumbasdiha | Tender Process
|  |  |  | 2 | 2 | Middle School, Pandu
3 | USSS-38 | vkSjaaxkckn |  | 1 | 1 | Middle School, Gamharia | MS MATESHWARI CONSTRUCTION, 7766886737 | [7 empty] | 1
|  |  |  | 2 | 2 | Middle School,Sondiha | [5 empty] | 0 |  |  | 1
|  |  |  | 3 | 3 | Middle School, Raslpur | [8 empty] | 1
4 | USSS-39 | vkSjaaxkckn |  | 1 | 1 | Middle School, Chourahi | MS MATESHWARI CONSTRUCTION, 7766886737 | [7 empty] | 1
|  |  |  | 2 | 2 | Middle School, Sonbarsa | [8 empty] | 1
|  |  |  | 3 | 3 | Middle School, Dandwan | [8 empty] | 1
5 | USSS-40 | vkSjaaxkckn |  | 1 | 1 | Middle School, Meh | MANOJ SINGH, 9939822131, 7033944511 | [7 empty] | 1
|  |  |  | 2 | 2 | Middle School, Tamoli | [8 empty] | 1
6 | USSS-41 | x;k |  | 1 | 1 | Middle School, Shyamnagar Nima | Tender Process
|  |  |  | 2 | 2 | Middle School, Khajuria
|  |  |  | 3 | 3 | Middle School, Parsawan Khurd
|  |  |  | 4 | 4 | Middle School, Belauti
|  |  |  | 5 | 5 | Middle School,Bindhua
7 | USSS-42 | x;k |  | 1 | 1 | Middle School, Sondiha | Tender Process
|  |  |  | 2 | 2 | Middle School, Angara
|  |  |  | 3 | 3 | Middle School, Punakalan
|  |  |  | 4 | 4 | Middle School, Noni
8 | USSS-43 | x;k |  | 1 | 1 | Upgraded Middle School, Pater | Mithlesh Kumar Singh, 9931471924 | [12 empty] | 1
|  |  |  | 2 | 2 | Middle School, Bitho | [8 empty] | 1
9 | USSS-44 | uoknk |  | 1 | 1 | Middle School, Bardhauna | Tender Process
|  |  |  | 2 | 2 | Upgraded Middle School, Puraini
|  |  |  | 3 | 3 | Middle School, Kalound
|  |  |  | 4 | 4 | Middle School, Paingari
|  |  |  | 5 | 5 | Upgraded Middle School, Bhatta
10 | USSS-123 | x;k | Gurua | 1 | 1 | Middle School, Mahadev Sthan | SANJAY KUMAR SINGH, 9973456006 | [9 empty] | 1
11 | USSS-130 | tgkukckn | Hulasganj | 1 | 1 | Middle School, Gangapur | M/S A K CHOUDHARY, 9470166345 |  |  |  | 104.36 | [8 empty] | 1
12 | USSS-162(A) | uoknk | Kawakol | 1 | 1 | UPS Rupai | SHRI CHANDRA MOULESHWAR, 9931911023 | [12 empty] | 1
13 | USSS-162(B) |  | Kawakol | 2 | 1 | UPS Lohgarwa | ASHIS RANJAN, 9931215326 | [11 empty] | 1
14 | USSS-163(A) | uoknk | Sirdala | 1 | 1 | UPS Hemja Bhart | MD RAIS KHAN, 9973622799 | [7 empty] | 1
15 | USSS-163(B) |  | Sirdala | 2 | 1 | M.S., Kharsari | SURENDRA KUMAR, 9934447377 | [7 empty] | 1
16 | USSS-163(C) |  | Sirdala | 3 | 1 | UPS Mahuliya Tanr | RAVI JALAN, 9546109122 | [7 empty] | 1
Total Number of Schools |  |  |  |  | 36 | [9 empty] | 12 | 0 | 1 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0

## Bhagalpur
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- BHAGALPUR | [20 empty] | Date:-31.05.2015
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[11 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | USSS-17 | Hkkxyiqj |  | 1 | Middle School Kishanpur | Tender Process
|  |  |  | 2 | Middle School Tarchha
2 | USSS-18 | Hkkxyiqj |  | 1 | Middle School Ghanshyamchak | Tender Process
3 | USSS-19 | Hkkxyiqj |  | 1 | Middle School Kalgiganj | MS Rungta Enterprises, 9431265821 | [9 empty] | 1
|  |  |  | 2 | Middle School Dayalpur | [10 empty] | 1
|  |  |  | 3 | Middle School Siya | [10 empty] | 1
|  |  |  | 4 | Middle School Kishunichak | [10 empty] | 1
4 | USSS-20 | ckadk |  | 1 | Middle School kairi | Tender Process
|  |  |  | 2 | Middle School Bank
|  |  |  | 3 | Middle School Pathdda
1 | USSS-106(A) | ckadk |  | 1 | U.M.S Kerwar | Marcominfra Pvt. Ltd., 9934361315 | [8 empty] | 1
2 | USSS-106(B) |  |  | 1 | U.M.S Burhawa Bathan | Marcominfra Pvt Ltd., 9934361315 |  |  |  |  | 1
3 | USSS-106(C) |  |  | 1 | U.M.S Upar Chak Marhdiya | Marcominfra Pvt. Ltd.,9934361315 |  |  |  |  | 1
4 | USSS-106(D) |  |  | 1 | M.S Jamdaha | Marcominfra Pvt. Ltd., 9934361315 |  |  |  |  | 1
5 | USSS-106(E) |  |  | 1 | M.S Mochanma | Marcominfra Pvt. Ltd., 9934361315 | [8 empty] | 1
6 | USSS-106(F) |  |  | 1 | U.M.S Lila waran | BINOD KUMAR SINGH, 9471749892 | [8 empty] | 1
7 | USSS-106(G) |  |  | 1 | U.M.S Dhevermoh | Tender Process
8 | USSS-107 | ckadk |  | 1 | M.S Bhavan Kormama | Tender Process
9 | USSS-108(A) | ckadk |  | 1 | M.S Madari | Tender Process
10 | USSS-108(B) |  |  | 1 | U.M.S Phaga | NIWESH KUMAR, 9576272505 | [6 empty] | 1
11 | USSS-109 | ckadk | Chandan | 1 | U.M.S Koriya | BINOD KUMAR SINGH, 9471749892 | [12 empty] | 1
|  |  | Chandan | 2 | M.S. Kendwar | [9 empty] | 1
12 | USSS-110 | ckadk |  | 1 | U.M.S Amjora | Tender Process
13 | USSS-111 | ckadk |  | 1 | U.M.S Hasiya | Tender Process
14 | USSS-112(A) | ckadk |  | 1 | M.S Darshniya | Tender Process
15 | USSS-112(B) |  |  | 1 | U.M.S, Bounka | Tender Process
16 | USSS-112(C) |  |  | 1 | U.M.S Chariya | Tender Process
17 | USSS-113 | Hkkxyiqj |  | 1 | U.M.S Asiachak | Rajendra Kumar |  |  |  |  | 1
Total Number of Schools |  |  |  | 28 | [6 empty] | 4 | 0 | 1 | 0 | 4 | 4 | 0 | 0 | 1 | 0 | 0

## Munger
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- MUNGER | [21 empty] | Date:-31.05.2015
Name & contact no. of EE :-Surendra Kumar (9939599803), Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | USSS-21 | ewaxsj |  | 1 | Middle School Harinmar Bishunpur | Tender Process
|  |  |  | 2 | Middle School Manik Mandal Tola
|  |  |  | 3 | Middle School Kalyanpur
|  |  |  | 4 | Middle School Teghara
|  |  |  | 5 | Middle School Dhudhaladih
2 | USSS-22 | ewaxsj |  | 1 | Middle School Ramcharit Maidan | Tender Process
|  |  |  | 2 | Middle School Madhura
|  |  |  | 3 | Middle School, Dhobai
|  |  |  | 4 | Middle School Nabgoi
3 | USSS-23 | y[khljk; |  | 1 | Middle School, Bahachha | SUGEET KUMAR,9504681342 | [10 empty] | 1
|  |  |  | 2 | Middle School Tarhari | [12 empty] | 1
|  |  |  | 3 | Middle School Nongarh | [12 empty] | 1
|  |  |  | 4 | Upgraded Middle School Surari | [7 empty] | 1
4 | USSS-24 | y[khljk; |  | 1 | Upgraded Middle School Bihraura | Tender Process
|  |  |  | 2 | Middle School Pokhrama
|  |  |  | 3 | Upgraded Middle School Dhoni Kundi
5 | USSS-25 | 'ks[kiqjk |  | 1 | Middle School, Akrama | Epitome Construction Pvt Ltd,8935825344 | [8 empty] | 1
|  |  |  | 2 | Upgraded Middle School, Diha | [10 empty] | 1
|  |  |  | 3 | Middle School, Kutout | [12 empty] | 1
6 | USSS-45 | tewbZ |  | 1 | Upgraded Middle School, Harla | Tender Process
|  |  |  | 2 | Middle School, Kairakado
|  |  |  | 3 | Middle School, Shobhakhan
|  |  |  | 4 | Middle School, Abgila Chourasa
7 | USSS-47 | Munger | Birpur | 1 | Middle School Parra | Tender Process
|  |  | Bakhari | 2 | Middle School Lauchhe
|  |  | Birpur | 3 | Middle School Kharmauli
|  |  | Sahebpur Kamal | 4 | Middle School Hira Tol
|  |  | Mansurchak | 5 | Middle School Makdhampur
8 | USSS-48 | Munger | Begusarai | 1 | Middle School Akaha | Tender Process
|  | Munger | Begusarai | 2 | Middle School Bhitsari
9 | USSS -124(A) | Munger | Khaira | 1 | M S Bujhayat | ASHOK AND CO NIVAS PVT LTD,9006613016 | [8 empty] | 1
10 | USSS -124(B) |  | Khaira | 1 | M.S Ghari Bishanpur | ASHOK AND CO NIVAS PVT LTD,9006613016 | [8 empty] | 1
11 | USSS -124(C) |  | Khaira | 1 | M S Ghari | Tender Process
12 | USSS-125(A) | Munger | Chakai | 1 | M S Saron | SUDHIR KUMAR,9973392397 | [11 empty] | 1
13 | USSS-125(B) |  | Chakai | 1 | M S Kiyajori | SUDHIR KUMAR,9973392397 | [11 empty] | 1
14 | USSS-125(C) |  | Chakai | 1 | M S Bamdah | AGRAGAMI INDIA CONSTRUCTION PRIVATE LIMITED,9939029899 | [11 empty] | 1
15 | USSS-125(D) |  | Chakai | 1 | M S Kewal | Tender Process
16 | USSS-126(A) | tewbZ |  | 1 | URaktrohaniya | RAJENDRA KUMAR,9939195777 | [8 empty] | 1
17 | USSS-126(B) |  |  | 1 | M S Sarebad | Tender Process
18 | USSS-126(C) |  |  | 1 | M S Agahra | Tender Process
19 | USSS-126(D) |  |  | 1 | M.S Charkapathar | Tender Process
20 | USSS-127(A) | teqbZ |  | 1 | M .S. Sewa | Tender Process
21 | USSS-127(B) |  |  | 1 | M,S,KEWAL | ASHOK AND CO NIVAS PVT LTD,9006613016 | [10 empty] | 1
22 | USSS-128 | teqbZ |  | 1 | M S Borwa | RAJENDRA KUMAR9939195777, | [9 empty] | 1
|  |  |  | 2 | U M S Chapa | [9 empty] | 1
23 | USSS-129(A) | teqbZ |  | 1 | U M S Hathiyawar Taljhari | ASHOK KUMAR SINGH, 8969398786 | [8 empty] | 1
24 | USSS-129(B) |  |  | 1 | U M S Taliyadih | MANGLAM CONSTRUCTION, 7631507878 | [6 empty] | 1
25 | USSS-129(C) |  |  | 1 | U M S Bela | MUKESH KUMAR,9973462715 | [8 empty] | 1
26 | USSS-129(D) |  |  | 1 | U M S Karra | Tender Process
27 | USSS-151 | y[khljk; |  | 1 | U M S Singhaul Tetariaya | Tender Process
28 | USSS-143 | [kxM+h;k |  | 1 | MS Icharua | Lal Babu Prasad | [6 empty] | 1
Total Number of Schools |  |  |  | 51 | [8 empty] | 3 | 0 | 7 | 2 | 2 | 6 | 0 | 0 | 0 | 0 | 0

## Kosi
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- KOSI | [20 empty] | Date:-31.05.2015
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | USSS-10 | lgjlk |  | 1 | Middle School Dhamsaina | Tender Process
2 | USSS-152 | e/ksiqjk |  | 1 | M.S Sonbarsha | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775, 9472103786 | [12 empty] | 1
3 | USSS-153 | e/ksiqjk |  | 1 | M.S. Rahi | Tender Process | [16 empty] | Cancel
4 | USSS-154 | e/ksiqjk |  | 1 | M.S Bhelva | SUNITA DEVI, 9162524068 | [8 empty] | 1
|  |  |  | 2 | M.S.Gadhiya | [6 empty] | 1
5 | USSS-155 | e/ksiqjk |  | 1 | M.S.Uda | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 | [10 empty] | 1
6 | USSS-195 | lgjlk |  | 1 | MS Partaha Barhara | Tender Process
7 | USSS-196 | lgjlk |  | 1 | MS Dhanupra | JEEVAN JYOTI CONTRACTORS PVT LTD,9431247387 | [9 empty] | 1
8 | USSS-197 | lgjlk |  | 1 | MS Samhar | JEEVAN JYOTI CONTRACTORS PVT LTD,9431247387 | [8 empty] | 1
9 | USSS-204 | lqikSy |  | 1 | MS Parmanandpur | Tender Process
|  |  |  | 2 | MS Bhawani pur
10 | USSS-205 | lqikSy |  | 1 | MS Bhimpur | Tender Process
11 | USSS-206(A) | lqikSy |  | 1 | MS sisauni | AKASH KUMAR,9334362048 | [5 empty] | 1
12 | USSS-206(B) |  |  | 1 | MS sukhashan | PRIYA RANJAN,9931546525 | [7 empty] | 1
13 | USSS-207(A) | lqikSy |  | 1 | MS saroja Bela | Tender Process
14 | USSS-207(B) |  |  | 1 | MS rasuaar | TRISHUL CONSTRUCTIONS,8252940655 | [11 empty] | 1
15 | USSS-207(C) |  |  | 1 | MS Hari | Tender Process
16 | USSS-208 | lqikSy |  | 1 | MS Bela sringarmoti | YOGENDRA PRASAD YADAV, 9631856613 | [5 empty] | 1
17 | USSS-209 | lqikSy |  | 1 | MS Lalganj | VATSALYA BUILDCON PRIVATE LIMITED, 9430965119 | [5 empty] | 1
18 | USSS-210 | lqikSy |  | 1 | MS Basbitti | Ashok Kumar, 9431091558 | [5 empty] | 1
|  |  |  | 2 | MS kaliganj | [6 empty] | 1
19 | USSS-211(A) | lqikSy |  | 1 | Durga MS Laharnia | PRIYA RANJAN, 9931546525 | [5 empty] | 1
20 | USSS-211(B) |  |  | 1 | MS Parsa Garhi | Madan Kumar singh | [5 empty] | 1
21 | USSS-211(C) |  |  | 1 | MS Mogla Ghat nandana | AKASH KUMAR, 9334362048 | [8 empty] | 1
Total Number of Schools |  |  |  | 24 | [7 empty] | 8 | 0 | 1 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Note on G10: Cancel

## Purnea
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- PURNEA | [21 empty] | Date:-31.05.2015
Name & contact no. of EE :-Manoj Kumar Pandey (9661818750) , AE :- Madan Mohan (9431413291), JE :- Uttam Kr. (9973563185)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | USSS-6 | vjfj;k |  | 1 | Middle School Mangalwar Chariya | Tender Process
|  |  |  | 2 | Middle School Maldwar East
2 | USSS-7 | fd'kuxat |  | 1 | Middle School Daula | BIRENDRA KUMAR SINGH,9473440405 | [6 empty] | 1
3 | USSS-8 | iwf.kZ;k¡ |  | 1 | Middle School Rupauli | Tender Process
|  |  |  | 2 | Middle School Rampur Tilak East
|  |  |  | 3 | Middle School ,Mahendra Nagar Diyara
4 | USSS-9 | dfVgkj |  | 1 | Middle School Belwa | BIRENDRA KUMAR SINGH, 9473440405 | [6 empty] | 1
|  |  |  | 2 | Middle School Kharsauta | [10 empty] | 1
|  |  |  | 3 | Middle School Kalyan Gaon | [8 empty] | 1
|  |  |  | 4 | Middle School Rampur | [9 empty] | 1
5 | USSS-101 | vjfj;k |  | 1 | A.M.S. Kala Balua | PRAKASH KUMAR SAH,9162909186 | [14 empty] | 1
6 | USSS-102 | vjfj;k |  | 1 | M.S. Barmasiya | Tender Process
7 | USSS-103 | vjfj;k |  | 1 | U.M.S. Sonamani Godam | PRAKRITI CONTRACTORS PVT LTD,9431440749 | [6 empty] | 1
8 | USSS-104 | vjfj;k |  | 1 | U.M.S. Subhankarpur | ASHA CONSTRUCTION,9431412711 | [7 empty] | 1
9 | USSS-105(A) | vjfj;k |  | 1 | M.S. Basmatiya | AKHILESH SINGH,9470048339 | [11 empty] | 1
10 | USSS-105(B) |  |  | 1 | M.S. Khaira | MD ARFIN,9006212706 | [8 empty] | 1
11 | USSS-105(C) |  |  | 1 | M.S. Maheshpatti | RABINDRA SINGH,9472524322 | [11 empty] | 1
12 | USSS-105(D) |  |  | 1 | M.S. Tamganj | SHAILENDRA KUMAR,9334855523 | [6 empty] | 1
13 | USSS-131 | dVhgkj |  | 1 | M.S. Bathilli | Tender Process
14 | USSS-132 | dVhgkj |  | 1 | M.S. Dwasay | BIRENDRA KUMAR SINGH, 9473440405 | [11 empty] | 1
|  |  |  | 2 | R M.S. Souriya | [12 empty] | 1
15 | USSS-133 | dVhgkj |  | 1 | M.S. Padam Pur | PRAKASH KUMAR SAH,9162909186 | [11 empty] | 1
16 | USSS-134 | dVhgkj |  | 1 | M.S. Makai Pur | BIRENDRA KUMAR SINGH, 9473440405 | [11 empty] | 1
|  |  |  | 2 | M.S. Kheria | [14 empty] | 1
|  |  |  | 3 | M.S. Pawai | [11 empty] | 1
|  |  |  | 4 | M.S. Rautara | [14 empty] | 1
|  |  |  | 5 | M.S. Dighree | [12 empty] | 1
|  |  |  | 6 | M.S. Chandwa Rupaspur | [9 empty] | 1
17 | USSS-135 | dVhgkj |  | 1 | M.S. Kathria | BIRENDRA KUMAR SINGH, 9473440405 | [6 empty] | 1
18 | USSS-136 | dVhgkj |  | 1 | M.S. Nawabganj | BIRENDRA KUMAR SINGH, 9473440405 | [11 empty] | 1
|  |  |  | 2 | M.S. Chakla Khaira | [11 empty] | 1
19 | USSS-137 | dVhgkj |  | 1 | M.S. Bharsia | BIRENDRA KUMAR SINGH, 9473440405 | [8 empty] | 1
|  |  |  | 2 | M.S. Mohammad Nagar Rajdhani | [12 empty] | 1
|  |  |  | 3 | M.S. Dermahi | [8 empty] | 1
|  |  |  | 4 | U M.S. Musapur Ranga Kol | [11 empty] | 1
|  |  |  | 5 | U M.S. Tapua Gobindpur | [11 empty] | 1
20 | USSS-138(A) | dVhgkj |  | 1 | U M.S. Hajiyaar Palsa | MS EXCELLENT CONSTRUCTION, 9472021967 | [9 empty] | 1
21 | USSS-138(B) |  |  | 1 | U M.S. Chilha Para | MS EXCELLENT CONSTRUCTION, 9472021967 | [6 empty] | 1 | [10 empty] | insufficient land
22 | USSS-139 | dVhgkj |  | 1 | M.S. Parbheli | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 | [11 empty] | 1
23 | USSS-140(A) | dVhgkj |  | 1 | M.S. Mukuria Dakshin Tola | RANA BIRESH PRATAP SINGH, 9430683578 | [8 empty] | 1
24 | USSS-140(B) |  |  | 1 | M.S. Sikitia | MS EXCELLENT CONSTRUCTION, 9472021967 | [6 empty] | 1
25 | USSS-141 | dVhgkj |  | 1 | M.S. Budhanagar | Tender Process
26 | USSS-142 | dVhgkj |  | 1 | M.S. Kanta Kosh | PRAKASH KUMAR SAH,9162909186 | [14 empty] | 1
27 | USSS-144 | fd'kuxat |  | 1 | UMS Teusa | ASHOK KUMAR SINGH,9430467620 | [6 empty] | 1
28 | USSS-145 | fd'kuxat |  | 1 | M.S Farabari | BIRENDRA KUMAR SINGH, 9473440405 | [6 empty] | 1
|  |  |  | 2 | M.S Kuwari | [9 empty] | 1
29 | USSS-146 | fd'kuxat |  | 1 | M.S Gilhabari Kanya | BIRENDRA KUMAR SINGH, 9473440405 | [8 empty] | 1
|  |  |  | 2 | M.S Shitalpur | [10 empty] | 1
|  |  |  | 3 | U. M.S Kusiyari | [10 empty] | 1
|  |  |  | 4 | U.M,S Nawnadi | [9 empty] | 1
30 | USSS-147 | fd'kuxat |  | 1 | M.S Bourigacch | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1
|  |  |  | 2 | M.S Ruidhasa | [8 empty] | 1
|  |  |  | 3 | M.S Barchondi | [10 empty] | 1
31 | USSS-148 | fd'kuxat |  | 1 | M.S Talgacch | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1
|  |  |  | 2 | M.S. Gandharvdanga | [8 empty] | 1
|  |  |  | 3 | U.M.S Talwarbandha | [10 empty] | 1
32 | USSS-149 | fd'kuxat |  | 1 | U.M.S Masangoan | BIRENDRA KUMAR SINGH, 9473440405 | [8 empty] | 1
|  |  |  | 2 | M.S Shameswar | [10 empty] | 1
|  |  |  | 3 | M.S Natuapara | [7 empty] | 1
|  |  |  | 4 | M.S Khodaganj | [11 empty] | 1
|  |  |  | 5 | U.M.S Gopalpur Haat | [11 empty] | 1
33 | USSS-150 | fd'kuxat |  | 1 | U.M.S Kochgarh Purndha | BIRENDRA KUMAR SINGH, 9473440405 | [8 empty] | 1
34 | USSS-184 (A) | iwf.kZ;k¡ |  | 1 | M.S. Routi Basha | Tender Process
35 | USSS-184 (B) |  |  | 1 | M.S. Talbari | Tender Process
36 | USSS-185 | iwf.kZ;k¡ |  | 1 | M.S. Sirsi | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 | [6 empty] | 1
37 | USSS-186 | iwf.kZ;k¡ |  | 1 | M.S. Amirganj | Tender Process
38 | USSS-187 | iwf.kZ;k¡ |  | 1 | M.S. Laxmipur | VATSALYA BUILDCON PRIVATE LIMITED, 9430965119 | [11 empty] | 1
39 | USSS-188 (A) | iwf.kZ;k¡ |  | 1 | M.S. Sauraha | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | [9 empty] | 1
40 | USSS-188 (B) |  |  | 1 | M.S. Pranpatti | HARIMOHAN BISHWAS,9955713757 | [6 empty] | 1
41 | USSS-188 (C) |  |  | 1 | M.S. Kajha | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | [8 empty] | 1
42 | USSS-189 (A) | iwf.kZ;k¡ |  | 1 | M.S.Chandpur Bhanha | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED,9973239801 | [6 empty] | 1
43 | USSS-189 (B) |  |  | 1 | M.S. Harimurhi | Tender Process
44 | USSS-190 (A) | iwf.kZ;k¡ |  | 1 | M.S. Dumri | Tender Process
45 | USSS-190 (B) |  |  | 1 | M.S. Goriar | ADITYA KUMAR SINGH,9546045749 | [8 empty] | 1
46 | USSS-191 | iwf.kZ;k¡ |  | 1 | M.S.Bishanpur | MD JAVIR, 9955418718 | [6 empty] | 1
47 | USSS-192 (A) | iwf.kZ;k¡ |  | 1 | M.S. Sanjha Ghat | MD MOJAMMIL HUSSAIN,9939824905 | [6 empty] | 1
48 | USSS-192 (B) |  |  | 1 | M.S.Champawati | MD MOJAMMIL HUSSAIN,9939824905 | [6 empty] | 1
49 | USSS-193 | iwf.kZ;k¡ |  | 1 | I. M. S. Garhi Baluwa | MS SHINING MADHUSUDHAN CONSTRUCTION,9431884876 | [8 empty] | 1
50 | USSS-194 (A) | iwf.kZ;k¡ |  | 1 | M.S. Kodheli | Tender Process
51 | USSS-194 (B) |  |  | 1 | M.S. Belgchhi | HARIMOHAN BISHWAS,9955713757 | [6 empty] | 1
52 | USSS-194 (C) |  |  | 1 | M.S. Babhni | HARIMOHAN BISHWAS,9955713757 | [6 empty] | 1
Total Number of Schools |  |  |  | 81 | [8 empty] | 18 | 5 | 13 | 10 | 6 | 11 | 0 | 2 | 2 | 0 | 0
Note on G26: Cancel
Note on G49: Cancel

## Tirhut (East)
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- TIRHUT (EAST) - Vaishali, Muzaffarpur & Sitamarhi | [22 empty] | Date:-31.05.2015
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | USSS-4 | lhrke<+h |  | 1 | Middle School Sutihara | Tender Process
|  |  |  | 2 | Middle School Bhantawari
|  |  |  | 3 | Middle School Rajwara
2 | USSS-12 | eqt¶Qjiqj |  | 1 | Middle School Bariyarpur | S R CONSTRUCTIONS PVT LTD,7739441850 | [9 empty] | 1
|  |  |  | 2 | Middle School Dhabauli | [7 empty] | 1
|  |  |  | 3 | Middle School Lakhanpur | [9 empty] | 1
3 | USSS-13 | eqt¶Qjiqj |  | 1 | Middle School Bhatauna | Tender Process
|  |  |  | 2 | Middle School Sirkohiya
4 | USSS-15 | oS'kkyh |  | 1 | Upgraded Middle School Panapur Silaut | Tender Process
|  |  |  | 2 | Upgraded Middle School Totha
|  |  |  | 3 | Middle School Shital Bhakurhar
5 | USSS-200 | lhrke<+h |  | 1 | M.S.Bishanpur | Tender Process
6 | USSS-201 | lhrke<+h |  | 1 | M.S. Indarwa-1 | RANJEETPUR CONSTRUCTIONS PRIVATE LIMITED,9334329734 | [14 empty] | 1
7 | USSS-202(A) | lhrke<+h |  | 1 | M.S.Mahuawa | Tender Process
8 | USSS-202(B) |  |  | 1 | M.S.Ghaghara Bazar | MANOJ KUMAR AZAD,9431636894 | [6 empty] | 1
9 | USSS-203(A) | lhrke<+h |  | 1 | M.S.Banaul | AMRESH KUMAR,9525120333 | [6 empty] | 1
10 | USSS-203(B) |  |  | 1 | M.S.Mahisautha | AKHILESH KUMAR CHAUDHARI,9431415700 | [6 empty] | 1
11 | USSS-212 | oS'kkyh |  | 1 | Gov.M.S.Baksama | RANA CONSTRUCTION, 9334104328 | [6 empty] | 1
12 | USSS-213 | oS'kkyh |  | 1 | MS Ajijpur Chande | Tender Process
Total Number of Schools |  |  |  | 19 | [8 empty] | 5 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0

## Tirhut (West)
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- TIRHUT (WEST) - East Champaran, West Champaran & Shivhar | [22 empty] | Date:-31.05.2015
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | USSS-1 | if'pe pEikj.k |  | 1 | Govt. Middle School Kumhiya | Tender Process
|  |  |  | 2 | Middle School Panchgawa
|  |  |  | 3 | Middle School Donwar
|  |  |  | 4 | Ugraded middle school malahi tola
2 | USSS-2 | iwohZ pEikj.k |  | 1 | Middle School Mali | ASIANA CONSTRACT PVT LTD, 9431088485 | [6 empty] | 1
|  |  |  | 2 | Middle School Chand parsa | [8 empty] | 1
|  |  |  | 3 | Middle School Sitalpur | [8 empty] | 1
3 | USSS-3 | f'kogj |  | 1 | Middle School Dhankaul | Tender Process
|  |  |  | 2 | Middle School Narayanpur
|  |  |  | 3 | Middle School Khairadarp
4 | USSS-164(A) | if'pe pEikj.k | Chanpatia | 1 | UMS Laukaria | MADHU ANAND CONSTRUCTION PVT LTD,9006671588 | [9 empty] | 1
5 | USSS-164(B) |  |  | 1 | MS Barharawa | Sanjay Kumar Jha | [7 empty] | 1
6 | USSS-165 | if'pe pEikj.k |  | 1 | UMS Kaulapur Bazar | MADHU ANAND CONSTRUCTION PVT LTD,9006671588 | [10 empty] | 1
7 | USSS-166 | if'pe pEikj.k |  | 1 | MS Ojhwalia | IRFAN AKHTAR,9162628011 | [12 empty] | 1
8 | USSS-167 | if'pe pEikj.k |  | 1 | MS Birawa | SHAKAL DEO MISHRA, 9006385958 | [8 empty] | 1
9 | USSS-168 | if'pe pEikj.k |  | 1 | UMS Bathuwaria | SHARDA CHANDEL CONTRACT PVT, 8986283451 | [10 empty] | 1
10 | USSS-169 | if'pe pEikj.k |  | 1 | MS Gonauli | AWADHESH SHUKLA, 9431203836 | [12 empty] | 1
|  |  |  | 2 | UMS Jawaharpur | [13 empty] | 1
11 | USSS-170 | if'pe pEikj.k |  | 1 | UMS Ghagwa Rupahi | SHARDA CHANDEL CONTRACT PVT, 8986283451 | [12 empty] | 1
12 | USSS-171 | if'pe pEikj.k |  | 1 | UMS Madhubani | SHARDA CHANDEL CONTRACT PVT,8986283451 | [12 empty] | 1
13 | USSS-172 | if'pe pEikj.k |  | 1 | UMS Sugha Bhawanipur | MS SARASWATI COMPANY, 9431491241 | [6 empty] | 1
14 | USSS-173 | if'pe pEikj.k |  | 1 | UMS Pipra Colony | MS C S CONSTRUCTION, | [11 empty] | 1
|  |  |  | 2 | MS Semri Dumari | [12 empty] | 1
|  |  |  | 3 | UMS Turkaulia | [12 empty] | 1
15 | USSS-174(A) | if'pe pEikj.k |  | 1 | UMS Sujnahi Ghorahawa | DHANANJAY KUMAR PANDEY, 9955002717 | [10 empty] | 1
16 | USSS-174(B) |  |  | 2 | UMS Parsauni | SHAKAL DEO MISHRA, 9006385958 | [6 empty] | 1
17 | USSS-175 | iwohZ pEikj.k |  | 1 | UMS Pokhariya | RADHIKA CONSTRUCTION CO7739855654, | [8 empty] | 1
18 | USSS-176 | iwohZ pEikj.k |  | 1 | GMS Ajgarwa | DESHBANDHU KUMAR SINGH, 7739855654 | [6 empty] | 1
19 | USSS-177 | iwohZ pEikj.k |  | 1 | GMS Bankatwa (Boys) | MS C S CONSTRUCTION, | [6 empty] | 1
|  |  |  | 2 | GMS Inarwa Phulwar | [9 empty] | 1
20 | USSS-178 | iwohZ pEikj.k |  | 1 | UMS Dharharwa | ANANTA CONSTRUCTION COMPANY, 7739855654 | [6 empty] | 1
21 | USSS-179 | iwohZ pEikj.k |  | 1 | GMS Tonwa | RADHIKA CONSTRUCTION CO7739855654, | [8 empty] | 1
22 | USSS-180 | iwohZ pEikj.k |  | 1 | GMS Murarpur | RAJNISH KUMAR SINGH | [6 empty] | 1
|  |  |  | 2 | GMS Bhada | [11 empty] | 1
23 | USSS-181 | iwohZ pEikj.k |  | 1 | UMS Dhekaha Math | Tender Process
24 | USSS-182 | iwohZ pEikj.k |  | 1 | GMS Majhar | VIKASH KUMAR GUPTA, 8084876850 | [8 empty] | 1
25 | USSS-183 | iwohZ pEikj.k |  | 1 | GMS Narha Panapur | DINESH GUPTA, | [11 empty] | 1
26 | USSS-199 | f'kogj |  | 1 | M/S Shyampur | Tender Process
Total Number of Schools |  |  |  | 38 | [8 empty] | 7 | 3 | 5 | 1 | 4 | 4 | 5 | 0 | 0 | 0 | 0

## Darbhanga
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- DARBHANGA | [22 empty] | Date:-31.05.2015
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | USSS-5 | e/kqcuh |  | 1 | Govt. Middle School Rudrapur | Kamlesh Kumar 934808205 | [14 empty] | 1
|  |  |  | 2 | Govt. Middle School Bhatra Ghat | [13 empty] | 1
2 | USSS-11 | njHkaxk |  | 1 | Upgraded Middle School Raj kharwar | Tender Process
|  |  |  | 2 | Upgraded Middle School Tilkeshwar Sthan
|  |  |  | 3 | Upgraded Middle School Raipur
3 | USSS-16 | leLrhiqj |  | 1 | Middle School Isar Tola | Tender Process
4 | USSS-114 | njHkaxk |  | 1 | U.M.S. Kaji Bahera | SANJAY KUMAR | [13 empty] | 1
|  |  |  | 2 | M.S. Basant | [14 empty] | 1
5 | USSS-115 | njHkaxk |  | 1 | M.S. Ghosrama | Tender Process
6 | USSS-116 (A) | njHkaxk |  | 1 | M.S. Basatpur | Madhav Construction, Darbhanga | [7 empty] | 1
7 | USSS-116 (B) |  |  | 1 | M.S. Dagarsam | Sanjay Kumar | [7 empty] | 1
8 | USSS-117 | njHkaxk |  | 1 | M.S. Kankpur | Tender Process
9 | USSS-118 | njHkaxk |  | 1 | U.M.S. Ganaun | Tender Process
10 | USSS-119(A) | njHkaxk |  | 1 | M.S. Kahuaa | S K CONSTRUCTION AND COMPANY, 9471006199 | [6 empty] | 1
11 | USSS-119(B) |  |  | 1 | M.S. Tarbara Ganaura | S K CONSTRUCTION AND COMPANY, 9471006199 | [6 empty] | 1
12 | USSS-120 | njHkaxk |  | 1 | U.M.S. Basuara | MALTI SINGH, 9471641892 | [14 empty] | 1
|  |  |  | 2 | U.M.S. Godhiyari | [7 empty] | 1
|  |  |  | 3 | U.M.S. Narsara | [7 empty] | 1
13 | USSS-121 | njHkaxk |  | 1 | U.M.S. Kathra | Tender Process
14 | USSS-122 | njHkaxk |  | 1 | M.S Kothram | Tender Process
15 | USSS-156 | e/kqcuh |  | 1 | Middle School Nagwas | Tender Process
16 | USSS-157 | e/kqcuh |  | 1 | Middle School Gaudhol | KAMLESH KUMAR, 9334808205 | [9 empty] | 1
17 | USSS-158(A) | e/kqcuh |  | 1 | Middle School Majhaura | Tender Process
18 | USSS-158(B) |  |  | 1 | Middle School Amhi | Tender Process
19 | USSS-159 | e/kqcuh |  | 1 | Middle School Gobraura | PRAKRITI CONTRACTORS PVT LTD,9431440749 | [6 empty] | 1
20 | USSS-160(A) | e/kqcuh |  | 1 | Middle School Kurso | MAA VASUNDHARA CONSTRUCTION,9006650591 | [10 empty] | 1
21 | USSS-160(B) |  |  | 1 | UPS Middle School Basipatti | KAMLESH KUMAR, 9334808205 | [9 empty] | 1
22 | USSS-161(A) | e/kqcuh |  | 1 | Middle School Basuki | SUBODH KUMAR, 9973164105 | [6 empty] | 1
23 | USSS-161(B) |  |  | 1 | Middle School Sujatpur | SATISH KUMAR, 8294867362 | [11 empty] | 1
24 | USSS-161(C) |  |  | 1 | Middle School Trimuhan | SHASHI KUMAR DEO, 9934640530 | [10 empty] | 1
25 | USSS-198 | leLrhiqj |  | 1 | Middle School Pulhara | VAISHALI CONSTRUCTION, 9430483150 | [6 empty] | 1
Total Number of Schools |  |  |  | 31 | [8 empty] | 7 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 2 | 0 | 0

## Saran
BSEIDC, PATNA
Progress report for the construction of USSS (Upgraded Senior Secondary School)
Name of Division :- SARAN | [21 empty] | Date:-31.05.2015
Name & contact no. of EE :- Uday Kumar Das (9431821558), AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | USSS-14 | lhoku |  | 1 | Middle School Sahadulpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [6 empty] | 1
|  |  |  | 2 | Middle School Gamiyar | [7 empty] | 1
|  |  |  | 3 | Middle School Daraunda | [13 empty] | 1
|  |  |  | 4 | Middle School, Baluya | [7 empty] | 1
|  |  |  | 5 | Middle School Barka Manjha | [11 empty] | 1
2 | USSS-46 | lhoku |  | 1 | Middle School Sikatiya | SHIV SHANKAR SINGH CONTRACT PVT LTD | [7 empty] | 1
|  |  |  | 2 | Middle School Kilpur | [8 empty] | 1
|  |  |  | 3 | Middle School Pratapur | [9 empty] | 1
|  |  |  | 4 | Middle School Shivpur Sakra | [7 empty] | 1
|  |  |  | 5 | Middle School Balaipur | [9 empty] | 1
Total Number of Schools |  |  |  | 10 | [8 empty] | 4 | 2 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0