## Summary
BSEIDC, PATNA
Progress report for the construction of Girl's Hostel building (2010-11) | [20 empty] | Date:31.10.2014
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | [6 empty] | Check
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna (East) | 8 | 18 | 2397.6427 | 8 | 18 | 2397.6427 |  | 0 | 1 | 1 | 1 | 1 | 3 | 2 | 6 | 3 | 15 | 0 | 873.82 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E. BSEIDC, Div.- Patna (West) | 3 | 6 | 798.68 | 3 | 6 | 798.68 |  | 0 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 6 | 0 | 202.21 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 4 | 9 | 1136.08 | 2 | 4 | 507.01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 172.33 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Bhagalpur | 6 | 11 | 1511.74 | 6 | 11 | 1511.74 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 4 | 1129.26 |  | 0
5 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 3 | 5 | 687.9 | 3 | 5 | 687.9 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 155.01 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 2 | 4 | 560.8 | 2 | 4 | 560.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 3 | 0 | 289.37 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750), E.E. BSEIDC, Div.- Purnia | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
8 | TIRHUT (EAST) | Anil Kumar Singh (9801494702), E.E. , BSEIDC, Div.-Tirhut (East) | 4 | 11 | 1480.3 | 2 | 5 | 669.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 0 | 142.4 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha (8544126916), EE, BSEIDC, Div.- Tirhut (West) | 6 | 12 | 1690.27 | 4 | 8 | 1123.67 |  | 0 | 1 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 8 | 0 | 322.52 |  | 0
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 8 | 20 | 2793.9 | 8 | 20 | 2793.9 |  | 1 | 0 | 0 | 1 | 3 | 5 | 3 | 6 | 1 | 19 | 0 | 1277.04 |  | 0
11 | SARAN | Uday Kumar Das (9431821558), EE BSEIDC, Div.- Saran | 7 | 17 | 2318.9 | 7 | 17 | 2318.9 |  | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 9 | 2 | 15 | 0 | 1195.03 |  | 0
Total (Girl's Hostel) |  |  | 51 | 113 | 15376.2126 | 45 | 98 | 13369.5226 | 0 | 1 | 4 | 3 | 6 | 9 | 11 | 9 | 37 | 14 | 80 | 4 | 5758.99 |  | 0

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- PATNA (EAST) - Patna , Nalanda & Bhojpur | [20 empty] | Date:31.10.2014
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | G.H-101 | Patna | Daniyawa | 1 | Rajkiyakrit H.S., Sigariyawa | Shristi Developers pvt.Ltd Krishiutpadan Bazar Samiti Katra Bazar Patna City | 268.46 |  |  | 108 SBD of 2013-14/ 18.09.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 126.86
|  |  | Khusrupur | 2 | Rajkiyakrit Mahadeo H.S., Fatuwa, Khusrupur | [13 empty] | 1 |  |  | Finishing-20/10/2014
2 | G.H-102 | Patna | Bakhtiyarpur | 1 | Rajkiyakrit H.S., Salimpur | SATISH KUSUMRAJ | 269.42 |  | 1 | 203 SBD of 2013-14/ 13.01.14 | [10 empty] | 74.77 | Land not available. Site to be changed
|  |  | Belchhi | 2 | Rajkiyakrit H.S., Saksohar | [12 empty] | 1 |  |  |  | B/W upto RL
3 | G.H-103 | Patna | Paliganj | 1 | Rajkiyakrit H.S., Paliganj | M/s Vivek & co.8/m/23 Bahadurpur Housing colony, Patna-26 | 395.48 |  |  | 135 SBD of 2013-14/ 10.10.2013 | 12 Month |  |  |  | 1 | [5 empty] | 106.43 | GF LL-20/10/2014
|  |  | Dulhin Bazar | 2 | Banshidhari H.S., Bharatpura | [8 empty] | 1 | [7 empty] | Foundation RCC
|  |  | Bikram | 3 | Parwati H.S., Bikram | [12 empty] | 1 |  |  |  | FF RL-20/10/2014
4 | G.H-104 | Patna | Masaurih | 1 | Smt. Girija Kuwar H.S., Masaurih | Shristi Developers pvt.Ltd Krishiutpadan Bazar Samiti Katra Bazar Patna City | 266.39 |  |  | 137 SBD of 2013-14/ 22.10.2013 | 12 Month | [5 empty] | 1 |  |  |  | 60.54 | FF LL-20/10/2014
|  |  | Punpun | 2 | Sahid Ramanand R. Govind H.S., Punpun | [7 empty] | 1 | [8 empty] | E/W
5 | G.H-105 | Patna | Patna Sadar (Gramin) | 1 | Rajkiyakrit Mahanth Hanuman Sharan H.S.School,Rajapur | M/s Vivek & co.8/m/23 Bahadurpur Housing colony, Patna-26 | 397.8127 |  | 1 | [11 empty] | 83.58 | Dispute
|  |  | Danapur | 2 | Baldeo Senior Secondary School, Danapur | [11 empty] | 1 |  |  |  |  | FF LL-20/10/2014
|  |  | Maner | 3 | Rajkiyakrit H/S, Maner | [11 empty] | 1 |  |  |  |  | FF LL-20/10/2014
6 | G.H-106 | Patna | Mokama | 1 | Railway Aided H.S., Mokama | M/S Rama Construction | 265.69 |  |  | 159 SBD of 2013-14/ 26.11.13 | [8 empty] | 1 |  | 161.04
|  |  | Ghoswari | 2 | Rajkiyakrit H.S., Kumhra | [13 empty] | 1 |  |  | Finishing-20/10/2014
7 | G.H-107 | Patna | Barh | 1 | Rajkiyakrit Anugrah Narayan Singh Senior Secondary School, Barh | M/S Rama Construction | 268.32 |  |  | 121 SBD 0f 2013-14/ 4.10.2013 | 12 Month | [7 empty] | 1 |  | 86.99 | Finishing-20/10/2014
|  |  | Pandarak | 2 | Laxmi Narayan Rajbanshi H.S., Dhibar |  |  |  | 1 | [12 empty] | Sufficient Land not available
8 | G.H-108 | Patna | Naubatpur | 1 | Rajkiyakrit H.S., Amarpura | M/s Ananya Construction | 266.07 |  |  | 54 SBD 0f 2013-14/ 19.7.2013 | 12 Month | [7 empty] | 1 |  | 173.61 | Finishing-20/10/2014
|  |  | Sampatchak | 2 | Gramin S.S.School Chakbairiya, Patna | [13 empty] | 1
| Total nos. of school |  |  | 18 |  |  | 2397.6427 | 0 | 3 |  |  | 0 | 1 | 1 | 1 | 1 | 3 | 2 | 6 | 0 | 873.82

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- PATNA (WEST) - Buxar, Rohtas & Kaimur (Bhabhuaa) | [20 empty] | Date:31.10.2014
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | G.H-109 | Buxar | Rajpur | 1 | H.S.Rajpur Compound | Sanjay Kumar 9931589813 | 402.36 | [5 empty] | 1 | [7 empty] | 17.03
|  |  | Itarhi | 2 | H.S.Itarhi | [7 empty] | 1 | [8 empty] | Foundation-17/10/2014
|  |  | Nawanagar | 3 | H.S. Nawanagar | [8 empty] | 1
2 | G.H-110 | Rohtas | Chenari | 1 | Middle School, Khurmabad, Chenari | Manoj kumar singh | 129.46 |  |  | 190 SBD of 2013-14/ 16.12.13 | [8 empty] | 1 |  | 91.65
3 | G.H-111 | Kaimur | Durgawati | 1 | K.G.B.V. Compound | Ajay Kumar singh | 266.86 | [9 empty] | 1 |  |  |  | 93.53
|  |  | Adhaura | 2 | K.G.B.V. Compound | [12 empty] | 1
| Total nos. of school |  |  | 6 |  |  | 798.68 | 0 | 0 |  |  | 0 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 202.21

## Magadh
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- MAGADH | [20 empty] | Date:31.10.2014
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | G.H-112 | Arwal | Karpi | 1 | High School, Karpi | Kaushlendra Kumar | 255.29 |  |  | 4.10.2013 | 12 Month | [7 empty] | 1 |  | 172.33
|  |  | Arwal | 2 | Balika High School, Arwal | [13 empty] | 1
2 | G.H-113 | Jehanabad | Jehanabad | 1 | H.S., Jehanabad | Retender (29.01.2014) | 377.77
|  |  | Kako | 2 | H.S. Pali Bazar
|  |  | Ghosi | 3 | H.S. Ghosi
3 | G.H-114 | Jehanabad | Ratni Faridpur | 1 | H.S. Dayalbagh, Nehalpur | Kaushlendra Kumar | 251.72 |  | 1
|  |  | Makhdumpur | 2 | S.S. Tehta |  |  |  | 1 | [12 empty] | Low land
4 | G.H-115 | Jehanabad | Hulashganj | 1 | H.S. Hulashganj | Retender (29.01.2014) | 251.3
|  |  | Modanganj | 2 | D.N.H.S. Bandhuganj
|  | Total nos. of school |  | 9 |  |  | 1136.08 | 0 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 172.33

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Bhagalpur | [20 empty] | Date:31.10.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | G.H-143 | Bhagalpur | Pirpaiti | 1 | M.S, Simanpur | M/S Rungta Enterprises | 396.23 | [11 empty] | 1 |  | 240.25
|  |  | Kahalgaon | 2 | Ram Sunder H.S, Rampur | [13 empty] | 1
|  |  | Sabour | 3 | H.S, Mamalkha | [13 empty] | 1
2 | G.H-144 | Bhagalpur | Goradih | 1 | M.S, Goradih | M/S Kuhu Construction | 265.93 |  |  | 22.10.2013 | 12 Month | [7 empty] | 1 |  | 186.63
|  |  | Sultanganj | 2 | K.N.S.M.H.S, Sultanganj | [13 empty] | 1
3 | G.H-145 | Bhagalpur | Bihpur | 1 | H.S, Jairampur | M/s Dayaram Singh | 266.74 |  |  | 30.10.2013 | 12 Month | [8 empty] | 1 | 247.98
|  |  | Naugachhia | 2 | Sahu H.S, Sahu Parbatta | [14 empty] | 1
4 | G.H-146 | Bhagalpur | Gopalpur | 1 | Proj. Girls H.S, Saidpur | M/s Dayaram Singh | 133.14 |  |  | 10.6.2013 | 12 Month | [8 empty] | 1 | 118.47
5 | G.H-147 | Bhagalpur | Shahkund | 1 | Proj. H.S, Shahkund | Lalan Kumar | 265.94 |  |  | 26.7.2013 | 12 Month | [7 empty] | 1 |  | 227.45
|  |  | Jagdishpur | 2 | Proj. Girls H.S, Jagdishpur | [14 empty] | 1
6 | G.H-148 | Banka | Rajaoun | 1 | R.H.S, Douni | Lalan Kumar | 183.76 |  |  | 26.7.2013 | 12 Month | [7 empty] | 1 |  | 108.48
| Total nos. of school |  |  | 11 |  |  | 1511.74 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 1129.26

## Munger
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Munger | [20 empty] | Date:31.10.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | G.H-149 | Munger | Tarapur | 1 | M.S, Tarapur | Rajendra Kumar | 137.45 |  |  | 11.9.2013 | 12 Month |  |  | 1
2 | G.H-150 | Jamui | Khaira | 1 | Project G.H.S, Khaira | Ashok & Co Nivas p(ltd) | 263.59 |  |  | 26.8.2013 | 12 Month | [7 empty] | 1 |  | 155.01
|  |  | Sono | 2 | Project H.S, Sona | [13 empty] | 1
3 | G.H-151 | Lakhisarai | Lakhisarai | 1 | M.V.M H.S.Nayatola, Lakhisarai | Lalan Kumar | 286.86 |  | 1 | 26.7.2013 | 12 Month | [10 empty] | Land problem
|  |  | Barahiya | 2 | S.R.R.S Girls H.S, Barahiya |  |  |  | 1 | [12 empty] | Land problem
| Total nos. of school |  |  | 5 |  |  | 687.9 |  | 2 |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 155.01

## Kosi
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Kosi | [21 empty] | Date:31.10.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Fin. Exp. (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[10 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | G.H-141 | Saharsa | Kahra | 1 | Govt. Girls H. S, Saharsa | Ashok Kumar | 281.46 |  |  |  | 9.7.2013 | 12 Month | [7 empty] | 1 |  | 205.1 | WORK STOPPED
|  |  | Saur Bazar | 2 | Gajadhar Sahu H.S, Saur Bazar | [14 empty] | 1 |  |  | WORK STOPPED
2 | G.H-142 | Saharsa | Salkhua | 1 | H.S, Salkhua | Ashok Kumar | 279.34 |  |  | 1 | [12 empty] | WORK NOT STARTED (LAND NOT AVAILABLE)
|  |  | Sonbarsa | 2 | Sir Hariballabh Inst. | [13 empty] | 1 |  |  | 84.27 | FIRST FLOOR ROOF LEVEL WORK IN PROGRESS
| Total nos. of school |  |  | 4 |  |  | 560.8 | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 289.37

## Purnea
BSEIDC, PATNA
Name of Division :- Purnea | [21 empty] | Date:31.10.2014
Name & contact no. of EE :- Manjo Kumar Pandey (9661818750) , AE :- Umesh Kumar (8986493581) & A.E.:- Madan Mohan Kumar (9431413291)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Fin. Exp. (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[10 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
Progress Report for the construction of Girls Hostel
| Total nos. of school |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Tirhut (East)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Tirhut (East) - Vaishali, Muzaffarpur & Sitamarhi | [19 empty] | Date:31.10.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702), Satendra Satyarthi, AE (9709677927), Rakesh Kumar, AE (8294246168)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | G.H-121 | Vaishali | Rajapakar | 1 | H.S.,Rajapakar | Sai Shree Balajee Construcrtion and developers pvt.Ltd | 266.79 | 1 | 30.7.2013 | 12 Month | [9 empty] | 91.18 | Land problem
|  |  | Mahua | 2 | M.S. Singhara | [12 empty] | 1 |  |  | Finishing-27/10/2014
2 | G.H-122 | Vaishali | Raghopur | 1 | B.S.J.S.H.S.Fatehpur, Vaishali | Shristi Developers & Pvt. Ltd. | 402.49 | 1 | 18.9.2013 | 12 Month | [9 empty] | 51.22 | Land problem
|  |  | Bidupur | 2 | S.S.V.M.H.S., Ramdauli | [12 empty] | 1 |  |  | Finishing-27/10/2014
|  |  | Deshri | 3 | H.S. Bhataulla |  |  | 1 | [12 empty] | Land problem
3 | G.H-123 | Vaishali | Patepur | 1 | S.R.C.H.S.,Patepur, Vaishali | Retender | 406.19
|  |  | Lalganj | 2 | G.A.H/S, Lalganj
|  |  | Goraul | 3 | H.S., Goraul
4 | G.H-124 | Vaishali | Vaishali | 1 | S.M.T.H.S., Vaishali | Retender (29.01.2014) | 404.83
|  |  | Bhagwanpur | 2 | M.S.Ratnapura Bhagwanpur
|  |  | Chehrakala | 3 | B.N. High School, Sehan *
| Total nos. of school |  |  | 11 |  |  | 1480.3 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 142.4
Note * School Name Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-13/2010289 dated 16 Apr.2013

## Tirhut (West)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Tirhut (West) - East Champaran, West Champaran & Shivhar | [19 empty] | Date:31.10.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | G.H-116 | East Champaran | Chakiya | 1 | K.G.B.N., Chakiya | Sushil Kumar | 279.99 |  |  |  |  | 1 | [7 empty] | 63.79
|  |  | Kalyanpur | 2 | K.G.B.N., Kalyanpur | [10 empty] | 1
2 | G.H-117 | East Champaran | Dhaka | 1 | K.G.B.N., Dhaka | M/S Combind Builders & Company | 285.39 | [7 empty] | 1 |  |  |  |  | 105.39
|  |  | Ghorasahan | 2 | K.G.B.N.,Ghorasahan | [10 empty] | 1
3 | G.H-118 | East Champaran | Kesariya | 1 | K.G.B.N., Kesariya | M/S Hitendra Kumar Mishra | 416.19 | [6 empty] | 1 | [5 empty] | 124.36
|  |  | Kotwa | 2 | K.G.B.N., Kotwa | [8 empty] | 1
|  |  | Sangrampur | 3 | K.G.B.N., Sangrampur | [8 empty] | 1
4 | G.H-119 | East Champaran | Madhuban | 1 | K.G.B.N., Madhuban | Retender | 420.5
|  |  | Mehsi | 2 | K.G.B.N., Mehsi
|  |  | Tetariya | 3 | K.G.B.N., Tetariya
5 | G.H-120 | East Champaran | Ramgharwa | 1 | K.G.B.N., Ramgharwa (Reshma devi Girls H.S.) | M/S S.G.K. Nirman Sansthan | 142.1 | [6 empty] | 1 | [5 empty] | 28.98
6 | G.H-125 | West Champaran | Bagha-1 | 1 | R.S. H.S. Parsuniform | Retender | 146.1
| Total nos. of school |  |  | 12 |  |  | 1690.27 | 0 |  |  | 0 | 1 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 322.52
Note * School Name Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-13/2010289 dated 16 Apr.2013

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Darbhanga | [19 empty] | Date:31.10.2014
Name & contact no. of EE :- Pramod Kumar (9939599803) , AE :- Ram Babu Mahto (9835619212), Mukesh Kumar Singh (9934945672)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | G.H-133 | Darbhanga | Keoti | 1 | Ramrikh Sundari H.S, Keoti | Avneesh Enterprises | 285.68 |  | 20.7.2013 | 12 Month | [7 empty] | 1 |  | 172.9
|  |  | Ghanshyampur | 2 | H.S, Pohadidibela | [12 empty] | 1
2 | G.H-134 | Darbhanga | Kusheswara | 1 | M.S, Kusheshwar Sthan | Avneesh Enterprises | 284.9 |  | 27.6.2013 | 12 Month | [5 empty] | 1 |  |  |  | 175.09
|  |  | Hanuman Nagar | 2 | Govt.High School, Kolhanta Patori | [12 empty] | 1
3 | G.H-135 | Darbhanga | Gora Bauram | 1 | H.S, Gourabauram | Avneesh Enterprises | 429.84 |  | 26.7.2013 | 12 Month | [6 empty] | 1 |  |  | 236.77
|  |  | Manigachhi | 2 | H.S, Balour | [12 empty] | 1
|  |  | Tardih | 3 | H.S, Narainpur | [12 empty] | 1
4 | G.H-136 | Madhubani | Kaulahi | 1 | H.S, Kaulahi | Sunil Kumar Purvey | 287.96 |  |  |  | 1 | [8 empty] | 118.69 | Land dispute
|  |  | Harlakhi | 2 | H.S, Umgaun | [12 empty] | 1
5 | G.H-137 | Samastipur | Kalyanpur | 1 | K.G.B.V, Kalyanpur | MS Jaysankar Kumar | 276.84 | 1 | [11 empty] | 76.11 | Land not available
|  |  | Pusa | 2 | Girls Inter School, Pusa | [11 empty] | 1
6 | G.H-138 | Samastipur | Ujiarpur | 1 | B.R.C, Ujiarpur Campus | Vinod Kumar Singh | 407.99 | [8 empty] | 1 |  |  |  | 175.17
|  |  | Sarayranjan | 2 | H.S, Bathua Bujurg | [10 empty] | 1
|  |  | Samastipur | 3 | Model Inter School, Samastipur | [8 empty] | 1
7 | G.H-139 | Samastipur | Vidyapati Nagar | 1 | Inter School,Vidyapati Nagar (North) | Vinod Kumar Singh | 407.54 | [7 empty] | 1 |  |  |  |  | 153.55
|  |  | Bibhutipur | 2 | M.S, Sirsi | [11 empty] | 1
|  |  | Dalsingh Sarai | 3 | C.H. Inter School, Dalsingh Sarai | [10 empty] | 1
8 | G.H-140 | Samastipur | Hasanpur | 1 | N.I.S.M.H.S, Hasanpur Road | Ray & Raj Engineering Pvt Ltd | 413.15 |  | 4.10.2013 | 12 Month | [5 empty] | 1 |  |  |  | 168.76
|  |  | Sihivaji nagar | 2 | H.S, Shivaji Nagar | [9 empty] | 1
|  |  | Khanpur | 3 | Inter School, Siropatti Khatu | [9 empty] | 1
| Total nos. of school |  |  | 20 |  |  | 2793.9 | 1 |  |  | 1 | 0 | 0 | 1 | 3 | 5 | 3 | 6 | 0 | 1277.04
Note * School Name Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-13/2010289 dated 16 Apr.2013

## Saran
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2010-11)
Name of Division :- Saran | [19 empty] | Date:31.10.2014
Name & contact no. of EE :- Uday Kumar Das (9431821558), AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time Of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | G.H-126 | Saran | Garkha | 1 | MS Chainpur Bhaiswara | Bajarangi Singh | 266.79 | [7 empty] | 1 |  |  |  |  | 129.54
|  |  | Maker | 2 | UMS Baghakol | [11 empty] | 1
2 | G.H-127 | Siwan | Maharajganj | 1 | H.S.Sikatiya | Shiv Shankar Singh Construction pvt. Ltd | 405.66 |  | 6.8.2013 | 12 Month | [7 empty] | 1 |  | 263.97
|  |  | Barhariya | 2 | Sri Krishan H.S. Kailgarh | [12 empty] | 1
|  |  | Bhagwanpur Hatt | 3 | S.S. High School, Bhagawanpur Hatt | [12 empty] | 1
3 | G.H-128 | Siwan | Goreya Kothi | 1 | Narayan Karmayogi H.S, Goreyakothi | Shiv Shankar Singh Construction pvt. Ltd | 404.53 |  | 6.8.2013 | 12 Month | [7 empty] | 1 |  | 263.17
|  |  | Basantpur | 2 | H.S, Basantpur | [12 empty] | 1
|  |  | Dharaunda | 3 | G.S. H.S, Ujaini | [12 empty] | 1
4 | G.H-129 | Gopalganj | Baikunthpur | 1 | H.S, Sirsa | Shiv Shankar Singh Construction pvt. Ltd | 410.97 |  | 6.8.2013 | 12 Month | [7 empty] | 1 |  | 197.27
|  |  | Sidhwaliya | 2 | H.S, Mahamadpur | [12 empty] | 1
|  |  | Manjha | 3 | H.S, Manjha |  |  | 1 | [12 empty] | Land not available
5 | G.H-130 | Gopalganj | Panchdewari | 1 | H.S, Jamunaha Bazar | Anand Mishra | 277.25 |  | 24.7.2013 | 12 Month | [7 empty] | 1 |  | 148.28
|  |  | Bhorey | 2 | H.S, Bhore | [9 empty] | 1
6 | G.H-131 | Gopalganj | Uchakagaon | 1 | H.S, Uchakagaon | Anand Mishra | 277.46 |  | 24.7.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 33.27
|  |  | Kateya | 2 | Kanya H.S, Kateya |  |  | 1 | [12 empty] | Land not available
7 | G.H-132 | Gopalganj | Kuchaikote | 1 | H.S, Sonekola | M/S Saheb Singh Construction | 276.24 |  | 16.9.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 159.53
|  |  | Gopalganj | 2 | S.S Girls Inter School, Gopalganj | [11 empty] | 1
| Total nos. of school |  |  | 17 |  |  | 2318.9 | 2 |  |  | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 9 | 0 | 1195.03