## CTE-14
BSEIDC Ltd., Patna
PROGRESS REPORT OF CTE
S.No. | SL NO. | Group No. | District | Name Of Institutional | S. No. | Name Of Building | Name of Agency with Mo- | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks |  | Division
[11 empty] | Not Start | Lay-out | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete |  |  |  | Agreement amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%)
[15 empty] | LL | RL | LL | RL | LL | RL |  |  |  | Scheme
53 | 1 | C-1 | MUZAFFARPUR | CTE TURKI | 1 | Institutional Building | Sanjay Constraction | 208 SBD OF 2015-16 (14.08.15) | [12 empty] | 1 |  | SOME ELECTRICAL WORK TO BE DONE | CTE | Tirhut East
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  | Complete | CTE | Tirhut East
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  | Complete | CTE | Tirhut East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  | Complete | CTE | Tirhut East
54 | 2 | C-2 | BHAGALPUR | CTE BHAGALPUR | 1 | Institutional Building | SAI HIGHWAY AND BUILDERS PVT. LTD. | 14 SBD OF 2016-17(25.04.2016) | [12 empty] | 1 |  |  | CTE | Bhagalpur
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  |  | CTE | Bhagalpur
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  |  | CTE | Bhagalpur
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | CTE | Bhagalpur
55 | 3 | C-3 | SAMASTIPUR | CTE SAMASTIPUR | 1 | Institutional Building | Tender Process | [13 empty] | 1 |  |  | CTE | Darbhanga
[5 empty] | 2 | Boys Hostel | [9 empty] | 1 | [7 empty] | CTE | Darbhanga
[5 empty] | 3 | Girls Hostel | [11 empty] | 1 | [5 empty] | CTE | Darbhanga
[5 empty] | 4 | Principal Quarter | [9 empty] | 1 | X | X | X | X |  |  |  | CTE | Darbhanga
56 | 4 | C-4 | SAHARSA | CTE SAHARSA | 1 | Institutional Building | R K CONSTRUCTION | [7 empty] | 1 | [8 empty] | CTE | Koshi
[5 empty] | 2 | Boys Hostel | [8 empty] | 1 | [8 empty] | CTE | Koshi
[5 empty] | 3 | Girls Hostel |  |  |  |  | 1 | [11 empty] | Not start | CTE | Koshi
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [5 empty] | X | X | X | X |  |  | Not start | CTE | Koshi
57 | 5 | C-5 | CHHAPRA | CTE CHHAPRA | 1 | Institutional Building | M/s. Krishnapali Construction Pvt. Ltd. Mobile : 94312 59756. |  |  |  | 1 | [11 empty] | Not start | CTE | Saran
[5 empty] | 2 | Boys Hostel | [6 empty] | 1 | [9 empty] | Not start | CTE | Saran
[5 empty] | 3 | Girls Hostel | [7 empty] | 1 | [9 empty] | CTE | Saran
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [5 empty] | X | X | X | X |  |  | Not start | CTE | Saran
58 | 6 | C-6 | GAYA | CTE GAYA | 1 | Institutional Building | Ramakant Singh | 709 SBD OF 2014-15 (23.02.15) |  |  | 1 | [11 empty] | Old Staff Quarter to be demolish | CTE | Magadh
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  |  | CTE | Magadh
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  |  | CTE | Magadh
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | CTE | Magadh
| 7 | C-7 | Patna | CTE, Barh | 1 | Institutional Building | MS VIMLESH PRASAD SINGH, 302, Abadh Kunj Appt. 9431267511 |  |  |  | 1 | [11 empty] | Required old building demolision | CTE | Patna East
[5 empty] | 2 | Boys Hostel |  |  |  |  | 1 | [11 empty] | Required old building demolision | CTE | Patna East
[5 empty] | 3 | Girls Hostel |  |  |  |  | 1 | [11 empty] | Required old building demolision | CTE | Patna East
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [11 empty] | Required old building demolision | CTE | Patna East
| 8 | C-8 | Munger | CTE, Haweli Kharagpur | 1 | Institutional Building | RAJENDRA PRASAD YADAV ,SHASTRI NAGAR, MUNGER , 8409097566 | [5 empty] | 1 | [9 empty] | Water Logged | CTE | Munger
[5 empty] | 2 | Boys Hostel | [6 empty] | 1 | [9 empty] | Water Logged | CTE | Munger
[5 empty] | 3 | Girls Hostel |  |  |  |  | 1 | [12 empty] | CTE | Munger
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [12 empty] | CTE | Munger
| 9 | C-9 | Purnea | CTE, Purnea | 1 | Institutional Building | RAJENDRA PRASAD PODDAR, MANGAL BAZAR, KATIHAR- 854105 (BIHAR), 9431884339 | [5 empty] | 1 | [10 empty] | CTE | Purnea
[5 empty] | 2 | Boys Hostel |  |  |  |  | 1 | [11 empty] | Not started due to tree obstacle | CTE | Purnea
[5 empty] | 3 | Girls Hostel | [9 empty] | 1 | [7 empty] | CTE | Purnea
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | CTE | Purnea
| 10 | C-10 | Buxar | CTE, Dumraon | 1 | Institutional Building | PRASAD ASSOCIATES, NILANCHAL KOTHI, PISKA MORE, RAATU ROAD, RANCHI-834005 ,9431363233 |  |  |  | 1 | [11 empty] | NOC is not issue by Principal | CTE | Patna West
[5 empty] | 2 | Boys Hostel |  |  |  |  | 1 | [12 empty] | CTE | Patna West
[5 empty] | 3 | Girls Hostel |  |  |  |  | 1 | [12 empty] | CTE | Patna West
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [12 empty] | CTE | Patna West
| 11 | C-11 | Aurangabad | CTE, Tarar | 1 | Institutional Building | PRASAD ASSOCIATES, NILANCHAL KOTHI, PISKA MORE, RAATU ROAD, RANCHI-834005 ,9431363233 |  |  |  | 1 | [11 empty] | Land Dispute | CTE | Magadh
[5 empty] | 2 | Boys Hostel |  |  |  |  | 1 | [11 empty] | Land Dispute | CTE | Magadh
[5 empty] | 3 | Girls Hostel | [8 empty] | 1 | [8 empty] | CTE | Magadh
[5 empty] | 4 | Principal Quarter | [5 empty] | 1 | [10 empty] | Water Logged | CTE | Magadh
| 12 | C-12 | East Champaran | CTE , Kumarbagh | 1 | Institutional Building | SANJAY CONSTRUCTION, LOHAR LANE,MUSALLAHPUR HAAT,MAHENDRU,PATNA,800006 ,MOB No.-9431877189,7544070707 |  |  |  | 1 | [12 empty] | CTE | Tirhut West
[5 empty] | 2 | Boys Hostel |  |  |  |  | 1 | [12 empty] | CTE | Tirhut West
[5 empty] | 3 | Girls Hostel |  |  |  |  | 1 | [12 empty] | CTE | Tirhut West
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [12 empty] | CTE | Tirhut West
| 13 | C-13 | SIWAN | CTE , siwan | 1 | Institutional Building | Retender |  | 1 | [13 empty] | Retender | CTE | Saran
[5 empty] | 2 | Boys Hostel |  |  | 1 | [13 empty] | Retender | CTE | Saran
[5 empty] | 3 | Girls Hostel |  |  | 1 | [13 empty] | Retender | CTE | Saran
[5 empty] | 4 | Principal Quarter |  |  | 1 | [13 empty] | Retender | CTE | Saran
| 14 | C-14 | Araria | CTE, Forbesganj | 1 | Institutional Building | J . CORP. | [6 empty] | 1 | [9 empty] | CTE | Purnea
[5 empty] | 2 | Boys Hostel | [7 empty] | 1 | [9 empty] | CTE | Purnea
[5 empty] | 3 | Girls Hostel | [9 empty] | 1 | [7 empty] | CTE | Purnea
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [12 empty] | CTE | Purnea
| Total No. of Institution |  |  |  | 14 |  |  |  | 4 | 0 | 23 | 1 | 4 | 3 | 3 | 4 | 0 | 1 | 0 | 0 | 13 | 0
| Total No. of Institution |  | Name of Institution |  | Total No. of Buildings | Name of Institutional Buildings | Total No. of Buildings |  | Retender | Tender Process | Physical Status
[11 empty] | Not Start | Layout | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL | LL | RL
| 14 |  | College of Teacher Education (CTE) |  | 14 | Institutional Building |  |  | 1 | 0 | 6 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
[5 empty] | 14 | Boys Hostel |  |  | 1 | 0 | 5 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 0
[5 empty] | 14 | Girls Hostel |  |  | 1 | 0 | 5 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 3 | 0
[5 empty] | 14 | Principal Quarter |  |  | 1 | 0 | 7 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
| Total No. of Institutional Buildings |  |  |  | 56 |  |  |  | 4 | 0 | 23 | 1 | 4 | 3 | 3 | 4 | 0 | 1 | 0 | 0 | 13 | 0