## Summary
BSEIDC, PATNA
Progress report for the construction of Girl's Hostel building (2009-10) | [20 empty] | Date:-30.09.2014
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna (East) | 2 | 2 | 260.51 | 2 | 2 | 260.51 |  | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 49.77 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E., BSEIDC, Div.- Patna (West) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 3 | 4 | 517.71 | 3 | 4 | 517.71 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 172.88 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Bhagalpur | 3 | 6 | 785.93 | 3 | 6 | 785.93 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 193.76 |  | 0
5 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 3 | 7 | 901.72 | 3 | 7 | 648.5 |  | 1 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 6 | 0 | 114.04 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 1 | 2 | 283.59 | 1 | 2 | 283.59 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 96.13 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 8 | 21 | 2835.27 | 7 | 18 | 2436.25 |  | 0 | 0 | 4 | 0 | 3 | 1 | 3 | 5 | 2 | 16 | 0 | 1053.61 |  | 0
8 | TIRHUT (EAST) | Anil Kumar Singh (9801494702), E.E. , BSEIDC, Div.-Tirhut (East) | 6 | 17 | 2375.32 | 4 | 11 | 1536.13 |  | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 6 | 2 | 9 | 0 | 561.06 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha, EE, BSEIDC, Div.- Tirhut (West) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 7 | 17 | 2389.61 | 7 | 17 | 2389.61 |  | 0 | 2 | 1 | 1 | 3 | 2 | 5 | 0 | 3 | 14 | 0 | 712.67 |  | 0
11 | SARAN | Uday Kumar Das, EE BSEIDC, Div.- Saran | 2 | 4 | 523.29 | 2 | 4 | 523.29 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 0 | 173.98 |  | 0
Total (Girl's Hostel) |  |  | 35 | 80 | 10872.95 | 32 | 71 | 9381.52 | 0 | 3 | 5 | 7 | 1 | 12 | 3 | 8 | 17 | 15 | 56 | 0 | 3127.9 |  | 0

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- Patna (East) - Patna, Nalanda & Bhojpur | [20 empty] | Date:-30.09.2014
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | GH-7 | Bhojpur | Agioan | 1 | D.N.H.S., Gorpa | Rakesh Chaubey, AT-JakkiBigha, Dehri-on-Sone, Distt.-Rohtas | 130.29 |  |  | 25 SBD of 2013-14/ 10.05.2013 | 12Month |  |  | 1 | [6 empty] | 13.37 | Way not available due to rain
2 | GH-8 | Bhojpur | Jagdishpur | 1 | Janta H.S., Baligaw | Himshikha Construction Pvt. Ltd., Setielite Road, Mecon Colony, Doranda, Ranchi-2. | 130.22 |  |  | 222 SBD of 2013-14/ 24.04.2013 | [5 empty] | 1 |  |  |  |  | 36.4 | 1/2 Part B/W upto RL & in 1/2 B/W above LL
|  | Total nos. of school |  | 2 |  |  | 260.51 | 0 | 0 |  |  | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 49.77

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- Patna (East) - Patna, Nalanda & Bhojpur | [20 empty] | Date:-30.09.2014
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
|  | Total nos. of school |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Magadh
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- MAGADH | [20 empty] | Date:-30.09.2014
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | GH-9 | Aurangabad | Madanpur | 1 | Anugrah H.S., Madanpur | Jay Kumar, New Area, Nutan Nagar, Gaya- 823001 | 258.63 |  |  | 9.4.2013 | 12 Month | [7 empty] | 1 |  | 172.88
|  |  | Rafiganj | 2 | R.B.R. High School, Rafiganj | [13 empty] | 1
2 | GH-10 | Aurangabad | Haspura | 1 | Haspura H.S., Haspura | Raj Mangal Singh | 130.59 |  | 1 | [12 empty] | Land Disput,court-stay
3 | GH-11 | Aurangabad | Kutumba | 1 | Govt. Middle School, Kutumba | Raj Mangal Singh | 128.49 |  | 1 | [12 empty] | Insufficient land
|  | Total nos. of school |  | 4 |  |  | 517.71 | 0 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 172.88

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- BHAGALPUR | [20 empty] | Date:-30.09.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | GH-30 | Bhagalpur | Sanhoula | 1 | M.S., Arar, Sanhoula | Kailash Prasad Yadav, Babu Tola, Banka. | 130 |  |  | 26.2.2013 | 15 Month | [7 empty] | 1 |  | 97.22 | 1st on A/C Bill Paid
2 | GH-31 | Bhagalpur | Nathnagar | 1 | M.S., Kanjhiya, Nathnagar | Shristi Developers Pvt. Ltd., Patna city | 260.97 |  | 1 | 19.7.2013 | 15 Month | [9 empty] | 96.54 | Local Hindrence
|  |  | Narayanpur | 2 | M.S., Manoharpur, Narayanpur | [13 empty] | 1 |  |  | 1st on A/C Bill Paid
3 | GH-32 | Bhagalpur | Rangra Chowk | 1 | M.S, Rangra Chowk | M/S Krishna Construction Bhagalpur | 394.96 |  |  |  |  | 1 | [9 empty] | Local Hindrence
|  |  | Kharik Bazar | 2 | Govt. Basic School Teldih* |  |  |  | 1 | [12 empty] | No Drawing
|  |  | Ishmailpur | 3 | M.S.Parvatta* |  |  |  | 1 | [12 empty] | No Drawing
| Total nos. of school |  |  | 6 |  |  | 785.93 | 0 | 3 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 193.76
Note * School Name hasbeen Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-100/2008-34 dated 16 jan.2013

## Munger
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- MUNGER | [20 empty] | Date:-30.09.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | GH-33 | Munger | Haveli Kharagpur | 1 | Govt.+2 H.S., Haweli Kharagpur | Shristi Developers Pvt. Ltd., Patna city | 394.27 |  |  | 19.7.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 100.5 | 1st A/C bill paid
|  |  | Dharahara | 2 | K.R.S.K.H H.S., Dharahra |  |  |  | 1 | [12 empty] | no Land
|  |  | Tetiabamber | 3 | Jagannath H.S Tetia Bamber | [10 empty] | 1
2 | GH-34 | Lakhisarai | Surajgarha | 1 | Project K. K.H., Surajgarha | Rinku Kumar, Vill- Jakarpura, P.O.- Surajgarha, Distt.- Lakhisarai. | 253.22 |  |  |  |  | 1
|  |  | Pipariya | 2 | M.M.P. H.S., Walipur | [7 empty] | 1
3 | GH-35 | Lakhisarai | Halsi | 1 | High School, Halsi | Rajendra Kumar | 254.23 | [6 empty] | 1 | [6 empty] | 13.54
|  |  | Ramgarh Chowk | 2 | D.M H.S., Sharma | [7 empty] | 1
| Total nos. of school |  |  | 7 |  |  | 901.72 | 0 | 1 |  |  | 1 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 114.04
Note * School Name hasbeen Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-100/2008-34 dated 16 jan.2013

## Kosi
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- KOSI | [20 empty] | Date:-30.09.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[9 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | GH-21 | Supaul | Raghopur | 1 | M.S., Kajayan, Raghopur | Kailash Prasad Yadav Const.Pvt. Ltd., P.O-Hulas, P.S-Raghopur, Distt.-Supaul, Pin-852111 | 283.59 |  |  | 20.4.2012 | 12 Month |  |  |  |  | 1 |  |  |  |  | 96.13 | GROUND FLOOR ROOF LEVEL WORK IN PROGRESS
|  |  | Pratapganj | 2 | Public H.S., Pratapganj | [13 empty] | 1 |  |  | FIRST FLOOR ROOF LEVEL WORK IN PROGRESS
| Total nos. of school |  |  | 2 |  |  | 283.59 |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 96.13

## Purnea
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- PURNEA | [21 empty] | Date:-30.09.2014
Name & contact no. of EE :- Manjo Kumar Pandey (9661818750) , AE :- Umesh Kumar (8986493581) & A.E.:- Madan Mohan Kumar (9431413291)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Fin. Exp. (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[10 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1 | GH-22 | Purnia | Dhamdaha | 1 | H.S., Dhamdaha | Chandan Abhishek, Vill-Araria, Azad Nagar, Distt.-Araria. | 417.03 |  |  |  | 22.8.2013 | 12 Month | [5 empty] | 1 |  |  |  | 142.86
|  |  | Rupouli | 2 | Project Girl's H.S., Rupouli | [11 empty] | 1
|  |  | Bhawanipur | 3 | H.S., Bhawanipur | [11 empty] | 1
2 | GH-23 | Purnia | Barharakothi | 1 | Shyama H.S., Bhatotar | Chandan Abhishek, Vill-Araria, Azad Nagar, Distt.-Araria. | 266.32 |  |  |  | 3.6.2013 | 12 Month | [7 empty] | 1 |  | 151.74
|  |  | K. Nagar | 2 | H.S., Champanagar | [13 empty] | 1
3 | GH-24 | Purnia | Purnia East | 1 | Proj. Girl's H.S., Ranipatra | Rajendra Prasad Poddar | 396.95 |  |  | 1 | [11 empty] | 175.1
|  |  | Jalalgarh | 2 | N.D Rungata H.S., Jalalgarh | [13 empty] | 1
|  |  | Kasba | 3 | Kalanand H.S., Garabnaili | [13 empty] | 1
4 | GH-25 | Purnia | Dagarua | 1 | Abul Kalam H.S., Ichalo | Retender | 399.02
|  |  | Srinagar | 2 | Govt. S.S., Srinagar
|  |  | Baisi | 3 | Proj. Girl's School Baisi
5 | GH-26 | Purnia | Baisa | 1 | H.S., Rauta | Birendra Kr. Singh Katihar | 267.09 | [7 empty] | 1 | [6 empty] | 32.83
|  |  | Amour | 2 | Project Girl's School, Amour | [9 empty] | 1
6 | GH-27 | Katihar | Kadwa | 1 | N.C.C. Smarak H.S Balia Belon | Uma Kant Singh, Mirchaibari, Officer Colony, Katihar-854105 | 409.41 |  |  |  | 23.8.2013 | 12 Month | [7 empty] | 1 |  | 250.12
|  |  | Balrampur | 2 | S.S., High School, Telta | [9 empty] | 1
|  |  | Sameli | 3 | D.G.H.S., Krishna Nagar | [14 empty] | 1
7 | GH-28 | Katihar | Manihari | 1 | B.P.S.P.H.S., Manihari | Uma Kant Singh, Mirchaibari, Officer Colony, Katihar-854105 | 406.34 |  |  |  | 23.9.2013 | 12 Month | [7 empty] | 1 |  | 217.57
|  |  | Azamnagar | 2 | H.S., Salmari | [14 empty] | 1
|  |  | Pranpur | 3 | M.S., Bastol |  |  |  |  | 1
8 | GH-29 | Katihar | Falka | 1 | B.S.M.High School, Pothiya | M/S Amar Construction Patna | 273.11 |  |  |  | 17.5.2013 | 12 Month |  |  | 1 | [6 empty] | 83.39
|  |  | Kursela | 2 | Sampat Raj Devi Girl's H.S., Kursela | [11 empty] | 1
| Total nos. of school |  |  | 21 |  |  | 2835.27 |  |  | 2 |  |  | 0 | 0 | 4 | 0 | 3 | 1 | 3 | 5 | 0 | 1053.61

## Tirhut (East)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- TIRHUT (EAST) - Vaishali, Muzaffarpur & Sitamarhi | [19 empty] | Date:-30.09.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | GH-1 | Sitamarhi | Parihar | 1 | S.G.H.S., Parihar | Malti Singh, Vill+P.O-Jogiara, P.S-Jalley, Distt.-Darbhanga | 418.03 |  | 16.3.2013 | 12 Month | [7 empty] | 1 |  | 248.01
|  |  | Sonbarsa | 2 | H.S., Bhutahi | [12 empty] | 1
|  |  | Bathnaha | 3 | H.S., Yogibana Bazar | [12 empty] | 1
2 | GH-2 | Sitamarhi | Parsauni | 1 | H.S., Parsauni Chowk | Retender | 422.44
|  |  | Riga | 2 | H.S., Rewasi
|  |  | Belsand | 3 | H.S., Belsand
3 | GH-3 | Sitamarhi | Bairgania | 1 | Jaurimal H.S., Bairgania | R. S. Construction E. Champaran, 9939926400 | 429.49 |  |  |  | 1
|  |  | Suppi | 2 | H.S., Suppi |  |  | 1
|  |  | Majarganj | 3 | H.S., Majarganj |  |  | 1
4 | GH-4 | Sitamarhi | Sursand | 1 | Saryu H.S., Sursand | Retender | 416.75
|  |  | Pupri | 2 | Proj. H.S., Pupri
|  |  | Choraut | 3 | H.S., Choraut
5 | GH-5 | Sitamarhi | Bajpatti | 1 | H.S., Bajpatti | Malti Singh, Vill+P.O-Jogiara, P.S-Jalley, Distt.-Darbhanga | 414.91 |  | 16.3.2013 | 12 Month | [7 empty] | 1 |  | 244.74
|  |  | Nanpur | 2 | H.S., Janipur | [12 empty] | 1
|  |  | Bokhra | 3 | H.S., Kharka | [12 empty] | 1
6 | GH-6 | Sitamarhi | Dumra | 1 | K.G.H.S., Dumra | Malti Singh, Vill+P.O-Jogiara, P.S-Jalley, Distt.-Darbhanga | 273.7 |  | 16.3.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 68.31
|  |  | Runni saidpur | 2 | H.S., Morsand | [6 empty] | 1
| Total nos. of school |  |  | 17 |  |  | 2375.32 | 2 |  |  | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 6 | 0 | 561.06
Note * School Name has been Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-100/2008-33 dated 16 jan.2013

## Tirhut (West)
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- TIRHUT (West) - East Champaran, West Champan & Shivhar | [19 empty] | Date:-30.09.2014
Name & contact no. of EE :- Sunil Kumar Sinha , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
| Total nos. of school |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note * School Name has been Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-100/2008-33 dated 16 jan.2013

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- DARBHANGA | [19 empty] | Date:-30.09.2014
Name & contact no. of EE :- Pramod Kumar (9939599803) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | GH-14 | Madhubani | Benipatti | 1 | Sri Baccha Jha Janta H.S. Adher* | Malti Singh, Vill+P.O-Jogiara, Near Gandhi Chowk,P.S- Jale, Distt.-Darbhanga. | 282.46 |  | 16.3.2013 | 12 Month | [6 empty] | 1 |  |  | 76.73
|  |  | Bisfi | 2 | H.S. Bisfi * | [6 empty] | 1
2 | GH-15 | Madhubani | Madhepur | 1 | H.S. Madhepur* | Avneesh Enterprises Ghaziabad | 427.48 |  | 15.7.2013 | 12 Month | [6 empty] | 1 |  |  | 218.81
|  |  | Lakhanaur | 2 | Project Girl H.S. Lakhanaur* | [11 empty] | 1
|  |  | Andarathari | 3 | M.S., Andarathari | [9 empty] | 1
3 | GH-16 | Madhubani | Rajnagar | 1 | Rameshwar H.S.Raj Nagar* | M/S Laxman Sharma | 421.92 | 1 |  | 12 Month | [9 empty] | 73.38 | land dispute
|  |  | Pandaul | 2 | Anup Lal Project Girls H.S. Barmotra Pandaul* | [7 empty] | 1
|  |  | Babubarhi | 3 | M.S., Bhupatti | [9 empty] | 1
4 | GH-17 | Madhubani | Ladania | 1 | M.S., Ladania Girl's | Rajesh Kumar Patna | 287.4 | 1 | 20.8.2013 | 12 Month | [9 empty] | 72.75 | Land not available
|  |  | Jainagar | 2 | M.S., Dullipatti | [11 empty] | 1
5 | GH-18 | Madhubani | Basopatti | 1 | H.S. Basopatti * | Avneesh Enterprises Ghaziabad | 427.61 |  | 15.7.2013 | 12 Month | [5 empty] | 1 |  |  |  | 163.29
|  |  | Madhwapur | 2 | H.S. Madhwapur* | [10 empty] | 1
|  |  | Ghoghardiha | 3 | H.S., Dewadh | [8 empty] | 1
6 | GH-19 | Samastipur | Singhia | 1 | K.G., Academy, Singhia | Binod Kumar Singh, AT+P.O-Ahmadpur, | 273.19 | 1 | [11 empty] | 65.23 | Land not available
|  |  | Bithan | 2 | H.S., Bithan | [11 empty] | 1
7 | GH-20 | Samastipur | Warisnagar | 1 | M.S., Hajpurwa, Warisnagar | Sudhakant Enterprises Pvt. Ltd., Punjabi Colony, Dharmpur, Samastipur. | 269.55 |  |  | 12 Month |  |  |  |  | 1 |  |  |  |  | 42.48
|  |  | Marwa | 2 | H.S., Morwa | [6 empty] | 1 | [8 empty] | Land Problem
| Total nos. of school |  |  | 17 |  |  | 2389.61 | 3 |  |  | 0 | 2 | 1 | 1 | 3 | 2 | 5 | 0 | 0 | 712.67
Note * School Name has been Changed as per direction of SPD (BMSP) Vide letter no 9/0 M.S.-100/2008-33 dated 16 jan.2013

## Saran
BSEIDC, PATNA
Progress Report for the construction of Girls Hostel (2009-10)
Name of Division :- SARAN | [19 empty] | Date:-30.09.2014
Name & contact no. of EE :- Uday Kumar Das, AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | GH-12 | Saran | Marhourah | 1 | U.M.S., Awari, Marhourah | M/S Nitish Raj, AT- Narayan Nagar, Rathour Nowaji Tola, P.O- Gurukul Mehiyan, Distt.- Saran. | 262.24 | [7 empty] | 1 |  |  |  |  | 51.93
|  |  | Taraiyan | 2 | M.S., Gawandary, Taria |  |  | 1 | [12 empty] | Land not available
2 | GH-13 | Saran | Parsa | 1 | M.S., Bishnupur, Parsa | M/S Ananya Construction Patna | 261.05 |  | 8.7.2013 | 12 Month | [7 empty] | 1 |  | 122.05
|  |  | Ishuapur | 2 | U.M.S., Satasi, Ishuapur |  |  | 1 | [12 empty] | Land problem
| Total nos. of school |  |  | 4 |  |  | 523.29 | 2 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 173.98