## Summary
BSEIDC, PATNA
Progress report for the construction of SSS (Sanctioned Year 2012-13) | [20 empty] | Date:-30.09.2014
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna | 23 | 45 | 4803.64 | 23 | 45 | 4803.64 |  | 0 | 13 | 6 | 13 | 3 | 0 | 0 | 0 | 10 | 35 | 0 | 362.29 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E. BSEIDC, Div.- Patna (West) | 27 | 54 | 5660.29 | 26 | 50 | 5241.28 |  | 0 | 8 | 4 | 13 | 13 | 0 | 0 | 1 | 11 | 39 | 0 | 803 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 49 | 99 | 10187.99 | 34 | 72 | 7411.81 |  | 3 | 29 | 25 | 4 | 1 | 0 | 0 | 0 | 10 | 62 | 0 | 735.07 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Bhagalpur | 24 | 50 | 5261.89 | 17 | 37 | 3795.44 |  | 1 | 6 | 9 | 2 | 4 | 2 | 0 | 0 | 12 | 24 | 1 | 426.17 |  | 0
5 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 36 | 84 | 8874.22 | 29 | 66 | 6860.18 |  | 6 | 15 | 12 | 3 | 3 | 1 | 0 | 2 | 24 | 42 | 0 | 602.28 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 28 | 76 | 8646.37 | 18 | 46 | 3375.05 |  | 4 | 6 | 2 | 8 | 11 | 0 | 0 | 0 | 15 | 31 | 0 | 758.81 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 24 | 62 | 6535.42 | 14 | 26 | 2882.46 |  | 6 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 7 | 19 | 0 | 118.87 |  | 0
8 | TIRHUT (EAST) | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 38 | 117 | 12635.95 | 29 | 76 | 8173.59 |  | 2 | 15 | 5 | 3 | 8 | 0 | 1 | 0 | 42 | 34 | 0 | 375.74 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha, EE, BSEIDC, Div.- Tirhut (West) | 34 | 84 | 9326.39 | 29 | 73 | 8107.66 |  | 0 | 25 | 5 | 7 | 10 | 0 | 0 | 0 | 26 | 47 | 598.44 | 598.44 |  | -598.44
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 36 | 100 | 11094.84 | 16 | 28 | 3047.8 |  | 0 | 3 | 8 | 5 | 4 | 0 | 0 | 0 | 8 | 20 | 0 | 463.86 |  | 0
11 | SARAN | Uday Kumar Das, EE BSEIDC, Div.- Saran | 24 | 53 | 5748.06 | 21 | 47 | 2830.95 |  | 8 | 9 | 12 | 4 | 1 | 0 | 1 | 0 | 12 | 35 | 0 | 423.71 |  | 0
Total (SSS) |  |  | 343 | 824 | 88775.06 | 256 | 566 | 56529.86 | 0 | 30 | 135 | 92 | 65 | 58 | 3 | 2 | 3 | 177 | 388 | 599.44 | 5668.24 |  | -598.44

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- PATNA (EAST) - Patna, Nalanda & Bhojpur | [22 empty] | Date:-30.09.2014
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-98 | iVuk | fcgVk | 1 | e/; fo¦ky;] jk?kksiqj] fcgVk] iVuk | Jai Mata di Construction |  |  | 105.51 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 20.38 | B/W above L.L.
2 | SSS-99 | iVuk | nkukiqj | 1 | mRØfer e/; fo¦ky;] cfj;kjiqj | Jai Mata di Construction |  |  | 106.32 |  |  | 15 Months | 1 | [10 empty] | School not locate
3 | SSS-100 | ukyUnk | bLykeiqj | 1 | e/; fo¦ky;] dksfcy | Baba Hans Construction Pvt. Ltd. | Canal Road, Patna Mob# 9430407767 |  | 208.37 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 25.18 | B/w upto RL
|  |  |  | 2 | e/; fo¦ky;] pkSjek | [9 empty] | 1 | [8 empty] | Tie Beam (water logged)
4 | SSS-101 | ukyUnk | fcgkj | 1 | mRØfer e/; fo¦ky;] gosyh | Pinku Kumari | Nalanda, Bihar |  | 104.25 |  |  | 15 Months |  |  | 1 | [8 empty] | BFS (water logged)
5 | SSS-102 | ukyUnk | fcgkj'kjhQ | 1 | mRØfer e/; fo¦ky;] gjxk¡o | Krishandeo prasad | Mumurabad, Nalanda |  | 314.06 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 15.06 | G.L. (water logged)
|  |  |  | 2 | mRØfer e/; fo¦ky;] ldjkSy | [7 empty] | 1 | [10 empty] | Land not available
|  |  |  | 3 | mRØfer e/; fo¦ky;] ijkSgk | [9 empty] | 1 | [8 empty] | Earth Excavation (water logged)
6 | SSS-103 | ukyUnk | fgylk | 1 | e/; fo¦ky;] diflvkou | Prem Kumar Sinha | Maheshpur, Nalanda |  | 209.37 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 12.56 | Sill Band
7 | SSS-104 | ukyUnk | flyko | 1 | mnwZ e/; fo¦ky;] lkscbZr | Raj Kumar Singh Raja Construction Pvt. Ltd. | Patna-25 |  | 520.78 |  |  | 15 Months |  |  | 1 | [8 empty] | Up to GL
|  |  |  | 2 | e/; fo¦ky;] pk¡nh ekWm | [9 empty] | 1 | [8 empty] | Tie beam
|  |  |  | 3 | e/; fo¦ky;] dqy | [9 empty] | 1 | [8 empty] | G.L.
|  |  |  | 4 | mRØfer e/; fo¦ky;] ikadh | [7 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] t;fd'kqu fcxgk | [9 empty] | 1 | [8 empty] | E/W (water logged)
8 | SSS-105 | ukyUnk | fxfj;d | 1 | e/; fo¦ky;] vkneiqj | M/S Rama Construction | Aunta, Patna |  | 208.16 |  |  | 15 Months | 1 | [9 empty] | 18.93 | Land not available
|  |  |  | 2 | e/; fo¦ky;] pkSjlqvk | [12 empty] | 1
9 | SSS-106 | ukyUnk | gjukSr | 1 | e/; fo¦ky;] usgqlk | Prem Kumar Sinha | Nalanda |  | 105.36 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 15.26
10 | SSS-107 | ukyUnk | ijoyiqj | 1 | m0vk0e/; fo¦ky;] ebZ | Pappu Singh | Bihar Sharif, Patna |  | 104.52 |  |  | 15 Months | 1 | [10 empty] | Land not available
11 | SSS-108 | ukyUnk | jgqbZ | 1 | e/; fo¦ky;] eksM+kryko | Vikash Kumar Singh | Patna-26 |  | 210.57 |  |  | 15 Months | 1 | [10 empty] | Land not available
|  |  |  | 2 | e/; fo¦ky;] dFkkSyh | [12 empty] | 1 | [5 empty] | Water Logged
12 | SSS-109 | ukyUnk | ljesjk | 1 | e/; fo¦ky;] dkthpd | Budha Infrastructure Pvt. Ltd | Patna |  | 210.42 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 23.42 | Water Logged
|  |  |  | 2 | e/; fo¦ky;] eykou | [10 empty] | 1 | [7 empty] | Water Logged
13 | SSS-120 | ukyUnk | uwjljk; | 1 | e/; fo¦ky;] eeqjknkckn | M/S Uma Shankar & Company | Naya Gaon, Patna |  | 209.96 |  |  | 15 Months |  |  | 1 | [7 empty] | 12.48 | G.L. (way not available)
|  |  |  | 2 | e/; fo¦ky;] ljnkjfoxgk | [9 empty] | 1 | [8 empty] | 11000 v wire (BFS)
14 | SSS-121 | ukyUnk | vLFkkok¡ | 1 | mnZw e/; fo¦ky;] mxkou | Budha Infrastructure Pvt. Ltd. | Hanuman Nagar, Patna |  | 521.31 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] vksb;kc | [11 empty] | 1 | [5 empty] | 52.38
|  |  |  | 3 | e/; fo¦ky;] [ksryiqjk | [11 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] tkuk | [7 empty] | 1 | [10 empty] | Land problem
|  |  |  | 5 | e/; fo¦ky;] vkSUMk | [10 empty] | 1
15 | SSS-122 | Hkkstiqj | cM+gjk | 1 | e/; fo¦ky;] uFkeyiqj | Bhawani Buidcon & Project Pvt. Ltd. | C/o Sanjay Kumar Singh, Patna |  | 103.58 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 17.97
16 | SSS-123 | Hkkstiqj | fcfg;kW | 1 | mRØfer e/; fo¦ky;] ohjiqj | Sudarshan Mahato | Jagdishpur, Ara |  | 208.81 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 13.19
|  |  |  | 2 | çk;ksfxd e/; fo¦ky;] fcfg;kW | [7 empty] | 1 | [10 empty] | Required old building demolision
17 | SSS-124 | Hkkstiqj | ihjks | 1 | mRØfer e/; fo¦ky;] ,;kj | Manoj Kumar | Bhojpur |  | 210.14 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 16.52 | B/W upto PL
|  |  |  | 2 | e/; fo¦ky;] ygjkckn | [9 empty] | 1 | [8 empty] | E/W in progress
18 | SSS-125 | Hkkstiqj | lans'k | 1 | e/; fo¦ky;] ppkj | M/S Kalaratri Associates | Nawada, Bhojpur |  | 104.91 |  |  | 15 Months |  |  | 1 | [8 empty] | E/W in progress
19 | SSS-126 | Hkkstiqj | lkgiqj | 1 | e/; fo¦ky;] ygax Mqefj;k | M/S Kalaratri Associates | Nawada, Bhojpur |  | 104.55 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 19.24
20 | SSS-127 | Hkkstiqj | mnoUruxj | 1 | mRØfer e/; fo¦ky;] [kyhlk | Ashok Kumar | Jokta, Bhojpur |  | 309.13 |  |  | 15 Months | 1 | [9 empty] | 18.07 | Work stop by DEO
|  |  |  | 2 | mRØfer e/; fo¦ky;] ckeikWyh | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky; ohjeiqj | [10 empty] | 1 | [7 empty] | Foundation PCC
21 | SSS-128 | Hkkstiqj | rjkjh | 1 | e/; fo¦ky;] pank | Sadhu Saran Singh | Pawar,Ara |  | 208.58 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 27.97 | Tie beam work in prog.
|  |  |  | 2 | e/; fo¦ky;] csjbZ | [9 empty] | 1 | [8 empty] | Tie Beam
22 | SSS-129 | Hkkstiqj | txnh'kiqj | 1 | mRØfer e/; fo¦ky;] nkWok | Sudarshan Mahto | ,Jagdishpur,Ara |  | 209.45 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 36.61
|  |  |  | 2 | mRØfer e/; fo¦ky;] cSjgh | [10 empty] | 1 | [7 empty] | RCC in foundation
23 | SSS-130 | Hkkstiqj | vkjk | 1 | e/; fo¦ky;] [ktqfj;kW | Janardan Yadav | ,Agarsanda,Bhojpur |  | 205.53 |  |  | 15 Months |  |  | 1 | [7 empty] | 17.07 | RCC in foundation
|  |  |  | 2 | mRØfer e/; fo¦ky;] y{e.kiqj | [11 empty] | 1
| Total No. of Schools |  |  | 45 |  |  |  |  | 4803.64 |  |  |  | 10 | 0 | 13 | 6 | 13 | 3 | 0 | 0 | 0 | 0 | 362.29

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- PATNA (WEST) - Buxar, Rohtas & Kaimur (Bhabhua) | [22 empty] | Date:-30.09.2014
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-131 | jksgrkl | djxgj | 1 | e/; fo¦ky;] efu;kjh | Krishna Ganeshpur, PO- Mamrejpur, PS- chenari, Rohtas |  |  | 208.93 |  |  | 15 Months |  |  | 1 | [8 empty] | BFS (water logged)
|  |  |  | 2 | mRØfer e/; fo¦ky;] :iSBk | [7 empty] | 1 | [10 empty] | Way not available
2 | SSS-132 | jksgrkl | dkspl | 1 | mRdzfer e/; fo¦ky;] ygsjh | Vikash Kumar | Koilwar,Ara |  | 209.97 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] dq:lk | [7 empty] | 1
3 | SSS-133 | jksgrkl | f'kolkxj | 1 | e/; fo¦ky;] eqgEeniqj | M/S Shree Jogmaya Infrastructure Co. Pvt. Ltd. | ,Sasaram,Bihar |  | 414.24 |  |  | 15 Months | 1 | [9 empty] | 79.48 | Dispute
|  |  |  | 2 | mRdzfer e/; fo¦ky;] xksrgj | [12 empty] | 1 | [5 empty] | R/C
|  |  |  | 3 | mRdzfer e/; fo¦ky;] lsejh | [7 empty] | 1 | [10 empty] | Dispute
|  |  |  | 4 | e/; fo¦ky;] FkuqvkW | [12 empty] | 1 | [5 empty] | Shuttering & Steel Binding
4 | SSS-134 | jksgrkl | fMgjh | 1 | mRdzfer e/; fo¦ky;] HkMdqfM;k | Uday Nath Dubey,Pahari Tola,Ranchi |  |  | 206.54 |  |  | 15 Months |  |  | 1 | [8 empty] | E/W
|  |  |  | 2 | e/; fo¦ky;] nqxkZiqj | [7 empty] | 1 | [10 empty] | Land problem
5 | SSS-135 | jksgrkl | fnukjk | 1 | e/; fo¦ky;] osyoS;k | Retender |  |  | 419.01 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cjk<hdyk
|  |  |  | 3 | e/; fo¦ky;] esnuhiqj
|  |  |  | 4 | mRdzfer e/; fo¦ky;] [kylkiqj
6 | SSS-136 | jksgrkl | frykSFkq | 1 | e/; fo¦ky;] lsogh | Anil Ray,Rohtas |  |  | 103.43 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 18.99 | Shuttering
7 | SSS-137 | jksgrkl | frykSFkw | 1 | e/; fo¦ky;] Hknks[kjk | Chandra Bhushan Roy,Kaimur |  |  | 103.43 |  |  | 15 Months | 1 | [10 empty] | Low Land about 12'-0"
8 | SSS-138 | jksgrkl | Lkklkjke | 1 | mRdzfer e/; fo¦ky;] nouiqj | M/S Shree Jogmaya Infrastrunture Co. Pvt. Ltd,Sasaram.Bihar |  |  | 308.31 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 108.27 | R/C
|  |  |  | 2 | e/; fo¦ky;] nfjxkao | [12 empty] | 1 | [5 empty] | Shuttering
|  |  |  | 3 | e/; fo¦ky;] xksVik | [12 empty] | 1 | [5 empty] | Shuttering
9 | SSS-139 | jksgrkl | lklkjke | 1 | e/; fo¦ky;] HkSlgha | M/S A.K.Construction,Rohtas,Bihar |  |  | 309.4 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 60.55
|  |  |  | 2 | e/; fo¦ky;] ukSxkbZ | [9 empty] | 1 | [8 empty] | PCC
|  |  |  | 3 | e/; fo¦ky;] ifr;k< | [11 empty] | 1
10 | SSS-140 | jksgrkl | psukjh | 1 | e/; fo¦ky;] HkqMdqfM;k | Krishna,Ganeshpur,Rohtas |  |  | 209.19 |  |  | 15 Months |  |  | 1 | [7 empty] | 17.67 | Earth Excavation
|  |  |  | 2 | mRdzfer e/; fo¦ky;] x.ks'kiqj | [12 empty] | 1
11 | SSS-141 | jksgrkl | uks[kk | 1 | e/; fo¦ky;] ef<;kW | Maa Pragati ConstructionCo-Ramanand Singh,Rohtas |  |  | 103.58 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 19
12 | SSS-142 | jksgrkl | ukSgêk | 1 | mRØfer e/; fo¦ky;] HkoukFkiqj | M/S Manoj Singh,Rohtas |  |  | 106.15 |  |  | 15 Months |  |  | 1 | [8 empty] | Tie Beam
13 | SSS-143 | jksgrkl | vdks<+hxksyk | 1 | mRdzfer e/; fo¦ky;] lyS;k | Sidheshwar Singh,Rohtas,Bihar |  |  | 205.83 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 100.53 | Shuttering
|  |  |  | 2 | e/; fo¦ky;] dkSik | [15 empty] | 1
14 | SSS-144 | cDlj | bVk<+h | 1 | e/; fo¦ky;] fc>kSjk | Buxar Construction |  |  | 211.32 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] cSjh | [10 empty] | 1
15 | SSS-145 | cDlj | cDlj | 1 | e/; fo¦ky;] cksDlk | Bablu Kumar Singh Ram Jee chak,Patna |  |  | 210.92 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 39.65
|  |  |  | 2 | e/; fo¦ky;] tklks | [11 empty] | 1
16 | SSS-146 | cDlj | czãiqj | 1 | g0m0 e/; fo¦ky;] j?kqukFkiqj | Sharda Construction,sri Kung,Patna |  |  | 212.63 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] cjk<+h | [9 empty] | 1
17 | SSS-147 | cDlj | flejh | 1 | d0 e/; fo¦ky;] nqYygiqj | Ranjan kumar Singh,Civil Lines,buxer,Bihar |  |  | 317.85 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 60.76
|  |  |  | 2 | e/; fo¦ky;] NksVdk flaguiqjk | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ,dkSuk | [11 empty] | 1
18 | SSS-148 | cDlj | jktiqj | 1 | e/; fo¦ky;] eaxjko | M/S Darshita Buildres and Developers pvt. Ltd,Kaimur,Bhabua |  |  | 106.38 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 19.59
19 | SSS-149 | cDlj | pkSlk | 1 | e/; fo¦ky;] iouh | Krishna pratap Singh,Ramgarh,kaimur-9801133880 |  |  | 317.65 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 58.97
|  |  |  | 2 | e/; fo¦ky;] lxjk | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] pqUuh | [11 empty] | 1
20 | SSS-150 | cDlj | ukokuxj | 1 | e/; fo¦ky;] Hknkj | M/S Aditya Construction,Govindpur,Buxer |  |  | 211.67 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] xksfoUniqj | [7 empty] | 1
21 | SSS-151 | dSewj | eksgfu;ka | 1 | mRØfer e/; fo¦ky;] nknj | M/S Ashtbhuja Construction,Kanchanapur,rohtas |  |  | 315.37 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 37.86 | Sill level
|  |  |  | 2 | e/; fo¦ky;] Hkj[kj | [7 empty] | 1 | [10 empty] | Land Not available
|  |  |  | 3 | mRØfer e/; fo¦ky;] vesB | [10 empty] | 1 | [7 empty] | Sill level
22 | SSS-152 | dSewj | HkHkqvk | 1 | e/; fo¦ky;] Hksdkl | Nav Nirman Construction,bhabhua,Kaimur |  |  | 104.49 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 30.93
23 | SSS-153 | dSewj | Hkxokuiqj | 1 | mRØfer e/; fo¦ky;] dlsj | Ajay kumar Singh,Bhabua,Kaimur |  |  | 210.11 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 43.13
|  |  |  | 2 | mRØfer e/; fo¦ky;] fla/kh | [12 empty] | 1
24 | SSS-154 | dSewj | nwxkZorh | 1 | mRØfer e/; fo¦ky;] xksjkj | Baba vishwannath construction,Nowan,Kaimur |  |  | 106.08 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 32
25 | SSS-155 | dSewj | pkWan | 1 | e/; fo¦ky;] Hkjkjh | M/S Gupta dham Construction,Kaimur,bhabhua |  |  | 106.27 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 18.52
26 | SSS-156 | dSewj | pSuiqj | 1 | e/; fo¦ky;] c<kSuk | M/S Gupta dham Construction,Kaimur,bhabhua |  |  | 105.13 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 32.76
27 | SSS-157 | dSewj | v/kkSjk | 1 | mRØfer e/; fo¦ky;] pQuk | Ajay Kumar Singh , Bhabua,Kaimur |  |  | 216.41 |  |  | 15 Months | 1 | [9 empty] | 24.34 | Land Problem
|  |  |  | 2 | mRØfer e/; fo¦ky;] U;w | [12 empty] | 1
| Total No. of Schools |  |  | 54 |  |  |  |  | 5660.29 |  |  |  | 11 | 0 | 8 | 4 | 13 | 13 | 0 | 0 | 1 | 0 | 803

## Magadh
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- MAGADH | [23 empty] | Date:-30.09.2014
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency Address and Mobile No | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[14 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[18 empty] | LL | RL | LL | RL
1 | SSS-254 | x;k | bekexat | 1 | e/; fo¦ky;] oa'kh | Mata Di Construction | C/o- Rina Devi, faya |  |  | 418.32 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] fojkt | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] f>dfV;kdyk | [8 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] olsrk | [8 empty] | 1
2 | SSS-255 | x;k | cFkkuh | 1 | mnwZ e/; fo¦ky;] oaMh | Roy Engineers | Danapur |  |  | 103.96 |  |  | 15 Months |  |  | 1 | [7 empty] | 11.45
3 | SSS-256 | x;k | ckads ctkj | 1 | e/; fo¦ky;] jkS'kuxat | Sanju kuamri | Gaya |  |  | 102.68 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 14.08
4 | SSS-257 | x;k | ckds ctkj | 1 | e/; fo¦ky;] yqVqvk | Rentender |  |  |  | 206.22 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eksus;k
5 | SSS-258 | x;k | ckjkpV~Vh | 1 | e/; fo¦ky;] fnofu;ka | Rentender |  |  |  | 208.04 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] uokMhg
6 | SSS-259 | x;k | cks/kx;k | 1 | e/; fo¦ky;] teM+h | M/s om Shakti Construction | Gaya |  |  | 408.89 |  |  | 15 Months |  |  | 1 | [7 empty] | 83.73
|  |  |  | 2 | e/; fo¦ky;] ijfj;k | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ekspkfje | [11 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] 'ksjokjk | [10 empty] | 1
7 | SSS-260 | x;k | cthjxat | 1 | e/; fo¦ky;] fo'kquiqj | M/s Sidhnath Construction | Gaya |  |  | 103.37 |  |  | 15 Months |  |  | 1
8 | SSS-261 | x;k | eksguiqj | 1 | e/; fo¦ky;] tsBqvkMkgk | Keol Construction |  |  |  | 206.84 |  |  | 15 Months |  |  | 1 | [7 empty] | 6.74
|  |  |  | 2 | e/; fo¦ky;] [kqMqvk | [10 empty] | 1
9 | SSS-262 | x;k | ekuiqj | 1 | e/; fo¦ky;] xsjs | Satish Kusum Raj | Patna |  |  | 205.11 |  |  | 15 Months |  |  | 1 | [7 empty] | 25.1
|  |  |  | 2 | e/; fo¦ky;] Hkksjs | [10 empty] | 1
10 | SSS-263 | x;k | f[ktjljk; | 1 | e/; fo¦ky;] lfj;k | Retender |  |  |  | 102.85 |  |  | 15 Months
11 | SSS-264 | x;k | 'ks[k?kkVh | 1 | e/; fo¦ky;] mfpjek | Narendra Yadav | Gaya |  |  | 307.28 |  |  | 15 Months |  |  | 1 | [7 empty] | 23.32
|  |  |  | 2 | e/; fo¦ky;] eksguiqj | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dpkSM+h | [10 empty] | 1
12 | SSS-265 | x;k | Mqefj;k | 1 | e/; fo¦ky;] cjgk | Retender |  |  |  | 209.37 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] gsljk jkeiqj
13 | SSS-266 | x;k | Qrsgiqj | 1 | e/; fo¦ky;] lyS;kdyk | Retender |  |  |  | 103.36 |  |  | 15 Months
14 | SSS-267 | x;k | uxj | 1 | xzke&dsokyh] Fkkuk laŒ&197 | Satish Kusum Raj | Patna |  |  | 307.3 |  |  | 15 Months |  |  | 1 | [7 empty] | 35.62
|  |  |  | 2 | e/; fo¦ky;] dksjeka | [10 empty] | 1
|  |  |  | 3 | xzke&/kqosZ Fkkuk laŒ&177 | [10 empty] | 1
15 | SSS-268 | x;k | vkel | 1 | e/; fo¦ky;] ';kedyk | Jai Kumar | Gaya |  |  | 204.74 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] fuek cq)kSy | [10 empty] | 1
16 | SSS-269 | x;k | Vsdkjh | 1 | e/; fo¦ky;] cych?kk | Retender |  |  |  | 102.78 |  |  | 15 Months
17 | SSS-270 | x;k | VudqIik | 1 | e/; fo¦ky;] ukSokx<+ | M/s Sidhnath Consdtruction | Gaya |  |  | 206.78 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 37.44
|  |  |  | 2 | e/; fo¦ky;] HksVkSjk | [11 empty] | 1
18 | SSS-271 | x;k | xq:vk | 1 | e/; fo¦ky;] 'ksjiqj | Retender |  |  |  | 409.65 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] ukSfMgk
|  |  |  | 3 | e/; fo¦ky;] fojfgek
|  |  |  | 4 | e/; fo¦ky;] dkt
19 | SSS-272 | uoknk | esLdkSj | 1 | mRØfer e/; fo¦ky;] iokbZ | M/s Om Shakti Construction | Anil Kumar |  |  | 203.7 |  |  | 15 Months |  |  | 1 | [7 empty] | 17.96
|  |  |  | 2 | mRØfer e/; fo¦ky;] vdfj | [10 empty] | 1
20 | SSS-273 | uoknk | fglqvk | 1 | mRØfer e/; fo¦ky;] ,dukj | Retender |  |  |  | 101.62 |  |  | 15 Months
21 | SSS-274 | uoknk | fljnyk | 1 | mRØfer e/; fo¦ky;] dksyfMgk | MD. Rais Khan | Nawada |  |  | 309.53 |  |  | 15 Months |  |  | 1 | [7 empty] | 7.56
|  |  |  | 2 | e/; fo¦ky;] [kuiqjk | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] vdEck | [8 empty] | 1
22 | SSS-275 | uoknk | idjhcjkok¡ | 1 | e/; fo¦ky;] ds'kkSjh | Retender |  |  |  | 101.8 |  |  | 15 Months
23 | SSS-276 | uoknk | jksg | 1 | e/; fo¦ky;] dqat | Retender |  |  |  | 102.21 |  |  | 15 Months
24 | SSS-277 | uoknk | jtkSyh | 1 | mRØfer e/; fo¦ky;] /kkeqpd | Retender |  |  |  | 206.72 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] pijk
25 | SSS-278 | uoknk | okjlyhxat | 1 | e/; fo¦ky;] Fksjk | Retender |  |  |  | 101.74 |  |  | 15 Months
26 | SSS-279 | uoknk | ujgV | 1 | mRØfer e/; fo¦ky;] cjcŸkk | Ramesh Kumar | Patna |  |  | 203.81 |  |  | 15 Months |  |  | 1 | [7 empty] | 8.28
|  |  |  | 2 | mRØfer e/; fo¦ky;] nkbZfcxgk | [10 empty] | 1
27 | SSS-280 | uoknk | uoknk | 1 | mRØfer e/; fo¦ky;] ifN;k Mhg | M/S Shiv Shakti Construction | Nawada |  |  | 101.67 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 20.82
28 | SSS-281 | uoknk | vdcjiqj | 1 | mRØfer e/; fo¦ky;] Qjgk | Dhirendra prasad | Nalanda |  |  | 513.18 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 70.56
|  |  |  | 2 | mRØfer e/; fo¦ky;] rsyHknzks | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Hkusy | [11 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] Qqyek | [11 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] ifl;k | [11 empty] | 1
29 | SSS-282 | uoknk | xksfoUniqj | 1 | mRØfer e/; fo¦ky;] rsrfj;k | Arbind Prasad | Sheikhpura |  |  | 208.27 |  |  | 15 Months |  |  | 1 | [7 empty] | 11.74
|  |  |  | 2 | e/; fo¦ky;] cq/kokM+k | [10 empty] | 1
30 | SSS-283 | vjoy | djih | 1 | e/; fo¦ky;] [ktqjh | Retender |  |  |  | 204.41 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] v/kkjpd
31 | SSS-284 | vjoy | dysj | 1 | e/; fo¦ky; mljh | Raj kumar Singh raja ConstructionPvt Ltd | Patna |  |  | 205.66 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky; ofynkn | [10 empty] | 1
32 | SSS-285 | vjoy | dqFkkZ | 1 | mRØfer e/; fo¦ky;] dSFkksyksnhiqj | Kaushlendra Kumar | Jehanabad |  |  | 101.87 |  |  | 15 Months | 1
33 | SSS-286 | vjoy | lksuHknz oa'kh lw;Ziqj | 1 | e/; fo¦ky;] iksfUny | Retender |  |  |  | 102.28 |  |  | 15 Months
34 | SSS-287 | vjoy | vjoy | 1 | e/; fo¦ky; jkeiqj pkSje | M/s Maa KamaKhya |  |  |  | 101.96 |  |  | 15 Months |  |  |  | 1
35 | SSS-288 | vkSjaxkckn | ck:.k | 1 | e/; fo¦ky;] dnks[kjh | Arvind Kumar Singh |  |  |  | 205.43 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] fiBuqvk |  | New area, Aurangabad | [7 empty] | 1
36 | SSS-289 | vkSjaxkckn | dqVqEck | 1 | e/; fo¦ky;] pkS[kMk | Maa Sharda Construction |  |  |  | 725.98 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 140.65
|  |  |  | 2 | e/; fo¦ky;] fd'kquiqj | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] cStkfcxgk | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] cSjko | [11 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ?ksmjk | [11 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] iksyk xksjMhgk | [11 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] ihijk cxkgh | [11 empty] | 1
37 | SSS-290 | vkSjaxkckn | jQhxat | 1 | e/; fo¦ky;] ljkod | Retender |  |  |  | 206.09 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] i[kukSj |  | Bhabua-9973920426
38 | SSS-291 | vkSjaxkckn | nso | 1 | e/; fo¦ky;] ukjk;.kiqj | M/s Darshita Builders & Developers Pvt Ltd. | Aurangabad |  |  | 102.77 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 20.67
39 | SSS-292 | vkSjaxkckn | nso | 1 | e/; fo¦ky;] cjaMk jkeiqj | M/s Hari Om Construction |  |  |  | 309.39 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 56.91
|  |  |  | 2 | e/; fo¦ky;] dVS;k | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] csyk | [11 empty] | 1
40 | SSS-293 | vkSjaxkckn | uchuxj | 1 | e/; fo¦ky;] jkeuxj | Satyendra Kumar Consyruction,Patna |  |  |  | 417.45 |  |  | 15 Months | 1 | [9 empty] | 36.71
|  |  |  | 2 | e/; fo¦ky;] e>hvko | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dadsj | [11 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] csykbZ | [9 empty] | 1
41 | SSS-294 | vkSjaxkckn | vkSjaxkckn | 1 | e/; fo¦ky;] cHkUMh | M/S Raj Construction, Aurangabad |  |  |  | 102.34 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 12.85
42 | SSS-295 | vkSjaxkckn | xksg | 1 | e/; fo¦ky;] ?kkVks | Retender |  |  |  | 204.57 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] 'ks[kiqjk
43 | SSS-296 | vkSjaxkckn |  | 1 | e/; fo¦ky;] rqjrk | Bhole Shankar Construction pvt Ltd,aurangabad |  |  |  | 104.08 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 15.14
44 | SSS-297 | tgkukckn | dkdks | 1 | mRØfer e/; fo¦ky;] nso/kjk | M/S Uma Shankar & Co,Patna-7 |  |  |  | 204.22 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 10.13
|  |  |  | 2 | mRØfer e/; fo¦ky;] mÙkjlsjFkq | [8 empty] | 1 | [10 empty] | Land not available
45 | SSS-298 | tgkukckn | e[knqeiqj | 1 | mRØfer e/; fo¦ky;] mnwZ eykBh | M/s shree krishna Engineering Works,Jehanabad |  |  |  | 102.6 |  |  | 15 Months |  |  | 1 | [7 empty] | 9.58
46 | SSS-299 | tgkukckn | eksnuxat | 1 | e/; fo¦ky;] oSuk | Rajesh Kumar |  | ,C/o shiva Hardware,Patna |  | 101.83 |  |  | 15 Months | 1
47 | SSS-300 | tgkukckn | gqyklxat | 1 | e/; fo¦ky;] dsmj | Retender |  |  |  | 102.47 |  |  | 15 Months
48 | SSS-301 | tgkukckn | jruh | 1 | e/; fo¦ky;] ?kstu | Kaushlendra Kumar |  |  |  | 408.76 |  |  | 15 Months |  |  | 1 | [7 empty] | 44.83
|  |  |  | 2 | mRØfer e/; fo¦ky;] iaMkSy | [12 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] tgk¡xhjiqj | [13 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] c<srk | [10 empty] | 1
49 | SSS-302 | tgkukckn | tgkukckn | 1 | mRØfer e/; fo¦ky;] /kqfj;k | M/s Shree Krishna Engineering |  |  |  | 102.04 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 13.2
| Total No. of Schools |  |  | 99 | [5 empty] | 10187.99 |  |  |  | 10 | 3 | 29 | 25 | 4 | 1 | 0 | 0 | 0 | 0 | 735.07

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- BHAGALPUR | [22 empty] | Date:-30.09.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788), AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-230 | Hkkxyiqj | [kjhd | 1 | e/; fo¦ky;] vykyiqj | Tender Process |  |  | 209.89 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cxMh
2 | SSS-231 | Hkkxyiqj | bLekbZyiqj | 1 | e/; fo¦ky;] jkeuxj | Tender Process |  |  | 210.17 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eksrh Vksyk
3 | SSS-232 | Hkkxyiqj | dgyxkao | 1 | e/; fo¦ky;] dVksfj;k | Daya Nand singh, 3-lp-2, Barari |  |  | 103.88 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 17.52
4 | SSS-233 | Hkkxyiqj | fcgiqj | 1 | e/; fo¦ky;] vkSfy;kokn | M/S Sai Highway & Builders pvt ltd, Patna |  |  | 106.37 |  |  | 15 Months |  |  | 1
5 | SSS-234 | Hkkxyiqj | ihjiSarh | 1 | e/; fo¦ky;] clariqj | Baba bateshwar Construction Pvt.Ltd,Bhagalpur |  |  | 415.75 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 37.55
|  |  |  | 2 | e/; fo¦ky;] nmok | [7 empty] | 1 | [10 empty] | Water loging
|  |  |  | 3 | e/; fo¦ky;] Kkuorh Viqvk | [9 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] ij'kqjkeiqj | [10 empty] | 1
6 | SSS-235 | Hkkxyiqj | jaxjk pkSd | 1 | e/; fo¦ky;] Hkokuhiqj Vksyk | Tender Process |  |  | 211.53 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cfu;k
7 | SSS-236 | Hkkxyiqj | 'kkgdqaM | 1 | e/; fo¦ky;] oklqnsoiqj | Kuhu Construction |  |  | 317.04 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 85.47
|  |  |  | 2 | e/; fo¦ky;] iap:[kh | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] HkaMkjou | [12 empty] | 1
8 | SSS-237 | Hkkxyiqj | lckSj | 1 | e/; fo¦ky;] cStukFkiqj | Shyam Sundar Yadav,Banka |  |  | 104.44 |  |  | 15 Months | 1
9 | SSS-238 | Hkkxyiqj | lUgkSyk | 1 | e/; fo¦ky;] rsykaS/kk | Tender Process |  |  | 104.06 |  |  | 15 Months
10 | SSS-239 | Hkkxyiqj | ukFkuxj | 1 | e/; fo¦ky;] fo'kuiqj | Tender Process |  |  | 104.28 |  |  | 15 Months
11 | SSS-240 | Hkkxyiqj | ukjk;.kiqj | 1 | e/; fo¦ky;] jk;iqj | Sudhir Prasad, Jamui |  |  | 319.01 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] Hkokuhiqj | [7 empty] | 1 | [10 empty] | No Drawing
|  |  |  | 3 | dU;k e/; fo¦ky;] eFkqjkiqj | [7 empty] | 1
12 | SSS-241 | Hkkxyiqj | uoxfN;k | 1 | e/; fo¦ky;] txriqj | Dharmendra Kumar Choudhary, Bhagalpur |  |  | 210.53 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] [kSjiqj | [7 empty] | 1
13 | SSS-242 | Hkkxyiqj | xksikyiqj | 1 | e/; fo¦ky;] edUniqj | M/S Daya Ram Singh, Begusarai |  |  | 105.23 |  |  | 15 Months | [9 empty] | 1 | 98.56
14 | SSS-243 | Hkkxyiqj | xksikyiqj | 1 | e/; fo¦ky;] ipxfN;k | Karnawati Builders Pvt. Ltd, Samastipur |  |  | 208.09 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] fMegk | [7 empty] | 1
15 | SSS-244 | Hkkxyiqj | xksjkMhg | 1 | e/; fo¦ky;] fo'kuiqj ftPNksa | Lalan Kumar Radha Rani Sinha road, Bhagalpur |  |  | 626.7 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 104.99
|  |  |  | 2 | e/; fo¦ky;] lksuwMhg | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] eksguiqj | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] xaxkdjgfj;k | [12 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] eqDrkiqj | [11 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] dk'khy | [10 empty] | 1
16 | SSS-245 | Hkkxyiqj | /kkSjS;k | 1 | e/; fo¦ky;] vLlh edSrk | Tender Process |  |  | 312.61 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] pUnkMhg
|  |  |  | 3 | e/; fo¦ky;] eFkqjkiqj
17 | SSS-246 | ckadk | ckadk | 1 | izksŒ e/; fo¦ky;] vejiqj | Amarpur Construction Co. Pvt. Ltd, Banka |  |  | 105.34 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 32.91
18 | SSS-247 | ckadk | ckjkgkV | 1 | izksŒ e/; fo¦ky;] egqvk | Bricks Liner |  |  | 104.91 |  |  | 15 Months | [6 empty] | 1 |  |  |  | 31
19 | SSS-248 | ckadk | ckSalh | 1 | izksŒ e/; fo¦ky;] cHkuxkek | Dilendra Prasad Singh, jamui |  |  | 209.98 |  |  | 15 Months |  | 1
|  |  |  | 2 | izksŒ e/; fo¦ky;] >ifu;ka | [10 empty] | 1
20 | SSS-249 | ckadk | csygj | 1 | e/; fo¦ky;] Jhuxj | Rajesh kumar Singh,Jamui |  |  | 108.09 |  |  |  | 1
21 | SSS-250 | ckadk | dVksfj;k | 1 | e/; fo¦ky;] bukjkoj.k | Dilendra Prasad Singh, jamui |  |  | 215.33 |  |  | 15 Months |  |  |  | 1
|  |  |  | 2 | izksŒ e/; fo¦ky;] Nkrkdq:e | [10 empty] | 1
22 | SSS-251 | ckadk | jtkSu | 1 | izksŒ e/; fo¦ky;] vyhiqj /kfu;ka | Tender Process |  |  | 209 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] y'kdjh
23 | SSS-252 | ckadk | QqYyhMwej | 1 | e/; fo¦ky;] dksfM+;k bukjkoj.k | M/s Satya Narayan singh, deoghar |  |  | 429.27 |  |  | 15 Months | 1
|  |  |  | 2 | izksŒ e/; fo¦ky;] /kkok dU;k | [7 empty] | 1
|  |  |  | 3 | izksŒ e/; fo¦ky;] lkniqj | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] /kudqfM+;k | [7 empty] | 1
24 | SSS-253 | ckadk | vejiqj | 1 | izksŒ e/; fo¦ky;] eSuek | M/s Tribhuwan prasad Singh & Co,Jamui |  |  | 210.39 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 18.17
|  |  |  | 2 | xjhciqj mjnq | M/s Tribhuwan prasad Singh & Co,Jamui | [5 empty] | 15 Months |  |  | 1
| Total No. of Schools |  |  | 50 |  |  |  |  | 5261.89 |  |  |  | 12 | 1 | 6 | 9 | 2 | 4 | 2 | 0 | 0 | 1 | 426.17

## Munger
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- MUNGER | [21 empty] | Date:-30.09.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-158 | eqaxsj | gŒ [kM+xiqj | 1 | e/; fo¦ky;] lenk gfFk;k | Retender |  |  | 420.22 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] yMqbZ
|  |  |  | 3 | e/; fo¦ky;] dUnuh
|  |  |  | 4 | e/; fo¦ky;] vxzg.k
2 | SSS-159 | eqaxsj | laxzkeiqj | 1 | e/; fo¦ky;] pUnfu;ka | Rajesh kumar Singh Sikandara,Jamui |  |  | 106.58 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 17.15
3 | SSS-160 | eqaxsj | rkjkiqj | 1 | e/; fo¦ky;] fcgek | Rajendra Kumar |  |  | 316.55 |  |  | 15 Months |  |  | 1 | [7 empty] | 12.97
|  |  |  | 2 | e/; fo¦ky;] jkeiqj | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] [kqfV;k | [9 empty] | 1
4 | SSS-161 | eqaxsj | tekyiqj | 1 | e/; fo¦ky;] ckspkgh | Puja Kumari |  |  | 104.22 |  |  | 15 Months |  | 1
5 | SSS-162 | eqaxsj | vljxat | 1 | e/; fo¦ky;] eklqexat | Rajesh kumar Singh Sikandara,Jamui |  |  | 105.1 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 13.67
6 | SSS-163 | eqaxsj | VsfV;kcEcj | 1 | e/; fo¦ky;] Hkquk | Retender |  |  | 211.8 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] /kkSjh
7 | SSS-164 | 'ks[kiqjk | vfj;kjh | 1 | mRØfer e/; fo¦ky;] djdh | Anil Kumar Singh |  |  | 311.86 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 37.53
|  |  |  | 2 | mRØfer e/; fo¦ky;] csyNh | [12 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] o:.kk | [10 empty] | 1
8 | SSS-165 | 'ks[kiqjk | psojk | 1 | e/; fo¦ky;] Nfr;kjk | Anil Kumar Singh,Sheikhpura |  |  | 104.2 |  |  | 15 Months |  |  | 1 | [7 empty] | 19.15
9 | SSS-166 | 'ks[kiqjk | 'ks[kiqjk | 1 | e/; fo¦ky;] cSfj;k ch?kk | Ashok Kumar ,Sheikhpura |  |  | 103.69 |  |  | 15 Months |  |  | 1
10 | SSS-167 | osxwljk; | [kksnkoUriqqj | 1 | mRØfer e/; fo¦ky;] elqjkt | M/S Balram Kumar |  |  | 214.48 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 65.43
|  |  |  | 2 | mRØfer e/; fo¦ky;] eq'kgjh | [10 empty] | 1
11 | SSS-168 | csxwljk; | c[kjh | 1 | e/; fo¦ky;] c[kjh | M/S BalramKumar |  |  | 214.48 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 58
|  |  |  | 2 | e/; fo¦ky;] pDdjehM] unSy | [13 empty] | 1
12 | SSS-169 | csxwljk; | cjkSuh | 1 | e/; fo¦ky;] fetkZiqj pkWn | Budha infrastructure Pvt. Ltd. |  |  | 520.63 |  |  | 15 Months | 1 | [9 empty] | 24.26 | No Land
|  |  |  | 2 | e/; fo¦ky;] Hkouxkek | [9 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] pdh;k iquokZl | [7 empty] | 1 | [10 empty] | Local Problem
|  |  |  | 4 | mRØfer e/; fo¦ky;] vlqjkjh | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ds'kos | [7 empty] | 1 | [10 empty] | No Land
13 | SSS-170 | osxwljk; | cjkSuh | 1 | e/; fo¦ky;] iijkSj | M/s Daya Ram singh |  |  | 103.94 |  |  | 15 Months | [8 empty] | 1 |  | 83.99
14 | SSS-171 | osxwljk; | csxwljk; | 1 | mRØfer e/; fo¦ky;] dqlekSr | Saheb Singh Construction |  |  | 104.7 |  |  | 15 Months | 1 | [10 empty] | Land Problem
15 | SSS-172 | osxwljk; | efVgkuh | 1 | e/; fo¦ky;] nfj;kiqj | M/S Daya Ram Singh, Begusarai |  |  | 210.48 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 96.76
|  |  |  | 2 | e/; fo¦ky;] xksnjxkek | [15 empty] | 1
16 | SSS-173 | osxwljk; | Hkxokuiqj | 1 | e/; fo¦ky;] rktiqj | M/S Brij Deo Singh, Begusarai |  |  | 104.62 |  |  | 15 Months |  |  | 1
17 | SSS-174 | osxwljk; | lkgsciqj deky | 1 | e/; fo¦ky;] lkniqj | M/S Imperial Foundation Pvt.Ltd. Kankarbag |  |  | 534.25 |  |  | 15 Months | 1 | [9 empty] | 43.82 | Land Problem
|  |  |  | 2 | e/; fo¦ky;] jgqvk | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jlyiqj | [7 empty] | 1 | [10 empty] | Land Problem
|  |  |  | 4 | e/; fo¦ky;] nhgk | [12 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] j?kqukFkiqj | [9 empty] | 1 | [8 empty] | Land Problem
18 | SSS-175 | osxwljk; | MaMkjh | 1 | mRØfer e/; fo¦ky;] u;k Vksyk] dY;k.kiqj | Retender |  |  | 323.47 |  |  | 15 Months | [11 empty] | School name change with Ref.No. 1815 NIT-45 (Retender)
|  |  |  | 2 | e/; fo¦ky;] jktksiqj
|  |  |  | 3 | e/; fo¦ky;] fllkSuh
19 | SSS-176 | osxwljk; | rs?kM+k | 1 | e/; fo¦ky;] vdkgk jkeiqj | M/S Chandra Shekhar Singh & Co.Bihat,Begusarai |  |  | 312.97 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 19.76
|  |  |  | 2 | mRØfer e/; fo¦ky;] vks>k Vksy | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fi<+kSyh | [7 empty] | 1 | [10 empty] | Land Problem
20 | SSS-177 | osxwljk; | ukodksBh | 1 | mRØfer e/; fo¦ky;] pdeqt¶Qj | Retender |  |  | 209.47 |  |  | 15 Months
|  |  |  | 2 | dU;k e/; fo¦ky;] igljk
21 | SSS-178 | osxwljk; | x<+iqjk | 1 | e/; fo¦ky;] eNjkgk] jtkSj | M/Raja Enterprises & Co.,Begusarai |  |  | 320.87 |  |  | 15 Months |  | 1 | [8 empty] | 48.16
|  |  |  | 2 | mRØfer e/; fo¦ky;] dksfj;ek | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] çk.kiqj fgUnh | [11 empty] | 1
22 | SSS-179 | y[khljk; | cM+fg;k | 1 | e/; fo¦ky;] izrkiiqj | Ravi Bhushan Singh, Alawaalpur |  |  | 206.21 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] y{ehiqj] lgtkniqj | [7 empty] | 1
23 | SSS-180 | y[khljk; | lw;Zx<+k dtjk f'k{kkapy | 1 | e/; fo¦ky;] ?kks?kh cfj;kjiqj | M/S Tribhuwan Prasad Singh, Jamui |  |  | 311.03 |  |  | 15 Months | 1 | [9 empty] | 19.92
|  |  |  | 2 | e/; fo¦ky;] uodkMhg mjSu | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dtjk | [10 empty] | 1
24 | SSS-181 | y[khljk; | pkuu | 1 | mRØfer e/; fo¦ky;] fr;kpd | Retender |  |  | 206.35 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] Hkkanj
25 | SSS-182 | y[khljk; | pkuu | 1 | e/; fo¦ky;] cUuw cxhpk | Dilendra Prasad Singh, Jamui |  |  | 206.92 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] clqvkpd | [9 empty] | 1
26 | SSS-183 | y[khljk; | y[khljk; | 1 | mRØfer e/; fo¦ky;] [kxkSj | Rama Construction |  |  | 102.53 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 20.23
27 | SSS-184 | teqbZ | [kSjk | 1 | e/; fo¦ky;] :ikosy | M/S Satyanarayan Singh, Deoghar |  |  | 417.75 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] /kjeiqj | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] fVfg;kfnukjh | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] dSM+kdknks | [7 empty] | 1
28 | SSS-185 | teqbZ | >k>k | 1 | e/; fo¦ky;] iSjxkgk | Rajesh Kumar Singh, Jamui |  |  | 317.07 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] lqUnjh VkaM | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ps;u | [9 empty] | 1
29 | SSS-186 | teqbZ | cjgV | 1 | e/; fo¦ky;] yk[ks; | Sudhir Prasad,Jamui |  |  | 208.66 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] iaps'ojh | [7 empty] | 1
30 | SSS-187 | teqbZ | fldUnjk | 1 | e/; fo¦ky;] lcych?kk | Dilendra Prasad Singh, jamui |  |  | 208.47 |  |  | 15 Months |  |  |  |  | 1
|  |  |  | 2 | e/; fo¦ky;]uodkMhg | [11 empty] | 1
31 | SSS-188 | teqbZ | pdkbZ | 1 | e/; fo¦ky;] /keukMhg | M/S Satyanarayan Singh, Deoghar |  |  | 873.92 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] flejk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] njok | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] ejgh clcqfV;k | [8 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ikaMsMhg | [8 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] Bk<+h | [7 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] ek/kksiqj | [7 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] flefj;k | [8 empty] | 1
32 | SSS-189 | teqbZ | teqbZ | 1 | e/; fo¦ky;] izrkiiqj | M/S tribhuwan Prasad Singh,Jamui |  |  | 103.51 |  |  | 15 Months | 1
33 | SSS-190 | teqbZ | y{ehiqj | 1 | mRØfer e/; fo¦ky;] flaf?k;k | Retender |  |  | 104.9 |  |  | 15 Months
34 | SSS-191 | [kxfM+;k | csynkSj | 1 | e/; fo¦ky;] cksfcy Qqyofj;k | Retender |  |  | 435.3 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] ekyh
|  |  |  | 3 | e/; fo¦ky;] ldjksgj
|  |  |  | 4 | e/; fo¦ky;] ipkSr
35 | SSS-192 | [kxfM+;k | ekulh | 1 | e/; fo¦ky;] veuh | Krishna Kumar Singh, khagaria |  |  | 106.17 |  |  | 15 Months |  |  | 1 | [7 empty] | 21.48
36 | SSS-193 | [kxfM+;k | pkSFke | 1 | e/; fo¦ky;] jksfg;kj | Puja kumari,Munger |  |  | 106.85 |  |  | 15 Months |  |  | 1
| Total No. of Schools |  |  | 84 |  |  |  |  | 8874.22 |  |  |  | 24 | 6 | 15 | 12 | 3 | 3 | 1 | 0 | 2 | 0 | 602.28

## Kosi
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- KOSI | [21 empty] | Date:-30.09.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-303 | lgjlk | cuek bVgjh | 1 | e/; fo¦ky;] ikjlcUuh | Tender Process |  |  | 109.52 |  |  | 15 Months
2 | SSS-304 | lgjlk | dgjk | 1 | e/; fo¦ky;] lqfyaUnkckn | Jiwan Laxmi Construction Pvt Ltd, Patna |  |  | 110.01 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 21.7 | GROUND FLOOR ABOVE PLINTH WORK IN PROGRESS
3 | SSS-305 | lgjlk | efg"kh | 1 | e/; fo¦ky;] dUnkgk | Tender Process |  |  | 441.01 |  |  | 15 Months | [11 empty] | NOT STARTED
|  |  |  | 2 | e/; fo¦ky;] Fkuokj | [18 empty] | NOT STARTED
|  |  |  | 3 | e/; fo¦ky;] rsygj | [18 empty] | NOT STARTED
|  |  |  | 4 | e/; fo¦ky;] eaxjkSuh | [18 empty] | NOT STARTED
4 | SSS-306 | lgjlk | flejh | 1 | e/; fo¦ky;] osyokjk | Archana Contractors Pvt Ltd, Patna |  |  | 110.44 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 33.98 | GROUND FLOOR ROOF LEVEL WORK IN PROGRESS
5 | SSS-307 | lgjlk | flejh c[fr;kjiqj | 1 | e/; fo¦ky;] dFkMqej | Tender Process |  |  | 109.38 |  |  | 15 Months
6 | SSS-308 | lgjlk | irj?kV | 1 | e/; fo¦ky;] fd'kuiqj | Tender Process |  |  | 220.38 |  |  | 15 Months
7 | SSS-309 | lgjlk | lksuo"kkZ | 1 | e/; fo¦ky;] xksnjke | M/S Alam Construction, Madhepura |  |  | 438.57 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] dksik | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] [ktqjkgk | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] vkjlh | [7 empty] | 1
8 | SSS-310 | lgjlk | lrj dVS;k | 1 | e/; fo¦ky;] fcgjk | Ashok Kumar |  |  | 110.56 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 23.91
9 | SSS-311 | lgjlk | ly[kqvk | 1 | e/; fo¦ky;] vyuh | M/s Krishna Construction,Saharsa |  |  | 220.7 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 61.09
|  |  |  | 2 | e/; fo¦ky;] [kkspjnsok | [11 empty] | 1
10 | SSS-312 | lgjlk | uogêk | 1 | dU;k e/; fo¦ky;] dkfleiqj | Bholi Nath Roy |  |  | 111.2 |  |  | 15 Months | 1
11 | SSS-313 | lqikSy | clariqj | 1 | e/; fo¦ky; cuSyhiÍh | Tender Process |  |  | 920.32 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] lenk
|  |  |  | 3 | e/; fo¦ky;] fueZyh
|  |  |  | 4 | e/; fo¦ky; <k<k
|  |  |  | 5 | e/; fo¦ky; gn;uxj
|  |  |  | 6 | e/; fo¦ky; iVsjok
|  |  |  | 7 | e/; fo¦ky;] ijlk mnwZ
|  |  |  | 8 | e/; fo¦ky;] fo'kuiqj pkS/kjh
12 | SSS-314 | lqikSy | çrkixat | 1 | e/; fo¦ky;] Vsdquk | M/S Sri Krishna Construction.Co.,C/Osudhila Swami Sdan,Gopalgang |  |  | 113.98 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 31.67
13 | SSS-315 | lqikSy | f=os.khxat | 1 | e/; fo¦ky;] xksugk | Tender Process |  |  | 563.29 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky; ijlkgh gkV
|  |  |  | 3 | e/; fo¦ky;] ik.Ms;iÍh
|  |  |  | 4 | e/; fo¦ky;] fejtkok
|  |  |  | 5 | e/; fo¦ky;] ekSu
14 | SSS-316 | lqikSy | fd'kuiqj | 1 | e/; fo¦ky;] deyngk | Dhiraj Kumar agarwal,Supaul |  |  | 113.01 |  |  | 15 Months | 1
15 | SSS-317 | lqikSy | fiijk | 1 | e/; fo¦ky;] clqyh | Madan Kumar Singh,Supaul |  |  | 112.37 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 34.04
16 | SSS-318 | lqikSy | jk?kksiqj | 1 | e/; fo¦ky;] jkeiqjdyk | M/s Durga Pratap Singh,Kidwaipuri,Patna |  |  | 698.88 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 91.02
|  |  |  | 2 | e/; fo¦ky; dkfj;kiÍh nsohiqj | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky; gqykl | [11 empty] | 1
|  |  |  | 4 | e/; fo¦ky; ckSjkgk] fgUnh | [7 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] eksfriqj | [9 empty] | 1
|  |  |  | 6 | jkeukFk e/; fo¦ky;] xkSliqj | [7 empty] | 1
17 | SSS-319 | lqikSy | ljk;x<+ | 1 | e/; fo¦ky;] fiijk[kqnZ | Kailash Prasad ydav,Supaul |  |  | 227.07 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] >Yyk Mqejh | [9 empty] | 1
18 | SSS-320 | lqikSy | ljk;x<+&HkifV;kgh | 1 | e/; fo¦ky;] ykyxat | Dhiraj Kumar agarwal,Supaul |  |  | 113.92 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 34.18
19 | SSS-321 | lqikSy | lqikSy | 1 | e/; fo¦ky;] cSjks | Ashok Kumar,Saharsa |  |  | 333.66 |  |  | 15 Months |  |  | 1 | [7 empty] | 78.48
|  |  |  | 2 | dU;k e/; fo¦ky;] ckM+k | [9 empty] | 1
|  |  |  | 3 | eqjyh euksgj e/; fo¦ky; cjSy | [9 empty] | 1
20 | SSS-322 | lqikSy | Nkrkiqj | 1 | e/; fo¦ky;] jrulkj | Satendra Kumar Construction Pvt. Ltd. |  |  | 567.02 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] dVgh | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fxfj/kjiÍh | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] egnhiqj | [7 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] 'ks[kVksyk y{ehfu;ka | [7 empty] | 1
21 | SSS-323 | e/ksiqjk | dqekj[kaM | 1 | e/; fo¦ky;] csykjh | M/S Alam Construction, Madhepura |  |  | 683.22 |  |  | 15 Months |  | 1 | [9 empty] | EXCAVATION WORK IN PROGRESS
|  |  |  | 2 | e/; fo¦ky;] j?kqfu;k | [8 empty] | 1 | [9 empty] | EXCAVATION WORK STOPPED DUE TO WATER LOGGING
|  |  |  | 3 | e/; fo¦ky; jhrk | [9 empty] | 1 | [8 empty] | TIE BEAM LEVEL WORK IN PROGRESS
|  |  |  | 4 | mRØfer e/; fo¦ky;] [kWwVgk jtsS | [8 empty] | 1 | [9 empty] | EXCAVATION WORK STOPPED DUE TO WATER LOGGING
|  |  |  | 5 | mRØfer e/; fo¦ky;] bljk;u xksB | [7 empty] | 1 | [10 empty] | NOT STARTED
|  |  |  | 6 | mRØfer e/; fo¦ky;] lqUnjuxj ¼v0tk0½ | [8 empty] | 1 | [9 empty] | EXCAVATION WORK IN PROGRESS
22 | SSS-324 | e/ksiqjk | eqjyhxat | 1 | e/; fo¦ky; frudksuek | Tender Process |  |  | 221.29 |  |  | 15 Months
|  |  |  | 2 | mRØfe.r e/; fo¦ky;] jtuh fefYyd
23 | SSS-325 | e/ksiqjk | eqjyhxat | 1 | e/; fo¦ky;] jruiÍh] Hksykgh | M/S alam Construction works & Company, Madhepura |  |  | 332.8 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 114.17
|  |  |  | 2 | e/; fo¦ky;] thrkiqj | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] fnX?kh | [12 empty] | 1
24 | SSS-326 | e/ksiqjk | fcgkjhxat | 1 | e/; fo¦ky;] dBkSfr;k | Tender Process |  |  | 332.51 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] y{ehiqj
|  |  |  | 3 | mRØfer e/; fo¦ky;] jkexat
25 | SSS-327 | e/ksiqjk | flags'oj | 1 | e/; fo¦ky;] rjgk MaMkjh | M/S alam Construction works & Company, Madhepura |  |  | 443.36 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 165.63
|  |  |  | 2 | e/; fo¦ky;] lcSyk | [12 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] ekuiqj | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] iVksjh | [12 empty] | 1
26 | SSS-328 | e/ksiqjk | mnkfd'kquxat | 1 | dchj xaxk e/; fo¦ky;] chM+hj.kiky | Tender Process |  |  | 221.2 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eatkSjk
27 | SSS-329 | e/ksiqjk | vkyeuxj | 1 | e/; fo¦ky;] fo"kiÍh | Avaneesh Enterprises, Ghaziabad |  |  | 334.29 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 68.94
|  |  |  | 2 | e/; fo¦ky;] gfjgjiqj ctjkgk | [11 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] difl;k | [10 empty] | 1
28 | SSS-330 | e/ksiqjk | XokyikM+k | 1 | e/; fo¦ky;] 'kkgiqj | Tender Process |  |  | 332.41 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] VsekHksyk
|  |  |  | 3 | e/; fo¦ky;] [kks[klh ckM+k] jkexat
| Total No. of Schools |  |  | 76 |  |  |  |  | 8646.37 |  |  |  | 15 | 4 | 6 | 2 | 8 | 11 | 0 | 0 | 0 | 0 | 758.81

## Purnea
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- PURNEA | [21 empty] | Date:-30.09.2014
Name & contact no. of EE :- Manjo Kumar Pandey (9661818750) , AE :- Umesh Kumar (8986493581) & A.E.:- Madan Mohan Kumar (9431413291)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-73 | iwf.kZ;k¡ | /kenkgk | 1 | ukScr yky eŒfoŒ dqdjkSu&2 | Retender
|  |  |  | 2 | e/; fo¦ky;] jaxiqjk
|  |  |  | 3 | vkŒ e/; fo¦ky;] uhjiqj
2 | SSS-74 | iwf.kZ;k¡ | chŒ dksBh | 1 | e/; fo¦ky;] xfgyLFkku | Retender |  |  | 766.44 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] fpduh iVjkgk
|  |  |  | 3 | e/; fo¦ky;] xqykcVksy eYyMhgk
|  |  |  | 4 | e/; fo¦ky;] Hkrlkjk
|  |  |  | 5 | e/; fo¦ky;] lq[klsuk
|  |  |  | 6 | e/; fo¦ky;] fuifu;k¡
|  |  |  | 7 | e/; fo¦ky;] lglkSy
3 | SSS-75 | iwf.kZ;k¡ | cueu[kh | 1 | e/; fo¦ky;] xaxSyh | Retender |  |  | 764.93 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] ft;uxaat e/;
|  |  |  | 3 | e/; fo¦ky;] dk>h
|  |  |  | 4 | e/; fo¦ky;] gfjiqjeknh
|  |  |  | 5 | e/; fo¦ky;] nsoksÙkj
|  |  |  | 6 | e/; fo¦ky;] cksjkgh
|  |  |  | 7 | e/; fo¦ky;] jkeiqj fryd iwoZ
4 | SSS-76 | iwf.kZ;k¡ | iwf.kZ;k¡ iwoZ | 1 | e/; fo¦ky;] ykyxat | Retender |  |  | 107.55 |  |  | 15 Months
5 | SSS-77 | iwf.kZ;k¡ | Jhuxj | 1 | vkŒ e/; fo¦ky;] glSyh [kqWÎh | Hari Mohan Bishwas Hasanganj Katihar-9955713757 |  |  | 108.53 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 20.8
6 | SSS-78 | vjfj;k | dqlkZdkaVk | 1 | mRØfer e/; fo¦ky;] fcduh | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 225.1 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 22.82
|  |  |  | 2 | mRØfer e/; fo¦ky;] gksfj;k | [10 empty] | 1
7 | SSS-79 | vjfj;k | fldVh | 1 | e/; fo¦ky;] Msfu;k | M/S R.P Construction Rahikatoal Araria-9431412396 |  |  | 112.71 |  |  | 15 Months |  |  | 1
8 | SSS-80 | vjfj;k | Hkjxkek | 1 | mRØfer e/; fo¦ky;] fljfl;k dyk | Hari Mohan VishwasHasnganj Katihar-9955713757 |  |  | 111.5 |  |  | 15 Months |  |  | 1
9 | SSS-81 | vjfj;k | iyklh | 1 | e/; fo¦ky;] neZxat | Retender |  |  | 337.4 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky; Qqyljk
|  |  |  | 3 | e/; fo¦ky;] Mkyk
10 | SSS-82 | vjfj;k | jkuhxat | 1 | e/; fo¦ky;] ykyiqj egqvk | M/S R.P Construction Rahikatoal Araria-9431412396 |  |  | 328.47 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky;] cM+gkjk | [9 empty] | 1
|  |  |  | 3 | dU;k e/; fo¦ky;] iksfB;k | [8 empty] | 1
11 | SSS-84 | vjfj;k | jkuhxat | 1 | e/; fo¦ky;] ekStgk | Hari Mohan Bishwas Hasanganj Katihar-9955713757 |  |  | 221.27 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] e/kqyrk | [9 empty] | 1
12 | SSS-85 | vjfj;k | Qkjfclxat | 1 | mRØfer e/; fo¦ky; xkSfj;k | M/S R.P Construction Rahikatoal Araria-9431412396 |  |  | 559.2 |  |  | 15 Months | 1 | [10 empty] | Obstruction (tree)
|  |  |  | 2 | e/; fo¦ky;] ijokgk gfjtu | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] clxM+k jkeiqj | [8 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] ckjk | [8 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] HkkxijHkkgk | [8 empty] | 1
13 | SSS-86 | vjfj;k | tksdhgkV | 1 | e/; fo¦ky;] nkseksguk 2 | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 109.56 |  |  | 15 Months |  |  | 1
14 | SSS-87 | vjfj;k | ujirxat | 1 | e/; fo¦ky;] lkgscxat | Retender |  |  | 451.24 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] MqejcUuk
|  |  |  | 3 | e/; fo¦ky;] x<+xkek
|  |  |  | 4 | e/; fo¦ky;] Hkokuhiqj
15 | SSS-88 | vjfj;k | vjfj;k | 1 | e/; fo¦ky;] csyokr | Retender |  |  | 332.98 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] dqfl;kjxkao
|  |  |  | 3 | mRØfer e/; fo¦ky;] frjgqrfcêk
16 | SSS-89 | dfVgkj | leSyh | 1 | e/; fo¦ky;] Nksgkj | Ashok Kumar Goushala- Katihar-9431096238 |  |  | 214.7 |  |  | 15 Months | 1 | [9 empty] | 21.33 | Land not avialable
|  |  |  | 2 | e/; fo¦ky;] eygfj;k | [11 empty] | 1
17 | SSS-90 | dfVgkj | dqlSyk | 1 | e/; fo¦ky;] dVfj;k | Retender |  |  | 214.68 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] tjykgh
18 | SSS-91 | dfVgkj | MaM[kksjk | 1 | e/; fo¦ky;] usigk | Pankaj Kumar Singh Gami Tola Katihar, Bihar-9431229327 |  |  | 216.75 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 37.57
|  |  |  | 2 | e/; fo¦ky;] fVdSyh | [11 empty] | 1
19 | SSS-92 | fd'kuxat | Bkdqjxat | 1 | mRØfer e/; fo¦ky;] yks/kk | Retender |  |  | 339.89 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] csgqynaxh
|  |  |  | 3 | mRØfer e/; fo¦ky;] iapxkNh
20 | SSS-93 | fd'kuxat | cgknwjxat | 1 | mRØfer e/; fo¦ky;] ykSpk | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 222.58 |  |  | 15 Months | 1 | [10 empty] | Land Not aviable
|  |  |  | 2 | mRØfer e/; fo¦ky;] eaMyVksyk Mksgj | [7 empty] | 1 | [10 empty] | Land Not aviable
21 | SSS-94 | fd'kuxat | dkspk/kkeu | 1 | mRØfer e/; fo¦ky;] ckykuxj | Sirajur Rahman Churipatti Road Kishanganj Bihar-9470866777 |  |  | 111.36 |  |  | 15 Months | 1 | [10 empty] | Land Not aviable
22 | SSS-95 | fd'kuxat | fd'kuxat | 1 | e/; fo¦ky;] iuhlky | Sirajur Rahman Churipatti Road Kishanganj Bihar-9470866777 |  |  | 110.65 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 16.35
23 | SSS-96 | fd'kuxat | iksfB;k | 1 | e/; fo¦ky;] tkyqpkSd | Retender |  |  | 337.85 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] lksukiqj
|  |  |  | 3 | e/; fo¦ky;] csyxkNh ohjiqj
24 | SSS-97 | fd'kuxat | Vs<+kxkN | 1 | mRØfer e/; fo¦ky;] vkfnoklh Vksyk Hkksjgk | MD. Iftakar Alam Jokihat Araria-9431835133 |  |  | 230.08 |  |  | 15 Months | 1 | [10 empty] | LOA not available
|  |  |  | 2 | e/; fo¦ky;] Hkkstiqj] cyok | [7 empty] | 1 | [10 empty] | LOA not available
| Total No. of Schools |  |  | 62 |  |  |  |  | 6535.42 |  |  |  | 7 | 6 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 118.87
10
Asst. Engineer
BSEIDC,Patna

## Tirhut (East)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- TIRHUT (EAST) - Vaishali, Muzaffarpur & Sitamarhi | [22 empty] | Date:-30.09.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-35 | lhrke<+h | :uh lSniqj | 1 | e/; fo¦ky;] egs'kk 1 | Akhilesh Kumar Chaudhary Sitamarhi-9431415700 |  |  | 217.84 |  |  | 15 Months | [7 empty] | 1 |  |  | 83.1
|  |  |  | 2 | e/; fo¦ky;] oxkgh | [12 empty] | 1
2 | SSS-36 | lhrke<+h | cFkukgk | 1 | e/; fo¦ky;] gjcsy | Retender |  |  | 442.74 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] jukSyh
|  |  |  | 3 | e/; fo¦ky;] ;equk cjgh
|  |  |  | 4 | e/; fo¦ky;] gjiqj cygk
3 | SSS-37 | lhrke<+h | cktiÍh | 1 | e/; fo¦ky;] clsiqj | Rajesh Kumar Sitamarhi-9931490405 |  |  | 109.69 |  |  | 15 Months |  |  | 1
4 | SSS-38 | lhrke<+h | csylaM | 1 | e/; fo¦ky;] Mqejk | Retender |  |  | 327.74 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] nekeh eB
|  |  |  | 3 | e/; fo¦ky;] e/kdkSy
5 | SSS-39 | lhrke<+h | ijlkSuh | 1 | e/; fo¦ky;] /kuxsj | Amresh Kumar Dumra Sitamarhi-9525120333 |  |  | 109.09 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 27.65
6 | SSS-40 | lhrke<+h | jhxk | 1 | e/; fo¦ky;] cqykdhiqj | Retender |  |  | 439.01 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] mljfg;k
|  |  |  | 3 | e/; fo¦ky;] nks?kjk
|  |  |  | 4 | e/; fo¦ky;] ikSlk
7 | SSS-41 | lhrke<+h | lksuo"kkZ | 1 | e/; fo¦ky;] clgh;k fgUnh | Sharda Construction Patna-9431829462 |  |  | 221.66 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 57.54
|  |  |  | 2 | e/; fo¦ky;] ejik dpkSj | [12 empty] | 1
8 | SSS-42 | lhrke<+h | lqjlaM | 1 | e/; fo¦ky;] dksfj;kgh | M/S Sheel Construction Sheohar Bihar-9473034622 |  |  | 221.32 |  |  | 15 Months | 1 | [9 empty] | 36.35
|  |  |  | 2 | e/; fo¦ky;] c[kjh | [12 empty] | 1
9 | SSS-43 | eqt¶Qjiqj | canjk | 1 | mRØfer e/; fo¦ky;] ?kksljkek dksBh | Retender |  |  | 437.38 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cuxgh
|  |  |  | 3 | e/; fo¦ky;] jruefu;k
|  |  |  | 4 | mRØfer e/; fo¦ky;] caxjk
10 | SSS-44 | eqt¶Qjiqj | ckspgkW | 1 | e/; fo¦ky;] /kjHkjk | Ashok Kumar Singh Muzaffarpur-8521110001 |  |  | 107.95 |  |  | 15 Months | 1
11 | SSS-45 | eqt¶Qjiqj | ckspkgkW | 1 | e/; fo¦ky;] okftriqj | Ravi Jalan Patna City-9546109122 |  |  | 216.48 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] vrgj | [7 empty] | 1
12 | SSS-46 | eqt¶Qjiqj | dkWVh | 1 | e/; fo¦ky;] cjfj;k | Retender |  |  | 538.14 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eqLrQkiqj
|  |  |  | 3 | mRØfer e/; fo¦ky;] e/kqcu
|  |  |  | 4 | e/; fo¦ky;] diyiqjk
|  |  |  | 5 | e/; fo¦ky;] ';keiqj Hkkstk
13 | SSS-47 | eqt¶Qjiqj | dkWVh | 1 | mRØfer e/; fo¦ky;] dksfB;kiqj | Maa Tara Construction |  |  | 214.97 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] jruiqjk | [7 empty] | 1
14 | SSS-48 | eqt¶Qjiqj | dq<+uh | 1 | e/; fo¦ky;] caxjk | M/S Sanjay Construction Mahendru Patna-9431877189 |  |  | 1071.95 |  |  | 15 Months |  |  | 1 | [7 empty] | 72.89
|  |  |  | 2 | e/; fo¦ky;] rsfy;k | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] djepUn jkeiqj cyjk | [9 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] Qrsgiqj | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] p<+qvk | [7 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] fd'kquiqj] e/kqcu | [12 empty] | 1
|  |  |  | 7 | e/; fo¦ky;] vej[k | [10 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] efjpk | [12 empty] | 1
|  |  |  | 9 | e/; fo¦ky;] flykSV | [12 empty] | 1
|  |  |  | 10 | e/; fo¦ky;] eksfjfuLd mnwZ | [7 empty] | 1
15 | SSS-49 | eqt¶Qjiqj | ehukiqj | 1 | e/; fo¦ky;] ed'kqniqj | Minni Devi Siwan 9162643061 |  |  | 431.81 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] [kfjdk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] dksngfj;k | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] flok;iÍh | [7 empty] | 1
16 | SSS-50 | eqt¶Qjiqj | eksrhiqj | 1 | e/; fo¦ky;] eksjlaMh | Devendra Kumar-Motipur Muzaffarpur-9473156515 |  |  | 322.17 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 30.18
|  |  |  | 2 | e/; fo¦ky;] vatukdksV | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] /kqeuxj | [11 empty] | 1
17 | SSS-51 | eqt¶Qjiqj | eMou | 1 | mRØfer e/; fo¦ky;] xolkjk | Ravi Shekhar 8002497100 |  |  | 212.61 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] cFkuk jke | [7 empty] | 1
18 | SSS-52 | eqt¶Qjiqj | eqjkSy | 1 | e/; fo¦ky;] cyqvk | Deam Eathcon Pvt. Ltd. 9431115629 |  |  | 432.38 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] fVVjk fo'kquiqj | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] eq'kgjk ykSru | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] fo¦k>kai | [7 empty] | 1
19 | SSS-53 | eqt¶Qjiqj | eq'kgjh | 1 | e/; fo¦ky;] idM+h LekbZy | Deam Eathcon Pvt. Ltd. 9431115629 |  |  | 426.65 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] [kcjk | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] izgykniqj | [7 empty] | 1
|  |  |  | 4 | mRØŒ e/; fo¦ky;] eqlgjh QkeZ | [7 empty] | 1
20 | SSS-54 | eqt¶Qjiqj | ik: | 1 | e/; fo¦ky;] jkepUnziqj | Retender |  |  | 321.71 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] lygiqj
|  |  |  | 3 | e/; fo¦ky;] l[kgjk
21 | SSS-55 | eqt¶Qjiqj | ldjk | 1 | e/; fo¦ky;] y{ehiqj | Mahesh Kumar Minapur Muzaffarpur-9931805726 |  |  | 107.99 |  |  | 15 Months | 1
22 | SSS-56 | eqt¶Qjiqj | ldjk | 1 | mRØfer e/; fo¦ky;] egenkiqj cuokjh | Retender |  |  | 975.54 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eFkqjkiqj] xksoZ/kuiqj
|  |  |  | 3 | e/; fo¦ky;] xfu;kjh
|  |  |  | 4 | e/; fo¦ky;] eglh
|  |  |  | 5 | e/; fo¦ky;] flejh
|  |  |  | 6 | e/; fo¦ky;] gfjiqj d`".k
|  |  |  | 7 | mRØfer e/; fo¦ky;] jfgeiqj jldk mnwZ
|  |  |  | 8 | e/; fo¦ky;] ljeLriqj
|  |  |  | 9 | e/; fo¦ky;] ipMgh
23 | SSS-57 | eqt¶Qjiqj | ljS;k | 1 | mRØfer e/; fo¦ky;] oklqnso | Hari Shankar Prasad |  |  | 427.74 |  |  | 15 Months |  |  | 1 | [7 empty] | 49.57
|  |  |  | 2 | mRØfer e/; fo¦ky;] fo".kqiqj clSFkk | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] xkSjhxkok | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] /kqch;kgh jked`".k | [7 empty] | 1
24 | SSS-58 | eqt¶Qjiqj | vkSjkb | 1 | e/; fo¦ky;] vkSjkb fgUnh | Retender |  |  | 542.43 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] 'kaHkqrk
|  |  |  | 3 | e/; fo¦ky;] HkjFkqvk
|  |  |  | 4 | e/; fo¦ky;] HknbZ
|  |  |  | 5 | e/; fo¦ky;] veukSj
25 | SSS-59 | eqt¶Qjiqj | xk;?kkV | 1 | e/; fo¦ky; cq'kgjk eu | Keshav Kumar Keshri Bihar-7779830772 |  |  | 106.52 |  |  | 15 Months |  |  | 1
26 | SSS-60 | f'kogj | rfj;kuh | 1 | e/; fo¦ky;] vkSjk | Retender |  |  | 437.67 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] eqlgjh
|  |  |  | 3 | e/; fo¦ky;] NrkSuh
|  |  |  | 4 | e/; fo¦ky;] exqjkgk
27 | SSS-61 | f'kogj | f'kogj | 1 | e/; fo¦ky;] lqanjiqj [kjkSuk | Sushil Kumar Brindavan Sheohar-9905176583 |  |  | 110.75 |  |  | 15 Months | 1
28 | SSS-62 | oS'kkyh | egqvk | 1 | mRØfer e/; fo¦ky;] ijekuaniqj | Prem Pratap Ray 9852833505 |  |  | 531.77 |  |  | 15 Months |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] 'kkgiqj pdqEej | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] gjiqj xaxkjke | [7 empty] | 1
|  |  |  | 4 | jktdh; e/; fo¦ky;] pdmej | [9 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] idM+h | [7 empty] | 1
29 | SSS-63 | oS'kkyh | egukj | 1 | e/; fo¦ky; etfyliqj | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 |  |  | 107.28 |  |  | 15 Months |  |  | 1
30 | SSS-64 | oS'kkyh | ikrsiqj | 1 | e/; fo¦ky;] ckftriqj] drkZj | Hitech Construction and Developers Pvt. Ltd. 9470836333 |  |  | 432.88 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] eksgEeniqj tqEeu | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] igkM+iqj | [7 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] cfyxkWo | [7 empty] | 1
31 | SSS-65 | oS'kkyh | ikrsiqj | 1 | e/; fo¦ky;] cyk<+ | Hitech Construction and Developers Pvt. Ltd. 9470836333 |  |  | 432.59 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] ekSng pkrqj | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ikrsiqj | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] iLrkjk | [7 empty] | 1
32 | SSS-66 | oS'kkyh | iVs<+h csylj | 1 | mRØfer e/; fo¦ky;] csylj gkV | Dilip Kumar Patepur Vaishali-8521072115 |  |  | 106.78 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 18.46
33 | SSS-67 | oS'kkyh | jk?kksiqj | 1 | pdflaxkj e/; fo¦ky; | M/S Sanjay Construction Musllahpur Hat Mahendru Patna-9431877189 |  |  | 214.77 |  |  | 15 Months | 1
|  |  |  | 2 | pkWniqjk e/; fo¦ky; | [7 empty] | 1
34 | SSS-68 | oS'kkyh | jktkikdj | 1 | mRØfer e/; fo¦ky;] xkSliqj | Er. A.P. Construction Pvt.Ltd. Hajipur Vaishali-9431450146 |  |  | 212.57 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky; cu?kkM+k | [7 empty] | 1
35 | SSS-69 | oS'kkyh | nsljh | 1 | mRØŒ e/; fo¦kŒ] eejstiqj dU;k | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 |  |  | 213.2 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] mQjkSy | [11 empty] | 1
36 | SSS-70 | oS'kkyh | oS'kkyh | 1 | e/; fo¦ky;] trdkSyh | M/S Satyendra Kumar & Co. Construction Pvt.Ltd Exhibition Road Patna-9308003925 |  |  | 638.72 |  |  | 15 Months |  |  |  | 1
|  |  |  | 2 | e/; fo¦ky;] cjfV;k e>kSyh | [8 empty] | 1
|  |  |  | 3 | e/; fo¦ky; pdvYgnkn ifjlj | [9 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] gqlSuiqj | [7 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] [ktqvrk | [9 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] nkmnuxj ifjlj | [7 empty] | 1
37 | SSS-71 | oS'kkyh | tUnkgk | 1 | mRØfer e/; fo¦ky;] lksgjFkh | Ravindra Prasad Sharma jorpura Samastipur-9006504477 |  |  | 107.39 |  |  | 15 Months | 1
38 | SSS-72 | oS'kkyh | ykyxat | 1 | mRØfer e/; fo¦ky;] txksMhg gfjtu | Er.A.P. Construction Pvt.Ltd. Hajipur Vaishali-9431450146 |  |  | 106.07 |  |  | 15 Months | 1
| Total No. of Schools |  |  | 117 |  |  |  |  | 12635.95 |  |  |  | 42 | 2 | 15 | 5 | 3 | 8 | 0 | 1 | 0 | 0 | 375.74

## Tirhut (West)
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- TIRHUT (WEST) - East Champaran, West Champaran & Shivhar | [22 empty] | Date:-30.09.2014
Name & contact no. of EE :-Sunil Kumar Sinha , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-1 | iwohZ paikj.k | pfd;k | 1 | mRØfer e/; fo¦ky;] [kSjh teqfu;k | Retender |  |  | 328.4 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] cSfj;k
|  |  |  | 3 | e/; fo¦ky;] jkedj.k idM+h
2 | SSS-2 | iwohZ paikj.k | rqjdkSfy;k | 1 | e/; fo¦ky;] liêh | M/S Sushil kumar Gayatri Nagar, Motihari-9430494360 |  |  | 218.19 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | mŒe/; fo¦kŒ Hkxr Vksyk] eksgCcr Nijk | [9 empty] | 1
3 | SSS-3 | iwohZ paikj.k | dksVok | 1 | e/; fo¦ky;] jketh Vksyk | Munna Kumar Singh East Champaran Bihar-9097820489 |  |  | 326.11 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 44.1
|  |  |  | 2 | e/; fo¦ky;] iêh] ¼egkRek½ | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] djfj;k tkxhj | [12 empty] | 1
4 | SSS-4 | iwohZ paikj.k | idMh+n;ky | 1 | e/; fo¦ky;] jktsiqj] uoknk | Ravi Bhusan Singh, Alawalpur patna-9431083150 |  |  | 218.7 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] /kukSth | [7 empty] | 1
5 | SSS-5 | iwohZ paikj.k | jkex<+ok | 1 | e/; fo¦ky;] eqjyk | Virendra Kumar Chaudhari, East Champaran Bihar- |  |  | 111.41 |  |  | 15 Months | 1
6 | SSS-6 | iwohZ paikj.k | gjlhnh | 1 | e/; fo¦ky;] mTtSu yksfg;kj | Smt.Radha Devi,East Champaran, Bihar-9471886673 |  |  | 109.83 |  |  | 15 Months |  |  | 1
7 | SSS-7 | iwohZ paikj.k | fiijkdksBh | 1 | mRØfer e/; fo¦ky;] gfFk;kgh | Sanjay Kumar Jha, East Champaran-9934244750 |  |  | 105.25 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 14.15
8 | SSS-8 | iwohZ paikj.k | lqxkSyh | 1 | mRØfer e/; fo¦ky;] ';keiqj | Munna Kumar Singh -East Champaran-9097820489 |  |  | 109.98 |  |  | 15 Months |  |  | 1
9 | SSS-9 | iwohZ paikj.k | esglh | 1 | e/; fo¦ky;] e>kSfy;k | Keshav Kumar Keshri East Champaran-7779830772 |  |  | 109.1 |  |  | 15 Months | 1
10 | SSS-10 | iwohZ paikj.k | fpjS;k | 1 | e/; fo¦ky;] gjkt?kkV | Sanjay Kumar Jha East Chaparan-9934244750 |  |  | 110.03 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 14.76
11 | SSS-11 | iwohZ paikj.k | eksfrgkjh | 1 | mRØfer e/; fo¦ky;] ePNgkW | Keshav Kumar Keshri East Champaran-7779830772 |  |  | 108.82 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 18.83
12 | SSS-12 | iwohZ paikj.k | vjsjkt | 1 | e/; fo¦ky;] jeflfj;k¡ | Retender |  |  | 219.01 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] >[kjk
13 | SSS-13 | iwohZ paikj.k | <+kdk | 1 | e/; fo¦ky;] rsygkjk dyk | R.S.Construction Telharakala.East Champaran |  |  | 110.53 |  |  | 15 Months |  |  | 1
14 | SSS-14 | iwohZ paikj.k | vnkiqj | 1 | mRØfer e/; fo¦ky;] cjok | Vijay Kumar Singh Persouni East Champaran-9471296790 |  |  | 335.31 |  |  | 15 Months | 1 | [9 empty] | 18.33
|  |  |  | 2 | mRØfer e/; fo¦ky;] y{ehiqj | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Hkokuhiqj cktkj | [9 empty] | 1
15 | SSS-15 | iwohZ paikj.k | igkjiqj | 1 | e/; fo¦ky;] jk;djfj;k | Alok Kumar Sangrampur East Champaran-9631044077 |  |  | 109.85 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 20.48
16 | SSS-16 | iwohZ paikj.k | Qsugjk | 1 | e/; fo¦ky;] fo'kquiqj clar | Vijay Kumar Singh Persouni, East Champaran-9471296790 |  |  | 329.08 |  |  | 15 Months |  |  | 1 | [7 empty] | 45.71
|  |  |  | 2 | e/; fo¦ky; Vsolk | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ijlkSuh dksBh | [9 empty] | 1
17 | SSS-17 | iwohZ paikj.k | jDlkSy | 1 | e/; fo¦ky;] tksfd;kjh | Vijay Kumar Singh Persouni, East Champaran-9471296790 |  |  | 112.06 |  |  | 15 Months |  |  | 1 | [7 empty] | 16.54
18 | SSS-18 | iwohZ paikj.k | catfj;k | 1 | mRØfer e/; fo¦ky; xkSfj;k | Retender |  |  | 219.2 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] vtxjok fgUnh
19 | SSS-19 | iwohZ paikj.k | dY;k.kiqj | 1 | e/; fo¦ky;] j?kqukFkiqj | Kiran Devi East Champaran Biha-9006524444 |  |  | 109.21 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 16.59
20 | SSS-20 | if'pe paikj.k | cxgk II | 1 | e/; fo¦ky;] egqvk | M/S C.S.Construction Gaytri Nagar,Motihari-9473290979 |  |  | 1014.79 |  |  | 15 Months |  |  | 1 | [7 empty] | 139.41
|  |  |  | 2 | e/; fo¦ky;] cksjoy | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky; csyok p[kuh | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] ukSruok | [12 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] fl/kko | [12 empty] | 1
|  |  |  | 6 | mRØfer e/; fo¦ky;] feJkSSyh | [12 empty] | 1
|  |  |  | 7 | mRØfer e/; fo¦ky; jeofy;k | [10 empty] | 1
|  |  |  | 8 | e/; fo¦ky;] egqvkj | [11 empty] | 1
|  |  |  | 9 | mRØfer e/; fo¦ky; ePNjxkoka] | [9 empty] | 1
21 | SSS-21 | if'pe paikj.k | jkeuxj | 1 | mRØfer e/; fo¦ky; tqM+k idM+h | Sabir Husain West Champaran Bihar-9430023820,9661948918 |  |  | 787.01 |  |  | 15 Months | 1 | [9 empty] | 177.78
|  |  |  | 2 | mRØfer e/; fo¦ky; Mqejh | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] f'koiqj dkWyuh | [12 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] chŒ,eŒlhŒ Qqydksy | [12 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] Hkkoy | [12 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] eqM+sjk | [9 empty] | 1
|  |  |  | 7 | e/; fo¦ky; cM+xks | [10 empty] | 1
22 | SSS-22 | if'pe paikj.k | ea>kSfy;k | 1 | mRØfer e/; fo¦ky; cSBfu;k | M/S M.K. Enterprises, Sansaraiya W.Champaran-9431212686 |  |  | 447.52 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 46.02
|  |  |  | 2 | e/; fo¦ky;] efB;k o`r cSBfu;k | [9 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] ijlk ckcw Vksyk | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] lsuqvfj;k | [11 empty] | 1
23 | SSS-23 | if'pe paikj.k | ujdfV;kxat | 1 | e/; fo¦ky;] euok ijlh | Sisley Construction Basantpur, W. Champaran |  |  | 446.42 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] cuofj;k | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jktiqj enku | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky; pxkSuk | [7 empty] | 1
24 | SSS-24 | if'pe paikj.k | fHkrgk | 1 | e/; fo¦ky;] fcugh | MS Maa Bindyavashani Construction 9801696390 |  |  | 226.23 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] [kSjok | [7 empty] | 1
25 | SSS-25 | if'pe paikj.k | xkSukgk | 1 | e/; fo¦ky;] gkSnk Mqejk | Sisley Construction Basantpur, W. Champaran |  |  | 562.82 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] fHkfrgjok | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] MjkSy | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] c[kjh | [7 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] /kekSjk | [7 empty] | 1
26 | SSS-26 | if'pe paikj.k | ;ksxkiÍh | 1 | mRØfer e/; fo¦ky;] cklksiÍh | Retender |  |  | 221.83 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] nqf/kvok
27 | SSS-27 | if'pe paikj.k | puifV;k | 1 | mRØfer e/; fo¦ky;] dksokgk | Shatrughan PrasadBettiah, W. Champaran-9431204259 |  |  | 551.94 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] ghjk ikdM+ | [9 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] HkjifV;k | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky; lcs;k dkyk | [9 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] eksgNh lqXxk | [9 empty] | 1
28 | SSS-28 | if'pe paikj.k | cSfj;k | 1 | mŒe/; fo¦ky;] r/kokuUniqj y[kuh cktkj | Ravi Bhushan Singh-Patna,Bihar-9431083150 |  |  | 330.94 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky; Kkuhth dk VksYkk | [7 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky; cyqvk jeiqjok | [7 empty] | 1
29 | SSS-29 | if'pe paikj.k | cxgk I | 1 | e/; fo¦ky;] pUnzgkW | Brijesh Kumar |  |  | 112.43 |  |  | 15 Months | 1
30 | SSS-30 | if'pe paikj.k | ukSru | 1 | mRØfer e/; fo¦ky; fl;kjgh | Prem Pratap Ray 9852833505 |  |  | 549.94 |  |  | 15 Months |  |  | 1
|  |  |  | 2 | vkn'kZ e/; fo¦ky;] eMqvkgkW | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Mcfj;k | [9 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] f'kojktiqj | [7 empty] | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] y{ehiqj nqcksfy;k | [9 empty] | 1
31 | SSS-31 | if'pe paikj.k | csfr;k | 1 | e/; fo¦ky;] flaXkkNkij | Sanjay Kumar Mishra West Champaran-9546215798 |  |  | 220.35 |  |  | 15 Months |  |  | 1 | [7 empty] | 25.74
|  |  |  | 2 | e/; fo¦ky;] 'ks[kkSuk | [9 empty] | 1
32 | SSS-32 | if'pe paikj.k | fldVk | 1 | e/; fo¦ky;] flfjfl;k | Asiana Contract Pvt.Ltd.Gopalganj-9431088485 |  |  | 112.28 |  |  | 15 Months | 1
33 | SSS-33 | if'pe paikj.k | e/kqcuh | 1 | e/; fo¦ky;] /kugk | Retender |  |  | 230.29 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] rudwgk
34 | SSS-34 | if'pe paikj.k | ykSfj;k | 1 | e/; fo¦ky;] cudVok | Radhey Krishna Construction |  |  | 111.53 |  |  | 15 Months |  |  | 1
| Total No. of Schools |  |  | 84 |  |  |  |  | 9326.39 |  |  |  | 26 | 0 | 25 | 5 | 7 | 10 | 0 | 0 | 0 | 0 | 598.44

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- DARBHANGA | [22 empty] | Date:-30.09.2014
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of LOA | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-194 | njHkaxk |  | 1 | e/; fo¦ky;] ?ku';keiqj | Retender |  |  | 111.07 |  |  | 15 Months
2 | SSS-195 | njHkaxk | dq0LFkku | 1 | mRØfer e/; fo¦ky;] mljh | Retender |  |  | 661 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] gjkSyh
|  |  |  | 3 | e/; fo¦ky;] vkSjkgh
|  |  |  | 4 | e/; fo¦ky;] gfjuxj
|  |  |  | 5 | e/; fo¦ky;] ?kksjnkSj
|  |  |  | 6 | e/; fo¦ky;] cjxkWo
3 | SSS-196 | njHkaxk | fcjkSy | 1 | e/; fo¦ky;] f'kouxj | Retender |  |  | 438.19 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] vEckfctqfy;k
|  |  |  | 3 | e/; fo¦ky;] yngks
|  |  |  | 4 | e/; fo¦ky;] lkgks
4 | SSS-197 | njHkaxk | guqekuuxj | 1 | mRØfer e/; fo¦ky;] jkeiqj | Madhav Construction, Darbhanga |  |  | 109.1 |  | 20-2-14 | 15 Months |  |  | 1
5 | SSS-198 | e/kqcuh | ?kks?kjMhgk | 1 | e/; fo¦ky;] fpduk | Retender |  |  | 340.65 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] dsoVuk
|  |  |  | 3 | mRØefr e/; fo¦ky;] clqvkjk
6 | SSS-199 | e/kqcuh | [kqVkSuk | 1 | e/; fo¦ky;] ugjh | Retender |  |  | 339.68 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] va/kkjou
|  |  |  | 3 | e/; fo¦ky;] fldfV;kgh
7 | SSS-200 | e/kqcuh | [ktkSyh | 1 | mRØfer e/; fo¦ky;] dqlekj | Retender |  |  | 557.96 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] dlek ejkj
|  |  |  | 3 | mRØfer e/; fo¦ky;] Nijk<+h
|  |  |  | 4 | e/; fo¦ky;] jlhniqj
|  |  |  | 5 | mRØfer e/; fo¦ky;] bujok iwjc
8 | SSS-201 | e/kqcuh | >a>kjiqj | 1 | e/; fo¦ky;] flejk | Retender |  |  | 332.21 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] flM+[kfj;k
|  |  |  | 3 | e/; fo¦ky;] vM+fj;k laxzke
9 | SSS-202 | e/kqcuh | ckcwcjgh | 1 | e/; fo¦ky;] dqYgfM+;k | Avaneesh Enterprises, 111-k-35/3A. Gaziabad |  |  | 337.09 |  | 20-2-14 | 15 Months |  |  |  | 1 | [6 empty] | 66.69
|  |  |  | 2 | e/; fo¦ky;] fodze'ksj | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] cyku'ksjiqjc | [10 empty] | 1
10 | SSS-203 | e/kqcuh | cklksiÍh | 1 | mRØfer e/; fo¦ky;] dkSvkgk | Retender |  |  | 565.95 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] pUnu dlsjk
|  |  |  | 3 | e/; fo¦ky;] xkSluxj
|  |  |  | 4 | mRØfer e/; fo¦ky;] egFkkSaj
|  |  |  | 5 | e/; fo¦ky;] ?kksM+cadh
11 | SSS-204 | e/kqcuh | csuhiêh | 1 | e/; fo¦ky;] tjSy | Subodh kumar , Madhubani |  |  | 106.38 |  | 20-2-14 | 15 Months | [5 empty] | 1 |  |  |  |  | 37.39
12 | SSS-205 | e/kqcuh | e/kokiqj | 1 | e/; fo¦ky;] iks[kjkSuh | Retender |  |  | 452.14 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] fcgkjh
|  |  |  | 3 | mRØfer e/; fo¦ky;] vkSjk
|  |  |  | 4 | mRØfer e/; fo¦ky;] dsjck
13 | SSS-206 | e/kqcuh | e/ksiqj | 1 | mRØfer e/; fo¦ky;] cdqvk | Retender |  |  | 449.51 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] }ky[k
|  |  |  | 3 | e/; fo¦ky;] Vsaxjkgk
|  |  |  | 4 | mRØfer e/; fo¦ky;] ijcyiqj
14 | SSS-207 | e/kqcuh | gjyk[kh | 1 | mRØfer e/; fo¦ky;] jkeiqj | M/S Subodh kumar Singh, Saran |  |  | 113.49 |  | 20-2-14 | 15 Months | [5 empty] | 1 |  |  |  |  | 39.23
15 | SSS-208 | e/kqcuh | iaMkSy | 1 | e/; fo¦ky;] HkkSj | Rajesh Kumar, C/o shiva Hardware |  |  | 334.39 |  | 20-2-14 | 15 Months | 1 | [9 empty] | 24.05 | Water Logging
|  |  |  | 2 | e/; fo¦ky;] uogFk | [9 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] Hkokuhiqj | [10 empty] | 1
16 | SSS-209 | e/kqcuh | jfgdk | 1 | mRØfer e/; fo¦ky;] ekM+j | Retender |  |  | 444.88 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] cfy;k
|  |  |  | 3 | e/; fo¦ky;] btjk
|  |  |  | 4 | mRØfer e/; fo¦ky;] uhek
17 | SSS-210 | e/kqcuh | jktuxj | 1 | mRØfer e/; fo¦ky;] jgh iwjc | Retender |  |  | 666.63 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] lqxkSuk iks[kj v0tk0
|  |  |  | 3 | e/; fo¦ky;] flejh
|  |  |  | 4 | mRØfer e/; fo¦ky;] cM+gkjk
|  |  |  | 5 | e/; fo¦ky;] tgjeksgjk
|  |  |  | 6 | mRØfer e/; fo¦ky;] jk/kksiqj
18 | SSS-211 | e/kqcuh | Qqyijkl | 1 | e/; fo¦ky;] vekStk | Retender |  |  | 339.7 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] egFkkSj [kqnZ
|  |  |  | 3 | e/; fo¦ky;] fltkSfy;k] xksB
19 | SSS-212 | e/kqcuh | t;uxj | 1 | e/; fo¦ky;] dqok<+ | Rajesh Kumar, C/o Shiva Hardware, Patna |  |  | 112.92 |  | 20-2-14 | 15 Months |  |  | 1 | [7 empty] | 14.88
20 | SSS-213 | e/kqcuh | va/kjkBk<+h | 1 | e/; fo¦ky;] enuiêh | Retender |  |  | 112.25 |  |  | 15 Months
21 | SSS-214 | e/kqcuh | ykSdgh | 1 | e/; fo¦ky;] HkjQksM+h | Retender |  |  | 802.14 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] ujsUnziqj
|  |  |  | 3 | mRØfer e/; fo¦ky;] dfj;kSr
|  |  |  | 4 | mRØfer e/; fo¦ky;] ujgh
|  |  |  | 5 | e/; fo¦ky;] csygh dpujok
|  |  |  | 6 | mRØfer e/; fo¦ky;] dqjhou
|  |  |  | 7 | mRØfer e/; fo¦ky;] Fk:vkjh
22 | SSS-215 | e/kqcuh | ynfu;k¡ | 1 | e/; fo¦ky;] ,dgjh | Retender |  |  | 459.22 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] Hkxorhiqj
|  |  |  | 3 | e/; fo¦ky;] dqej[kr
|  |  |  | 4 | e/; fo¦ky;] fla/ki ijlkgh
23 | SSS-216 | leLrhiqj | [kkuiqj | 1 | mRØfer e/; fo¦ky;] elhuk | Ray & Raj engineering Pvt.Ltd, Samastipur |  |  | 324.64 |  | 20-2-14 | 15 Months |  |  |  | 1 | [6 empty] | 58.98
|  |  |  | 2 | mRØfer e/; fo¦ky;] cFkukgk | [7 empty] | 1 | [10 empty] | LOW LAND MORE THAN 10 FEET
|  |  |  | 3 | e/; fo¦ky;] Hkkuiqj | [10 empty] | 1
24 | SSS-217 | leLrhiqj | dY;k.kiqj | 1 | mRØfer e/; fo¦ky;] /kksyh;kgh | Retender |  |  | 107.25 |  |  | 15 Months
25 | SSS-218 | leLrhiqj | eksjok | 1 | e/; fo¦ky; /keZiqj cans | M/S Maruti Enterprises,Hajipur |  |  | 107.63 |  | 2014-03-03 | 15 Months |  |  |  |  | 1 | [5 empty] | 23.23
26 | SSS-219 | leLrhiqj | f'kokthuxj | 1 | mRØfer e/; fo¦ky;] tUnkgk | M/S Maruti Enterprises,Hajipur |  |  | 108.17 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 30.06
27 | SSS-220 | leLrhiqj | flaf?k;k | 1 | mRØfer e/; fo¦ky;] ijgV | Retender |  |  | 218.21 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] uhjiqj Hkjfj;k
28 | SSS-221 | leLrhiqj | fo¦kifruxj | 1 | vkn'kZ jktdh; e/; fo¦ky;] dkaWpk | Vinod Kumar Singh, Samastipur |  |  | 214.36 |  | 20-2-14 | 15 Months |  |  |  | 1 | [6 empty] | 46.67
|  |  |  | 2 | mRØfer e/; fo¦ky;] lksBxkek | [11 empty] | 1
29 | SSS-222 | leLrhiqj | foHkqrhiqj | 1 | e/; fo¦ky;] dY;k.kiqj | Chandra Prakash, 305, Patna |  |  | 107.54 |  | 2014-03-03 | 15 Months | 1 | [10 empty] | LOW LAND MORE THAN 10 FEET DEEP IN HALF PORTION AND ENCROCHMENT IN HALF PORTION
30 | SSS-223 | leLrhiqj | gluiqj | 1 | mRØfer e/; fo¦ky;] nso?kk | Retender |  |  | 217.56 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] gluiqj
31 | SSS-224 | leLrhiqj | jksljk | 1 | mRØfer e/; fo¦ky;] xksfoUniqj | Smt. Rita Devi, Hanuman Nagar |  |  | 107.71 |  | 3.3.14 | 15 Months | 1 | [10 empty] | land dispute
32 | SSS-225 | leLrhiqj | jksljk | 1 | mRØfer e/; fo¦ky;] egqyh | Retender |  |  | 430.84 |  |  | 15 Months
|  |  |  | 2 | e/; fo¦ky;] iapxkek
|  |  |  | 3 | mRØfer e/; fo¦ky;] HkVksVj
|  |  |  | 4 | mRØfer e/; fo¦ky;] ihV/kknksHkh
33 | SSS-226 | leLrhiqj | leLrhiqj | 1 | e/; fo¦ky;] 'kaHkqiêh | Sudhakant enterprises Pvt. Ltd. Samastipur |  |  | 428.15 |  | 20-2-14 | 15 Months | [5 empty] | 1 |  |  |  |  | 50.26
|  |  |  | 2 | mRØfer e/; fo¦ky;] ckftriqj | [12 empty] | 1
|  |  |  | 3 | e/; fo¦ky; /kwjy[k | [7 empty] | 1 | [10 empty] | ENCROCHEMENT
|  |  |  | 4 | mRØfer e/; fo¦ky;] flykSV | [7 empty] | 1 | [10 empty] | Land not Avilab.
34 | SSS-227 | leLrhiqj | ljk;jatu | 1 | mRØfer e/; fo¦ky;] jlyiqj | Vinod kumar Singh, Samastipur |  |  | 321.51 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 72.42
|  |  |  | 2 | jktdh; e/; fo¦ky;] vf[r;kjiqj | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] ukSvkpd | [11 empty] | 1
35 | SSS-228 | leLrhiqj | mft;kjiqj | 1 | mRØfer e/; fo¦ky;] ijksfj;k | Arvind Kumar Singh, Samastipur |  |  | 107.54 |  |  | 15 Months | 1 | [10 empty] | PRIVATE LAND REGISTRATION REQUIRED
36 | SSS-229 | leLrhiqj | okfj"kuxj | 1 | mRØfer e/; fo¦ky;] gtiqjok | Satyendra Kumar Construction, Patna-800001 |  |  | 107.18 |  | 2014-03-03 | 15 Months | 1 | [10 empty] | MODEL/BUILDING TO BE DISMANTED
| Total No. of Schools |  |  | 100 |  |  |  |  | 11094.84 |  |  |  | 8 | 0 | 3 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 463.86

## Saran
BSEIDC, PATNA
Progress Report for the construction of SSS ( Sanc. Year 2012 - 13 )
Name of Division :- SARAN | [21 empty] | Date:-30.09.2014
Name & contact no. of EE :- Uday Kumar Das , AE :- Hemant kr. (7488022930), AE :- Chandramadhav Singh (9431474663)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSS-331 | lkj.k | tykyiqj | 1 | e/; fo¦ky;] dksBs;kW | Ms Jagdamba buildcon pvt ltd jai prakash nagar Ara |  |  | 213.66 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky;] vuoy | [9 empty] | 1
2 | SSS-332 | lkj.k | Nijk lnj | 1 | e/; fo¦ky;] clk<+h | Shiv Shankar Singh Construction pvt. Ltd |  |  | 536.83 |  |  | 15 Months | [7 empty] | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] me/kk | [9 empty] | 1
|  |  |  | 3 | dU;k e/; fo¦ky;] 'ksjiqj
|  |  |  | 4 | mRØfer e/; fo¦ky;] mn;iqjk | [7 empty] | 1 | 1
|  |  |  | 5 | mRØfer e/; fo¦ky;] cyou Vksyk
3 | SSS-333 | lkj.k | rjS;k | 1 | e/; fo¦ky;] gjiqj Qfjnu | Bajrangi Singh,chapra |  |  | 213.37 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 38.53
|  |  |  | 2 | e/; fo¦ky;] ljS;k clar | [10 empty] | 1
4 | SSS-334 | lkj.k | ,dek | 1 | mRØfer e/; fo¦ky;] xkSliqj | Shivasati Cons truction pvt ltd. Patliputra colony patna |  |  | 216.2 |  |  | 15 Months |  | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] ukSru | [8 empty] | 1
5 | SSS-335 | lkj.k | cfu;kiqj | 1 | mRØfer e/; fo¦ky;] djgh | Satrughan singh |  |  | 214.98 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 22.24
|  |  |  | 2 | mRØfer e/; fo¦ky;] fiiM+k | [8 empty] | 1
6 | SSS-336 | lkj.k | blqvkiqj | 1 | e/; fo¦ky;] fllokW | M/s Sethi Construction, Chapra |  |  | 106.73 |  |  | 15 Months | 1
7 | SSS-337 | lkj.k | ijlk | 1 | e/; fo¦ky;] HksYnh | M/s Gaurav Construction, Muzaffarpur |  |  | 105.27 |  |  | 15 Months |  |  | 1
8 | SSS-338 | lkj.k | e<+kSjk | 1 | e/; fo¦ky;] eqckjdiqj | Retender |  |  | 106.12 |  |  | 15 Months | 1
9 | SSS-339 | lkj.k | Eklj[k | 1 | e/; fo¦ky;] xaMkeu | Er. A p Construction Pvt Ltd,Gopalgang |  |  | 107.11 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 36.22
10 | SSS-340 | lhoku | ip:[kh | 1 | mRØfer e/; fo¦ky;] MVokW | M/s shailcon Construction, Gopalgang |  |  | 106.51 |  |  | 15 Months |  |  |  |  | 1 | [5 empty] | 38.27
11 | SSS-341 | xksikyxat | dVs;k | 1 | e/; fo¦ky;] /kjgjk esyk | M/s Shailon Construction, Gopalgang |  |  | 330.68 |  |  | 15 Months |  |  | 1 | [7 empty] | 15.27
|  |  |  | 2 | mRØfer e/; fo¦ky;] idM+h Mhg | [10 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] jlkSrh | [9 empty] | 1
12 | SSS-342 | xksikyxat | ek>kW | 1 | e/; fo¦ky;] rsfy;k ckW/k | Retender |  |  | 216.53 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] e/kq ljs;k
13 | SSS-343 | xksikyxat | cjkSyh | 1 | mRØfer e/; fo¦ky;] lksucjlk | Savitri technorats pvt ltd kaithwalia ward no. 7 gopalganj |  |  | 215.99 |  |  | 15 Months |  | 1
|  |  |  | 2 | e/; fo¦ky;] dY;k.kiqj | [8 empty] | 1
14 | SSS-344 | xksikyxat | cjkSyh | 1 | mRØfer e/; fo¦ky;] osylM | Asiana Contractor Pvt. Ltd.-9431088485 |  |  | 432.83 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] [ktqfj;k ckyd | [7 empty] | 1
|  |  |  | 3 | e/; fo¦ky;] ekMuiqj | [7 empty] | 1
|  |  |  | 4 | mRØfer e/; fo¦ky;] usmjh | [7 empty] | 1
15 | SSS-345 | xksikyxat | Hkksjs | 1 | e/; fo¦ky;] dqlgkW | Anand Mishra, Gopalgang |  |  | 665.15 |  |  | 15 Months |  |  | 1 | [7 empty] | 49.19
|  |  |  | 2 | mRØfer e/; fo¦ky;] egjknsmj | [8 empty] | 1 | [9 empty] | land problem
|  |  |  | 3 | e/; fo¦ky;] ftxuk nwcs | [10 empty] | 1
|  |  |  | 4 | e/; fo¦ky;] fllbZ | [9 empty] | 1
|  |  |  | 5 | e/; fo¦ky;] ykehpkSj | [9 empty] | 1
|  |  |  | 6 | e/; fo¦ky;] oudVk tkxhjnkjh | [9 empty] | 1
16 | SSS-346 | xksikyxat | fl/kofy;k | 1 | mRØfer e/; fo¦ky;] oq/klh | Retender |  |  | 325.86 |  |  | 15 Months
|  |  |  | 2 | mRØfer e/; fo¦ky;] cqfp;k
|  |  |  | 3 | e/; fo¦ky;] >>okW
17 | SSS-347 | xksikyxat | oSdq.Biqj | 1 | mRØfer e/; fo¦ky;] calrNkijk | Hariom construction vill-khaira po-jaihindtendua distt- Aurangabad |  |  | 216.78 |  |  | 15 Months | 1
|  |  |  | 2 | mRØfer e/; fo¦ky;] eMok | [7 empty] | 1
18 | SSS-348 | xksikyxat | dqpk;dksV | 1 | mRØfer e/; fo¦ky;] HkkstNkij | Anand mishra, Gopalgang |  |  | 328.8 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 70.46
|  |  |  | 2 | e/; fo¦ky;] fo'kEHkjiqj | [10 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] o`rHkkeh Vksyk | [10 empty] | 1
19 | SSS-349 | xksikyxat | xksikyxat | 1 | mRØfer e/; fo¦ky;] ekfudiqj dU;k | Sona Engicon Pvt Ltd, Gopalganj |  |  | 216.24 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 62.24
|  |  |  | 2 | mRØfer e/; fo¦ky;] [kSjfV;k jke uxj | [10 empty] | 1
20 | SSS-350 | xksikyxat | gFkqvk | 1 | e/; fo¦ky;] lsejko | Shiv Shankar Singh Construction pvt. Ltd |  |  | 216.22 |  |  | 15 Months | 1
|  |  |  | 2 | e/; fo¦ky;] pSuiqj | [7 empty] | 1
21 | SSS-351 | xksikyxat | Qqyofj;k | 1 | mRØfer e/; fo¦ky;] exgkW | Kumar manash Construction, Gopalganj |  |  | 326.91 |  |  | 15 Months |  |  |  | 1 | [6 empty] | 48.56
|  |  |  | 2 | e/; fo¦ky;] ekMhiqj | [11 empty] | 1
|  |  |  | 3 | mRØfer e/; fo¦ky;] laxzkeiqj xksiky | [7 empty] | 1 | [10 empty] | no land
22 | SSS-352 | xksikyxat | mpdkxkWo | 1 | mRØfer e/; fo¦ky;] eqMk edlwniqj | M/s Pawan Construction, Uchakagawn |  |  | 109.2 |  |  | 15 Months | [5 empty] | 1 |  |  |  |  | 42.73
23 | SSS-353 | xksikyxat | iapnsojh | 1 | mRØfer e/; fo¦ky;] fiijgh | Anand mishra |  |  | 109.69 |  |  | 15 Months |  |  |  | 1
24 | SSS-354 | xksikyxat | fot;hiqj | 1 | e/; fo¦ky;] lqvjgkW gadkjiqj | Ashok construction vill+po- Chhitwana, Gopalganj |  |  | 110.4 |  |  | 15 Months |  |  |  | 1
| Total No. of Schools |  |  | 53 |  |  |  |  | 5748.06 |  |  |  | 12 | 8 | 9 | 12 | 4 | 1 | 0 | 1 | 0 | 0 | 423.71