## List(DIET-PTEC-CTE-BITE)
BSEIDC Ltd., Patna
PROGRESS REPORT OF DIET , PTEC, CTE & BITE BUILDING
S.No. | SL NO. | Group No. | District | Name Of School | S. No. | Name Of Building | Name of Agency with Mo- | [8 empty] | L.O.A/ Date of Issue | [6 empty] | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks | Scheme | Division
[8 empty] | A/A | T/S | BOQ Amount(in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting |  | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date |  |  |  | Not Start | Lay-out | Foundation | PL | Gro |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete |  |  |  | Agreement amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%)
[30 empty] | LL | RL | LL | RL | LL | RL
1 | 1 | D-1 | Banka | DIET Babu Tola | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 1002.5 | 1081.41 | 972.5416 | 41509 | 41544 | 41555 |  |  | issued/15-05-14 | 94540797 | 2551000 |  |  |  |  | 455 SBD OF 14-15 (15.11.14) | [11 empty] | 1 |  |  |  | DIET | Bhagalpur | 945.4077 |  | 0
2 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Bhagalpur
3 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Bhagalpur
4 | 2 | D-2 | Buxar | DIET Dumraon | 1 | Institutional Building | Recon Construction mo-9771496617 | 1002.5 | 1084.95 | 975.2904 | 41509 | 41544 | 41555 |  |  | ISSUED-18/01/14 | 98982223 | 1980000 |  |  | 1953/24-4-2014 | 1128/9-5-14 | 341 SBD OF 2014-2015(18.09.14) |  |  |  |  | 1 | [10 empty] | DIET | Patna West | 989.8222 | 83.87 | 8.47
5 |  |  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | DIET | Patna West
6 |  |  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | DIET | Patna West
7 | 3 | D-3 | Kaimur | DIET Mohaniya | 1 | Institutional Building | Recon Construction mo-9771496617 | 1002.5 | 1076.74 | 968.3349 | 41509 | 41544 | 41555 |  |  | ISSUED-18/01/14 | 96823809 | [5 empty] | 340 SBD OF 2014-2015(18.09.14) |  |  |  |  | 1 | [10 empty] | DIET | Patna West | 968.2381 | 150.82 | 15.58
8 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Patna West
9 |  |  |  |  | 3 | Girl Hostel | [23 empty] | 1 | [8 empty] | DIET | Patna West
10 | 4 | D-4 | Kishanganj | DIET Chaklaghat Kishanganj | 1 | Institutional Building | Ashok Kumar mo-9431096238 | 1002.5 | 1125.34 | 1012.0557 | 41509 | 41544 | 41555 | 41591 |  | ISSUED-28/11/13 | 92289355 | 4758000 |  |  |  |  | 236 SBD OF 2015-15(29.08.15) | [11 empty] | 1 |  |  |  | DIET | Purnea | 922.8936 |  | 0
11 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Purnea
12 |  |  |  |  | 3 | Girl Hostel | [28 empty] | 1 |  |  |  | DIET | Purnea
13 | 5 | D-5 | Lakhisarai | DIET Lakhisarai | 1 | Institutional Building | Sai highway & builder Pvt. Ltd. | 1002.5 | 1055.44 | 9491.5562 | 41509 | 41544 | 41555 | [9 empty] | 35 SBD OF 2016-17(19.05.16) |  |  |  |  | 1 | [10 empty] | DIET | Munger |  |  | #DIV/0!
14 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Munger
15 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Munger
16 |  |  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | x | X |  |  |  | DIET | Munger
17 | 6 | D-6 | Araria | DIET Forbesganj | 1 | Institutional Building | Topline Infrastructure Mo-943188439 | 1002.5 | 1152.8 | 1036.7862 | 41509 | 41544 | 41555 |  |  | Issued | 97924458 | 3452000 |  |  | 3760/27-12-2013 | 41654 | 227 SBD of 2013-14(24-2-2014) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Purnea | 979.24 | 688.69 | 70.33
18 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
19 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
20 | 7 | D-7 | Gopalganj | DIET Thawe | 1 | Institutional Building | C.K.infrastructure | 1002.5 | 1113.89 | 1002.0338 | 41449 | 41480 | 41491 |  |  | Issued | [6 empty] | 383SBD OF 2014-2014(10.10.14) | [7 empty] | 1 | [7 empty] | DIET | Saran | 1011.0521 | 161.79 | 16
21 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Saran
22 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Saran
23 | 8 | D-8 | Madhubani | DIET Narar | 1 | Institutional Building | Phular Construction Pvt.Ltd Mo-9431813608 | 1002.5 | 1136.02 | 1021.9448 | 41449 | 41480 | 41491 |  |  | ISSUED-26/11/13 | 103676105 | 2074000 |  |  | 3398/05-12-2013 | 41683 | 233 SBD of 2013-14(6-3-2014) | [13 empty] | 1 |  | DIET | Darbhanga | 1036.76 | 866.62 | 83.59
24 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 |  | DIET | Darbhanga
25 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | DIET | Darbhanga
26 | 9 | D-9 | Saran | DIET Sonpur | 1 | Institutional Building | Phular Construction Pvt.Ltd Mo-9431813608 | 1002.5 | 1081.05 | 972.4822 | 41449 | 41480 | 41491 |  |  | ISSUED-26/11/13 | 94194625 | 2624000 |  |  | 3398/05-12-2013 | 41684 | 233 SBD of 2013-14(6-3-2014) | [13 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran | 941.94 | 342.75 | 36.39
27 |  |  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Land problem | DIET | Saran
28 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
29 | 10 | D-10 | Samastipur | DIET Pusa | 1 | Institutional Building | Delco Infrastructure ph-011-28042498 | 1002.5 | 1113.69 | 1001.8586 | 41449 | 41480 | 41491 |  |  | Issued | 98081956 | 2477000 |  |  | 3550/016-12-2013 | 41631 | 220 SBD of 2013-14(5-2-2014) |  |  | 1 | [11 empty] | old building dismalting | DIET | Darbhanga | 980.81 | 202.9 | 20.69
30 |  |  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | DIET | Darbhanga
31 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Darbhanga
32 | 11 | D-11 | Madhepura | DIET Madhepura | 1 | Institutional Building | Delco Infrastructure ph-011-28042498 | 1002.5 | 1115.31 | 1003.3143 | 41449 | 41480 | 41491 |  |  | ISSUED-26/11/13 | 101786235 | 2036000 |  |  | 3550/16-12-2013 | 41631 | 221 SBD of 2013-14(5-2-2014) | [7 empty] | 1 | [7 empty] | DIET | Koshi | 1017.86 | 373.89 | 36.73
33 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Koshi
34 |  |  |  |  | 3 | Girl Hostel | [20 empty] | 1 | [11 empty] | DIET | Koshi
35 | 12 | D-12 | Siwan | DIET Siwan | 1 | Institutional Building | Durga Pratap Singh Mo-7781003700 | 1002.5 | 1094.93 | 984.9746 | 41449 | 41480 | 41491 | 41570 |  | ISSUED-04/12/13 | 100467413 | 2010000 |  |  | 3761/27-12-2013 | 41592 | 169 SBD of 2013-14(30-11-2013) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Saran | 1004.67 | 854.33 | 85.04
36 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
37 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
38 | 13 | D-13 | Aurangabad | DIET Tarar | 1 | Institutional Building | Satyendra Kumar construction | 1002.5 | 1168.14 | 954.8882 | 41681 | 41719 | 41726 | 41788 |  |  | 97877070 | 2822000 |  |  |  |  | 19 SBD OF 2016-17 (05.05.16) |  |  |  |  | 1 | [10 empty] | DIET | Magadh |  |  | #DIV/0!
39 |  |  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | DIET | Magadh
40 |  |  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | DIET | Magadh
41 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | DIET | Magadh
42 | 14 | D-14 | Katihar | DIET Tikkapatti | 1 | Institutional Building | Topline Infrastructure Mo-943188439 | 1002.5 | 1119.54 | 1007.1135 | 41449 | 41480 | 41491 |  |  | ISSUED-28/11/13 |  | 3154000 |  |  | 3761/27-12-2013 | 41689 | 48 SBD OF 2014-15 (29.05.14 | [10 empty] | X | X | 1 |  |  | DIET | Purnea | 955.7507 | 453.36 | 47.43
43 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Purnea
44 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Purnea
45 | 15 | D-15 | Nalanda | DIET Noorsarai | 1 | Institutional Building | Shristi Devloper Pvt.Ltd Mo-9334998030 | 1002.5 | 1048.63 | 943.3133 | 41449 | 41480 | 41491 | 41612 | 41631 | ISSUED-18/01/14 | 96151923 | 1924000 |  |  | 1888/16-04-2014 |  | 214 SBD OF 2014-15 (31.07.14) | [11 empty] | 1 |  |  |  | DIET | Patna East | 961.5192 | 127.32 | 13.24
46 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Patna East
47 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Patna East
48 | 16 | D-16 | East Champaran | DIET Chhatauni, Motihari | 1 | Institutional Building | Ramesh Kumar mo-8294249534 | 1002.5 | 1132.13 | 1018.4547 | 41449 | 41480 | 41491 | 41570 |  | ISSUED-01/11/13 | 98209588 | 2946000 |  |  | 2966/30-10-2013 | 41578 | 144SBD OF 2013-14 (1-11-13) | [13 empty] | 1 |  | DIET | Tirhut West | 982.09 | 726.89 | 74.01
49 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 |  | DIET | Tirhut West
50 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | DIET | Tirhut West
51 | 17 | D-17 | Patna | DIET Vikram | 1 | Institutional Building | Arvind Kumar | 1002.5 | 1165.32 | 1048.04 | 41681 | 41719 | 41726 |  |  | ISSUED 2926/12.06.14 | 98212263 | 3826000 |  |  |  |  | 458 SBD OF 14-15 (17.11.14) | [10 empty] | X | X |  | 1 | Handover | DIET | Patna East | 982.1226 | 500.93 | 51
52 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Patna East
53 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | DIET | Patna East
54 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 |  | DIET | Patna East
55 | 18 | D-18 | Shahpur | DIET Begusarai | 1 | Institutional Building | M/S VIKASH CONSTRUCTION | 1002.5 |  | 1059.5 | 41778 | 41816 | 41827 |  |  | ISSUED | [6 empty] | 716 SBD OF 2014-15 (25.02.15) | [9 empty] | 1 | [5 empty] | DIET | Munger | 1001.1239 | 425.08 | 42.46
56 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Munger
57 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Munger
58 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | DIET | Munger
59 | 19 | D-19 | Darbhanga | DIET Kilaghat | 1 | Institutional Building | Tender Process | 1002.5 |  |  | 41681 | 41719 | 41719 | [11 empty] | 1 | [12 empty] | NIT-19(2016-17) | DIET | Darbhanga |  |  | #DIV/0!
60 |  |  |  |  | 2 | Boys Hostel | [31 empty] | NIT-19(2016-17) | DIET | Darbhanga
61 |  |  |  |  | 3 | Girl Hostel | [31 empty] | NIT-19(2016-17) | DIET | Darbhanga
62 | 20 | D-20 | Nawada | DIET Jawahar Nagar | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 1002.5 | 1143.38 | 1028.3 | 41681 | 41719 | 41726 |  |  | 3759/ISSUED | 98161055 | [5 empty] | 453SBD OF 14-15 (15.11.14) | [13 empty] | 1 |  | DIET | Magadh | 981.6105 | 266.23 | 27.12
63 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Magadh
64 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Magadh
65 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | DIET | Magadh
66 | 21 | D-21 | Munger | DIET Purabsarai | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 1002.5 | 1168.14 | 1050.58 | 41681 | 41719 | 41726 |  |  | ISSUED | 101276222 | [5 empty] | 114 SBD OF 2015-16 (15.06.15) |  |  |  |  | 1 | [9 empty] | RCC in foundation | DIET | Munger | 1012.7622 |  | 0
67 |  |  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | DIET | Munger
68 |  |  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | DIET | Munger
69 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | DIET | Munger
70 | 22 | D-22 | Khagaria | DIET Ramganj | 1 | Institutional Building | Surender Prasad Singh | 1002.5 | 1194.49 | 1074.29 | 41681 | 41719 | 41726 |  |  | 2927/12-6-14 | 104152071 | 2878000 |  |  |  |  | 549 SBD OF 2014-15 (22.12.14) | [10 empty] | x | x |  | 1 | Inaugurated 16.07.2016 | DIET | Munger | 1041.5207 | 304.99 | 29.28 | 1``
71 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Munger
72 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Munger
73 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Munger
74 | 23 | D-23 | Sheikhpura | DIET Sheikhpura | 1 | Institutional Building | Satay Narayan Singh | 1002.5 | 1170.69 | 1052.87 | 41681 | 41719 | 41726 |  |  | Issued | 100548285 | 3143000 |  |  |  |  | 113 SBD OF 2015-16 (15.06.15) |  |  |  | 1 | [11 empty] | DIET | Munger | 1005.4828 |  | 0
75 |  |  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | DIET | Munger
76 |  |  |  |  | 3 | Girl Hostel | [20 empty] | 1 | [11 empty] | DIET | Munger
77 |  |  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | DIET | Munger
78 | 24 | D-24 | Purnea | DIET Purnea | 1 | Institutional Building | Top Line Infrastructure Mo-943188439 | 1002.5 | 1224.03 | 1100.87 | 41681 | 41719 | 41726 |  |  | Issued | 105121986 | 3288000 |  |  |  |  | 502 SBD OF 14-15 (12.12.14 | [10 empty] | X | X | 1 |  |  | DIET | Purnea | 1051.2199 | 452.49 | 43.04
79 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Purnea
80 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Purnea
81 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | DIET | Purnea
82 | 25 | D-25 | West Champaran | DIET Kumarbag, West Champaran | 1 | Institutional Building | Satyendra kumar construction | 1002.5 | 1268.28 | 1140.68 | 41681 | 41719 | 41726 |  |  |  | 108615677 | 3645000 |  |  |  |  | 20 SBD OF 2016-17 (05.05.2016) | [7 empty] | 1 | [7 empty] | DIET | Tirhut West |  |  | #DIV/0!
83 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Tirhut West
84 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Tirhut West
85 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | DIET | Tirhut West
86 | 26 | D-26 | Sheohar | DIET Sheohar | 1 | Institutional Building | SHASHIKANT SINGH | 1002.5 | 1243.2 | 1118.11 | 41681 | 41719 | 41726 |  |  |  | 108613047 | [5 empty] | 11 SBD OF 2016-17(20.04.2016) | [7 empty] | 1 | [7 empty] | DIET | Tirhut West |  |  | #DIV/0!
87 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Tirhut West
88 |  |  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | DIET | Tirhut West
89 |  |  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | DIET | Tirhut West
90 | 27 | P-1 | Bhojpur | PTEC BIHIYA | 1 | Institutional Building | Dilip Kumar Sharma | 1000 | 1054.91 | 948.7 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2268(13-05-14) | 92902897 | 2381000 |  |  |  |  | 324 SBD OF 2014-2015(12.09.14) | [12 empty] | 1 |  |  | PTEC | Patna East
91 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
92 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
93 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 |  | PTEC | Patna East
94 | 28 | P-2 | PATNA | PTEC MAHENDRU | 1 | Institutional Building | UMAKANT SINGH | 1000 | 1068.57 | 960.99 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2264(13-05-14) | 94371674 | [5 empty] | 550 SBD OF 14-15 (23.12.14 | [7 empty] | 1 | [6 empty] | Shuttering & Steel Binding (M.H. Footing to be casted) | PTEC | Patna East
95 |  |  |  |  | 2 | Boys Hostel | [26 empty] | 1 |  |  |  |  | Shuttering | PTEC | Patna East
96 |  |  |  |  | 3 | Girl Hostel | [22 empty] | 1 | [8 empty] | column casting upto RL (except 12 pile cap) | PTEC | Patna East
97 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | PTEC | Patna East
98 | 29 | P-3 | PATNA | PTEC MASAURHI | 1 | Institutional Building | ARVIND KUMAR | 1000 | 1061.08 | 954.25 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2269(13-05-14) | 89903853 | 3277000 |  |  |  |  | 694 SBD OF 2014-15 (14.02.15) | [10 empty] | X | X | 1 |  |  | PTEC | Patna East
99 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
100 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
101 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Patna East
102 | 30 | P-4 | ROHTAS | PTEC SASARAM | 1 | Institutional Building | M/S HARIOM CONSTRUCTION | 1000 | 1037.97 | 933.46 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | issued(20-02-14) | 92322005 | 211000 |  |  |  |  | 59 SBD OF 2014-15 (06.06.14 |  |  | 1 | [11 empty] | Not start | PTEC | Patna West
103 |  |  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | PTEC | Patna West
104 |  |  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | PTEC | Patna West
105 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | PTEC | Patna West
106 | 31 | P-5 | MUZAFFARPUR | PTEC CHANDWARA | 1 | Institutional Building | Sanjay kumar Singh | 1000 | 1086.26 | 976.91 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2267(13-05-14) | 95447562 | 2458000 |  |  |  |  | 257 SBDOF 2014-15(14.08.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
107 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
108 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
109 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
110 | 32 | P-6 | MUZAFFARPUR | PTEC PATAHI | 1 | Institutional Building | Rakesh Ranjan | 1000 | 1085.58 | 976.3 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | LOA ISSUED | [6 empty] | 182 SBD OF 2014-15 (15.07.14) | [12 empty] | 1 |  |  | PTEC | Tirhut East
111 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
112 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
113 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Tirhut East
114 | 33 | P-7 | VAISHALI | PTEC SORHATTHA | 1 | Institutional Building | Vimlesh pd. Singh | 1000 | 1085.45 | 976.18 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | ISSUED | [6 empty] | 530 SBD OF 14-15 (17.12.14 | [12 empty] | 1 |  |  | PTEC | Tirhut East
115 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
116 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
117 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Tirhut East
118 | 34 | P-8 | BHAGALPUR | PTEC PHULWARIA | 1 | Institutional Building | Lalan kumar | 1000 | 1055.66 | 949.38 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2263(13-05-14) | 91001706 | 2765000 |  |  |  |  | 397 SBD OF 2014-2014(13.10.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
119 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
120 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
121 |  |  |  |  | 4 | Principal Quarter | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
122 | 35 | P-9 | BHAGALPUR | PTEC NAGARPARA | 1 | Institutional Building | SAI HIGHWAY AND BUILDERS PVT. LTD. | 1000 | 1053.26 | 947.22 | 2014-05-19 | 2014-06-26 | 2014-07-07 |  |  | 7634 (21.08.15) | [6 empty] | 272 SBD OF 2015-16( 02.09.15) | [12 empty] | 1 |  |  | PTEC | Bhagalpur
123 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Bhagalpur
124 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Bhagalpur
125 |  |  |  |  | 4 | Principal Quarter | [29 empty] | 1 |  |  | PTEC | Bhagalpur
126 | 36 | P-10 | Aurangabad | PTEC SHAHPUR | 1 | Institutional Building | M/S HARIOM CONSTRUCTION | 1000 | 1035.79 | 931.5 | 2013-11-14 |  | 2013-12-31 |  |  | issued(20-02-14) |  | 214000 |  |  |  |  | 63 SBD OF 2014-15 (06.06.14) |  |  |  |  | 1 | [10 empty] | PTEC | Magadh
127 |  |  |  |  | 2 | Boys Hostel | [20 empty] | 1 | [11 empty] | PTEC | Magadh
128 |  |  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | PTEC | Magadh
129 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [11 empty] | Not start | PTEC | Magadh
130 | 37 | P-11 | BEGUSARAI | PTEC VISHNUPUR | 1 | Institutional Building | M/S SURENDRA PD. SINGH | 1000 | 1063.89 | 956.78 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2266(13-05-14) | 91805534 | 2766000 |  |  |  |  | 405 SBD OF 2014-2014(20.10.14) | [9 empty] | 1 | [5 empty] | PTEC | Munger
131 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Munger
132 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | PTEC | Munger
133 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 |  | PTEC | Munger
134 | 38 | P-12 | SARAN | PTEC BANGRA | 1 | Institutional Building | Indian Progressive construction pvt. Ltd | 1000 | 1076.97 | 968.55 | 2014-05-19 | 2014-06-26 | 2014-07-07 |  |  | issued | [6 empty] | 4 SBD OF 15-16(01.04.15) | [12 empty] | 1 |  |  | PTEC | Saran
135 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | PTEC | Saran
136 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Saran
137 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Saran
138 | 39 | P-13 | MADHEPURA | PTEC SUKHSAN MANHARA MADHEPURA | 1 | Institutional Building | UMAKANT SINGH | 1000 | 1119.56 | 1006.87 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2265(13-05-14) | 98818167 | 2436000 |  |  |  |  | 551 SBD OF 14-15 (23.12.14 | [11 empty] | 1 |  |  | WORK IN PROGRESS | PTEC | Koshi
139 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  | WORK IN PROGRESS | PTEC | Koshi
140 |  |  |  |  | 3 | Girl Hostel | [25 empty] | 1 | [5 empty] | BRICK WORK IN PROGRESS | PTEC | Koshi
141 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  | WORK IN PROGRESS | PTEC | Koshi
142 | 40 | P-14 | SAMASTIPUR | PTEC RAMPUR JALALPUR | 1 | Institutional Building | M/S SURENDRA PD. SINGH | 1000 | 1079.68 | 970.99 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 3175/25-6-14 | [6 empty] | 482 SBD OF 14-15 (28.11.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
143 |  |  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
144 |  |  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
145 |  |  |  |  | 4 | Principal Quarter | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
146 | 41 | P-15 | MADHUBANI | PTEC GHOGHARDIHA | 1 | Institutional Building | Phular Construction | 1000 | 1148.14 | 1017.83 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2570(27-05-14) | 103261496 | 2066200 |  |  |  |  | 224 SBD OF 2014-15 (02.08.14 | [12 empty] | 1 |  |  | PTEC | Darbhanga
147 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Darbhanga
148 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Darbhanga
149 |  |  |  |  | 4 | Principal Quarter | [23 empty] | 1 |  | X | X | X | X |  |  |  | PTEC | Darbhanga
150 | 42 | P-16 | PATNA | PTEC BARH | 1 | Institutional Building | M/S S.K ENTERPRISES | 1000 |  | 1074.48 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | ISSUED | [6 empty] | 715 SBD OF 2014-15 (24.02.15) |  |  |  |  | 1 | [9 empty] | RCC Found. Work in progress | PTEC | Patna East
151 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  | Shuttering | PTEC | Patna East
152 |  |  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [9 empty] | RCC Foundation | PTEC | Patna East
153 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Patna East
154 | 43 | P-17 | GAYA | PTEC SHERGHATI | 1 | Institutional Building | Budha Cons. Pvt. Ltd. | 1000 |  | 1025.2 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 389 SBD of 2015 -16 | [7 empty] | 1 | [7 empty] | PTEC | Magadh
155 |  |  |  |  | 2 | Boys Hostel | [23 empty] | 1 | [8 empty] | PTEC | Magadh
156 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | PTEC | Magadh
157 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Magadh
158 | 44 | P-18 | PATNA | PTEC TRAINING COLLEGE GULJARBAG | 1 | Institutional Building | M/S S.K ENTERPRISES | 1000 |  | 1045.03 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | ISSUED | [6 empty] | 715 SBD OF 2014-15 (24.02.15) | [9 empty] | 1 |  |  |  |  | Multi purpose Hall to be casted | PTEC | Patna East
159 |  |  |  |  | 2 | Boys Hostel | [25 empty] | 1 | [6 empty] | PTEC | Patna East
160 |  |  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Required old building demolision | PTEC | Patna East
161 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Patna East
162 | 45 | P-19 | MUZAFFARPUR | PTEC POKHRAIRA | 1 | Institutional Building | M/S C.S CONSTRUCTION | 1000 |  | 1072.11 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 465 SBD OF 2015-16 (30.03.16) | [8 empty] | 1 | [6 empty] | PTEC | Tirhut East
163 |  |  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | PTEC | Tirhut East
164 |  |  |  |  | 3 | Girl Hostel | [28 empty] | 1 |  |  |  | PTEC | Tirhut East
165 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Tirhut East
166 | 46 | P-20 | MUNGER | PTEC HAWELI KHARGPUR | 1 | Institutional Building | Budha Infrastructure Private Limited, Hanuman Nagar, Kankarbagh | 1000 |  | 1060.65 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 388 SBD OF 2015-16 (03.02.16 |  |  |  |  | 1 | [10 empty] | PTEC | Munger
167 |  |  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | PTEC | Munger
168 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | PTEC | Munger
169 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Munger
170 | 47 | P-21 | SIWAN | PTEC SIWAN | 1 | Institutional Building | Durga Pratap Singh | 1000 |  | 968.55 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 410 SBD OF 2015-16 (17.02.16) | [7 empty] | 1 | [7 empty] | PTEC | Saran
171 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | PTEC | Saran
172 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | PTEC | Saran
173 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Saran
174 | 48 | P-22 | SAMASTIPUR | PTEC SHAHPUR PATORI | 1 | Institutional Building | Tender Process | 1000 |  | 1079.78 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [11 empty] | 1 | [12 empty] | NIT-19(2016-17) | PTEC | Darbhanga
175 |  |  |  |  | 2 | Boys Hostel | [31 empty] | NIT-19(2016-17) | PTEC | Darbhanga
176 |  |  |  |  | 3 | Girl Hostel | [31 empty] | NIT-19(2016-17) | PTEC | Darbhanga
177 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  |  | NIT-19(2016-17) | PTEC | Darbhanga
178 | 49 | B-1 | East Champaran | BITE Dariyapur | 1 | Institutional Building | M/S C.S CONSTRUCTION |  |  | 1105.76 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 466SBD OF 2015-16 (30.-03-2016) | [7 empty] | 1 | [7 empty] | BITE | Tirhut West
179 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | BITE | Tirhut West
180 |  |  |  |  | 3 | Girl Hostel | [22 empty] | 1 | [9 empty] | BITE | Tirhut West
181 |  |  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | X | X |  |  |  | BITE | Tirhut West
182 | 50 | B-2 | West Champaran | BITE Balmikinagar | 1 | Institutional Building | C.S CONSTRACTION |  |  | 1124.7 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | 3139/17.04.15 | [6 empty] | 344 SBD OF 2015-16 (23-12-2015) | [5 empty] | 1 | [9 empty] | BITE | Tirhut West
183 |  |  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | BITE | Tirhut West
184 |  |  |  |  | 3 | Girl Hostel | [26 empty] | 1 | [5 empty] | BITE | Tirhut West
185 |  |  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | BITE | Tirhut West
186 | 51 | B-3 | Katihar | BITE Musapur katihar | 1 | Institutional Building | Pankaj kumar singh |  |  | 1071.2 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 442 SBD OF 2015-16(03.03.16) | [7 empty] | 1 | [7 empty] | BITE | Purnea
187 |  |  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | BITE | Purnea
188 |  |  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | BITE | Purnea
189 |  |  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | BITE | Purnea
190 | 52 | B-4 | Darbhanga | BITE Madhopatti | 1 | Institutional Building | Joyti Construction |  |  | 1098.43 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 414 SBD OF 2015-16 (20.02.16) | [12 empty] | 1 |  |  | BITE | Darbhanga
191 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | BITE | Darbhanga
192 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | BITE | Darbhanga
193 |  |  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | BITE | Darbhanga
194 | 53 | C-1 | MUZAFFARPUR | CTE TURKI | 1 | Institutional Building | M/S Sanjay Constraction |  |  | 1102.91 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | issued | [6 empty] | 208 SBD OF 2015-16 (14.08.15) | [7 empty] | 1 | [7 empty] | CTE | Tirhut East
195 |  |  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | CTE | Tirhut East
196 |  |  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | CTE | Tirhut East
197 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | CTE | Tirhut East
198 | 54 | C-2 | BHAGALPUR | CTE BHAGALPUR | 1 | Institutional Building | SAI HIGHWAY AND BUILDERS PVT. LTD. |  |  | 1068.42 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 14 SBD OF 2016-17(25.04.2016) | [5 empty] | 1 | [9 empty] | CTE | Bhagalpur
199 |  |  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | CTE | Bhagalpur
200 |  |  |  |  | 3 | Girl Hostel | [26 empty] | 1 | [5 empty] | CTE | Bhagalpur
201 |  |  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | X | X |  |  |  | CTE | Bhagalpur
202 | 55 | C-3 | SAMASTIPUR | CTE SAMASTIPUR | 1 | Institutional Building | Tender Process |  |  | 1093.33 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [11 empty] | 1 | [12 empty] | NIT-19(2016-17) | CTE | Darbhanga
203 |  |  |  |  | 2 | Boys Hostel | [31 empty] | NIT-19(2016-17) | CTE | Darbhanga
204 |  |  |  |  | 3 | Girl Hostel | [31 empty] | NIT-19(2016-17) | CTE | Darbhanga
205 |  |  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  |  | NIT-19(2016-17) | CTE | Darbhanga
206 | 56 | C-4 | SAHARSA | CTE SAHARSA | 1 | Institutional Building | R K CONSTRUCTION |  |  | 1117.8 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [12 empty] | 1 | [11 empty] | Not start | CTE | Koshi
207 |  |  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Koshi
208 |  |  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Koshi
209 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | CTE | Koshi
210 | 57 | C-5 | CHAPRA | CTE CHAPRA | 1 | Institutional Building | M/s. Krishnapali Construction Pvt. Ltd. Mobile : 94312 59756. |  |  | 1078.18 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [12 empty] | 1 | [11 empty] | Not start | CTE | Saran
211 |  |  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Saran
212 |  |  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Saran
213 |  |  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | CTE | Saran
214 | 58 | C-6 | GAYA | CTE GAYA | 1 | Institutional Building | Ramakant Singh |  |  | 1041.5 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | issued | [6 empty] | 709 SBD OF 2014-15 (23.02.15) |  |  | 1 | [11 empty] | Old Staff Quarter to be demolish | CTE | Magadh
215 |  |  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | CTE | Magadh
216 |  |  |  |  | 3 | Girl Hostel | [28 empty] | 1 |  |  |  | CTE | Magadh
217 |  |  |  |  | 4 | Principal Quarter | [23 empty] | 1 |  | X | X | X | X |  |  |  | CTE | Magadh
Total No. of School (BITE,CTE,DIET & PTEC) |  |  |  |  | 58 | [18 empty] | 0 | 3 | 22 | 4 | 22 | 7 | 4 | 35 | 3 | 9 | 0 | 14 | 49 | 37
|  |  | District Education and Training Institute | ( DIET ) | 26 | Institutional Building | [17 empty] | 0 | 1 | 1 | 1 | 5 | 0 | 0 | 4 | 0 | 1 | 0 | 3 | 2 | 8
[6 empty] | Boys Hostel | [17 empty] | 0 |  | 2 | 0 | 3 | 0 | 0 | 6 | 0 | 1 | 0 | 3 | 5 | 5
[6 empty] | Girl Hostel | [17 empty] | 0 |  | 1 | 2 | 3 | 0 | 1 | 6 | 0 | 0 | 0 | 1 | 5 | 7
[6 empty] | Principal Quarter | [17 empty] | 0 |  | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2
|  |  | Primary Teacher Training Institute | ( PTEC ) | 22 | Institutional Building | [17 empty] | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 3 | 1 | 2 | 0 | 1 | 7 | 3
[6 empty] | Boys Hostel | [17 empty] | 0 |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 4 | 7 | 3
[6 empty] | Girl Hostel | [17 empty] | 0 |  | 2 | 0 | 2 | 1 | 0 | 3 | 1 | 0 | 0 | 1 | 7 | 4
[6 empty] | Principal Quarter | [17 empty] | 0 |  | 3 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 7 | 5
|  |  | Teacher Education College | ( CTE ) | 6 | Institutional Building | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 3 | 0 | 6 | 0 | 1 | 4 | 2 |  |  |  | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Boys Hostel | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2 | 0 | 3 | 0 | 2 | 8 | 2 |  |  |  | 0 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
[6 empty] | Girl Hostel | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 8 | 3 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0
[6 empty] | Principal Quarter | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 7 | 4 |  |  |  | 0 |  | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  |  | Block Teacher Education Institute | ( BITE ) | 4 | Institutional Building | 0 | 1 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
[6 empty] | Boys Hostel | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0
[6 empty] | Girl Hostel | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0
[6 empty] | Principal Quarter | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | 0 |  | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## DIET (hidden)
BSEIDC Ltd., Patna
PROGRESS REPORT OF DIET
SL. NO. | Group No. | District | Name Of School | S. No. | Name Of Building | Name of Agency with Mo- | [8 empty] | L.O.A/ Date of Issue | [6 empty] | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks | Scheme | Division
[7 empty] | A/A | T/S | BOQ Amount(in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting |  | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date |  |  |  | Not Start | Lay-out | Foundation | PL | Gro |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[29 empty] | LL | RL | LL | RL | LL | RL
1 | D-1 | Banka | DIET Babu Tola | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 1002.5 | 1081.41 | 972.5416 | 41509 | 41544 | 41555 |  |  | issued/15-05-14 | 94540797 | 2551000 |  |  |  |  | 455 SBD OF 14-15 (15.11.14) | [9 empty] | 1 | [5 empty] | DIET | Bhagalpur
|  |  |  | 2 | Boys Hostel | [23 empty] | 1 | [8 empty] | DIET | Bhagalpur
|  |  |  | 3 | Girl Hostel | [23 empty] | 1 | [8 empty] | DIET | Bhagalpur
2 | D-2 | Buxar | DIET Dumraon | 1 | Institutional Building | Recon Construction mo-9771496617 | 1002.5 | 1084.95 | 975.2904 | 41509 | 41544 | 41555 |  |  | ISSUED-18/01/14 | 98982223 | 1980000 |  |  | 1953/24-4-2014 | 1128/9-5-14 | 341 SBD OF 2014-2015(18.09.14) |  |  |  |  | 1 | [10 empty] | DIET | Patna West
|  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | DIET | Patna West
|  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | DIET | Patna West
3 | D-3 | Kaimur | DIET Mohaniya | 1 | Institutional Building | Recon Construction mo-9771496617 | 1002.5 | 1076.74 | 968.3349 | 41509 | 41544 | 41555 |  |  | ISSUED-18/01/14 | 96823809 | [5 empty] | 340 SBD OF 2014-2015(18.09.14) |  |  |  |  | 1 | [10 empty] | DIET | Patna West
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Patna West
|  |  |  | 3 | Girl Hostel | [23 empty] | 1 | [8 empty] | DIET | Patna West
4 | D-4 | Kishanganj | DIET Chaklaghat Kishanganj | 1 | Institutional Building | Ashok Kumar mo-9431096238 | 1002.5 | 1125.34 | 1012.0557 | 41509 | 41544 | 41555 | 41591 |  | ISSUED-28/11/13 | 92289355 | 4758000 |  |  |  |  | 236 SBD OF 2015-15(29.08.15) | [10 empty] | 1 |  |  |  |  | DIET | Purnea
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Purnea
|  |  |  | 3 | Girl Hostel | [28 empty] | 1 |  |  |  | DIET | Purnea
5 | D-5 | Lakhisarai | DIET Lakhisarai | 1 | Institutional Building | Sai highway & builder Pvt. Ltd. | 1002.5 | 1055.44 | 9491.5562 | 41509 | 41544 | 41555 | [9 empty] | 35 SBD OF 2016-17(19.05.16) |  |  |  |  | 1 | [10 empty] | DIET | Munger
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Munger
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Munger
|  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | x | X |  |  |  | DIET | Munger
6 | D-6 | Araria | DIET Forbesganj | 1 | Institutional Building | Topline Infrastructure Mo-943188439 | 1002.5 | 1152.8 | 1036.7862 | 41509 | 41544 | 41555 |  |  | Issued | 97924458 | 3452000 |  |  | 3760/27-12-2013 | 41654 | 227 SBD of 2013-14(24-2-2014) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Purnea
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
7 | D-7 | Gopalganj | DIET Thawe | 1 | Institutional Building | C.K.infrastructure | 1002.5 | 1113.89 | 1002.0338 | 41449 | 41480 | 41491 |  |  | Issued | [6 empty] | 383SBD OF 2014-2014(10.10.14) | [7 empty] | 1 | [7 empty] | DIET | Saran
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Saran
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Saran
8 | D-8 | Madhubani | DIET Narar | 1 | Institutional Building | Phular Construction Pvt.Ltd Mo-9431813608 | 1002.5 | 1136.02 | 1021.9448 | 41449 | 41480 | 41491 |  |  | ISSUED-26/11/13 | 103676105 | 2074000 |  |  | 3398/05-12-2013 | 41683 | 233 SBD of 2013-14(6-3-2014) | [13 empty] | 1 |  | DIET | Darbhanga
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 |  | DIET | Darbhanga
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | DIET | Darbhanga
9 | D-9 | Saran | DIET Sonpur | 1 | Institutional Building | Phular Construction Pvt.Ltd Mo-9431813608 | 1002.5 | 1081.05 | 972.4822 | 41449 | 41480 | 41491 |  |  | ISSUED-26/11/13 | 94194625 | 2624000 |  |  | 3398/05-12-2013 | 41684 | 233 SBD of 2013-14(6-3-2014) | [12 empty] | 1 |  | Inaugurated 16.07.2016 | DIET | Saran
|  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Land problem | DIET | Saran
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
10 | D-10 | Samastipur | DIET Pusa | 1 | Institutional Building | Delco Infrastructure ph-011-28042498 | 1002.5 | 1113.69 | 1001.8586 | 41449 | 41480 | 41491 |  |  | Issued | 98081956 | 2477000 |  |  | 3550/016-12-2013 | 41631 | 220 SBD of 2013-14(5-2-2014) |  |  | 1 | [11 empty] | old building dismalting | DIET | Darbhanga
|  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | DIET | Darbhanga
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Darbhanga
11 | D-11 | Madhepura | DIET Madhepura | 1 | Institutional Building | Delco Infrastructure ph-011-28042498 | 1002.5 | 1115.31 | 1003.3143 | 41449 | 41480 | 41491 |  |  | ISSUED-26/11/13 | 101786235 | 2036000 |  |  | 3550/16-12-2013 | 41631 | 221 SBD of 2013-14(5-2-2014) | [7 empty] | 1 | [7 empty] | DIET | Koshi
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Koshi
|  |  |  | 3 | Girl Hostel | [20 empty] | 1 | [11 empty] | DIET | Koshi
12 | D-12 | Siwan | DIET Siwan | 1 | Institutional Building | Durga Pratap Singh Mo-7781003700 | 1002.5 | 1094.93 | 984.9746 | 41449 | 41480 | 41491 | 41570 |  | ISSUED-04/12/13 | 100467413 | 2010000 |  |  | 3761/27-12-2013 | 41592 | 169 SBD of 2013-14(30-11-2013) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Saran
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
13 | D-13 | Aurangabad | DIET Tarar | 1 | Institutional Building | Satyendra Kumar construction | 1002.5 | 1168.14 | 954.8882 | 41681 | 41719 | 41726 | 41788 |  |  | 97877070 | 2822000 |  |  |  |  | 19 SBD OF 2016-17 (05.05.16) |  |  |  |  | 1 | [10 empty] | DIET | Magadh
|  |  |  | 2 | Boys Hostel | [20 empty] | 1 | [11 empty] | DIET | Magadh
|  |  |  | 3 | Girl Hostel | [20 empty] | 1 | [11 empty] | DIET | Magadh
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | DIET | Magadh
14 | D-14 | Katihar | DIET Tikkapatti | 1 | Institutional Building | Topline Infrastructure Mo-943188439 | 1002.5 | 1119.54 | 1007.1135 | 41449 | 41480 | 41491 |  |  | ISSUED-28/11/13 |  | 3154000 |  |  | 3761/27-12-2013 | 41689 | 48 SBD OF 2014-15 (29.05.14 | [10 empty] | X | X | 1 |  |  | DIET | Purnea
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Purnea
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Purnea
15 | D-15 | Nalanda | DIET Noorsarai | 1 | Institutional Building | Shristi Devloper Pvt.Ltd Mo-9334998030 | 1002.5 | 1048.63 | 943.3133 | 41449 | 41480 | 41491 | 41612 | 41631 | ISSUED-18/01/14 | 96151923 | 1924000 |  |  | 1888/16-04-2014 |  | 214 SBD OF 2014-15 (31.07.14) | [9 empty] | 1 | [5 empty] | DIET | Patna East
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | DIET | Patna East
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Patna East
16 | D-16 | East Champaran | DIET Chhatauni, Motihari | 1 | Institutional Building | Ramesh Kumar mo-8294249534 | 1002.5 | 1132.13 | 1018.4547 | 41449 | 41480 | 41491 | 41570 |  | ISSUED-01/11/13 | 98209588 | 2946000 |  |  | 2966/30-10-2013 | 41578 | 144SBD OF 2013-14 (1-11-13) | [13 empty] | 1 |  | DIET | Tirhut West
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 |  | DIET | Tirhut West
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | DIET | Tirhut West
17 | D-17 | Patna | DIET Vikram | 1 | Institutional Building | Arvind Kumar | 1002.5 | 1165.32 | 1048.04 | 41681 | 41719 | 41726 |  |  | ISSUED 2926/12.06.14 | 98212263 | 3826000 |  |  |  |  | 458 SBD OF 14-15 (17.11.14) | [10 empty] | X | X |  | 1 |  | DIET | Patna East
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Patna East
|  |  |  | 3 | Girl Hostel | [28 empty] | 1 |  |  |  | DIET | Patna East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 |  | DIET | Patna East
18 | D-18 | Shahpur | DIET Begusarai | 1 | Institutional Building | M/S VIKASH CONSTRUCTION | 1002.5 |  | 1059.5 | 41778 | 41816 | 41827 |  |  | ISSUED | [6 empty] | 716 SBD OF 2014-15 (25.02.15) | [9 empty] | 1 | [5 empty] | DIET | Munger
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Munger
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Munger
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | DIET | Munger
19 | D-19 | Darbhanga | DIET Kilaghat | 1 | Institutional Building | Tender Process | 1002.5 |  |  | 41681 | 41719 | 41719 | [11 empty] | 1 | [12 empty] | NIT-19(2016-17) | DIET | Darbhanga
|  |  |  | 2 | Boys Hostel | [31 empty] | NIT-19(2016-17) | DIET | Darbhanga
|  |  |  | 3 | Girl Hostel | [31 empty] | NIT-19(2016-17) | DIET | Darbhanga
20 | D-20 | Nawada | DIET Jawahar Nagar | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 1002.5 | 1143.38 | 1028.3 | 41681 | 41719 | 41726 |  |  | 3759/ISSUED | 98161055 | [5 empty] | 453SBD OF 14-15 (15.11.14) | [13 empty] | 1 |  | DIET | Magadh
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | DIET | Magadh
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Magadh
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | DIET | Magadh
21 | D-21 | Munger | DIET Purabsarai | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 1002.5 | 1168.14 | 1050.58 | 41681 | 41719 | 41726 |  |  | ISSUED | 101276222 | [5 empty] | 114 SBD OF 2015-16 (15.06.15) |  |  |  |  | 1 | [10 empty] | DIET | Munger
|  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | DIET | Munger
|  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | DIET | Munger
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | DIET | Munger
22 | D-22 | Khagaria | DIET Ramganj | 1 | Institutional Building | Surender Prasad Singh | 1002.5 | 1194.49 | 1074.29 | 41681 | 41719 | 41726 |  |  | 2927/12-6-14 | 104152071 | 2878000 |  |  |  |  | 549 SBD OF 2014-15 (22.12.14) | [10 empty] | x | x |  | 1 | Inaugurated 16.07.2016 | DIET | Munger
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Munger
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | DIET | Munger
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Munger
23 | D-23 | Sheikhpura | DIET Sheikhpura | 1 | Institutional Building | Satay Narayan Singh | 1002.5 | 1170.69 | 1052.87 | 41681 | 41719 | 41726 |  |  | Issued | 100548285 | 3143000 |  |  |  |  | 113 SBD OF 2015-16 (15.06.15) |  |  |  | 1 | [11 empty] | DIET | Munger
|  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | DIET | Munger
|  |  |  | 3 | Girl Hostel | [20 empty] | 1 | [11 empty] | DIET | Munger
|  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | DIET | Munger
24 | D-24 | Purnea | DIET Purnea | 1 | Institutional Building | Top Line Infrastructure Mo-943188439 | 1002.5 | 1224.03 | 1100.87 | 41681 | 41719 | 41726 |  |  | Issued | 105121986 | 3288000 |  |  |  |  | 502 SBD OF 14-15 (12.12.14 | [10 empty] | X | X | 1 |  |  | DIET | Purnea
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | DIET | Purnea
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | DIET | Purnea
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | DIET | Purnea
25 | D-25 | West Champaran | DIET West Champaran | 1 | Institutional Building | Satyendra kumar construction | 1002.5 | 1268.28 | 1140.68 | 41681 | 41719 | 41726 |  |  |  | 108615677 | 3645000 |  |  |  |  | 20 SBD OF 2016-17 (05.05.2016) |  |  |  |  | 1 | [10 empty] | DIET | Tirhut West
|  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | DIET | Tirhut West
|  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | DIET | Tirhut West
|  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | DIET | Tirhut West
26 | D-26 | Sheohar | DIET Sheohar | 1 | Institutional Building | SHASHIKANT SINGH | 1002.5 | 1243.2 | 1118.11 | 41681 | 41719 | 41726 |  |  |  | 108613047 | [5 empty] | 11 SBD OF 2016-17(20.04.2016) | [6 empty] | 1 | [8 empty] | DIET | Tirhut West
|  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | DIET | Tirhut West
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | DIET | Tirhut West
|  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | DIET | Tirhut West
Total Number of DIET (District Education and Training Institute) |  |  |  |  | 56 | [17 empty] | 0 | 1 | 7 | 5 | 14 | 1 | 4 | 11 | 0 | 4 | 1 | 6 | 13 | 20
[5 empty] | Institutional Building | [17 empty] | 0 | 1 | 1 | 1 | 6 | 0 | 1 | 2 | 0 | 3 | 1 | 0 | 3 | 7
[5 empty] | Boys Hostel | [17 empty] | 0 | 0 | 3 | 1 | 3 | 0 | 1 | 4 | 0 | 1 | 0 | 4 | 3 | 5
[5 empty] | Girl Hostel | [17 empty] | 0 | 0 | 1 | 3 | 1 | 0 | 2 | 4 | 0 | 0 | 0 | 2 | 5 | 6
[5 empty] | Principal Quarter | [17 empty] | 0 | 0 | 2 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2

## PTEC (hidden)
BSEIDC Ltd., Patna
PROGRESS REPORT OF PTEC
SL. No. | Group No. | District | Name Of School | S. No. | Name Of Building | Name of Agency with Mo- | [8 empty] | L.O.A/ Date of Issue | [6 empty] | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks | Scheme | Division
[7 empty] | A/A | T/S | BOQ Amount(in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting |  | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date |  |  |  | Not Start | Lay-out | Foundation | PL | Gro |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[29 empty] | LL | RL | LL | RL | LL | RL
1 | P-1 | Bhojpur | PTEC BIHIYA | 1 | Institutional Building | Dilip Kumar Sharma | 1000 | 1054.91 | 948.7 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2268(13-05-14) | 92902897 | 2381000 |  |  |  |  | 324 SBD OF 2014-2015(12.09.14) | [9 empty] | 1 | [5 empty] | PTEC | Patna East
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 | RC | PTEC | Patna East
2 | P-2 | PATNA | PTEC MAHENDRU | 1 | Institutional Building | UMAKANT SINGH | 1000 | 1068.57 | 960.99 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2264(13-05-14) | 94371674 | [5 empty] | 550 SBD OF 14-15 (23.12.14 | [7 empty] | 1 | [6 empty] | Shuttering & Steel Binding (M.H. Footing to be casted) | PTEC | Patna East
|  |  |  | 2 | Boys Hostel | [26 empty] | 1 |  |  |  |  | Shuttering | PTEC | Patna East
|  |  |  | 3 | Girl Hostel | [22 empty] | 1 | [8 empty] | column casting upto RL (except 12 pile cap) | PTEC | Patna East
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | PTEC | Patna East
3 | P-3 | PATNA | PTEC MASAURHI | 1 | Institutional Building | ARVIND KUMAR | 1000 | 1061.08 | 954.25 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2269(13-05-14) | 89903853 | 3277000 |  |  |  |  | 694 SBD OF 2014-15 (14.02.15) | [9 empty] | 1 | [5 empty] | PTEC | Patna East
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Patna East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Patna East
4 | P-4 | ROHTAS | PTEC SASARAM | 1 | Institutional Building | M/S HARIOM CONSTRUCTION | 1000 | 1037.97 | 933.46 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | issued(20-02-14) | 92322005 | 211000 |  |  |  |  | 59 SBD OF 2014-15 (06.06.14 |  |  | 1 | [11 empty] | Not start | PTEC | Patna West
|  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | PTEC | Patna West
|  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | PTEC | Patna West
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | PTEC | Patna West
5 | P-5 | MUZAFFARPUR | PTEC CHANDWARA | 1 | Institutional Building | Sanjay kumar Singh | 1000 | 1086.26 | 976.91 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2267(13-05-14) | 95447562 | 2458000 |  |  |  |  | 257 SBDOF 2014-15(14.08.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
6 | P-6 | MUZAFFARPUR | PTEC PATAHI | 1 | Institutional Building | Rakesh Ranjan | 1000 | 1085.58 | 976.3 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | LOA ISSUED | [6 empty] | 182 SBD OF 2014-15 (15.07.14) | [12 empty] | 1 |  |  | PTEC | Tirhut East
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Tirhut East
7 | P-7 | VAISHALI | PTEC SORHATTHA | 1 | Institutional Building | Vimlesh pd. Singh | 1000 | 1085.45 | 976.18 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | ISSUED | [6 empty] | 530 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | [5 empty] | PTEC | Tirhut East
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Tirhut East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Tirhut East
8 | P-8 | BHAGALPUR | PTEC PHULWARIA | 1 | Institutional Building | Lalan kumar | 1000 | 1055.66 | 949.38 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2263(13-05-14) | 91001706 | 2765000 |  |  |  |  | 397 SBD OF 2014-2014(13.10.14) | [12 empty] | 1 |  | Inaugurated 16.07.2016 | PTEC | Bhagalpur
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  | Inaugurated 16.07.2016 | PTEC | Bhagalpur
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  | Inaugurated 16.07.2016 | PTEC | Bhagalpur
|  |  |  | 4 | Principal Quarter | [29 empty] | 1 |  | Inaugurated 16.07.2016 | PTEC | Bhagalpur
9 | P-9 | BHAGALPUR | PTEC NAGARPARA | 1 | Institutional Building | SAI HIGHWAY AND BUILDERS PVT. LTD. | 1000 | 1053.26 | 947.22 | 2014-05-19 | 2014-06-26 | 2014-07-07 |  |  | 7634 (21.08.15) | [6 empty] | 272 SBD OF 2015-16( 02.09.15) | [9 empty] | 1 | [5 empty] | PTEC | Bhagalpur
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Bhagalpur
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Bhagalpur
|  |  |  | 4 | Principal Quarter | [29 empty] | 1 |  |  | PTEC | Bhagalpur
10 | P-10 | Aurangabad | PTEC SHAHPUR | 1 | Institutional Building | M/S HARIOM CONSTRUCTION | 1000 | 1035.79 | 931.5 | 2013-11-14 |  | 2013-12-31 |  |  | issued(20-02-14) |  | 214000 |  |  |  |  | 63 SBD OF 2014-15 (06.06.14) |  |  |  |  | 1 | [10 empty] | PTEC | Magadh
|  |  |  | 2 | Boys Hostel | [20 empty] | 1 | [11 empty] | PTEC | Magadh
|  |  |  | 3 | Girl Hostel | [21 empty] | 1 | [10 empty] | PTEC | Magadh
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [11 empty] | Not start | PTEC | Magadh
11 | P-11 | BEGUSARAI | PTEC VISHNUPUR | 1 | Institutional Building | M/S SURENDRA PD. SINGH | 1000 | 1063.89 | 956.78 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2266(13-05-14) | 91805534 | 2766000 |  |  |  |  | 405 SBD OF 2014-2014(20.10.14) | [9 empty] | 1 | [5 empty] | PTEC | Munger
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Munger
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 |  | PTEC | Munger
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  | 1 |  | PTEC | Munger
12 | P-12 | SARAN | PTEC BANGRA | 1 | Institutional Building | Indian Progressive construction pvt. Ltd | 1000 | 1076.97 | 968.55 | 2014-05-19 | 2014-06-26 | 2014-07-07 |  |  | issued | [6 empty] | 4 SBD OF 15-16(01.04.15) | [12 empty] | 1 |  |  | PTEC | Saran
|  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | PTEC | Saran
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Saran
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Saran
13 | P-13 | MADHEPURA | PTEC SUKHSAN MANHARA MADHEPURA | 1 | Institutional Building | UMAKANT SINGH | 1000 | 1119.56 | 1006.87 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2265(13-05-14) | 98818167 | 2436000 |  |  |  |  | 551 SBD OF 14-15 (23.12.14 | [11 empty] | 1 |  |  | WORK IN PROGRESS | PTEC | Koshi
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  | WORK IN PROGRESS | PTEC | Koshi
|  |  |  | 3 | Girl Hostel | [25 empty] | 1 | [5 empty] | BRICK WORK IN PROGRESS | PTEC | Koshi
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  | WORK IN PROGRESS | PTEC | Koshi
14 | P-14 | SAMASTIPUR | PTEC RAMPUR JALALPUR | 1 | Institutional Building | M/S SURENDRA PD. SINGH | 1000 | 1079.68 | 970.99 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 3175/25-6-14 | [6 empty] | 482 SBD OF 14-15 (28.11.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
|  |  |  | 2 | Boys Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
|  |  |  | 3 | Girl Hostel | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
|  |  |  | 4 | Principal Quarter | [30 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
15 | P-15 | MADHUBANI | PTEC GHOGHARDIHA | 1 | Institutional Building | Phular Construction | 1000 | 1148.14 | 1017.83 | 2013-11-14 | 2013-12-19 | 2013-12-31 |  |  | 2570(27-05-14) | 103261496 | 2066200 |  |  |  |  | 224 SBD OF 2014-15 (02.08.14 | [12 empty] | 1 |  |  | PTEC | Darbhanga
|  |  |  | 2 | Boys Hostel | [29 empty] | 1 |  |  | PTEC | Darbhanga
|  |  |  | 3 | Girl Hostel | [29 empty] | 1 |  |  | PTEC | Darbhanga
|  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | X | X |  |  |  | PTEC | Darbhanga
16 | P-16 | PATNA | PTEC BARH | 1 | Institutional Building | M/S S.K ENTERPRISES | 1000 |  | 1074.48 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | ISSUED | [6 empty] | 715 SBD OF 2014-15 (24.02.15) |  |  |  | 1 | [10 empty] | RCC Found. Work in progress | PTEC | Patna East
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  | Shuttering | PTEC | Patna East
|  |  |  | 3 | Girl Hostel | [20 empty] | 1 | [10 empty] | RCC Foundation | PTEC | Patna East
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Patna East
17 | P-17 | GAYA | PTEC SHERGHATI | 1 | Institutional Building | Budha Cons. Pvt. Ltd. | 1000 |  | 1025.2 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 389 SBD of 2015 -16 | [5 empty] | 1 | [9 empty] | PTEC | Magadh
|  |  |  | 2 | Boys Hostel | [22 empty] | 1 | [9 empty] | PTEC | Magadh
|  |  |  | 3 | Girl Hostel | [23 empty] | 1 | [8 empty] | PTEC | Magadh
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Magadh
18 | P-18 | PATNA | PTEC TRAINING COLLEGE GULJARBAG | 1 | Institutional Building | M/S S.K ENTERPRISES | 1000 |  | 1045.03 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | ISSUED | [6 empty] | 715 SBD OF 2014-15 (24.02.15) | [9 empty] | 1 | [5 empty] | PTEC | Patna East
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | PTEC | Patna East
|  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Required old building demolision | PTEC | Patna East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Patna East
19 | P-19 | MUZAFFARPUR | PTEC POKHRAIRA | 1 | Institutional Building | M/S C.S CONSTRUCTION | 1000 |  | 1072.11 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 465 SBD OF 2015-16 (30.03.16) | [7 empty] | 1 | [7 empty] | PTEC | Tirhut East
|  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | PTEC | Tirhut East
|  |  |  | 3 | Girl Hostel | [26 empty] | 1 | [5 empty] | PTEC | Tirhut East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | PTEC | Tirhut East
20 | P-20 | MUNGER | PTEC HAWELI KHARGPUR | 1 | Institutional Building | Budha Infrastructure Private Limited, Hanuman Nagar, Kankarbagh | 1000 |  | 1060.65 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 388 SBD OF 2015-16 (03.02.16 |  |  |  |  | 1 | [10 empty] | PTEC | Munger
|  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | PTEC | Munger
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | PTEC | Munger
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Munger
21 | P-21 | SIWAN | PTEC SIWAN | 1 | Institutional Building | Durga Pratap Singh | 1000 |  | 968.55 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 410 SBD OF 2015-16 (17.02.16) | [7 empty] | 1 | [7 empty] | PTEC | Saran
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | PTEC | Saran
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | PTEC | Saran
|  |  |  | 4 | Principal Quarter | [24 empty] | 1 | X | X | X | X |  |  |  | PTEC | Saran
22 | P-22 | SAMASTIPUR | PTEC SHAHPUR PATORI | 1 | Institutional Building | Tender Process | 1000 |  | 1079.78 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [11 empty] | 1 | [12 empty] | NIT-19(2016-17) | PTEC | Darbhanga
|  |  |  | 2 | Boys Hostel | [31 empty] | NIT-19(2016-17) | PTEC | Darbhanga
|  |  |  | 3 | Girl Hostel | [31 empty] | NIT-19(2016-17) | PTEC | Darbhanga
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  |  | NIT-19(2016-17) | PTEC | Darbhanga
[5 empty] | Institutional Building | [17 empty] | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 3 | 0 | 6 | 0 | 1 | 4 | 2
[5 empty] | Boys Hostel | [17 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2 | 0 | 3 | 0 | 2 | 8 | 2
[5 empty] | Girl Hostel | [17 empty] | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 8 | 3
[5 empty] | Principal Quarter | [17 empty] | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 5 | 4

## CTE (hidden)
BSEIDC Ltd., Patna
PROGRESS REPORT OF CTE
SL NO. | Group No. | District | Name Of School | S. No. | Name Of Building | Name of Agency with Mo- | [8 empty] | L.O.A/ Date of Issue | [6 empty] | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks | Scheme | Division
[7 empty] | A/A | T/S | BOQ Amount(in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting |  | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date |  |  |  | Not Start | Lay-out | Foundation | PL | Gro |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[29 empty] | LL | RL | LL | RL | LL | RL
1 | C-1 | MUZAFFARPUR | CTE TURKI | 1 | Institutional Building | M/S Sanjay Constraction |  |  | 1102.91 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | issued | [6 empty] | 208 SBD OF 2015-16 (14.08.15) | [6 empty] | 1 | [8 empty] | CTE | Tirhut East
|  |  |  | 2 | Boys Hostel | [28 empty] | 1 |  |  |  | CTE | Tirhut East
|  |  |  | 3 | Girl Hostel | [28 empty] | 1 |  |  |  | CTE | Tirhut East
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X | 1 |  |  | CTE | Tirhut East
2 | C-2 | BHAGALPUR | CTE BHAGALPUR | 1 | Institutional Building | SAI HIGHWAY AND BUILDERS PVT. LTD. |  |  | 1068.42 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 14 SBD OF 2016-17(25.04.2016) | [5 empty] | 1 | [9 empty] | CTE | Bhagalpur
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | CTE | Bhagalpur
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | CTE | Bhagalpur
|  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | X | X |  |  |  | CTE | Bhagalpur
3 | C-3 | SAMASTIPUR | CTE SAMASTIPUR | 1 | Institutional Building | Tender Process |  |  | 1093.33 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [11 empty] | 1 | [12 empty] | NIT-19(2016-17) | CTE | Darbhanga
|  |  |  | 2 | Boys Hostel | [31 empty] | NIT-19(2016-17) | CTE | Darbhanga
|  |  |  | 3 | Girl Hostel | [31 empty] | NIT-19(2016-17) | CTE | Darbhanga
|  |  |  | 4 | Principal Quarter | [25 empty] | X | X | X | X |  |  | NIT-19(2016-17) | CTE | Darbhanga
4 | C-4 | SAHARSA | CTE SAHARSA | 1 | Institutional Building | R K CONSTRUCTION |  |  | 1117.8 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [12 empty] | 1 | [11 empty] | Not start | CTE | Koshi
|  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Koshi
|  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Koshi
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | CTE | Koshi
5 | C-5 | CHAPRA | CTE CHAPRA | 1 | Institutional Building | M/s. Krishnapali Construction Pvt. Ltd. Mobile : 94312 59756. |  |  | 1078.18 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [12 empty] | 1 | [11 empty] | Not start | CTE | Saran
|  |  |  | 2 | Boys Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Saran
|  |  |  | 3 | Girl Hostel | [19 empty] | 1 | [11 empty] | Not start | CTE | Saran
|  |  |  | 4 | Principal Quarter | [19 empty] | 1 | [5 empty] | X | X | X | X |  |  | Not start | CTE | Saran
6 | C-6 | GAYA | CTE GAYA | 1 | Institutional Building | Ramakant Singh |  |  | 1041.5 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | issued | [6 empty] | 709 SBD OF 2014-15 (23.02.15) |  |  | 1 | [11 empty] | Old Staff Quarter to be demolish | CTE | Magadh
|  |  |  | 2 | Boys Hostel | [21 empty] | 1 | [10 empty] | CTE | Magadh
|  |  |  | 3 | Girl Hostel | [26 empty] | 1 | [5 empty] | CTE | Magadh
|  |  |  | 4 | Principal Quarter | [23 empty] | 1 |  | X | X | X | X |  |  |  | CTE | Magadh

## BITE (hidden)
BSEIDC Ltd., Patna
PROGRESS REPORT OF BITE
SL NO. | Group No. | District | Name Of School | S. No. | Name Of Building | Name of Agency with Mo- | [8 empty] | L.O.A/ Date of Issue | [6 empty] | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks | Scheme | Division
[7 empty] | A/A | T/S | BOQ Amount(in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting |  | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date |  |  |  | Not Start | Lay-out | Foundation | PL | Gro |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[29 empty] | LL | RL | LL | RL | LL | RL
1 | B-1 | East Champaran | BITE Dariyapur | 1 | Institutional Building | M/S C.S CONSTRUCTION |  |  | 1105.76 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 466SBD OF 2015-16 (30.-03-2016) | [7 empty] | 1 | [7 empty] | BITE | Tirhut West
|  |  |  | 2 | Boys Hostel | [22 empty] | 1 | [9 empty] | BITE | Tirhut West
|  |  |  | 3 | Girl Hostel | [24 empty] | 1 | [7 empty] | BITE | Tirhut West
|  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | BITE | Tirhut West
2 | B-2 | West Champaran | BITE Balmikinagar | 1 | Institutional Building | C.S CONSTRACTION |  |  | 1124.7 | 2014-05-19 | 2014-07-01 | 2014-07-12 |  |  | 3139/17.04.15 | [6 empty] | 344 SBD OF 2015-16 (23-12-2015) | [9 empty] | 1 | [5 empty] | BITE | Tirhut West
|  |  |  | 2 | Boys Hostel | [26 empty] | 1 | [5 empty] | BITE | Tirhut West
|  |  |  | 3 | Girl Hostel | [22 empty] | 1 | [9 empty] | BITE | Tirhut West
|  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | BITE | Tirhut West
3 | B-3 | Katihar | BITE Musapur katihar | 1 | Institutional Building | Pankaj kumar singh |  |  | 1071.2 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 442 SBD OF 2015-16(03.03.16) | [7 empty] | 1 | [7 empty] | BITE | Purnea
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | BITE | Purnea
|  |  |  | 3 | Girl Hostel | [22 empty] | 1 | [9 empty] | BITE | Purnea
|  |  |  | 4 | Principal Quarter | [21 empty] | 1 |  |  |  | X | X | X | X |  |  |  | BITE | Purnea
4 | B-4 | Darbhanga | BITE Madhopatti | 1 | Institutional Building | Joyti Construction |  |  | 1098.43 | 2014-05-19 | 2014-07-01 | 2014-07-12 | [9 empty] | 414 SBD OF 2015-16 (20.02.16) | [9 empty] | 1 | [5 empty] | BITE | Darbhanga
|  |  |  | 2 | Boys Hostel | [24 empty] | 1 | [7 empty] | BITE | Darbhanga
|  |  |  | 3 | Girl Hostel | [26 empty] | 1 | [5 empty] | BITE | Darbhanga
|  |  |  | 4 | Principal Quarter | [22 empty] | 1 |  |  | X | X | X | X |  |  |  | BITE | Darbhanga