## Tharuhat
Progress Report for the Construction of Tharhut Project (400 Bedded School)
Name of Division : - Tirhut West
S. No. | Group No. | Name of District | Name of Block | Name of Panchayat | Name of School | Name of Agency |  | Agreement No. & Date | NIT | Time of Completion | Physical Status
[7 empty] | Contract Price ( in Lakh ) |  |  |  | Not Start | Layout | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete | Remarks
[15 empty] | LL | RL | LL | RL | LL | RL
1 | THARU-1-1 | West Champaran | Bagaha-2 | Kadmahwa | Hostel Block - I | M/S C.S. Construction, Gayatri Nagar, Motihari, East Champaran | 1316.0252 | 128 SBD of 2013-14 (08.10.13) | NIT-25 (2012-13) | 18 Month | [11 empty] | 1
| THARU-1-2 |  |  |  | Hostel Block - II | [16 empty] | 1
| THARU-1-3 |  |  |  | Hostel Block - III | [16 empty] | 1
| THARU-1-4 |  |  |  | Hostel Block - IV | [16 empty] | 1
| THARU-1-5 |  |  |  | Teacher Residence | [16 empty] | 1
| THARU-1-6 |  |  |  | Principal Residence | [16 empty] | 1
| THARU-1-7 |  |  |  | Academic Block | [16 empty] | 1
| THARU-1-8 |  |  |  | Class IV Staff Residence - I | [16 empty] | 1
| THARU-1-9 |  |  |  | Class IV Staff Residence - II | [16 empty] | 1
2 | THARU-2-1 | West Champaran | Ramnagar | Belatandi | Hostel Block - I | Cancel |  |  | NIT-25 (2012-13) & NIT-01 (2013-14) | 18 Month | 1
| THARU-2-2 |  |  |  | Hostel Block - II | [5 empty] | 1
| THARU-2-3 |  |  |  | Hostel Block - III | [5 empty] | 1
| THARU-2-4 |  |  |  | Hostel Block - IV | [5 empty] | 1
| THARU-2-5 |  |  |  | Teacher Residence | [5 empty] | 1
| THARU-2-6 |  |  |  | Principal Residence | [5 empty] | 1
| THARU-2-7 |  |  |  | Academic Block | [5 empty] | 1
| THARU-2-8 |  |  |  | Class IV Staff Residence - I | [5 empty] | 1
| THARU-2-9 |  |  |  | Class IV Staff Residence - II | [5 empty] | 1
3 | THARU-3-1 | West Champaran | Ramnagar | Madhubani | Hostel Block - I | M/S C.S. Construction, Gayatri Nagar, Motihari, East Champaran | 1319.9381 | 129 SBD of 2013-14 (08.10.13) | NIT-25 (2012-13) | 18 Month | [11 empty] | 1
| THARU-3-2 |  |  |  | Hostel Block - II | [16 empty] | 1
| THARU-3-3 |  |  |  | Hostel Block - III | [16 empty] | 1
| THARU-3-4 |  |  |  | Hostel Block - IV | [16 empty] | 1
| THARU-3-5 |  |  |  | Teacher Residence | [16 empty] | 1
| THARU-3-6 |  |  |  | Principal Residence | [16 empty] | 1
| THARU-3-7 |  |  |  | Academic Block | [16 empty] | 1
| THARU-3-8 |  |  |  | Class IV Staff Residence - I | [16 empty] | 1
| THARU-3-9 |  |  |  | Class IV Staff Residence - II | [16 empty] | 1
4 | THARU-4-1 | West Champaran | Dudhura (Mainatand) | Bhirbhiriya | Hostel Block - I | M/S S.S. Construction, East Champaran | 1348.8697 | 166 SBD of 2013-14 (28.11.13) | NIT-25 (2012-13) & NIT-01 (2013-14) | 18 Month | [11 empty] | 1
| THARU-4-2 |  |  |  | Hostel Block - II | [16 empty] | 1
| THARU-4-3 |  |  |  | Hostel Block - III | [16 empty] | 1
| THARU-4-4 |  |  |  | Hostel Block - IV | [16 empty] | 1
| THARU-4-5 |  |  |  | Teacher Residence | [16 empty] | 1
| THARU-4-6 |  |  |  | Principal Residence | [16 empty] | 1
| THARU-4-7 |  |  |  | Academic Block | [16 empty] | 1
| THARU-4-8 |  |  |  | Class IV Staff Residence - I | [16 empty] | 1
| THARU-4-9 |  |  |  | Class IV Staff Residence - II | [16 empty] | 1
5 | THARU-5-1 | West Champaran | Gaunaha | Belsandi | Hostel Block - I | M/S C.S. Construction, Gayatri Nagar, Motihari, East Champaran | 1322.5547 | 80 SBD of 2013-14 (20.08.13) | NIT-25 (2012-13) | 18 Month | [11 empty] | 1
| THARU-5-2 |  |  |  | Hostel Block - II | [16 empty] | 1
| THARU-5-3 |  |  |  | Hostel Block - III | [16 empty] | 1
| THARU-5-4 |  |  |  | Hostel Block - IV | [16 empty] | 1
| THARU-5-5 |  |  |  | Teacher Residence | [16 empty] | 1
| THARU-5-6 |  |  |  | Principal Residence | [16 empty] | 1
| THARU-5-7 |  |  |  | Academic Block | [16 empty] | 1
| THARU-5-8 |  |  |  | Class IV Staff Residence - I | [16 empty] | 1
| THARU-5-9 |  |  |  | Class IV Staff Residence - II | [16 empty] | 1
6 | THARU-6-1 | West Champaran | Gaunaha | Dhamaura | Hostel Block - I | M/S C.S. Construction, Gayatri Nagar, Motihari, East Champaran |  |  | NIT-25 (2012-13) & NIT-01 (2013-14) | 18 Month | [10 empty] | 1
| THARU-6-2 |  |  |  | Hostel Block - II | [15 empty] | 1
| THARU-6-3 |  |  |  | Hostel Block - III | [15 empty] | 1
| THARU-6-4 |  |  |  | Hostel Block - IV | [15 empty] | 1
| THARU-6-5 |  |  |  | Teacher Residence | [15 empty] | 1
| THARU-6-6 |  |  |  | Principal Residence | [15 empty] | 1
| THARU-6-7 |  |  |  | Academic Block | [15 empty] | 1
| THARU-6-8 |  |  |  | Class IV Staff Residence - I | [15 empty] | 1
| THARU-6-9 |  |  |  | Class IV Staff Residence - II | [15 empty] | 1
Summary of Physical Status
[5 empty] | Name of School Buildings |  |  | Name of Schools Buidlings |  |  | Not started | Layout | Foundation | Plinth | GF-LL | GF-RL | FF-LL | FF-RL | SF-LL | SF-RL | Finishing | Completed
[5 empty] | Hostel Block - I |  |  | Hostel Block - I |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Hostel Block - II |  |  | Hostel Block - II |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Hostel Block - III |  |  | Hostel Block - III |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Hostel Block - IV |  |  | Hostel Block - IV |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Teacher Residence |  |  | Teacher Residence |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Principal Residence |  |  | Principal Residence |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Academic Block |  |  | Academic Block |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Class IV Staff Residence - I |  |  | Class IV Staff Residence - I |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[5 empty] | Class IV Staff Residence - II |  |  | Class IV Staff Residence - II |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
[8 empty] | Grand Total |  |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 36