## USSS (2013-14)
BSEIDC Ltd., Patna
Physical Status of USSS (2013-14)
S.N. | Group No. | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Retender | Tender Process | Physical Status | [10 empty] | Session
[10 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USSS-123-1 | Magadh | x;k | Gurua | 1 | Middle School, Mahadev Sthan | SANJAY KUMAR SINGH, 9973456006 | [11 empty] | 1 |  | 2013-14
2 | USSS-130-1 | Magadh | tgkukckn | Hulasganj | 1 | Middle School, Gangapur | M/S A K CHOUDHARY, 9470166345 | [10 empty] | 1 |  | Few Parts of Electric & PHE. Works Remaining | 2013-14
3 | USSS-162 (A) | Magadh | uoknk | Kawakol | 1 | UPS Rupai | SHRI CHANDRA MOULESHWAR, 9931911023 | [11 empty] | 1 |  | 2013-14
4 | USSS-162 (B) | Magadh | uoknk | Kawakol | 1 | UPS Lohgarwa | ASHIS RANJAN, 9931215326 | [11 empty] | 1 |  | 2013-14
5 | USSS-163 (A) | Magadh | uoknk | Sirdala | 1 | UPS Hemja Bhart | MD RAIS KHAN, 9973622799 | [11 empty] | 1 |  | 2013-14
6 | USSS-163 (B) | Magadh | uoknk | Sirdala | 1 | M.S., Kharsari | SURENDRA KUMAR, 9934447377 |  |  | 1 | [9 empty] | Land not available | 2013-14
7 | USSS-163 (C ) | Magadh | uoknk | Sirdala | 1 | UPS Mahuliya Tanr | RAVI JALAN, 9546109122 |  |  | 1 | [9 empty] | Not Start | 2013-14
8 | USSS-106 (A) | Bhagalpur | ckadk |  | 1 | U.M.S Kerwar | Marcominfra Pvt. Ltd., 9934361315 | [11 empty] | 1 |  | 2013-14
9 | USSS-106 (B) | Bhagalpur | ckadk |  | 1 | U.M.S Burhawa Bathan | Marcominfra Pvt Ltd., 9934361315 | [8 empty] | 1 |  |  |  |  | 2013-14
10 | USSS-106 (C) | Bhagalpur | ckadk |  | 1 | U.M.S Upar Chak Marhdiya | Marcominfra Pvt. Ltd.,9934361315 | [11 empty] | 1 |  | 2013-14
11 | USSS-106 (D) | Bhagalpur | ckadk |  | 1 | M.S Jamdaha | Marcominfra Pvt. Ltd., 9934361315 | [11 empty] | 1 |  | 2013-14
12 | USSS-106 (E) | Bhagalpur | ckadk |  | 1 | M.S Mochanma | Marcominfra Pvt. Ltd., 9934361315 | [11 empty] | 1 |  | 2013-14
13 | USSS-106 (F) | Bhagalpur | ckadk |  | 1 | U.M.S Lila waran | BINOD KUMAR SINGH, 9471749892 | [11 empty] | 1 |  | 2013-14
14 | USSS-106 (G) | Bhagalpur | ckadk |  | 1 | U.M.S Dhevermoh | Bricks Liner Infrastructure Pvt | [10 empty] | 1 |  |  | 2013-14
15 | USSS-107-1 | Bhagalpur | ckadk |  | 1 | M.S Bhavan Kormama | Nimbark engineering pvt. Ltd. | [10 empty] | 1 |  |  | 2013-14
16 | USSS-108 (A) | Bhagalpur | ckadk |  | 1 | M.S Madari | Binod Kumar Singh | [11 empty] | 1 |  | 2013-14
17 | USSS-108 (B) | Bhagalpur | ckadk |  | 1 | U.M.S Phaga | NIWESH KUMAR, 9576272505 | [11 empty] | 1 |  | 2013-14
18 | USSS-109-1 | Bhagalpur | ckadk | Chandan | 1 | U.M.S Koriya | BINOD KUMAR SINGH, 9471749892 | [11 empty] | 1 | Handover | 2013-14
19 | USSS-109-2 | Bhagalpur | ckadk | Chandan | 2 | M.S. Kendwar | BINOD KUMAR SINGH, 9471749892 | [11 empty] | 1 |  | 2013-14
20 | USSS-110-1 | Bhagalpur | ckadk |  | 1 | U.M.S Amjora | Anand Kumar, S. K. Nagar, Patna | [9 empty] | 1 |  |  |  | 2013-14
21 | USSS-111-1 | Bhagalpur | ckadk |  | 1 | U.M.S Hasiya | KUNDAN KUMAR SINGH | [10 empty] | 1 |  |  | 2013-14
22 | USSS-112 (A) | Bhagalpur | ckadk |  | 1 | M.S Darshniya | Binod Kumar Singh | [11 empty] | 1 |  | 2013-14
23 | USSS-112 (B) | Bhagalpur | ckadk |  | 1 | U.M.S, Bounka | Binod Kumar Singh | [11 empty] | 1 |  | 2013-14
24 | USSS-112 (C) | Bhagalpur | ckadk |  | 1 | U.M.S Chariya | Binod Kumar Singh |  |  | 1 | [9 empty] | Land Problem | 2013-14
25 | USSS-113-1 | Bhagalpur | Hkkxyiqj |  | 1 | U.M.S Asiachak | Rajendra Kumar | [7 empty] | 1 | [5 empty] | 2013-14
26 | USSS -124 (A) | Munger | Munger | Khaira | 1 | M S Bujhayat | ASHOK AND CO NIVAS PVT LTD, 9006613016 | [10 empty] | 1 |  |  | 2013-14
27 | USSS -124 (B) | Munger | Munger | Khaira | 1 | M.S Ghari Bishanpur | ASHOK AND CO NIVAS PVT LTD, 9006613016 | [10 empty] | 1 |  |  | 2013-14
28 | USSS -124 (C) | Munger | Munger | Khaira | 1 | M S Ghari | MAHNAR INFRATECH PVT LTD | [8 empty] | 1 |  |  |  |  | 2013-14
29 | USSS-125 (A) | Munger | Munger | Chakai | 1 | M S Saron | SUDHIR KUMAR,9973392397 | [11 empty] | 1 |  | 2013-14
30 | USSS-125 (B) | Munger | Munger | Chakai | 1 | M S Kiyajori | SUDHIR KUMAR,9973392397 | [11 empty] | 1 |  | 2013-14
31 | USSS-125 (C) | Munger | Munger | Chakai | 1 | M S Bamdah | AGRAGAMI INDIA CONSTRUCTION PRIVATE LIMITED, 9939029899 | [10 empty] | 1 |  |  | 2013-14
32 | USSS-125 (D) | Munger | Munger | Chakai | 1 | M S Kewal | AMIT KUMAR | [10 empty] | 1 |  |  | 2013-14
33 | USSS-126 (A) | Munger | tewbZ |  | 1 | URaktrohaniya | RAJENDRA KUMAR, 9939195777 | [10 empty] | 1 |  |  | 2013-14
34 | USSS-126 (B) | Munger | tewbZ |  | 1 | M S Sarebad | Ashish Ranjan | [11 empty] | 1 |  | 2013-14
35 | USSS-126 (C) | Munger | tewbZ |  | 1 | M S Agahra | Ashish Ranjan | [10 empty] | 1 |  |  | 2013-14
36 | USSS-126 (D) | Munger | tewbZ |  | 1 | M.S Charkapathar | Ashish Ranjan | [10 empty] | 1 |  | S.F.R.L.(G+2) | 2013-14
37 | USSS-127 (A) | Munger | teqbZ |  | 1 | M .S. Sewa | Ashok and Co Nivas | [10 empty] | 1 |  |  | 2013-14
38 | USSS-127 (B) | Munger | teqbZ |  | 1 | M,S,KEWAL | ASHOK AND CO NIVAS PVT LTD,9006613016 | [10 empty] | 1 |  |  | 2013-14
39 | USSS-128-1 | Munger | teqbZ |  | 1 | M S Borwa | RAJENDRA KUMAR9939195777, | [10 empty] | 1 |  | DIST AREA WORK STOPPED | 2013-14
40 | USSS-128-2 | Munger | teqbZ |  | 2 | U M S Chapa | RAJENDRA KUMAR9939195777, | [10 empty] | 1 |  |  | 2013-14
41 | USSS-129 (A) | Munger | teqbZ |  | 1 | U M S Hathiyawar Taljhari | ASHOK KUMAR SINGH, 8969398786 | [10 empty] | 1 |  |  | 2013-14
42 | USSS-129 (B) | Munger | teqbZ |  | 1 | U M S Taliyadih | MANGLAM CONSTRUCTION, 7631507878 | [10 empty] | 1 |  |  | 2013-14
43 | USSS-129 (C) | Munger | teqbZ |  | 1 | U M S Bela | MUKESH KUMAR, 9973462715 | [10 empty] | 1 |  |  | 2013-14
44 | USSS-129 (D) | Munger | teqbZ |  | 1 | U M S Karra | Sunil Kumar, (Bricks Liner Infrastructure Pvt) | [10 empty] | 1 |  |  | 2013-14
45 | USSS-151-1 | Munger | y[khljk; |  | 1 | U M S Singhaul Tetariaya | VIJAY KUMAR |  |  | 1 | [9 empty] | Land not available | 2013-14
46 | USSS-143-1 | Munger | [kxM+h;k |  | 1 | MS Icharua | Lal Babu Prasad | [10 empty] | 1 |  |  | 2013-14
47 | USSS-152-1 | Kosi | e/ksiqjk |  | 1 | M.S Sonbarsha | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775, 9472103786 | [10 empty] | 1 |  |  | 2013-14
48 | USSS-153-1 | Kosi | e/ksiqjk |  | 1 | M.S. Rahi | Retender | [8 empty] | 1 |  |  |  |  | 2013-14
49 | USSS-154-1 | Kosi | e/ksiqjk |  | 1 | M.S Bhelva | SUNITA DEVI, 9162524068 | [9 empty] | 1 |  |  |  | 2013-14
50 | USSS-154-2 | Kosi | e/ksiqjk |  | 2 | M.S.Gadhiya | SUNITA DEVI, 9162524068 | [5 empty] | 1 | [7 empty] | 2013-14
51 | USSS-155-1 | Kosi | e/ksiqjk |  | 1 | M.S.Uda | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 | [11 empty] | 1 | Handover | 2013-14
52 | USSS-195-1 | Kosi | lgjlk |  | 1 | MS Partaha Barhara | Sarveshwar Kumar Ojha, Gopalganj |  |  | 1 | [9 empty] | Not Start | 2013-14
53 | USSS-196-1 | Kosi | lgjlk |  | 1 | MS Dhanupra | JEEVAN JYOTI CONTRACTORS PVT LTD,9431247387 | [8 empty] | 1 |  |  |  |  | 2013-14
54 | USSS-197-1 | Kosi | lgjlk |  | 1 | MS Samhar | JEEVAN JYOTI CONTRACTORS PVT LTD,9431247387 | [7 empty] | 1 | [5 empty] | 2013-14
55 | USSS-204-1 | Kosi | lqikSy |  | 1 | MS Parmanandpur | Madan Kumar singh |  |  |  | 1 | [9 empty] | 2013-14
56 | USSS-204-2 | Kosi | lqikSy |  | 2 | MS Bhawani pur | AKASH KUMAR,9334362048 |  |  | 1 | [9 empty] | Not Start | 2013-14
57 | USSS-205-1 | Kosi | lqikSy |  | 1 | MS Bhimpur | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 |  |  | 1 | [9 empty] | Land not Available | 2013-14
58 | USSS-206(A) | Kosi | lqikSy |  | 1 | MS sisauni | AKASH KUMAR,9334362048 | [7 empty] | 1 | [5 empty] | 2013-14
59 | USSS-206(B) | Kosi | lqikSy |  | 1 | MS sukhashan | PRIYA RANJAN,9931546525 | [9 empty] | 1 |  |  | Kota Work in progress | 2013-14
60 | USSS-207(A) | Kosi | lqikSy |  | 1 | MS saroja Bela | Tender Process |  | 1 | [10 empty] | No Bidder | 2013-14
61 | USSS-207(B) | Kosi | lqikSy |  | 1 | MS rasuaar | TRISHUL CONSTRUCTIONS,8252940655 | [10 empty] | 1 |  |  | 2013-14
62 | USSS-207(C) | Kosi | lqikSy |  | 1 | MS Hari | Adarsh Construction | [9 empty] | 1 |  |  |  | 2013-14
63 | USSS-208-1 | Kosi | lqikSy |  | 1 | MS Bela sringarmoti | YOGENDRA PRASAD YADAV, 9631856613 |  |  | 1 | [9 empty] | Cancelled | 2013-14
64 | USSS-209-1 | Kosi | lqikSy |  | 1 | MS Lalganj | VATSALYA BUILDCON PRIVATE LIMITED, 9430965119 |  |  | 1 | [9 empty] | Cancelled | 2013-14
65 | USSS-210-1 | Kosi | lqikSy |  | 1 | MS Basbitti | Ashok Kumar, 9431091558 |  |  | 1 | [9 empty] | Cancelled | 2013-14
66 | USSS-210-2 | Kosi | lqikSy |  | 2 | MS kaliganj | Ashok Kumar, 9431091558 | [10 empty] | 1 |  |  | 2013-14
67 | USSS-211(A) | Kosi | lqikSy |  | 1 | Durga MS Laharnia | PRIYA RANJAN, 9931546525 |  |  | 1 | [9 empty] | Cancelled | 2013-14
68 | USSS-211(B) | Kosi | lqikSy |  | 1 | MS Parsa Garhi | Madan Kumar singh | [11 empty] | 1 | Handover | 2013-14
69 | USSS-211(C) | Kosi | lqikSy |  | 1 | MS Mogla Ghat nandana | AKASH KUMAR, 9334362048 | [7 empty] | 1 | [5 empty] | 2013-14
70 | USSS-101-1 | Purnea | vjfj;k |  | 1 | A.M.S. Kala Balua | PRAKASH KUMAR SAH,9162909186 | [11 empty] | 1 | Handover | 2013-14
71 | USSS-102-1 | Purnea | vjfj;k |  | 1 | M.S. Barmasiya | MD. Iftakhar Alam | [7 empty] | 1 | [5 empty] | 2013-14
72 | USSS-103-1 | Purnea | vjfj;k |  | 1 | U.M.S. Sonamani Godam | PRAKRITI CONTRACTORS PVT LTD,9431440749 | [10 empty] | 1 |  |  | 2013-14
73 | USSS-104-1 | Purnea | vjfj;k |  | 1 | U.M.S. Subhankarpur | ASHA CONSTRUCTION,9431412711 | [11 empty] | 1 |  | 2013-14
74 | USSS-105(A) | Purnea | vjfj;k |  | 1 | M.S. Basmatiya | AKHILESH SINGH,9470048339 | [11 empty] | 1 | Handover | 2013-14
75 | USSS-105(B) | Purnea | vjfj;k |  | 1 | M.S. Khaira | MD ARFIN,9006212706 | [11 empty] | 1 |  | 2013-14
76 | USSS-105(C) | Purnea | vjfj;k |  | 1 | M.S. Maheshpatti | RABINDRA SINGH,9472524322 | [11 empty] | 1 | Handover | 2013-14
77 | USSS-105(D) | Purnea | vjfj;k |  | 1 | M.S. Tamganj | SHAILENDRA KUMAR,9334855523 | [10 empty] | 1 |  |  | 2013-14
78 | USSS-131-1 | Purnea | dVhgkj |  | 1 | M.S. Bathilli | Cancel | 1 | [11 empty] | Double scheme | 2013-14
79 | USSS-132-1 | Purnea | dVhgkj |  | 1 | M.S. Dwasay | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
80 | USSS-132-2 | Purnea | dVhgkj |  | 2 | R M.S. Souriya | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  | 2013-14
81 | USSS-133-1 | Purnea | dVhgkj |  | 1 | M.S. Padam Pur | PRAKASH KUMAR SAH,9162909186 | [11 empty] | 1 | Handover | 2013-14
82 | USSS-134-1 | Purnea | dVhgkj |  | 1 | M.S. Makai Pur | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
83 | USSS-134-2 | Purnea | dVhgkj |  | 2 | M.S. Kheria | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
84 | USSS-134-3 | Purnea | dVhgkj |  | 3 | M.S. Pawai | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
85 | USSS-134-4 | Purnea | dVhgkj |  | 4 | M.S. Rautara | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
86 | USSS-134-5 | Purnea | dVhgkj |  | 5 | M.S. Dighree | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
87 | USSS-134-6 | Purnea | dVhgkj |  | 6 | M.S. Chandwa Rupaspur | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
88 | USSS-135-1 | Purnea | dVhgkj |  | 1 | M.S. Kathria | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Double scheme | 2013-14
89 | USSS-136-1 | Purnea | dVhgkj |  | 1 | M.S. Nawabganj | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
90 | USSS-136-2 | Purnea | dVhgkj |  | 2 | M.S. Chakla Khaira | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
91 | USSS-137-1 | Purnea | dVhgkj |  | 1 | M.S. Bharsia | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Double scheme | 2013-14
92 | USSS-137-2 | Purnea | dVhgkj |  | 2 | M.S. Mohammad Nagar Rajdhani | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
93 | USSS-137-3 | Purnea | dVhgkj |  | 3 | M.S. Dermahi | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2013-14
94 | USSS-137-4 | Purnea | dVhgkj |  | 4 | U M.S. Musapur Ranga Kol | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
95 | USSS-137-5 | Purnea | dVhgkj |  | 5 | U M.S. Tapua Gobindpur | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
96 | USSS-138(A) | Purnea | dVhgkj |  | 1 | U M.S. Hajiyaar Palsa | MS EXCELLENT CONSTRUCTION, 9472021967 | [11 empty] | 1 | Handover | 2013-14
97 | USSS-138(B) | Purnea | dVhgkj |  | 1 | U M.S. Chilha Para | MS EXCELLENT CONSTRUCTION, 9472021967 | [11 empty] | 1 |  | 2013-14
98 | USSS-139-1 | Purnea | dVhgkj |  | 1 | M.S. Parbheli | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 | [11 empty] | 1 | Handover | 2013-14
99 | USSS-140(A) | Purnea | dVhgkj |  | 1 | M.S. Mukuria Dakshin Tola | RANA BIRESH PRATAP SINGH, 9430683578 | [10 empty] | 1 |  |  | 2013-14
100 | USSS-140(B) | Purnea | dVhgkj |  | 1 | M.S. Sikitia | MS EXCELLENT CONSTRUCTION, 9472021967 |  |  | 1 | [9 empty] | Double scheme | 2013-14
101 | USSS-141-1 | Purnea | dVhgkj |  | 1 | M.S. Budhanagar | Tender Process |  |  | 1 | [9 empty] | Double scheme | 2013-14
102 | USSS-142-1 | Purnea | dVhgkj |  | 1 | M.S. Kanta Kosh | PRAKASH KUMAR SAH,9162909186 | [11 empty] | 1 | Handover | 2013-14
103 | USSS-144-1 | Purnea | fd'kuxat |  | 1 | UMS Teusa | ASHOK KUMAR SINGH,9430467620 | [11 empty] | 1 |  | 2013-14
104 | USSS-145-1 | Purnea | fd'kuxat |  | 1 | M.S Farabari | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | land not available | 2013-14
105 | USSS-145-2 | Purnea | fd'kuxat |  | 2 | M.S Kuwari | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  | 1 | [8 empty] | work stopped by contractor (during excavation) since long time, letter issued | 2013-14
106 | USSS-146-1 | Purnea | fd'kuxat |  | 1 | M.S Gilhabari Kanya | BIRENDRA KUMAR SINGH, 9473440405 | [6 empty] | 1 | [6 empty] | 2013-14
107 | USSS-146-2 | Purnea | fd'kuxat |  | 2 | M.S Shitalpur | BIRENDRA KUMAR SINGH, 9473440405 | [5 empty] | 1 | [6 empty] | work stopped by contractor since long time, letter issued | 2013-14
108 | USSS-146-3 | Purnea | fd'kuxat |  | 3 | U. M.S Kusiyari | BIRENDRA KUMAR SINGH, 9473440405 | [5 empty] | 1 | [6 empty] | work stopped by contractor since long time, letter issued | 2013-14
109 | USSS-146-4 | Purnea | fd'kuxat |  | 4 | U.M,S Nawnadi | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Old building to be demolished | 2013-14
110 | USSS-147-1 | Purnea | fd'kuxat |  | 1 | M.S Bourigacch | BIRENDRA KUMAR SINGH, 9473440405 | [5 empty] | 1 | [7 empty] | 2013-14
111 | USSS-147-2 | Purnea | fd'kuxat |  | 2 | M.S Ruidhasa | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Land made available for small drawing, | 2013-14
112 | USSS-147-3 | Purnea | fd'kuxat |  | 3 | M.S Barchondi | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2013-14
113 | USSS-148-1 | Purnea | fd'kuxat |  | 1 | M.S Talgacch | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  | 2013-14
114 | USSS-148-2 | Purnea | fd'kuxat |  | 2 | M.S. Gandharvdanga | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | insufficeint land, small drawing work in progress | 2013-14
115 | USSS-148-3 | Purnea | fd'kuxat |  | 3 | U.M.S Talwarbandha | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 |  |  |  |  | work stopped by contractor since long time, letter issued | 2013-14
116 | USSS-149-1 | Purnea | fd'kuxat |  | 1 | U.M.S Masangoan | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  | 2013-14
117 | USSS-149-2 | Purnea | fd'kuxat |  | 2 | M.S Shameswar | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2013-14
118 | USSS-149-3 | Purnea | fd'kuxat |  | 3 | M.S Natuapara | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Land Dispute | 2013-14
119 | USSS-149-4 | Purnea | fd'kuxat |  | 4 | M.S Khodaganj | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2013-14
120 | USSS-149-5 | Purnea | fd'kuxat |  | 5 | U.M.S Gopalpur Haat | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2013-14
121 | USSS-150-1 | Purnea | fd'kuxat |  | 1 | U.M.S Kochgarh Purndha | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2013-14
122 | USSS-184 (A) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Routi Basha | Retender | 1 | [11 empty] | Retender | 2013-14
123 | USSS-184 (B) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Talbari | Binod Yadav | [7 empty] | 1 | [5 empty] | 2013-14
124 | USSS-185-1 | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Sirsi | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 |  |  | 1 | [9 empty] | old building to be demolished | 2013-14
125 | USSS-186-1 | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Amirganj | Retender | 1 | [11 empty] | Retender | 2013-14
126 | USSS-187-1 | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Laxmipur | VATSALYA BUILDCON PRIVATE LIMITED, 9430965119 | [11 empty] | 1 | Handover | 2013-14
127 | USSS-188 (A) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Sauraha | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | [7 empty] | 1 | [5 empty] | 2013-14
128 | USSS-188 (B) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Pranpatti | HARIMOHAN BISHWAS,9955713757 | [7 empty] | 1 | [5 empty] | 2013-14
129 | USSS-188 (C) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Kajha | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | [5 empty] | 1 | [7 empty] | 2013-14
130 | USSS-189 (A) | Purnea | iwf.kZ;k¡ |  | 1 | M.S.Chandpur Bhanha | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED,9973239801 | [10 empty] | 1 |  |  | 2013-14
131 | USSS-189 (B) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Harimurhi | CS CONSTRUCTION | [11 empty] | 1 |  | 2013-14
132 | USSS-190 (A) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Dumri | CS CONSTRUCTION | [11 empty] | 1 |  | 2013-14
133 | USSS-190 (B) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Goriar | ADITYA KUMAR SINGH,9546045749 | [11 empty] | 1 |  | 2013-14
134 | USSS-191-1 | Purnea | iwf.kZ;k¡ |  | 1 | M.S.Bishanpur | MD JAVIR, 9955418718 |  |  | 1 | [9 empty] | land not registered in the name of school. | 2013-14
135 | USSS-192 (A) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Sanjha Ghat | MD MOJAMMIL HUSSAIN,9939824905 | [10 empty] | 1 |  |  | 2013-14
136 | USSS-192 (B) | Purnea | iwf.kZ;k¡ |  | 1 | M.S.Champawati | MD MOJAMMIL HUSSAIN, 9939824905 | [6 empty] | 1 | [6 empty] | 2013-14
137 | USSS-193-1 | Purnea | iwf.kZ;k¡ |  | 1 | I. M. S. Garhi Baluwa | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [10 empty] | 1 |  |  | 2013-14
138 | USSS-194 (A) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Kodheli | KUMAR CHAMAN | [10 empty] | 1 |  |  | 2013-14
139 | USSS-194 (B) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Belgchhi | HARIMOHAN BISHWAS, 9955713757 | [10 empty] | 1 |  |  | 2013-14
140 | USSS-194 (C) | Purnea | iwf.kZ;k¡ |  | 1 | M.S. Babhni | HARIMOHAN BISHWAS, 9955713757 | [9 empty] | 1 |  |  |  | 2013-14
141 | USSS-200-1 | Tirhut East | lhrke<+h |  | 1 | M.S.Bishanpur | AMRESH KUMAR, 9525120333 | [11 empty] | 1 | Handover | 2013-14
142 | USSS-201-1 | Tirhut East | lhrke<+h |  | 1 | M.S. Indarwa-1 | RANJEETPUR CONSTRUCTIONS PRIVATE LIMITED, 9334329734 | [11 empty] | 1 |  | 2013-14
143 | USSS-202(A) | Tirhut East | lhrke<+h |  | 1 | M.S.Mahuawa | Sanjeev Sharma | [10 empty] | 1 |  | plaster complete,. kota flooring progress | 2013-14
144 | USSS-202(B) | Tirhut East | lhrke<+h |  | 1 | M.S.Ghaghara Bazar | MANOJ KUMAR AZAD,9431636894 | [10 empty] | 1 |  | Internal Plaster Just Started | 2013-14
145 | USSS-203(A) | Tirhut East | lhrke<+h |  | 1 | M.S.Banaul | AMRESH KUMAR,9525120333 | [11 empty] | 1 |  | 2013-14
146 | USSS-203(B) | Tirhut East | lhrke<+h |  | 1 | M.S.Mahisautha | AKHILESH KUMAR CHAUDHARI, 9431415700 | [11 empty] | 1 |  | 2013-14
147 | USSS-212-1 | Tirhut East | oS'kkyh |  | 1 | Gov.M.S.Baksama | RANA CONSTRUCTION, 9334104328 |  |  | 1 | [9 empty] | Land Dispute | 2013-14
148 | USSS-213-1 | Tirhut East | oS'kkyh |  | 1 | MS Ajijpur Chande | VIPIN KUMAR SAHNI | [7 empty] | 1 | [5 empty] | 2013-14
149 | USSS-164(A) | Tirhut West | if'pe pEikj.k | Chanpatia | 1 | UMS Laukaria | MADHU ANAND CONSTRUCTION PVT LTD, 9006671588 | [11 empty] | 1 |  | 2013-14
150 | USSS-164(B) | Tirhut West | if'pe pEikj.k | Chanpatia | 1 | MS Barharawa | Sanjay Kumar Jha | [9 empty] | 1 |  |  |  | 2013-14
151 | USSS-165-1 | Tirhut West | if'pe pEikj.k |  | 1 | UMS Kaulapur Bazar | MADHU ANAND CONSTRUCTION PVT LTD, 9006671588 | [11 empty] | 1 |  | 2013-14
152 | USSS-166-1 | Tirhut West | if'pe pEikj.k |  | 1 | MS Ojhwalia | IRFAN AKHTAR, 9162628011 | [11 empty] | 1 |  | 2013-14
153 | USSS-167-1 | Tirhut West | if'pe pEikj.k |  | 1 | MS Birawa | SHAKAL DEO MISHRA, 9006385958 | [10 empty] | 1 |  |  | 2013-14
154 | USSS-168-1 | Tirhut West | if'pe pEikj.k |  | 1 | UMS Bathuwaria | SHARDA CHANDEL CONTRACT PVT, 8986283451 | [10 empty] | 1 |  |  | 2013-14
155 | USSS-169-1 | Tirhut West | if'pe pEikj.k |  | 1 | MS Gonauli | AWADHESH SHUKLA, 9431203836 | [11 empty] | 1 | Handover | 2013-14
156 | USSS-169-2 | Tirhut West | if'pe pEikj.k |  | 2 | UMS Jawaharpur | AWADHESH SHUKLA, 9431203836 | [11 empty] | 1 | Handover | 2013-14
157 | USSS-170-1 | Tirhut West | if'pe pEikj.k |  | 1 | UMS Ghagwa Rupahi | SHARDA CHANDEL CONTRACT PVT, 8986283451 | [11 empty] | 1 |  | 2013-14
158 | USSS-171-1 | Tirhut West | if'pe pEikj.k |  | 1 | UMS Madhubani | SHARDA CHANDEL CONTRACT PVT,8986283451 | [11 empty] | 1 |  | 2013-14
159 | USSS-172-1 | Tirhut West | if'pe pEikj.k |  | 1 | UMS Sugha Bhawanipur | MS SARASWATI COMPANY, 9431491241 |  |  | 1 | [9 empty] | Not Start | 2013-14
160 | USSS-173-1 | Tirhut West | if'pe pEikj.k |  | 1 | UMS Pipra Colony | MS C S CONSTRUCTION, | [10 empty] | 1 |  |  | 2013-14
161 | USSS-173-2 | Tirhut West | if'pe pEikj.k |  | 2 | MS Semri Dumari | MS C S CONSTRUCTION, | [10 empty] | 1 |  |  | 2013-14
162 | USSS-173-3 | Tirhut West | if'pe pEikj.k |  | 3 | UMS Turkaulia | MS C S CONSTRUCTION, | [10 empty] | 1 |  |  | 2013-14
163 | USSS-174(A) | Tirhut West | if'pe pEikj.k |  | 1 | UMS Sujnahi Ghorahawa | DHANANJAY KUMAR PANDEY, 9955002717 | [11 empty] | 1 |  | 2013-14
164 | USSS-174(B) | Tirhut West | if'pe pEikj.k |  | 2 | UMS Parsauni | SHAKAL DEO MISHRA, 9006385958 | [10 empty] | 1 |  |  | 2013-14
165 | USSS-175-1 | Tirhut West | iwohZ pEikj.k |  | 1 | UMS Pokhariya | RADHIKA CONSTRUCTION CO7739855654, | [11 empty] | 1 |  | 2013-14
166 | USSS-176-1 | Tirhut West | iwohZ pEikj.k |  | 1 | GMS Ajgarwa | DESHBANDHU KUMAR SINGH, 7739855654 | [10 empty] | 1 |  |  | 2013-14
167 | USSS-177-1 | Tirhut West | iwohZ pEikj.k |  | 1 | GMS Bankatwa (Boys) | MS C S CONSTRUCTION, | [9 empty] | 1 |  |  |  | 2013-14
168 | USSS-177-2 | Tirhut West | iwohZ pEikj.k |  | 2 | GMS Inarwa Phulwar | MS C S CONSTRUCTION, | [10 empty] | 1 |  |  | 2013-14
169 | USSS-178-1 | Tirhut West | iwohZ pEikj.k |  | 1 | UMS Dharharwa | ANANTA CONSTRUCTION COMPANY, 7739855654 | [9 empty] | 1 |  |  |  | 2013-14
170 | USSS-179-1 | Tirhut West | iwohZ pEikj.k |  | 1 | GMS Tonwa | RADHIKA CONSTRUCTION CO7739855654, | [11 empty] | 1 |  | 2013-14
171 | USSS-180-1 | Tirhut West | iwohZ pEikj.k |  | 1 | GMS Murarpur | RAJNISH KUMAR SINGH | [10 empty] | 1 |  |  | 2013-14
172 | USSS-180-2 | Tirhut West | iwohZ pEikj.k |  | 2 | GMS Bhada | RAJNISH KUMAR SINGH | [11 empty] | 1 |  | 2013-14
173 | USSS-181-1 | Tirhut West | iwohZ pEikj.k |  | 1 | UMS Dhekaha Math | Tender Process |  | 1 | [10 empty] | Cancel | 2013-14
174 | USSS-182-1 | Tirhut West | iwohZ pEikj.k |  | 1 | GMS Majhar | VIKASH KUMAR GUPTA, 8084876850 | [9 empty] | 1 |  |  |  | 2013-14
175 | USSS-183-1 | Tirhut West | iwohZ pEikj.k |  | 1 | GMS Narha Panapur | DINESH GUPTA, | [11 empty] | 1 |  | 2013-14
176 | USSS-199-1 | Tirhut West | f'kogj |  | 1 | M/S Shyampur | DIBYESHWAR PRASAD | [7 empty] | 1 | [5 empty] | 2013-14
177 | USSS-114-1 | Darbhanga | njHkaxk |  | 1 | U.M.S. Kaji Bahera | SANJAY KUMAR | [11 empty] | 1 |  | 2013-14
178 | USSS-114-2 | Darbhanga | njHkaxk |  | 2 | M.S. Basant | SANJAY KUMAR | [11 empty] | 1 |  | 2013-14
179 | USSS-115-1 | Darbhanga | njHkaxk |  | 1 | M.S. Ghosrama | Avinash kumar | [10 empty] | 1 |  |  | 2013-14
180 | USSS-116 (A) | Darbhanga | njHkaxk |  | 1 | M.S. Basatpur | Madhav Construction, Darbhanga | [10 empty] | 1 |  |  | 2013-14
181 | USSS-116 (B) | Darbhanga | njHkaxk |  | 1 | M.S. Dagarsam | Sanjay Kumar | [10 empty] | 1 |  |  | 2013-14
182 | USSS-117-1 | Darbhanga | njHkaxk |  | 1 | M.S. Kankpur | City creation | [10 empty] | 1 |  |  | 2013-14
183 | USSS-118-1 | Darbhanga | njHkaxk |  | 1 | U.M.S. Ganaun | City creation | [7 empty] | 1 | [5 empty] | 2013-14
184 | USSS-119(A) | Darbhanga | njHkaxk |  | 1 | M.S. Kahuaa | S K CONSTRUCTION AND COMPANY, 9471006199 | [7 empty] | 1 | [5 empty] | 2013-14
185 | USSS-119(B) | Darbhanga | njHkaxk |  | 1 | M.S. Tarbara Ganaura | S K CONSTRUCTION AND COMPANY, 9471006199 | [8 empty] | 1 |  |  |  |  | 2013-14
186 | USSS-120-1 | Darbhanga | njHkaxk |  | 1 | U.M.S. Basuara | MALTI SINGH, 9471641892 | [11 empty] | 1 |  | 2013-14
187 | USSS-120-2 | Darbhanga | njHkaxk |  | 2 | U.M.S. Godhiyari | MALTI SINGH, 9471641892 |  |  |  |  | 1 | [8 empty] | 2013-14
188 | USSS-120-3 | Darbhanga | njHkaxk |  | 3 | U.M.S. Narsara | MALTI SINGH, 9471641892 |  |  |  | 1 | [9 empty] | 2013-14
189 | USSS-121-1 | Darbhanga | njHkaxk |  | 1 | U.M.S. Kathra | City Creation | [10 empty] | 1 |  |  | 2013-14
190 | USSS-122-1 | Darbhanga | njHkaxk |  | 1 | M.S Kothram | Om Shree Construction |  |  | 1 | [9 empty] | Land Dispute | 2013-14
191 | USSS-156-1 | Darbhanga | e/kqcuh |  | 1 | Middle School Nagwas | Malti Singh, | [10 empty] | 1 |  |  | 2013-14
192 | USSS-157-1 | Darbhanga | e/kqcuh |  | 1 | Middle School Gaudhol | KAMLESH KUMAR, 9334808205 | [11 empty] | 1 |  | 2013-14
193 | USSS-158(A) | Darbhanga | e/kqcuh |  | 1 | Middle School Majhaura | Retender | [8 empty] | 1 |  |  |  |  | 2013-14
194 | USSS-158(B) | Darbhanga | e/kqcuh |  | 1 | Middle School Amhi | Tender Process | [10 empty] | 1 |  |  | 2013-14
195 | USSS-159-1 | Darbhanga | e/kqcuh |  | 1 | Middle School Gobraura | PRAKRITI CONTRACTORS PVT LTD, 9431440749 | [9 empty] | 1 |  |  |  | 2013-14
196 | USSS-160(A) | Darbhanga | e/kqcuh |  | 1 | Middle School Kurso | MAA VASUNDHARA CONSTRUCTION, 9006650591 | [10 empty] | 1 |  |  | 2013-14
197 | USSS-160(B) | Darbhanga | e/kqcuh |  | 1 | UPS Middle School Basipatti | KAMLESH KUMAR, 9334808205 | [10 empty] | 1 |  |  | 2013-14
198 | USSS-161(A) | Darbhanga | e/kqcuh |  | 1 | Middle School Basuki | SUBODH KUMAR, 9973164105 | [10 empty] | 1 |  |  | 2013-14
199 | USSS-161(B) | Darbhanga | e/kqcuh |  | 1 | Middle School Sujatpur | SATISH KUMAR, 8294867362 | [11 empty] | 1 |  | 2013-14
200 | USSS-161(C) | Darbhanga | e/kqcuh |  | 1 | Middle School Trimuhan | SHASHI KUMAR DEO, 9934640530 | [11 empty] | 1 |  | 2013-14
201 | USSS-198-1 | Darbhanga | leLrhiqj |  | 1 | Middle School Pulhara | VAISHALI CONSTRUCTION, 9430483150 | [10 empty] | 1 |  |  | 2013-14
Total No. of USSS (2013-14) |  |  |  |  | 201 |  |  | 3 | 2 | 25 | 3 | 1 | 5 | 2 | 18 | 6 | 13 | 66 | 57
Note on H53: Cancel
Note on H83: Cancel
Note on H106: Cancel