## CDPO
BSEIDC Ltd., PATNA
Progress Report for the construction of CDPO BUILDING
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of Work | Name of Agency | Mobile | Date of Tender | L.O.A &Issued Date | Date of Aggrement | Retender | Tender Process | Physical Status | [11 empty] | Agreement Amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%) | Financial Achievement (%) | Remarks | Division
[13 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL | LL | RL
1 | CDPO-1 | Madhepura | Kumarkhand |  | Child Development Project Office co-housing (CDPO) at Kumarkhand | BAMBAM KUMAR SINGH | 9934071093 | NIT-40 12.02.15 | 3847/16.05.15 | 83 SBD OF 2015-16 (04.06.15) | [13 empty] | 1 | 123.0744 | 39.32 | 32.21 |  |  | Koshi
2 | CDPO-2 | Madhepura | Bihariganj |  | Child Development Project Office co-housing (CDPO) at Bihariganj | BAMBAM KUMAR SINGH | 9934071093 | NIT-40 12.02.15 | 3847/16.05.15 | 84 SBD OF 2015-16 (04.06.15) |  |  | 1 | [11 empty] | 122.0866 |  | #REF! |  | Land not Available. Work Drop | Koshi
3 | CDPO-3 | Madhepura | Gwalpara |  | Child Development Project Office co-housing (CDPO) at Gwalpara | SHIV CHANDRA KUMAR | 9431046145 | NIT-40 12.02.15 | 3847/16.05.15 | 241 SBD OF 2015-16 (29.08.15) |  |  | 1 | [11 empty] | 121.9103 |  | 0 |  | Land not Available. Work Drop | Koshi
4 | CDPO-4 | Supaul | Basantpur |  | Child Development Project Office co-housing (CDPO) at Batihani( basantpur) | AKASH KUMAR | 9334362048 | NIT-40 12.02.15 | 3847/16.05.15 | 310 SBD OF 2015-16 (07.09.15) | [11 empty] | 1 |  |  | 129.676 |  | 0 |  |  | Koshi
5 | CDPO-5 | Supaul | Pipra |  | Child Development Project Office co-housing (CDPO) at Pipra | BAMBAM KUMAR SINGH | 9934071093 | NIT-40 12.02.15 | 4391/08.06.15 | 177 SBD OF 2015-16 (23-07-15) | [13 empty] | 1 | 126.8432 | 28.02 | 22.09 |  |  | Koshi
6 | CDPO-6 | Supaul | Kishanpur |  | Child Development Project Office co-housing (CDPO) at Kishanpure | BAMBAM KUMAR SINGH | 9934071093 | NIT-40 12.02.15 | 3847/16.05.15 | 85 SBD OF 2015-16 (04.06.15) | [13 empty] | 1 | 125.0252 | 40.35 | 32.27 |  |  | Koshi
7 | CDPO-7 | Supaul | Triveniganj |  | Child Development Project Office co-housing (CDPO) at Triveniganj | BAMBAM KUMAR SINGH, | 9934071093 | NIT-40 12.02.15 | 4052/25.05.15 | 178 SBD OF 2015-16 (23-07-15) | [13 empty] | 1 | 123.6204 | 39.5 | 31.95 |  |  | Koshi
8 | CDPO-8 | Purnea | Bhawanipur |  | Child Development Project Office co-housing (CDPO) at Bhawanipur | BABLU KUMAR BHAGAT | 9431280775 | NIT-40 12.02.15 | 3847/16.05.15 | 245 SBD OF 2015-16 (31.08.15) | [13 empty] | 1 | 125.783 | 38.3 | 30.45 |  | Handover | Purnea
9 | CDPO-9 | Purnea | Srinagar |  | Child Development Project Office co-housing (CDPO) at Srinagar | Sunil Kumar Suman | 9430969973 | NIT-40 12.02.15 | 3847/16.05.15 | 239 SBD OF 2015-16 (29.08.15) | [13 empty] | 1 | 124.2528 | 23.02 | 18.53 |  | Handover | Purnea
10 | CDPO-10 | Arariya | Raniganj |  | Child Development Project Office co-housing (CDPO) at Raniganj | VIDHATA CONSTRUCTION | 9939230691 | NIT-40 12.02.15 | 4052/25.05.15 | 274 SBD OF 2015-16 (2.09.15) | [12 empty] | 1 |  | 121.4178 |  | 0 |  |  | Purnea
11 | CDPO-11 | Arariya | Arariya |  | Child Development Project Office co-housing (CDPO) at Arariya | C S CONSTRUCTION | 9431284224 | NIT-40 12.02.15 | 4052/25.05.15 | [14 empty] | 1 |  |  | #DIV/0! |  |  | Purnea
12 | CDPO-12 | Arariya | Palashi |  | Child Development Project Office co-housing (CDPO) at Palashi | BABLU KUMAR BHAGAT | 9431280775 | NIT-40 12.02.15 | 3847/16.05.15 | 244 SBD OF 2015-16 (31.08.15) | [12 empty] | 1 |  | 123.7937 |  | 0 |  |  | Purnea
13 | CDPO-13 | Arariya | Narpatganj |  | Child Development Project Office co-housing (CDPO) at Narpatganj | AKASH KUMAR | 9334362048 | NIT-40 12.02.15 | 3847/16.05.15 | 257 SBD OF 2015-16 (01.09.15) | [11 empty] | 1 |  |  | 130.114 |  | 0 |  |  | Purnea
14 | CDPO-14 | Arariya | Bhargama |  | Child Development Project Office co-housing (CDPO) at Bhargama | AKASH KUMAR | 9334362048 | NIT-40 12.02.15 | 3847/16.05.16 | 258 SBD OF 2015-16 (01.09.15) | [12 empty] | 1 |  | 126.3785 | 26.96 | 21.33 |  |  | Purnea
15 | CDPO-15 | Arariya | Kursakatta |  | Child Development Project Office co-housing (CDPO) at Kursakatta | PRADEEP KUMAR | 9934276003, | NIT-40 12.02.15 | 3847/16.05.17 | 295 SBD OF 2015-16 (04.09.15) | [12 empty] | 1 |  | 134.21 |  | 0 |  |  | Purnea
16 | CDPO-16 | Sheohar | Taryiani |  | Child Development Project Office co-housing (CDPO) at Taryiani | RITESH KUMAR | 9304956871 | NIT-40 12.02.15 | 3847/16.05.18 | 246 SBD OF 2015-16 (31.08.15) |  |  | 1 | [11 empty] | 121.6844 |  | 0 |  | Not Start. (Land is 7' Below From Ground Level). Work Drop | Tirhut West
17 | CDPO-17 | Kishanganj | Kochadhaman |  | Child Development Project Office co-housing (CDPO) at Kochadhaman | PAWAN KUMAR AGRAWAL | 094312-32056 | NIT-40 12.02.15 | 3847/16.05.19 | 207 SBD OF 2015-16 (14.08.15) | [12 empty] | 1 |  | 128.2715 |  | 0 |  |  | Purnea
18 | CDPO-18 | Kishanganj | Digal-Bank |  | Child Development Project Office co-housing (CDPO) at Digal-Bank | AKASH KUMAR | 9334362048 | NIT-40 12.02.15 | 3847/16.05.20 | 258 SBD OF 2015-16 (01.09.15) | [11 empty] | 1 |  |  | 129.35 |  | 0 |  |  | Purnea
19 | CDPO-19 | Kishanganj | Pothiya |  | Child Development Project Office co-housing (CDPO) at Pothiya | MAHMAD JAFIRUDDIN | 8051267203 | NIT-40 12.02.15 | 3847/16.05.21 | 294 SBD OF 2015-16 (04.09.15) | [13 empty] | 1 | 129.9387 | 30.16 | 23.21 |  | Handover | Purnea
20 | CDPO-20 | Kishanganj | Teragachi |  | Child Development Project Office co-housing (CDPO) at Teragachi | R. P. AGARWAL | 9472807310 | NIT-40 12.02.15 | 3847/16.05.22 | 176 SBD OF 2015-16 (22-07-15) | [12 empty] | 1 |  | 128.2377 |  | 0 |  |  | Purnea
21 | CDPO-21 | Jamui | Sikandra |  | Child Development Project Office co-housing (CDPO) at Sikandra | ANKUR ENTERPRISES | 9931147610 | NIT-40 12.02.15 | 4052/25.05.15 | 273 SBD OF 2015-16 (02.09.15) |  |  | 1 | [11 empty] | 115.9959 |  | 0 |  | Work Stopped | Munger
22 | CDPO-22 | Jamui | Chakai |  | Child Development Project Office co-housing (CDPO) at Chakai | LAL RUPAK KUMAR SINGH | 9006614038 | NIT-40 12.02.15 | 4052/25.05.15 | 240 SBD OF 2015-16 (29.08.15) | [12 empty] | 1 |  | 119.335 |  | 0 |  |  | Munger
23 | CDPO-23 | Jamui | Sono |  | Child Development Project Office co-housing (CDPO) at Sono | Balkrishna Bhalotia Construction Pvt. Ltd. |  |  |  | 24 SBD 2016-17 (12.05.16) AV.-96.06 | [12 empty] | 1 | [6 empty] | Munger
24 | CDPO-24 | Madhubani | Pandaul |  | Child Development Project Office co-housing (CDPO) at Pandaul | Kumari Sindhu, Patna | [17 empty] | 1 | [5 empty] | Darbhanga
25 | CDPO-25 | Madhubani | Bisfi |  | Child Development Project Office co-housing (CDPO) at Bisfi | Dev Enterprises, Patna | [16 empty] | 1 | [6 empty] | Darbhanga
26 | CDPO-26 | Madhubani | Harlakhi |  | Child Development Project Office co-housing (CDPO) at Harlakhi | Jyoti Corporation, Patna | [16 empty] | 1 | [6 empty] | Darbhanga
27 | CDPO-27 | Madhubani | Madhavpur |  | Child Development Project Office co-housing (CDPO) at Madhavpur | Subodh Kumar | [16 empty] | 1 | [6 empty] | Darbhanga
28 | CDPO-28 | Madhubani | Khutauna |  | Child Development Project Office co-housing (CDPO) at Khutauna | Saroj Kumar Yadav, Madhubani | [13 empty] | 1 | [9 empty] | Darbhanga
29 | CDPO-29 | Banka | Dhoraiya |  | Child Development Project Office co-housing (CDPO) at Dhoraiya | Himanshu Kumar, Bhagalpur | [17 empty] | 1 | [5 empty] | Bhagalpur
30 | CDPO-30 | Banka | Barhat |  | Child Development Project Office co-housing (CDPO) at Barhat | Niwesh Kumar, Banka | [16 empty] | 1 | [6 empty] | Bhagalpur
31 | CDPO-31 | Banka | Banka |  | Child Development Project Office co-housing (CDPO) at Banka | M. K. Enterprise, Begusarai | [15 empty] | 1 | [7 empty] | Bhagalpur
32 | CDPO-32 | Banka | Belhar |  | Child Development Project Office co-housing (CDPO) at Belhar | Uma Shankar Roy, Munger | [6 empty] | 1 | [15 empty] | Work drop | Bhagalpur
33 | CDPO-33 | Banka | Chandan |  | Child Development Project Office co-housing (CDPO) at Chandan | Uma Shankar Roy , Munger | [16 empty] | 1 | [6 empty] | Bhagalpur
Total Number of CDPO Buildings |  |  |  |  | 33 | [5 empty] | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 13 | 10 | 2630.9992 | 265.63 | #REF! | 0