## USSS (2013-14)
BSEIDC Ltd., Patna
Physical Status of USSS (2013-14)
S.N. | Group No. | BMSP portion Expenses | STATE GOVT. Portion Expenses | TOTAL Expenses | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Aggrement No & date | Retender | Tender Process | Physical Status | [9 empty] | Remarks | Date of Completion | Session
[14 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[18 empty] | LL | RL | LL | RL
1 | USSS-123-1 | 6919175 |  | 6919175 | Magadh | GAYA | Gurua | 1 | Middle School, Mahadev Sthan | SANJAY KUMAR SINGH, 9973456006 | [12 empty] | 1 |  |  | 2013-14
2 | USSS-130-1 | 7949000 | 1519737 | 9468737 | Magadh | JAHANABAD | Hulasganj | 1 | Middle School, Gangapur | M/S A K CHOUDHARY, 9470166345 | [12 empty] | 1 | Few Parts of Electric & PHE. Works Remaining |  | 2013-14
3 | USSS-162 (A) | 7949000 | 3396612 | 11345612 | Magadh | NAWADA | Kawakol | 1 | UPS Rupai | SHRI CHANDRA MOULESHWAR, 9931911023 | [12 empty] | 1 |  |  | 2013-14
4 | USSS-162 (B) | 7949000 | 3405801 | 11354801 | Magadh | NAWADA | Kawakol | 1 | UPS Lohgarwa | ASHIS RANJAN, 9931215326 | [12 empty] | 1 |  |  | 2013-14
5 | USSS-163 (A) | 7949000 | 572504 | 8521504 | Magadh | NAWADA | Sirdala | 1 | UPS Hemja Bhart | MD RAIS KHAN, 9973622799 | [12 empty] | 1 |  |  | 2013-14
6 | USSS-163 (B) |  | 0 |  | Magadh | NAWADA | Sirdala | 1 | M.S., Kharsari | SURENDRA KUMAR, 9934447377 |  |  |  | 1 | [9 empty] | Land not available |  | 2013-14
7 | USSS-163 (C ) |  | 0 |  | Magadh | NAWADA | Sirdala | 1 | UPS Mahuliya Tanr | RAVI JALAN, 9546109122 |  |  |  | 1 | [9 empty] | Not Start |  | 2013-14
8 | USSS-106 (A) | 7949000 | 3996986 | 11945986 | Bhagalpur | BANKA |  | 1 | U.M.S Kerwar | Marcominfra Pvt. Ltd., 9934361315 | [12 empty] | 1 |  |  | 2013-14
9 | USSS-106 (B) | 6035425 | 0 | 6035425 | Bhagalpur | BANKA |  | 1 | U.M.S Burhawa Bathan | Marcominfra Pvt Ltd., 9934361315 | [12 empty] | 1 |  |  | 2013-14
10 | USSS-106 (C) | 7949000 | 2997424 | 10946424 | Bhagalpur | BANKA |  | 1 | U.M.S Upar Chak Marhdiya | Marcominfra Pvt. Ltd.,9934361315 | [12 empty] | 1 |  |  | 2013-14
11 | USSS-106 (D) | 7949000 | 3543475 | 11492475 | Bhagalpur | BANKA |  | 1 | M.S Jamdaha | Marcominfra Pvt. Ltd., 9934361315 | [12 empty] | 1 |  |  | 2013-14
12 | USSS-106 (E) | 7949000 | 3207898 | 11156898 | Bhagalpur | BANKA |  | 1 | M.S Mochanma | Marcominfra Pvt. Ltd., 9934361315 | [12 empty] | 1 |  |  | 2013-14
13 | USSS-106 (F) | 7949000 | 2240404 | 10189404 | Bhagalpur | BANKA |  | 1 | U.M.S Lila waran | BINOD KUMAR SINGH, 9471749892 | [12 empty] | 1 |  |  | 2013-14
14 | USSS-106 (G) | 7949000 | 3242282 | 11191282 | Bhagalpur | BANKA |  | 1 | U.M.S Dhevermoh | Bricks Liner Infrastructure Pvt | [12 empty] | 1 |  |  | 2013-14
15 | USSS-107-1 | 7949000 | 1617019 | 9566019 | Bhagalpur | BANKA |  | 1 | M.S Bhavan Kormama | Nimbark engineering pvt. Ltd. | [12 empty] | 1 |  |  | 2013-14
16 | USSS-108 (A) | 7949000 | 3431621 | 11380621 | Bhagalpur | BANKA |  | 1 | M.S Madari | Binod Kumar Singh | [12 empty] | 1 |  |  | 2013-14
17 | USSS-108 (B) | 7949000 | 3044405 | 10993405 | Bhagalpur | BANKA |  | 1 | U.M.S Phaga | NIWESH KUMAR, 9576272505 | [12 empty] | 1 |  |  | 2013-14
18 | USSS-109-1 | 7949000 | 3270615 | 11219615 | Bhagalpur | BANKA | Chandan | 1 | U.M.S Koriya | BINOD KUMAR SINGH, 9471749892 | [12 empty] | 1 | Handover |  | 2013-14
19 | USSS-109-2 | 7949000 | 3270615 | 11219615 | Bhagalpur | BANKA | Chandan | 2 | M.S. Kendwar | BINOD KUMAR SINGH, 9471749892 | [12 empty] | 1 |  |  | 2013-14
20 | USSS-110-1 | 6584249 | 0 | 6584249 | Bhagalpur | BANKA |  | 1 | U.M.S Amjora | Anand Kumar, S. K. Nagar, Patna | [10 empty] | 1 |  |  |  |  | 2013-14
21 | USSS-111-1 | 7949000 | 3958094 | 11907094 | Bhagalpur | BANKA |  | 1 | U.M.S Hasiya | KUNDAN KUMAR SINGH | [12 empty] | 1 |  |  | 2013-14
22 | USSS-112 (A) | 7949000 | 4545906 | 12494906 | Bhagalpur | BANKA |  | 1 | M.S Darshniya | Binod Kumar Singh | [12 empty] | 1 |  |  | 2013-14
23 | USSS-112 (B) | 7949000 | 4522502 | 12471502 | Bhagalpur | BANKA |  | 1 | U.M.S, Bounka | Binod Kumar Singh | [12 empty] | 1 |  |  | 2013-14
24 | USSS-112 (C) |  | 0 |  | Bhagalpur | BANKA |  | 1 | U.M.S Chariya | Binod Kumar Singh |  |  |  | 1 | [9 empty] | Land not available |  | 2013-14
25 | USSS-113-1 | 3699277 | 0 | 3699277 | Bhagalpur | BHAGALPUR |  | 1 | U.M.S Asiachak | Rajendra Kumar | [8 empty] | 1 |  |  |  |  | Letter for Debar |  | 2013-14
26 | USSS -124 (A) | 6093639 | 0 | 6093639 | Munger | Munger | Khaira | 1 | M S Bujhayat | ASHOK AND CO NIVAS PVT LTD, 9006613016 | 49 SBD OF 15-16 (07.05.15) | [10 empty] | 1 |  |  |  | 2013-14
27 | USSS -124 (B) | 6486218 | 0 | 6486218 | Munger | Munger | Khaira | 1 | M.S Ghari Bishanpur | ASHOK AND CO NIVAS PVT LTD, 9006613016 | 50 SBD OF 15-16 (07.05.15) | [10 empty] | 1 |  |  |  | 2013-14
28 | USSS -124 (C) | 3354861 | 0 | 3354861 | Munger | Munger | Khaira | 1 | M S Ghari | MAHNAR INFRATECH PVT LTD | 447 SBD OF 2015-16(04.03.16) | [10 empty] | 1 |  | G+2 |  | 2013-14
29 | USSS-125 (A) | 7949000 | 2665034 | 10614034 | Munger | Munger | Chakai | 1 | M S Saron | SUDHIR KUMAR,9973392397 | 606 SBD OF 14-15 (08.01.15) | [11 empty] | 1 |  | 2016-02-25 | 2013-14
30 | USSS-125 (B) | 7949000 | 2625536 | 10574536 | Munger | Munger | Chakai | 1 | M S Kiyajori | SUDHIR KUMAR,9973392397 | 607 SBD OF 14-15 (08.01.15) | [11 empty] | 1 |  | 2016-02-25 | 2013-14
31 | USSS-125 (C) | 7689864 | 0 | 7689864 | Munger | Munger | Chakai | 1 | M S Bamdah | AGRAGAMI INDIA CONSTRUCTION PRIVATE LIMITED, 9939029899 | 615 SBD OF 14-15 (16.01.15) | [10 empty] | 1 |  |  |  | 2013-14
32 | USSS-125 (D) | 7949000 | 570143 | 8519143 | Munger | Munger | Chakai | 1 | M S Kewal | AMIT KUMAR | 220 SBD OF 2015-16 (25.08.15) | [10 empty] | 1 |  |  |  | 2013-14
33 | USSS-126 (A) | 7949000 | 1111249 | 9060249 | Munger | JAMUI |  | 1 | URaktrohaniya | RAJENDRA KUMAR, 9939195777 | 702SBD OF 14-15 (18.02.15 | [10 empty] | 1 |  |  |  | 2013-14
34 | USSS-126 (B) | 7949000 | 4008198 | 11957198 | Munger | JAMUI |  | 1 | M S Sarebad | Ashish Ranjan | 247 SBD OF 2015-15(31.08.15) | [11 empty] | 1 |  |  | 2013-14
35 | USSS-126 (C) | 7949000 | 4017253 | 11966253 | Munger | JAMUI |  | 1 | M S Agahra | Ashish Ranjan | 248 SBD OF 2015-15(31.08.15) | [11 empty] | 1 |  |  | 2013-14
36 | USSS-126 (D) | 7949000 | 1334011 | 9283011 | Munger | JAMUI |  | 1 | M.S Charkapathar | Ashish Ranjan | 249 SBD OF 2015-15(31.08.15) | [10 empty] | 1 |  | S.F.R.L.(G+2) |  | 2013-14
37 | USSS-127 (A) | 7949000 | 243557 | 8192557 | Munger | JAMUI |  | 1 | M .S. Sewa | Ashok and Co Nivas | 206 SBD 2015-16 (14.08.2015) | [11 empty] | 1 |  |  | 2013-14
38 | USSS-127 (B) | 7949000 | 1621879 | 9570879 | Munger | JAMUI |  | 1 | M,S,KEWAL | ASHOK AND CO NIVAS PVT LTD,9006613016 | 51 SBD OF 15-16 (07.05.15) | [11 empty] | 1 |  |  | 2013-14
39 | USSS-128-1 | 7949000 | 285366.995 | 8234366.995 | Munger | JAMUI |  | 1 | M S Borwa | RAJENDRA KUMAR9939195777, | 496 SBD OF 14-15 (08.12.14 | [10 empty] | 1 |  | DIST AREA WORK STOPPED |  | 2013-14
40 | USSS-128-2 | 7949000 | 285366.995 | 8234366.995 | Munger | JAMUI |  | 2 | U M S Chapa | RAJENDRA KUMAR9939195777, | [11 empty] | 1 |  |  |  | 2013-14
41 | USSS-129 (A) | 7351193 | 0 | 7351193 | Munger | JAMUI |  | 1 | U M S Hathiyawar Taljhari | ASHOK KUMAR SINGH, 8969398786 | 679 SBD 2014-2015(12.02.15) | [10 empty] | 1 |  |  |  | 2013-14
42 | USSS-129 (B) | 7685567 | 0 | 7685567 | Munger | JAMUI |  | 1 | U M S Taliyadih | MANGLAM CONSTRUCTION, 7631507878 | 752 SBD OF 2014-15 (13.03.15) | [10 empty] | 1 |  |  |  | 2013-14
43 | USSS-129 (C) | 7949000 | 771829 | 8720829 | Munger | JAMUI |  | 1 | U M S Bela | MUKESH KUMAR, 9973462715 | 781 SBD 2014-2015(31.03.15) | [10 empty] | 1 |  |  |  | 2013-14
44 | USSS-129 (D) | 7949000 | 770574 | 8719574 | Munger | JAMUI |  | 1 | U M S Karra | Sunil Kumar, (Bricks Liner Infrastructure Pvt) | 269 SBD OF 2015-16(02.09.15} | [10 empty] | 1 |  |  |  | 2013-14
45 | USSS-151-1 |  | 0 |  | Munger | LAKHISARAI |  | 1 | U M S Singhaul Tetariaya | VIJAY KUMAR |  |  |  | 1 | [9 empty] | Land not available |  | 2013-14
46 | USSS-143-1 | 7949000 | 745722 | 8694722 | Munger | KHAGARIA |  | 1 | MS Icharua | Lal Babu Prasad | 76 SBD OF 2015-16(25.05.15) | [10 empty] | 1 |  |  |  | 2013-14
47 | USSS-152-1 | 7949000 | 420725 | 8369725 | Kosi | MADHEPURA |  | 1 | M.S Sonbarsha | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775, 9472103786 | 339 SBD OF 2014-15 (17.09.14) | [10 empty] | 1 |  |  |  | 2013-14
48 | USSS-153-1 | 7362221 | 0 | 7362221 | Kosi | MADHEPURA |  | 1 | M.S. Rahi | Retender | [10 empty] | 1 |  |  |  |  | 2013-14
49 | USSS-154-1 | 3331891.995 | 0 | 3331891.995 | Kosi | MADHEPURA |  | 1 | M.S Bhelva | SUNITA DEVI, 9162524068 | 16 SBD OF 2015-16 (09.04.15) | [9 empty] | 1 |  |  |  |  | 2013-14
50 | USSS-154-2 | 3331891.995 | 0 | 3331891.995 | Kosi | MADHEPURA |  | 2 | M.S.Gadhiya | SUNITA DEVI, 9162524068 | 16 SBD OF 2015-16 (09.04.15) | [5 empty] | 1 | [8 empty] | 2013-14
51 | USSS-155-1 | 7949000 | 3814004 | 11763004 | Kosi | MADHEPURA |  | 1 | M.S.Uda | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 | 435SBD OF 14-15 (07.11.14) | [11 empty] | 1 | Handover |  | 2013-14
52 | USSS-195-1 |  | 0 |  | Kosi | SAHARSA |  | 1 | MS Partaha Barhara | Sarveshwar Kumar Ojha, Gopalganj | [7 empty] | 1 | [7 empty] | 2013-14
53 | USSS-196-1 | 6128817 | 0 | 6128817 | Kosi | SAHARSA |  | 1 | MS Dhanupra | JEEVAN JYOTI CONTRACTORS PVT LTD,9431247387 | 602 SBD OF 14-15 (07.01.15) | [8 empty] | 1 | [5 empty] | 2013-14
54 | USSS-197-1 | 5329909 | 0 | 5329909 | Kosi | SAHARSA |  | 1 | MS Samhar | JEEVAN JYOTI CONTRACTORS PVT LTD,9431247387 | 603 SBD OF 14-15 (07.01.15) | [7 empty] | 1 | [6 empty] | 2013-14
55 | USSS-204-1 |  | 0 |  | Kosi | SUPUAL |  | 1 | MS Parmanandpur | Madan Kumar singh | [6 empty] | 1 | [8 empty] | 2013-14
56 | USSS-204-2 |  | 0 |  | Kosi | SUPUAL |  | 2 | MS Bhawani pur | AKASH KUMAR,9334362048 |  |  |  | 1 | [9 empty] | Not Start |  | 2013-14
57 | USSS-205-1 |  | 0 |  | Kosi | SUPUAL |  | 1 | MS Bhimpur | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 |  |  |  | 1 | [9 empty] | Land not Available |  | 2013-14
58 | USSS-206(A) | 4759471 | 0 | 4759471 | Kosi | SUPUAL |  | 1 | MS sisauni | AKASH KUMAR,9334362048 | 260 SBD OF 2015-16 | [8 empty] | 1 | [5 empty] | 2013-14
59 | USSS-206(B) | 7949000 | 2432240 | 10381240 | Kosi | SUPUAL |  | 1 | MS sukhashan | PRIYA RANJAN,9931546525 | 721SBD OF 14-15 (25.02.15 | [9 empty] | 1 |  |  | Kota Work in progress |  | 2013-14
60 | USSS-207(A) |  | 0 | 0 | Kosi | SUPUAL |  | 1 | MS saroja Bela | Tender Process |  |  | 1 | [10 empty] | No Bidder |  | 2013-14
61 | USSS-207(B) | 7949000 | 2969769 | 10918769 | Kosi | SUPUAL |  | 1 | MS rasuaar | TRISHUL CONSTRUCTIONS,8252940655 | 636 SBD OF 14-15 (22.01.15) | [10 empty] | 1 |  |  |  | 2013-14
62 | USSS-207(C) | 6583799 | 0 | 6583799 | Kosi | SUPUAL |  | 1 | MS Hari | Adarsh Construction | [10 empty] | 1 |  |  |  |  | 2013-14
63 | USSS-208-1 |  | 0 | 0 | Kosi | SUPUAL |  | 1 | MS Bela sringarmoti | YOGENDRA PRASAD YADAV, 9631856613 |  |  |  | 1 | [9 empty] | Cancelled |  | 2013-14
64 | USSS-209-1 |  | 0 | 0 | Kosi | SUPUAL |  | 1 | MS Lalganj | VATSALYA BUILDCON PRIVATE LIMITED, 9430965119 |  |  |  | 1 | [9 empty] | Cancelled |  | 2013-14
65 | USSS-210-1 |  | 0 |  | Kosi | SUPUAL |  | 1 | MS Basbitti | Ashok Kumar, 9431091558 |  |  |  | 1 | [9 empty] | Cancelled |  | 2013-14
66 | USSS-210-2 | 7949000 | 2097083 | 10046083 | Kosi | SUPUAL |  | 2 | MS kaliganj | Ashok Kumar, 9431091558 | [11 empty] | 1 |  |  |  | 2013-14
67 | USSS-211(A) |  | 0 |  | Kosi | SUPUAL |  | 1 | Durga MS Laharnia | PRIYA RANJAN, 9931546525 | 720SBD OF 14-15 (25.02.15 |  |  | 1 | [9 empty] | Cancelled |  | 2013-14
68 | USSS-211(B) | 7949000 | 3666392 | 11615392 | Kosi | SUPUAL |  | 1 | MS Parsa Garhi | Madan Kumar singh | [12 empty] | 1 | Handover |  | 2013-14
69 | USSS-211(C) | 4840668 | 0 | 4840668 | Kosi | SUPUAL |  | 1 | MS Mogla Ghat nandana | AKASH KUMAR, 9334362048 | 730SBD OF 14-15 (04.03.15 | [8 empty] | 1 | [5 empty] | 2013-14
70 | USSS-101-1 | 7949000 | 3829296 | 11778296 | Purnea | ARARIA |  | 1 | A.M.S. Kala Balua | PRAKASH KUMAR SAH,9162909186 | 654 SBD OF 14-15 (29.01.15) | [11 empty] | 1 | Handover |  | 2013-14
71 | USSS-102-1 | 7949000 | 2090631 | 10039631 | Purnea | ARARIA |  | 1 | M.S. Barmasiya | MD. Iftakhar Alam | 373 SBD OF 15-16 (25.01.16) | [11 empty] | 1 |  |  | 2013-14
72 | USSS-103-1 | 7949000 | 4451355 | 12400355 | Purnea | ARARIA |  | 1 | U.M.S. Sonamani Godam | PRAKRITI CONTRACTORS PVT LTD,9431440749 | 722SBD OF 14-15 (02.03.15 | [11 empty] | 1 |  |  | 2013-14
73 | USSS-104-1 | 7949000 | 4539807 | 12488807 | Purnea | ARARIA |  | 1 | U.M.S. Subhankarpur | ASHA CONSTRUCTION,9431412711 | 678 SBD OF 2014-2015(12.02.15) | [11 empty] | 1 |  |  | 2013-14
74 | USSS-105(A) | 7949000 | 4517031 | 12466031 | Purnea | ARARIA |  | 1 | M.S. Basmatiya | AKHILESH SINGH,9470048339 | 623 SBD OF 14-15 (19.01.15) | [11 empty] | 1 | Handover |  | 2013-14
75 | USSS-105(B) | 7949000 | 5015415 | 12964415 | Purnea | ARARIA |  | 1 | M.S. Khaira | MD ARFIN,9006212706 | 05 SBD OF 15-16 (01.04.15) | [10 empty] | 1 |  | boring & paint |  | 2013-14
76 | USSS-105(C) | 7949000 | 4677143 | 12626143 | Purnea | ARARIA |  | 1 | M.S. Maheshpatti | RABINDRA SINGH,9472524322 | 622 SBD OF 14-15 (19.01.15) | [11 empty] | 1 | Handover |  | 2013-14
77 | USSS-105(D) | 7949000 | 5024706 | 12973706 | Purnea | ARARIA |  | 1 | M.S. Tamganj | SHAILENDRA KUMAR,9334855523 | 105 SBD OF 2015-16 (10.06.15) | [11 empty] | 1 |  |  | 2013-14
78 | USSS-131-1 |  | 0 |  | Purnea | KATIHAR |  | 1 | M.S. Bathilli | Cancel |  | 1 | [11 empty] | Double scheme |  | 2013-14
79 | USSS-132-1 | 7574395 | 0 | 7574395 | Purnea | KATIHAR |  | 1 | M.S. Dwasay | BIRENDRA KUMAR SINGH, 9473440405 | 507 SBD OF 14-15 (15.12.14 | [10 empty] | 1 |  |  |  | 2013-14
80 | USSS-132-2 | 7574396 | 0 | 7574396 | Purnea | KATIHAR |  | 2 | R M.S. Souriya | BIRENDRA KUMAR SINGH, 9473440405 | 507 SBD OF 14-15 (15.12.14 | [10 empty] | 1 |  |  |  | 2013-14
81 | USSS-133-1 | 7949000 | 3711301 | 11660301 | Purnea | KATIHAR |  | 1 | M.S. Padam Pur | PRAKASH KUMAR SAH,9162909186 | 655 SBD OF 14-15 (29.01.15) | [11 empty] | 1 | Handover |  | 2013-14
82 | USSS-134-1 | 7949000 | 1258982 | 9207982 | Purnea | KATIHAR |  | 1 | M.S. Makai Pur | BIRENDRA KUMAR SINGH, 9473440405 | 448SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
83 | USSS-134-2 | 7949000 | 1258982 | 9207982 | Purnea | KATIHAR |  | 2 | M.S. Kheria | BIRENDRA KUMAR SINGH, 9473440405 | 448SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
84 | USSS-134-3 | 7949000 | 1258982 | 9207982 | Purnea | KATIHAR |  | 3 | M.S. Pawai | BIRENDRA KUMAR SINGH, 9473440405 | 448SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
85 | USSS-134-4 | 7949000 | 1258982 | 9207982 | Purnea | KATIHAR |  | 4 | M.S. Rautara | BIRENDRA KUMAR SINGH, 9473440405 | 448SBD OF 14-15 (15.11.14) | [11 empty] | 1 |  |  | 2013-14
86 | USSS-134-5 | 7949000 | 1258982 | 9207982 | Purnea | KATIHAR |  | 5 | M.S. Dighree | BIRENDRA KUMAR SINGH, 9473440405 | 448SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
87 | USSS-134-6 | 7949000 | 1258982 | 9207982 | Purnea | KATIHAR |  | 6 | M.S. Chandwa Rupaspur | BIRENDRA KUMAR SINGH, 9473440405 | 448SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
88 | USSS-135-1 |  | 0 |  | Purnea | KATIHAR |  | 1 | M.S. Kathria | BIRENDRA KUMAR SINGH, 9473440405 | 449 SBD OF 14-15 (15.11.14) |  |  | 1 | [9 empty] | Double scheme |  | 2013-14
89 | USSS-136-1 | 7949000 | 1447092 | 9396092 | Purnea | KATIHAR |  | 1 | M.S. Nawabganj | BIRENDRA KUMAR SINGH, 9473440405 | 450SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
90 | USSS-136-2 | 7949000 | 1447093 | 9396093 | Purnea | KATIHAR |  | 2 | M.S. Chakla Khaira | BIRENDRA KUMAR SINGH, 9473440405 | 450SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
91 | USSS-137-1 |  | 0 |  | Purnea | KATIHAR |  | 1 | M.S. Bharsia | BIRENDRA KUMAR SINGH, 9473440405 | 451 SBD OF 14-15 (15.11.14) |  |  | 1 | [9 empty] | Double scheme |  | 2013-14
92 | USSS-137-2 | 7949000 | 943105 | 8892105 | Purnea | KATIHAR |  | 2 | M.S. Mohammad Nagar Rajdhani | BIRENDRA KUMAR SINGH, 9473440405 | 451 SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
93 | USSS-137-3 | 6276778 | 0 | 6276778 | Purnea | KATIHAR |  | 3 | M.S. Dermahi | BIRENDRA KUMAR SINGH, 9473440405 | 451 SBD OF 14-15 (15.11.14) | [9 empty] | 1 |  |  |  |  | 2013-14
94 | USSS-137-4 | 7949000 | 943105 | 8892105 | Purnea | KATIHAR |  | 4 | U M.S. Musapur Ranga Kol | BIRENDRA KUMAR SINGH, 9473440405 | 451 SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
95 | USSS-137-5 | 7949000 | 943105 | 8892105 | Purnea | KATIHAR |  | 5 | U M.S. Tapua Gobindpur | BIRENDRA KUMAR SINGH, 9473440405 | 451 SBD OF 14-15 (15.11.14) | [10 empty] | 1 |  |  |  | 2013-14
96 | USSS-138(A) | 7949000 | 4956148 | 12905148 | Purnea | KATIHAR |  | 1 | U M.S. Hajiyaar Palsa | MS EXCELLENT CONSTRUCTION, 9472021967 | 09 SBD OF 15-16 (02.14.15) | [11 empty] | 1 | Handover |  | 2013-14
97 | USSS-138(B) | 7949000 | 4776815 | 12725815 | Purnea | KATIHAR |  | 1 | U M.S. Chilha Para | MS EXCELLENT CONSTRUCTION, 9472021967 | 234 SBD OF 15-16 (28.08.15) | [11 empty] | 1 |  |  | 2013-14
98 | USSS-139-1 | 7949000 | 4769948 | 12718948 | Purnea | KATIHAR |  | 1 | M.S. Parbheli | VATSALYA BUILDCON PRIVATE LIMITED,9430965119 | 436 SBD OF 14-15 (07.11.14) | [11 empty] | 1 | Handover |  | 2013-14
99 | USSS-140(A) | 7949000 | 3005063 | 10954063 | Purnea | KATIHAR |  | 1 | M.S. Mukuria Dakshin Tola | RANA BIRESH PRATAP SINGH, 9430683578 | 78 SBD OF 2015-16 (27.05.15) | [11 empty] | 1 |  |  | 2013-14
100 | USSS-140(B) |  | 0 |  | Purnea | KATIHAR |  | 1 | M.S. Sikitia | MS EXCELLENT CONSTRUCTION, 9472021967 |  |  |  | 1 | [9 empty] | Double scheme |  | 2013-14
101 | USSS-141-1 |  | 0 |  | Purnea | KATIHAR |  | 1 | M.S. Budhanagar | Tender Process |  |  |  | 1 | [9 empty] | Double scheme |  | 2013-14
102 | USSS-142-1 | 7949000 | 4196982 | 12145982 | Purnea | KATIHAR |  | 1 | M.S. Kanta Kosh | PRAKASH KUMAR SAH,9162909186 | 656 SBD OF 14-15 (29.01.15) | [11 empty] | 1 | Handover |  | 2013-14
103 | USSS-144-1 | 7949000 | 4713453 | 12662453 | Purnea | KISHANGANJ |  | 1 | UMS Teusa | ASHOK KUMAR SINGH,9430467620 | 193 SBD OF 2015-16 (12.08.15) | [11 empty] | 1 |  |  | 2013-14
104 | USSS-145-1 |  | 0 |  | Purnea | KISHANGANJ |  | 1 | M.S Farabari | BIRENDRA KUMAR SINGH, 9473440405 | 567SBD OF 14-15 (30.12.14) |  |  | 1 | [9 empty] | land not available |  | 2013-14
105 | USSS-145-2 |  | 0 |  | Purnea | KISHANGANJ |  | 2 | M.S Kuwari | BIRENDRA KUMAR SINGH, 9473440405 | 567SBD OF 14-15 (30.12.14) |  |  |  |  | 1 | [7 empty] | work stopped by contractor (during excavation) since long time, letter issued |  | 2013-14
106 | USSS-146-1 | 3099006 | 0 | 3099006 | Purnea | KISHANGANJ |  | 1 | M.S Gilhabari Kanya | BIRENDRA KUMAR SINGH, 9473440405 | 521 SBD OF 14-15 (16.12.14 | [6 empty] | 1 | [7 empty] | 2013-14
107 | USSS-146-2 | 1936878 | 0 | 1936878 | Purnea | KISHANGANJ |  | 2 | M.S Shitalpur | BIRENDRA KUMAR SINGH, 9473440405 | 521 SBD OF 14-15 (16.12.14 | [5 empty] | 1 | [6 empty] | work stopped by contractor since long time, letter issued |  | 2013-14
108 | USSS-146-3 | 1936878 | 0 | 1936878 | Purnea | KISHANGANJ |  | 3 | U. M.S Kusiyari | BIRENDRA KUMAR SINGH, 9473440405 | 521 SBD OF 14-15 (16.12.14 | [5 empty] | 1 | [6 empty] | work stopped by contractor since long time, letter issued |  | 2013-14
109 | USSS-146-4 | 1549505 | 0 | 1549505 | Purnea | KISHANGANJ |  | 4 | U.M,S Nawnadi | BIRENDRA KUMAR SINGH, 9473440405 | 521 SBD OF 14-15 (16.12.14 |  |  |  |  | 1 | [9 empty] | 2013-14
110 | USSS-147-1 | 2556073 | 0 | 2556073 | Purnea | KISHANGANJ |  | 1 | M.S Bourigacch | BIRENDRA KUMAR SINGH, 9473440405 | 514 SBD OF 14-15 (15.12.14 | [5 empty] | 1 | [8 empty] | 2013-14
111 | USSS-147-2 | 2044860 | 0 | 2044860 | Purnea | KISHANGANJ |  | 2 | M.S Ruidhasa | BIRENDRA KUMAR SINGH, 9473440405 | 514 SBD OF 14-15 (15.12.14 | [5 empty] | 1 | [8 empty] | 2013-14
112 | USSS-147-3 | 7949000 | 741649 | 8690649 | Purnea | KISHANGANJ |  | 3 | M.S Barchondi | BIRENDRA KUMAR SINGH, 9473440405 | 514 SBD OF 14-15 (15.12.14 | [10 empty] | 1 |  |  |  | 2013-14
113 | USSS-148-1 | 6154189 | 0 | 6154189 | Purnea | KISHANGANJ |  | 1 | M.S Talgacch | BIRENDRA KUMAR SINGH, 9473440405 | 534 SBD OF 14-15 (17.12.14 | [9 empty] | 1 |  |  |  |  | 2013-14
114 | USSS-148-2 | 512849 | 0 | 512849 | Purnea | KISHANGANJ |  | 2 | M.S. Gandharvdanga | BIRENDRA KUMAR SINGH, 9473440405 | 534 SBD OF 14-15 (17.12.14 |  |  |  | 1 | [10 empty] | 2013-14
115 | USSS-148-3 | 4102794 | 0 | 4102794 | Purnea | KISHANGANJ |  | 3 | U.M.S Talwarbandha | BIRENDRA KUMAR SINGH, 9473440405 | 534 SBD OF 14-15 (17.12.14 | [7 empty] | 1 |  |  |  |  | work stopped by contractor since long time, letter issued |  | 2013-14
116 | USSS-149-1 | 5369665 | 0 | 5369665 | Purnea | KISHANGANJ |  | 1 | U.M.S Masangoan | BIRENDRA KUMAR SINGH, 9473440405 | 522 SBD OF 14-15 (16.12.14 | [9 empty] | 1 |  |  |  |  | 2013-14
117 | USSS-149-2 | 3579777 | 0 | 3579777 | Purnea | KISHANGANJ |  | 2 | M.S Shameswar | BIRENDRA KUMAR SINGH, 9473440405 | 522 SBD OF 14-15 (16.12.14 | [7 empty] | 1 | [6 empty] | 2013-14
118 | USSS-149-3 |  | 0 |  | Purnea | KISHANGANJ |  | 3 | M.S Natuapara | BIRENDRA KUMAR SINGH, 9473440405 | 522 SBD OF 14-15 (16.12.14 |  |  | 1 | [9 empty] | letter issued to contractor to start the work |  | 2013-14
119 | USSS-149-4 | 3579777 | 0 | 3579777 | Purnea | KISHANGANJ |  | 4 | M.S Khodaganj | BIRENDRA KUMAR SINGH, 9473440405 | 522 SBD OF 14-15 (16.12.14 | [7 empty] | 1 | [6 empty] | 2013-14
120 | USSS-149-5 | 4474722 | 0 | 4474722 | Purnea | KISHANGANJ |  | 5 | U.M.S Gopalpur Haat | BIRENDRA KUMAR SINGH, 9473440405 | 522 SBD OF 14-15 (16.12.14 | [8 empty] | 1 | [5 empty] | 2013-14
121 | USSS-150-1 | 5453058 | 0 | 5453058 | Purnea | KISHANGANJ |  | 1 | U.M.S Kochgarh Purndha | BIRENDRA KUMAR SINGH, 9473440405 | 568SBD OF 14-15 (30.12.14) | [10 empty] | 1 |  |  |  | 2013-14
122 | USSS-184 (A) |  | 0 |  | Purnea | PURNEA |  | 1 | M.S. Routi Basha | Retender |  | 1 | [11 empty] | Retender |  | 2013-14
123 | USSS-184 (B) | 4174029 | 0 | 4174029 | Purnea | PURNEA |  | 1 | M.S. Talbari | Binod Yadav | [8 empty] | 1 | [6 empty] | 2013-14
124 | USSS-185-1 |  | 0 |  | Purnea | PURNEA |  | 1 | M.S. Sirsi | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 | 18 SBD OF 2015-16 (15.04.15) |  |  | 1 | [9 empty] | old building to be demolished |  | 2013-14
125 | USSS-186-1 |  | 0 |  | Purnea | PURNEA |  | 1 | M.S. Amirganj | Retender |  | 1 | [11 empty] | Retender |  | 2013-14
126 | USSS-187-1 | 7949000 | 4833408 | 12782408 | Purnea | PURNEA |  | 1 | M.S. Laxmipur | VATSALYA BUILDCON PRIVATE LIMITED, 9430965119 | 599 SBD OF 14-15 (06.01.15) | [11 empty] | 1 | Handover |  | 2013-14
127 | USSS-188 (A) | 5424470 | 0 | 5424470 | Purnea | PURNEA |  | 1 | M.S. Sauraha | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | 19 SBD OF 2015-16 (15.04.15) | [7 empty] | 1 | [6 empty] | 2013-14
128 | USSS-188 (B) | 5667007 | 0 | 5667007 | Purnea | PURNEA |  | 1 | M.S. Pranpatti | HARIMOHAN BISHWAS,9955713757 | 55 SBD OF 15-16 (14.05.15) | [7 empty] | 1 | [6 empty] | 2013-14
129 | USSS-188 (C) | 2296692 | 0 | 2296692 | Purnea | PURNEA |  | 1 | M.S. Kajha | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | 20 SBD OF 2015-16 (15.04.15) | [5 empty] | 1 | [8 empty] | 2013-14
130 | USSS-189 (A) | 7882650 | 0 | 7882650 | Purnea | PURNEA |  | 1 | M.S.Chandpur Bhanha | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED,9973239801 | 75 SBD OF 2015-16 (25.05.15) | [10 empty] | 1 |  |  |  | 2013-14
131 | USSS-189 (B) | 7949000 | 5577158 | 13526158 | Purnea | PURNEA |  | 1 | M.S. Harimurhi | CS CONSTRUCTION | [12 empty] | 1 |  |  | 2013-14
132 | USSS-190 (A) | 7949000 | 4707017 | 12656017 | Purnea | PURNEA |  | 1 | M.S. Dumri | CS CONSTRUCTION | 358 SBD OF 15-16 (08.01.16) | [11 empty] | 1 |  |  | 2013-14
133 | USSS-190 (B) | 7949000 | 4990108 | 12939108 | Purnea | PURNEA |  | 1 | M.S. Goriar | ADITYA KUMAR SINGH,9546045749 | 107 SBD OF 2015-16 (10.06.15) | [11 empty] | 1 |  |  | 2013-14
134 | USSS-191-1 |  | 0 |  | Purnea | PURNEA |  | 1 | M.S.Bishanpur | MD JAVIR, 9955418718 |  |  |  | 1 | [9 empty] | land not registered in the name of school. |  | 2013-14
135 | USSS-192 (A) | 7949000 | 1289862 | 9238862 | Purnea | PURNEA |  | 1 | M.S. Sanjha Ghat | MD MOJAMMIL HUSSAIN,9939824905 | 443 SBD OF 15-16 (3.03.16) | [11 empty] | 1 |  |  | 2013-14
136 | USSS-192 (B) | 3976884 | 0 | 3976884 | Purnea | PURNEA |  | 1 | M.S.Champawati | MD MOJAMMIL HUSSAIN, 9939824905 | 444 SBD 15-16 (03.03.16) | [10 empty] | 1 |  |  |  | 2013-14
137 | USSS-193-1 | 7949000 | 2113726 | 10062726 | Purnea | PURNEA |  | 1 | I. M. S. Garhi Baluwa | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | 485 SBD OF 14-15 (29.11.14 | [10 empty] | 1 |  |  |  | 2013-14
138 | USSS-194 (A) | 7949000 | 1789525 | 9738525 | Purnea | PURNEA |  | 1 | M.S. Kodheli | KUMAR CHAMAN | [12 empty] | 1 |  |  | 2013-14
139 | USSS-194 (B) | 7949000 | 2819583 | 10768583 | Purnea | PURNEA |  | 1 | M.S. Belgchhi | HARIMOHAN BISHWAS, 9955713757 | 56 SBD OF 15-16 (14.05.15) | [10 empty] | 1 |  |  |  | 2013-14
140 | USSS-194 (C) | 6722495 | 0 | 6722495 | Purnea | PURNEA |  | 1 | M.S. Babhni | HARIMOHAN BISHWAS, 9955713757 | 57 SBD OF 15-16 (14.05.15) | [9 empty] | 1 |  |  |  |  | 2013-14
141 | USSS-200-1 | 7949000 | 3059785 | 11008785 | Tirhut East | SITAMARHI |  | 1 | M.S.Bishanpur | AMRESH KUMAR, 9525120333 | [12 empty] | 1 | Handover |  | 2013-14
142 | USSS-201-1 | 7949000 | 4662015 | 12611015 | Tirhut East | SITAMARHI |  | 1 | M.S. Indarwa-1 | RANJEETPUR CONSTRUCTIONS PRIVATE LIMITED, 9334329734 | [12 empty] | 1 |  |  | 2013-14
143 | USSS-202(A) | 7949000 | 3617395 | 11566395 | Tirhut East | SITAMARHI |  | 1 | M.S.Mahuawa | Sanjeev Sharma | [12 empty] | 1 |  |  | 2013-14
144 | USSS-202(B) | 7949000 | 4603652 | 12552652 | Tirhut East | SITAMARHI |  | 1 | M.S.Ghaghara Bazar | MANOJ KUMAR AZAD,9431636894 | [12 empty] | 1 |  |  | 2013-14
145 | USSS-203(A) | 7949000 | 3796942 | 11745942 | Tirhut East | SITAMARHI |  | 1 | M.S.Banaul | AMRESH KUMAR,9525120333 | [12 empty] | 1 |  |  | 2013-14
146 | USSS-203(B) | 7949000 | 4023539 | 11972539 | Tirhut East | SITAMARHI |  | 1 | M.S.Mahisautha | AKHILESH KUMAR CHAUDHARI, 9431415700 | [12 empty] | 1 |  |  | 2013-14
147 | USSS-212-1 |  | 0 |  | Tirhut East | VAISHALI |  | 1 | Gov.M.S.Baksama | RANA CONSTRUCTION, 9334104328 |  |  |  | 1 | [9 empty] | Land Dispute |  | 2013-14
148 | USSS-213-1 | 7949000 | 2739631 | 10688631 | Tirhut East | VAISHALI |  | 1 | MS Ajijpur Chande | VIPIN KUMAR SAHNI | [12 empty] | 1 |  | 28.02.2016 | 2013-14
149 | USSS-164(A) | 7949000 | 3667510 | 11616510 | Tirhut West | WEST CHAMPARAN | Chanpatia | 1 | UMS Laukaria | MADHU ANAND CONSTRUCTION PVT LTD, 9006671588 | [12 empty] | 1 | Handover |  | 2013-14
150 | USSS-164(B) | 7395551 | 0 | 7395551 | Tirhut West | WEST CHAMPARAN | Chanpatia | 1 | MS Barharawa | Sanjay Kumar Jha | [12 empty] | 1 |  |  | 2013-14
151 | USSS-165-1 | 7949000 | 3106350 | 11055350 | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Kaulapur Bazar | MADHU ANAND CONSTRUCTION PVT LTD, 9006671588 | [12 empty] | 1 | Handover |  | 2013-14
152 | USSS-166-1 | 7949000 | 3718032 | 11667032 | Tirhut West | WEST CHAMPARAN |  | 1 | MS Ojhwalia | IRFAN AKHTAR, 9162628011 | [12 empty] | 1 | Handover |  | 2013-14
153 | USSS-167-1 | 7949000 | 3933056 | 11882056 | Tirhut West | WEST CHAMPARAN |  | 1 | MS Birawa | SHAKAL DEO MISHRA, 9006385958 | [12 empty] | 1 |  |  | 2013-14
154 | USSS-168-1 | 7949000 | 2666091 | 10615091 | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Bathuwaria | SHARDA CHANDEL CONTRACT PVT, 8986283451 | [11 empty] | 1 |  |  |  | 2013-14
155 | USSS-169-1 | 7949000 | 4403393 | 12352393 | Tirhut West | WEST CHAMPARAN |  | 1 | MS Gonauli | AWADHESH SHUKLA, 9431203836 | [12 empty] | 1 | Handover |  | 2013-14
156 | USSS-169-2 | 7949000 | 4403393 | 12352393 | Tirhut West | WEST CHAMPARAN |  | 2 | UMS Jawaharpur | AWADHESH SHUKLA, 9431203836 | [12 empty] | 1 | Handover |  | 2013-14
157 | USSS-170-1 | 7949000 | 3519791 | 11468791 | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Ghagwa Rupahi | SHARDA CHANDEL CONTRACT PVT, 8986283451 | [12 empty] | 1 | Handover |  | 2013-14
158 | USSS-171-1 | 7949000 | 3860772 | 11809772 | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Madhubani | SHARDA CHANDEL CONTRACT PVT,8986283451 | [12 empty] | 1 | Handover |  | 2013-14
159 | USSS-172-1 |  | 0 |  | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Sugha Bhawanipur | MS SARASWATI COMPANY, 9431491241 |  |  |  | 1 | [9 empty] | Not Start. Pending Agreement |  | 2013-14
160 | USSS-173-1 | 7949000 | 3082990 | 11031990 | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Pipra Colony | MS C S CONSTRUCTION, | [12 empty] | 1 |  |  | 2013-14
161 | USSS-173-2 | 7949000 | 1428194 | 9377194 | Tirhut West | WEST CHAMPARAN |  | 2 | MS Semri Dumari | MS C S CONSTRUCTION, | [11 empty] | 1 |  |  |  | 2013-14
162 | USSS-173-3 | 7949000 | 3082990 | 11031990 | Tirhut West | WEST CHAMPARAN |  | 3 | UMS Turkaulia | MS C S CONSTRUCTION, | [12 empty] | 1 |  |  | 2013-14
163 | USSS-174(A) | 7949000 | 4512108 | 12461108 | Tirhut West | WEST CHAMPARAN |  | 1 | UMS Sujnahi Ghorahawa | DHANANJAY KUMAR PANDEY, 9955002717 | [12 empty] | 1 | Handover |  | 2013-14
164 | USSS-174(B) | 7949000 | 2676947 | 10625947 | Tirhut West | WEST CHAMPARAN |  | 2 | UMS Parsauni | SHAKAL DEO MISHRA, 9006385958 | [12 empty] | 1 |  |  | 2013-14
165 | USSS-175-1 | 7949000 | 4723874 | 12672874 | Tirhut West | EAST CHAMPARAN |  | 1 | UMS Pokhariya | RADHIKA CONSTRUCTION CO7739855654, | [12 empty] | 1 |  |  | 2013-14
166 | USSS-176-1 | 7949000 | 2524042 | 10473042 | Tirhut West | EAST CHAMPARAN |  | 1 | GMS Ajgarwa | DESHBANDHU KUMAR SINGH, 7739855654 | [12 empty] | 1 |  |  | 2013-14
167 | USSS-177-1 | 7133172.995 | 0 | 7133172.995 | Tirhut West | EAST CHAMPARAN |  | 1 | GMS Bankatwa (Boys) | MS C S CONSTRUCTION, | [10 empty] | 1 |  |  |  |  | 2013-14
168 | USSS-177-2 | 7133173.995 | 0 | 7133173.995 | Tirhut West | EAST CHAMPARAN |  | 2 | GMS Inarwa Phulwar | MS C S CONSTRUCTION, | [11 empty] | 1 |  |  |  | 2013-14
169 | USSS-178-1 | 6477693 | 0 | 6477693 | Tirhut West | EAST CHAMPARAN |  | 1 | UMS Dharharwa | ANANTA CONSTRUCTION COMPANY, 7739855654 | [11 empty] | 1 |  |  |  | 2013-14
170 | USSS-179-1 | 7949000 | 4556690 | 12505690 | Tirhut West | EAST CHAMPARAN |  | 1 | GMS Tonwa | RADHIKA CONSTRUCTION CO7739855654, | [12 empty] | 1 |  |  | 2013-14
171 | USSS-180-1 | 7949000 | 2606571 | 10555571 | Tirhut West | EAST CHAMPARAN |  | 1 | GMS Murarpur | RAJNISH KUMAR SINGH | [12 empty] | 1 |  |  | 2013-14
172 | USSS-180-2 | 7949000 | 2606571 | 10555571 | Tirhut West | EAST CHAMPARAN |  | 2 | GMS Bhada | RAJNISH KUMAR SINGH | [12 empty] | 1 | Handover |  | 2013-14
173 | USSS-181-1 |  | 0 |  | Tirhut West | EAST CHAMPARAN |  | 1 | UMS Dhekaha Math | Tender Process |  |  | 1 | [10 empty] | Cancel. No Agreement |  | 2013-14
174 | USSS-182-1 | 7874409 | 0 | 7874409 | Tirhut West | EAST CHAMPARAN |  | 1 | GMS Majhar | VIKASH KUMAR GUPTA, 8084876850 | [11 empty] | 1 |  |  |  | 2013-14
175 | USSS-183-1 | 7949000 | 3715575 | 11664575 | Tirhut West | EAST CHAMPARAN |  | 1 | GMS Narha Panapur | DINESH GUPTA, | [12 empty] | 1 | Handover |  | 2013-14
176 | USSS-199-1 | 6896653 | 0 | 6896653 | Tirhut West | SHEOHAR |  | 1 | M/S Shyampur | DIBYESHWAR PRASAD | [10 empty] | 1 |  |  |  |  | 2013-14
177 | USSS-114-1 | 7949000 | 4395207 | 12344207 | Darbhanga | DARBHANGA |  | 1 | U.M.S. Kaji Bahera | SANJAY KUMAR | [12 empty] | 1 |  | 29.1.2016 | 2013-14
178 | USSS-114-2 | 7949000 | 4395207 | 12344207 | Darbhanga | DARBHANGA |  | 2 | M.S. Basant | SANJAY KUMAR | [12 empty] | 1 |  | 29.1.2016 | 2013-14
179 | USSS-115-1 | 7949000 | 1137224 | 9086224 | Darbhanga | DARBHANGA |  | 1 | M.S. Ghosrama | Avinash kumar | [11 empty] | 1 |  |  |  | 2013-14
180 | USSS-116 (A) | 7949000 | 2951158 | 10900158 | Darbhanga | DARBHANGA |  | 1 | M.S. Basatpur | Madhav Construction, Darbhanga | [11 empty] | 1 |  |  |  | 2013-14
181 | USSS-116 (B) | 7949000 | 2190271 | 10139271 | Darbhanga | DARBHANGA |  | 1 | M.S. Dagarsam | Sanjay Kumar | [11 empty] | 1 |  |  |  | 2013-14
182 | USSS-117-1 | 7949000 | 2970227 | 10919227 | Darbhanga | DARBHANGA |  | 1 | M.S. Kankpur | City creation | [12 empty] | 1 |  |  | 2013-14
183 | USSS-118-1 | 2523995 | 0 | 2523995 | Darbhanga | DARBHANGA |  | 1 | U.M.S. Ganaun | City creation | [8 empty] | 1 | [6 empty] | 2013-14
184 | USSS-119(A) | 7949000 | 49424 | 7998424 | Darbhanga | DARBHANGA |  | 1 | M.S. Kahuaa | S K CONSTRUCTION AND COMPANY, 9471006199 | [11 empty] | 1 |  |  |  | 2013-14
185 | USSS-119(B) | 4253388 | 0 | 4253388 | Darbhanga | DARBHANGA |  | 1 | M.S. Tarbara Ganaura | S K CONSTRUCTION AND COMPANY, 9471006199 | [9 empty] | 1 | [5 empty] | 2013-14
186 | USSS-120-1 | 7949000 | 1439153 | 9388153 | Darbhanga | DARBHANGA |  | 1 | U.M.S. Basuara | MALTI SINGH, 9471641892 | [12 empty] | 1 | 15.10.15 |  | 2013-14
187 | USSS-120-2 | 5632892 | 0 | 5632892 | Darbhanga | DARBHANGA |  | 2 | U.M.S. Godhiyari | MALTI SINGH, 9471641892 | [10 empty] | 1 |  |  |  |  | 2013-14
188 | USSS-120-3 | 469407 | 0 | 469407 | Darbhanga | DARBHANGA |  | 3 | U.M.S. Narsara | MALTI SINGH, 9471641892 |  |  |  |  | 1 | [10 empty] | 2013-14
189 | USSS-121-1 | 7949000 | 4935979 | 12884979 | Darbhanga | DARBHANGA |  | 1 | U.M.S. Kathra | City Creation | [11 empty] | 1 |  |  |  | 2013-14
190 | USSS-122-1 |  | 0 |  | Darbhanga | DARBHANGA |  | 1 | M.S Kothram | Om Shree Construction | [7 empty] | 1 | [7 empty] | 2013-14
191 | USSS-156-1 | 7949000 | 2162528 | 10111528 | Darbhanga | MADHUBANI |  | 1 | Middle School Nagwas | Malti Singh, | [12 empty] | 1 |  |  | 2013-14
192 | USSS-157-1 | 7949000 | 4845729 | 12794729 | Darbhanga | MADHUBANI |  | 1 | Middle School Gaudhol | KAMLESH KUMAR, 9334808205 | [12 empty] | 1 |  |  | 2013-14
193 | USSS-158(A) | 5560419 | 0 | 5560419 | Darbhanga | MADHUBANI |  | 1 | Middle School Majhaura | Retender | [10 empty] | 1 |  |  |  |  | 2013-14
194 | USSS-158(B) | 7949000 | 5787522 | 13736522 | Darbhanga | MADHUBANI |  | 1 | Middle School Amhi | Tender Process | [12 empty] | 1 |  |  | 2013-14
195 | USSS-159-1 | 7607556 | 0 | 7607556 | Darbhanga | MADHUBANI |  | 1 | Middle School Gobraura | PRAKRITI CONTRACTORS PVT LTD, 9431440749 | [11 empty] | 1 |  |  |  | 2013-14
196 | USSS-160(A) | 7949000 | 1458118 | 9407118 | Darbhanga | MADHUBANI |  | 1 | Middle School Kurso | MAA VASUNDHARA CONSTRUCTION, 9006650591 | [11 empty] | 1 |  |  |  | 2013-14
197 | USSS-160(B) | 7949000 | 3275618 | 11224618 | Darbhanga | MADHUBANI |  | 1 | UPS Middle School Basipatti | KAMLESH KUMAR, 9334808205 | [11 empty] | 1 |  |  |  | 2013-14
198 | USSS-161(A) | 7949000 | 527239 | 8476239 | Darbhanga | MADHUBANI |  | 1 | Middle School Basuki | SUBODH KUMAR, 9973164105 | [12 empty] | 1 |  |  | 2013-14
199 | USSS-161(B) | 7949000 | 5653876 | 13602876 | Darbhanga | MADHUBANI |  | 1 | Middle School Sujatpur | SATISH KUMAR, 8294867362 | [12 empty] | 1 | 4.1.2016 |  | 2013-14
200 | USSS-161(C) | 7949000 | 5708467 | 13657467 | Darbhanga | MADHUBANI |  | 1 | Middle School Trimuhan | SHASHI KUMAR DEO, 9934640530 | [12 empty] | 1 | 26.4.2016 |  | 2013-14
201 | USSS-198-1 | 7949000 | 2659492 | 10608492 | Darbhanga | SAMASTIPUR |  | 1 | Middle School Pulhara | VAISHALI CONSTRUCTION, 9430483150 | [11 empty] | 1 |  |  |  | 2013-14
Total No. of USSS (2013-14) | [7 empty] | 201 |  |  |  | 3 | 2 | 20 | 2 | 2 | 7 | 3 | 9 | 5 | 13 | 50 | 85
Note on K53: Cancel
Note on K83: Cancel
Note on K106: Cancel

## Sheet2 (hidden)
Row Labels | Completed
ARARIA | 5
BANKA | 15
BHAGALPUR
DARBHANGA | 4
EAST CHAMPARAN | 4
GAYA | 1
JAHANABAD
JAMUI | 3
KATIHAR | 5
KATIHAR | 1
KHAGARIA
KISHANGANJ | 1
LAKHISARAI
MADHEPURA | 1
MADHUBANI | 4
Munger | 2
NAWADA | 3
PURNEA | 4
SAHARSA
SAMASTIPUR
SHEOHAR
SITAMARHI | 5
SUPUAL | 1
VAISHALI
WEST CHAMPARAN | 12
(blank) | 71
Grand Total | 142

## Sheet1 (hidden)
BSEIDC Ltd., Patna
Physical Status of USSS (2013-14)
S.N. | Group No. | Division | Name of District | Name of Schools | Physical Status | Remarks
1 | USSS-163 (B) | Magadh | NAWADA | M.S., Kharsari |  | Land not available
2 | USSS-163 (C ) | Magadh | NAWADA | UPS Mahuliya Tanr |  | Not Start
3 | USSS-112 (C) | Bhagalpur | BANKA | U.M.S Chariya |  | Land Problem
4 | USSS-128-1 | Munger | JAMUI | M S Borwa | FINISH | DIST AREA WORK STOPPED
5 | USSS-151-1 | Munger | LAKHISARAI | U M S Singhaul Tetariaya |  | Land not available
6 | USSS-195-1 | Kosi | SAHARSA | MS Partaha Barhara |  | Not Start
7 | USSS-204-2 | Kosi | SUPUAL | MS Bhawani pur |  | Not Start
8 | USSS-205-1 | Kosi | SUPUAL | MS Bhimpur |  | Land not Available
9 | USSS-208-1 | Kosi | SUPUAL | MS Bela sringarmoti |  | Cancelled
10 | USSS-209-1 | Kosi | SUPUAL | MS Lalganj |  | Cancelled
11 | USSS-210-1 | Kosi | SUPUAL | MS Basbitti |  | Cancelled
12 | USSS-211(A) | Kosi | SUPUAL | Durga MS Laharnia |  | Cancelled
13 | USSS-145-1 | Purnea | KISHANGANJ | M.S Farabari |  | land not available
14 | USSS-145-2 | Purnea | KISHANGANJ | M.S Kuwari | FOUNDATION | work stopped by contractor (during excavation) since long time, letter issued
15 | USSS-146-2 | Purnea | KISHANGANJ | M.S Shitalpur | PLINTH | work stopped by contractor since long time, letter issued
16 | USSS-146-3 | Purnea | KISHANGANJ | U. M.S Kusiyari | PLINTH | work stopped by contractor since long time, letter issued
17 | USSS-148-3 | Purnea | KISHANGANJ | U.M.S Talwarbandha | GF-RL | work stopped by contractor since long time, letter issued
18 | USSS-185-1 | Purnea | PURNEA | M.S. Sirsi |  | old building to be demolished
19 | USSS-191-1 | Purnea | PURNEA | M.S.Bishanpur |  | land not registered in the name of school.
20 | USSS-212-1 | Tirhut East | VAISHALI | Gov.M.S.Baksama |  | Land Dispute
21 | USSS-172-1 | Tirhut West | WEST CHAMPARAN | UMS Sugha Bhawanipur |  | Not Start. Pending Agreement
22 | USSS-181-1 | Tirhut West | EAST CHAMPARAN | UMS Dhekaha Math |  | Cancel. No Agreement