## List of USS
BSEIDC , Patna
Physical Status of USS (Central Fund) - 2009-10 & 2010-11
S.N. | Group No. | Name of District | Name of Block | Name of School | Physical Status | [9 empty] | Remarks | Division | Session
[5 empty] | Not Start | Layout | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[9 empty] | LL | RL | LL | RL | [5 empty] | Group No.
1 | USS-1-1 | Nalanda | p.Mh | eŒfoŒlwedk 9931607862 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-77-2 | Inaugurated
2 | USS-1-2 | Nalanda | bLykeiqj | eŒfoŒenkjxat 9631262679 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-77-3 | Inaugurated
3 | USS-1-3 | Nalanda | fgylk | eŒfoŒvdcjiqj 9470085363 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-77-4 | Inaugurated
4 | USS-1-4 | Nalanda | fcgkj 'kjhQ | eŒfoŒflaxFkq 9204881769 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-78-1 | Inaugurated
5 | USS-2-1 | Nalanda | fxfj;d | eŒfoŒblqvk 9934451313 | 1 | [9 empty] | sufficient land not available, work not possible, Proposal for drop | Patna East | 2009-10 | USS-78-2 | Inaugurated
6 | USS-2-2 | Nalanda | drjhljk; | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-78-3 | Inaugurated
7 | USS-2-3 | Nalanda | jktxhj | eŒfoŒygqvkj 9798642205@9504394778 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-78-4 | Inaugurated
8 | USS-2-4 | Nalanda | flyko | eŒfoŒujgj fcxgk 8002186727 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-79-2 | Inaugurated
9 | USS-2-5 | Nalanda | uwjljk; | eŒfoŒdqUnh 9798241195 | 1 | [9 empty] | sufficient land not available, work not possible, Proposal for drop | Patna East | 2009-10 | USS-79-4 | Inaugurated
10 | USS-3-1 | Patna | ck<+ | eŒfoŒngkSj 8804003367 | 1 | [9 empty] | Project Director Inauguratedstruct to DEO to arrange land with corporation of local public work not possible, Proposal for drop | Patna East | 2009-10 | USS-199 B-1 | Inaugurated
11 | USS-3-2 | Patna | ck<+ | eŒfoŒeqckjdiqj 9631978359 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-199 B-2 | Inaugurated
12 | USS-3-3 | Patna | Qrqgk¡ | eŒfoŒMqejh 8521893444 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-199 B-3 | Inaugurated
13 | USS-3-4 | Patna | Qrqgk¡ | mRØŒeŒfoŒip:f[k;k 9801459905 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-29-1 | Inaugurated
14 | USS-3-5 | Patna | [kq'k:iqj | mRØŒeŒfoŒfueZyhpd 9097610852 | 1 | [9 empty] | sufficient land not available work not possible, proposal for drop | Patna East | 2009-10 | USS-29-4 | Inaugurated
15 | USS-4-1 | Patna | nkukiqj | eŒfoŒvdhyiqj 9835490244 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-30-1 | Inaugurated
16 | USS-4-2 | Patna | ukScriqj | eŒfoŒvgqvkjk 9939680617 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-30-3 | Inaugurated
17 | USS-4-3 | Patna | ikyhxat | eŒfoŒHksM+gfj;k 9199997796 | 1 | [9 empty] | dispute, work not possible, Proposal for drop | Patna East | 2009-10 | USS-30-4 | Inaugurated
18 | USS-5-1 | Patna | /ku:vk | eŒfoŒdkslqr 9973270948@9974270948 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-31-3 | Inaugurated
19 | USS-5-2 | Patna | elkS<+h | eŒfoŒNkrk 8084994281 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-154-1 | Inaugurated
20 | USS-5-3 | Patna | lairpd | eŒfoŒyadk dNqvkjk 9162137790 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-154-2 | Inaugurated
21 | USS-5-4 | Patna | iquiqu | eŒfoŒdY;k.kiqj 9507549063 | [9 empty] | 1 | . | Patna East | 2009-10 | USS-154-4 | Inaugurated
22 | USS-6-1 | Bhojpur | ihjks | eŒfoŒrkj 8969213005 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-154-5 | Inaugurated
23 | USS-6-2 | Bhojpur | ihjks | mRØŒeŒfoŒ nsopUnk 9386992853 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-155-1 | Inaugurated
24 | USS-6-3 | Bhojpur | rjkjh | eŒfoŒ[kqVgk¡ 7631530412 | 1 | [9 empty] | low land available, work not possible | Patna East | 2009-10 | USS-155-2 | Inaugurated
25 | USS-7-1 | Bhojpur | fcfg;k¡ | eŒfoŒ:nzuxj 9308401427 | [8 empty] | 1 |  | Inaugurated. काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-155-4 | Inaugurated
26 | USS-7-2 | Bhojpur | txnh'kiqj | eŒfoŒtaxynkok¡ 9931492812 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-156-3 | Inaugurated
27 | USS-7-3 | Bhojpur | 'kkgiqj | eŒfoŒykyw Msjk 8873932298@9973022234 |  |  |  |  | 1 | [5 empty] | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-84-2 | Inaugurated
28 | USS-8-1 | Bhojpur | vfxvk¡o | eŒfoŒukjk;.kiqj 9852411014 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-84-3 | Inaugurated
29 | USS-8-2 | Bhojpur | cM+gjk | eŒfoŒxqaMh 7739111542 | [6 empty] | 1 |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-84-4 | Inaugurated
30 | USS-8-3 | Bhojpur | mnoUruxj | eŒfoŒds'kksiqj cdjh 9771242640 |  |  | 1 | [7 empty] | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-85-2 | Inaugurated
31 | USS-8-4 | Bhojpur | dksbyoj | mRØŒeŒfoŒ folquiqjk 9334151672 | [8 empty] | 1 |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-86-2 | Inaugurated
32 | USS-101-1 | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-201-4 | Inaugurated | SF
33 | USS-101-2 | Nalanda | Ben | M.S. Akouna 9570951336 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-202-1 | Inaugurated | SF
34 | USS-101-3 | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-202-2 | Inaugurated | SF
35 | USS-101-4 | Nalanda | Silao | Urdu.M.S. Barakar 9931004916 |  |  |  |  | 1 | [5 empty] | Invalid list | Patna East | 2010-11 | USS-202-4 | Inaugurated | SF
36 | USS-101-5 | Nalanda | Ben | M.S. Ramganj 9135849205 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-202-5 | Inaugurated | SF
37 | USS-102-1 | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-203-1 | Inaugurated | SF
38 | USS-102-2 | Nalanda | Biharsarif | M.S. Majidpur 9570625433 | [8 empty] | 1 |  |  | Patna East | 2010-11 | USS-203-2 | Inaugurated | SF
39 | USS-102-3 | Nalanda | Chandi | M.S. Dariya Bigha 9931236900 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11 | USS-203-3 | Inaugurated | SF
40 | USS-102-4 | Nalanda | Chandi | Urdu.M.S. Baisa 9939043903 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11 | USS-203-4 | Inaugurated | SF
41 | USS-102-5 | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 | [9 empty] | 1 | . | Patna East | 2010-11 | USS-207-1 | Inaugurated | SF
42 | USS-102-6 | Nalanda | Sarmera | M.S.Singhaul 9934212058 | [9 empty] | 1 | . | Patna East | 2010-11 | USS-207-2 | Inaugurated | SF
43 | USS-103-1 | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-207-3 | Inaugurated | SF
44 | USS-103-2 | Nalanda | Hilsa | M.S. Rasai Bigha 9934593683 | 1 | [9 empty] | Retender | Patna East | 2010-11 | USS-207-4 | Inaugurated | SF
45 | USS-103-3 | Nalanda | Islampur | M.S. Bargounw 9279149331 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-27-5 | Inaugurated
46 | USS-103-4 | Nalanda | Islampur | M.S. Banbag 9934487509 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-142-2 | Inaugurated
47 | USS-104-1 | Patna | Khushrupur | M.S. Jagmal Bigha 9771442400 | 1 | [9 empty] | Insufficient land | Patna East | 2010-11 | USS-142-3 | Inaugurated
48 | USS-104-2 | Patna | Khushrupur | U.M.S. Arrai Benipur 9135748584 | 1 | [9 empty] | Insufficient land | Patna East | 2010-11 | USS-32-3 | Inaugurated
49 | USS-104-3 | Patna | Barh | U.M.S. Malahi 7250940590 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-32-4 | Inaugurated
50 | USS-104-4 | Patna | Fatuha | M.S. Gabaspur 9955241716 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-1 | Inaugurated
51 | USS-105-1 | Patna | Patna Sadar | M.S. Khokhna 9135334773 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-2 | Inaugurated
52 | USS-105-2 | Patna | Patna Sadar | M.S. Marchi 9430934711 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-3 | Inaugurated
53 | USS-105-3 | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-4 | Inaugurated
54 | USS-105-4 | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-34 A-2 | Inaugurated
55 | USS-106-1 | Patna | Bihta | M.S. Kateshar 7250695245 | 1 | [9 empty] | Low Land about 12'-0", work not possible | Patna East | 2010-11 | USS-34 B-1 | Inaugurated
56 | USS-106-2 | Patna | Bikram | M.S. Barah 8084301353 | 1 | [9 empty] | Land not regitered to school, work not possible | Patna East | 2010-11 | USS-34 A-3 | Inaugurated
57 | USS-106-3 | Patna | Bihta | M.S. Kanhauli 9386873458 | 1 | [9 empty] | Land dispute between School & college, work not possible | Patna East | 2010-11 | USS-34 B-2 | Inaugurated
58 | USS-107-1 | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-151-1 | Inaugurated
59 | USS-108-2 | Bhojpur | Agioan | M.S. Berath 09955434210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-151-2 | Inaugurated
60 | USS-108-3 | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-151-3 | Inaugurated
61 | USS-108-4 | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-152-1 | Inaugurated
62 | USS-108-5 | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 | [9 empty] | 1 |  | Patna East | 2010-11 | USS-152-2 | Inaugurated
63 | USS-108-6 | Bhojpur | Agioan | M.S. Lasarhi 9661399087 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11 | USS-152-5 | Inaugurated
64 | USS-109-1 | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-152-6 | Inaugurated
65 | USS-109-2 | Bhojpur | Garhani | M.S. Kaup 9708602077 | [5 empty] | 1 | [5 empty] | Patna East | 2010-11 | USS-183-1 | Inaugurated
66 | USS-109-3 | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-183-2 | Inaugurated
67 | USS-109-4 | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-183-4 | Inaugurated
68 | USS-109-5 | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-184-1 | Inaugurated
69 | USS-110-1 | Bhojpur | Barhara | U.M.S. Shaligram Singh Ka Tola 8409626973 | [8 empty] | 1 |  | . | Patna East | 2010-11 | USS-184-2 | Inaugurated
70 | USS-110-2 | Bhojpur | Barhara | M.S. Pakri 9304856454 | [7 empty] | 1 |  |  |  | Patna East | 2010-11 | USS-184-3 | Inaugurated
71 | USS-110-3 | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 | [9 empty] | 1 | . | Patna East | 2010-11 | USS-185-1 | Inaugurated
72 | USS-110-4 | Bhojpur | Koilwar | M.S. Khesarhiyan 9973554537 | [5 empty] | 1 | [5 empty] | Patna East | 2010-11 | USS-185-3 | Inaugurated
73 | USS-110-5 | Bhojpur | Koilwar | M.S. Khangaown 9631265664 | [8 empty] | 1 |  | . | Patna East | 2010-11 | USS-186-1 | Inaugurated
74 | USS-111-1 | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-186-2 | Inaugurated
75 | USS-111-2 | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-23-2 | Inaugurated
76 | USS-111-3 | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-143-2 | Inaugurated
77 | USS-111-4 | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-143-4 | Inaugurated
78 | USS-112-1 | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 | [9 empty] | 1 |  | Patna East | 2010-11 | USS-63-2 | Inaugurated
79 | USS-112-2 | Bhojpur | Bihiyan | M.S. Kouriya 9431438960 | [7 empty] | 1 |  |  | Inaugurated | Patna East | 2010-11 | USS-64-1 | Inaugurated
80 | USS-112-3 | Bhojpur | Shahpur | M.S. Jawainiya 8083447757 7677504269 |  |  |  | 1 | [6 empty] | B/W upto RL | Patna East | 2010-11 | USS-64-2 | Inaugurated
81 | USS-112-4 | Bhojpur | Shahpur | M.S. Suhiya 9471919316 | [7 empty] | 1 |  |  |  | Patna East | 2010-11 | USS-64-3 | Inaugurated
82 | USS-113-1 | Bhojpur | Tarari | M.S.Gahruan 9472135231 9162748057 | [8 empty] | 1 |  | RC | Patna East | 2010-11 | USS-65-1 | Inaugurated
83 | USS-113-2 | Bhojpur | Tarari | M.S.Kurmuri 9576176655 | [7 empty] | 1 |  |  | 1st Floor Sill Level | Patna East | 2010-11 | USS-65-2 | Inaugurated
84 | USS-113-3 | Bhojpur | Tarari | M.S. Tarari 9631136009 | [8 empty] | 1 |  | . | Patna East | 2010-11 | USS-65-3 | Inaugurated
85 | USS-113-4 | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-66-2 | Inaugurated
86 | USS-113-5 | Bhojpur | Tarari | M.S.Bagar 9801629878 | [8 empty] | 1 |  | RC | Patna East | 2010-11 | USS-191-3 | Inaugurated
87 | USS-114-1 | Bhojpur | Sandesh | U.M.S.Nasratpur 9334673203 | 1 | [9 empty] | Land Dispute | Patna East | 2010-11 | USS-191-4 | Inaugurated
88 | USS-114-2 | Bhojpur | Sahar | M.S. Baruhi 9199571702 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-191-5 | Inaugurated
89 | USS-114-3 | Bhojpur | Ara | M.S. Basantpur 09308735308 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-193-1 | Inaugurated
90 | USS-114-4 | Bhojpur | Sahar | M.S. Nawada 9934483628 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-193-2 | Inaugurated
91 | USS-9-1 | Buxar | cDlj | eŒfoŒd`riqjk 9576622685 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-193-4 | Inaugurated
92 | USS-9-2 | Buxar | pkSlk | eŒfoŒcukjiqj 8873946373 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-146 (C) | Inaugurated
93 | USS-9-3 | Buxar | jktiqj | eŒfoŒjlsu 9006272320 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-102-1 | Inaugurated
94 | USS-9-4 | Buxar | bVkM+h | eŒfoŒcSdqUBiqj 9931755863 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-3-4 | Inaugurated
95 | USS-10-1 | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-5-2 | Inaugurated
96 | USS-10-2 | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-104-3 | Inaugurated
97 | USS-10-3 | Buxar | czg~eiqj | eŒfoŒegqvkj 7250949713 | 1 | [10 empty] | Patna West | 2009-10 | USS-104-4 | Inaugurated
98 | USS-10-4 | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-1 | Inaugurated
99 | USS-11-1 | Kaimur | dqnjk | eŒfoŒvojS;k 9973613935 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-2 | Inaugurated
100 | USS-11-2 | Kaimur | eksgfu;k¡ | eŒfoŒdVjkdyk 9006263731 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-3 | Inaugurated
101 | USS-11-3 | Kaimur | jkex<+ | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-4 | Inaugurated
102 | USS-11-4 | Kaimur | nqxkZorh | eŒfoŒnqxkZorh 9430340748@9955221828 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-107-1 | Inaugurated
103 | USS-12-1 | Kaimur | HkHkqvk | eŒfoŒdqM+klu 9031437647 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-39-1 | Inaugurated
104 | USS-12-2 | Kaimur | pSuiqj | eŒfoŒdasok 9430026932 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-39-3 | Inaugurated
105 | USS-13-1 | Rohtas | djxgj | eŒfoŒrksjuh 9631253327 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-160-3 | Inaugurated
106 | USS-13-2 | Rohtas | f'kolkxj | eŒfoŒxMqjk 9771022208 | 1 | [9 empty] | Foundation work stopped due to local disturbance (Inaugurated school campus sufficient land available & soil test also done Inaugurated schl. Campus but some local public want to construct this build. Inaugurated other land wich is situated out of campus & no aproach road available & about 800 m(aprox.) away from campus | Patna West | 2009-10 | USS-81-1 | Inaugurated
107 | USS-13-3 | Rohtas | lklkjke | eŒfoŒfldfj;k 9431464894 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-81-2 | Inaugurated
108 | USS-13-4 | Rohtas | dkspl | eŒfoŒegqvkjh 9661222301 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-82-1 | Inaugurated
109 | USS-14-1 | Rohtas | fMgjh | eŒfoŒxaxkSyh 7352200057 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-82-2 | Inaugurated
110 | USS-14-2 | Rohtas | fnukjk | eŒfoŒljuk 9771634397 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-82-4 | Inaugurated
111 | USS-14-3 | Rohtas | dkjkdkV | eŒfoŒeksguiqj 9801296392 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-194-1 | Inaugurated
112 | USS-14-4 | Rohtas | uks[kk | eŒfoŒ?kksjfMgk 9801894133 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-42-4 | Inaugurated
113 | USS-115-1 | Buxar | Buxar | M.S.Nadanw 9234866577 9430015496 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-44-1 | Inaugurated
114 | USS-115-2 | Buxar | Buxar | M.S.Manjharia 9472951603 | 1 | [9 empty] | No Way | Patna West | 2010-11 | USS-44-4 | Inaugurated
115 | USS-115-3 | Buxar | Rajpur | M.S. Khiri 9470753325 | [5 empty] | 1 |  |  |  |  | Sill level of GL | Patna West | 2010-11 | USS-159-4 | Inaugurated
116 | USS-115-4 | Buxar | Rajpur | Urdu M.S. Banni 9973105344 | 1 | [9 empty] | Land not available | Patna West | 2010-11 | USS-9-4 | Inaugurated
117 | USS-116 (A) | Buxar | Dumraon | M.S.Nuaon 9939391144 | [7 empty] | 1 |  |  |  | Patna West | 2010-11 | USS-10-1 | Inaugurated
118 | USS-116 (B) | Buxar | Dumraon | M.S. Kanjharua 9955867071 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-10-2 | Inaugurated
119 | USS-116 (C) | Buxar | Dumraon | M.S. Mathila 9931890937 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-10-4 | Inaugurated
120 | USS-116 (D) | Buxar | Dumraon | M.S. Karuaj 9931281346 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-18-1 | Inaugurated
121 | USS-116 (E) | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-25-2 | Inaugurated
122 | USS-117 (A) | Buxar | Nawanagar | M.S.Pramanpur 9386827434 |  |  | 1 | [8 empty] | Patna West | 2010-11 | USS-139-2 | Inaugurated
123 | USS-117 (B) | Buxar | Ithari | M.S. Barkagaon 8651239720 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-139-3 | Inaugurated
124 | USS-117 (C) | Buxar | Ithari | M.S. Harpur 9939590039 | [11 empty] | Patna West | 2010-11 | USS-139-4 | Inaugurated
125 | USS-117 (D) | Buxar | Ithari | M.S. Basawan Kala 7739120173 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-139-5 | Inaugurated
126 | USS-118-1 | Buxar | Simiri | M.S.Dhanpura 9199795834 | 1 | [10 empty] | Patna West | 2010-11 | USS-140-3 | Inaugurated
127 | USS-118-2 | Buxar | Simiri | M.S. Barka Singhnpura 9934740004 | 1 | [10 empty] | Patna West | 2010-11 | USS-16-1 | Inaugurated
128 | USS-118-3 | Buxar | Simiri | M.S. Kharha Tarnh 9199359782 | 1 | [10 empty] | Patna West | 2010-11 | USS-16-2 | Inaugurated
129 | USS-119 (A) | Kaimur | Bhabhua | M.S.Miun | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-16-3 | Inaugurated
130 | USS-119 (B) | Kaimur | Bhabhua | M.S.Piliyan | [9 empty] | 1 | . | Patna West | 2010-11 | USS-130-1 | Inaugurated
131 | USS-119 (C) | Kaimur | Bhabhua | M.S. Mehsuan | [5 empty] | 1 | [5 empty] | Patna West | 2010-11 | USS-130-2 | Inaugurated
132 | USS-119 (D) | Kaimur | Bhabhua | M.S. Mohan Darwan | [9 empty] | 1 | . | Patna West | 2010-11 | USS-130-3 | Inaugurated
133 | USS-120 (A) | Kaimur | Ramgarh | M.S.Sijhua | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-130-4 | Inaugurated
134 | USS-120 (B) | Kaimur | Ramgarh | M.S.Upari 9939613033 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-130-5 | Inaugurated
135 | USS-120 (C) | Kaimur | Nuaon | Govt. Basic School Kari Ram Akhili | 1 | [9 empty] | Tender Process | Patna West | 2010-11 | USS-127 (C) | Inaugurated
136 | USS-120 (D) | Kaimur | Nuaon | M.S.Mushiyan 9546505256 |  |  |  |  | 1 | [6 empty] | Patna West | 2010-11 | USS-108-2 | Inaugurated
137 | USS-120 (E) | Kaimur | Durgawati | U.M.S Nuaon 9199361709 | [5 empty] | 1 | [5 empty] | Patna West | 2010-11 | USS-108-3 | Inaugurated
138 | USS-121 (A) | Rohtas | Karakat | M.S.Dewmarkande 8969878557 | [8 empty] | 1 |  | Roof slab casted of GF | Patna West | 2010-11 | USS-108-4 | Inaugurated
139 | USS-121 (B) | Rohtas | Karakat | Girl's M.S.Motha 9162106111 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-109-1 | Inaugurated
140 | USS-121 (C) | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-109-3 | Inaugurated
141 | USS-121 (D) | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-109-4 | Inaugurated
142 | USS-121 (E) | Rohtas | Akorhigola | M.S.Chhapra 9934757484 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-109-5 | Inaugurated
143 | USS-122-1 | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-111-1 | Inaugurated
144 | USS-122-2 | Rohtas | Dinara | M.S.Sarwan ,8084920823 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-111-2 | Inaugurated
145 | USS-122-3 | Rohtas | Dinara | M.S. Baliyan, 9931111475 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-111-3 | Inaugurated
146 | USS-122-4 | Rohtas | Dinara | M.S. Bararhi, 9955083783 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-111-4 | Inaugurated
147 | USS-122-5 | Rohtas | Bikramganj | M.S. Jamorhi, 9955952582 | 1 | [10 empty] | Patna West | 2010-11 | USS-112-2 | Inaugurated
148 | USS-122-6 | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-113-4 | Inaugurated
149 | USS-123-1 | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-114-2 | Inaugurated
150 | USS-123-2 | Rohtas | Kochas | M.S. Ubadhi, 8002578689 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-114-3 | Inaugurated
151 | USS-123-3 | Rohtas | Kochas | M.S. Kuchila, 8002537247 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-114-4 | Inaugurated
152 | USS-123-4 | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-219-1 | Inaugurated | SF
153 | USS-123-5 | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-71-2 | Inaugurated
154 | USS-123-6 | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | [9 empty] | 1 | . | Patna West | 2010-11 | USS-71-3 | Inaugurated
155 | USS-124-1 | Rohtas | Chenari | M.S. Ramgarh 9771746971 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-71-4 | Inaugurated
156 | USS-124-2 | Rohtas | Chenari | M.S. Chandrakaithi, 9934281842 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-199 D-2 | Inaugurated
157 | USS-124-3 | Rohtas | Sheosagar | M.S. Alampur, 9572407040 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-135-1 | Inaugurated
158 | USS-124-4 | Rohtas | Sheosagar | M.S. Sonhar 9006103550 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-135-2 | Inaugurated
159 | USS-124-5 | Rohtas | Sasaram | M.S. Akasi , 9204460486 | [8 empty] | 1 |  | . | Patna West | 2010-11 | USS-136-1 | Inaugurated
160 | USS-125-1 | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | [9 empty] | 1 | Inaugurated | Patna West | 2010-11 | USS-136-3 | Inaugurated
161 | USS-28-1 | Jehanabad | tgkukckn | eŒfoŒveSu 9473327625 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-1 | Inaugurated
162 | USS-28-2 | Jehanabad | dkdks | eŒfoŒHknljk 9006927848 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-2 | Inaugurated
163 | USS-28-3 | Jehanabad | e[knqeiqj | eŒfoŒdksgjk 9162155024 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-3 | Inaugurated
164 | USS-28-4 | Jehanabad | jruhQjhniqj | mRØŒeŒfoŒyk[kkiqj 9934235714 | 1 | [10 empty] | Magadh | 2009-10 | USS-137-4 | Inaugurated
165 | USS-29-1 | Aurangabad | nso | eŒfoŒcs<+uh 9631266207 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-5 | Inaugurated
166 | USS-29-2 | Aurangabad | enuiqj | eŒfoŒfijok¡ 9934340488 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-51-3 | Inaugurated
167 | USS-29-3 | Aurangabad | jQhxat | eŒfoŒ[kjks[kj 9006027690 | [8 empty] | 1 |  |  | Magadh | 2009-10 | USS-167-1 | Inaugurated
168 | USS-29-4 | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-2 | Inaugurated
169 | USS-30-1 | Aurangabad | vkscjk | eŒfoŒ'kadjiqj 7739690373 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-3 | Inaugurated
170 | USS-30-2 | Aurangabad | nkmnuxj | eŒfoŒteqvkok¡ 9801563600 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-4 | Inaugurated
171 | USS-30-3 | Aurangabad | nkmnuxj | eŒfoŒpkSjh 9934434990 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-5 | Inaugurated
172 | USS-30-4 | Aurangabad | gliqjk | eŒfoŒdksbyok¡ 9135312996 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-1 | Inaugurated
173 | USS-31-1 | Aurangabad | dqVqEck | eŒfoŒfjfl;i 9955874942 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-2 | Inaugurated
174 | USS-31-2 | Aurangabad | uohuxj | eŒfoŒiM+fj;k 9931622753 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-3 | Inaugurated
175 | USS-31-3 | Aurangabad | ok:.k | eŒfoŒikSFkq 9471060433 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-4 | Inaugurated
176 | USS-32-1 | Gaya | cks/k x;k | eŒfoŒchjgqr 9934480418 | [9 empty] | 1 | . | Magadh | 2009-10 | USS-169-1 | Inaugurated
177 | USS-32-2 | Gaya | uxj fuxe | eŒfoŒpwjh 9199466924 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-2 | Inaugurated
178 | USS-32-3 | Gaya | osykxat | mRØŒeŒfoŒve>j 9931835374 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-3 | Inaugurated
179 | USS-32-4 | Gaya | fVdkjh | eŒfoŒrkik Qrsgiqj 9430070517 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-4 | Inaugurated
180 | USS-33-1 | Gaya | MksHkh | eŒfoŒihjklhu 9473140628 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-5 | Inaugurated
181 | USS-33-2 | Gaya | dksp | eŒfoŒfnX?kh 9576852929 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-170-1 | Inaugurated
182 | USS-33-3 | Gaya | f[ktjljk; | eŒfoŒvkneiqj 9771084118 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-170-5 | Inaugurated
183 | USS-33-4 | Gaya | cthjxat | eŒfoŒikys 9955418354 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-171-1 | Inaugurated
184 | USS-34 A-1 | Gaya | ckjkpV~Vh | mRØŒeŒfoŒ/kuxbZ 9931313425 | 1 | [9 empty] | Approach road unavailable | Magadh | 2009-10 | USS-172-1 | Inaugurated
185 | USS-34 A-2 | Gaya | Qrsgiqj | eŒfoŒckiwxzke 9934840966 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-2 | Inaugurated
186 | USS-34 A-3 | Gaya | eksguiqj | eŒfoŒvedksyk 9955837262 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-3 | Inaugurated
187 | USS-34 B-1 | Gaya | xq:vk | eŒfoŒpk¡lh 9006129640 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-4 | Inaugurated
188 | USS-34 B-2 | Gaya | bekexat | mRØŒeŒfoŒ]dksBh 9931625800 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-5 | Inaugurated
189 | USS-35-1 | Nawada | uoknk | eŒfoŒiVok ljk; 9006212577 | [5 empty] | 1 |  |  |  |  | Inaugurated | Magadh | 2009-10 | USS-13-1 | Inaugurated
190 | USS-35-2 | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 | [9 empty] | 1 |  | Magadh | 2009-10 | USS-14-1 | Inaugurated
191 | USS-35-3 | Nawada | jksg 1 | mRØŒeŒfoŒf'k[kjiqj 9661237533 | [5 empty] | 1 | [5 empty] | Magadh | 2009-10 | USS-125-1 | Inaugurated
192 | USS-35-4 | Nawada | okfjlyhxat | mRØŒeŒfoŒelwnk 9708007113 | [8 empty] | 1 |  | . | Magadh | 2009-10 | USS-52-1 | Inaugurated
193 | USS-36-1 | Nawada | vdcjiqj | eŒfoŒrs;kj | 1 | [9 empty] | Approach road unavailable | Magadh | 2009-10 | USS-53-1 | Inaugurated
194 | USS-36-2 | Nawada | jtkSyh | mRØŒeŒfoŒ]ckjkVk¡M loS;k | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-53-2 | Inaugurated
195 | USS-36-3 | Nawada | fljnyk | eŒfoŒlka< 9771960601 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-53-3 | Inaugurated
196 | USS-143-1 | Jehanabad | Kako | M.S.Kajisarai 9934814478 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-164-1 | Inaugurated
197 | USS-143-2 | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-164-2 | Inaugurated
198 | USS-143-3 | Jehanabad | Kako | M.S.Pinzour 9931803275 | 1 | [9 empty] | Insufficient Land | Magadh | 2010-11 | USS-132-1 | Inaugurated
199 | USS-143-4 | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-132-2 | Inaugurated
200 | USS-144 (A) | Jehanabad | Hulasganj | M.S.Vira, 9771693433 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-132-3 | Inaugurated
201 | USS-144 (B) | Jehanabad | Makhdumpur | M.S.Akbarpur, 9934858600 | 1 | [9 empty] | Tender Process | Magadh | 2010-11 | USS-132-4 | Inaugurated
202 | USS-144 (C) | Jehanabad | Jehanabad | M.S.Bazartali, 9955297199 |  |  |  | 1 | [7 empty] | Magadh | 2010-11 | USS-132-5 | Inaugurated
203 | USS-145-1 | Nawada | Nawada | U.M.S. Jhunathi, 9631172127 | [6 empty] | 1 |  |  |  |  | Magadh | 2010-11 | USS-73-1 | Inaugurated
204 | USS-145-2 | Nawada | Akbarpur | U.M.S. Derma, 9931232692 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-73-2 | Inaugurated
205 | USS-145-3 | Nawada | Akbarpur | M.S. Kuhaila, 9771085197 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-73-3 | Inaugurated
206 | USS-145-4 | Nawada | Akbarpur | M.S. Paharpur, 9771672098 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-72-3 | Inaugurated
207 | USS-145-5 | Nawada | Nawada | M.S. Wermi, 9708857028 | 1 | [9 empty] | Land not available | Magadh | 2010-11 | USS-60-1 | Inaugurated
208 | USS-146 (A) | Nawada | Govindpur | M.S. Rampur, 9771867218 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-60-2 | Inaugurated
209 | USS-146 (B) | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-60-3 | Inaugurated
210 | USS-146 (C) | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-60-4 | Inaugurated
211 | USS-146 (D) | Nawada | Pakribarawan | M.S. Ukaorah | [9 empty] | 1 | . | Magadh | 2010-11 | USS-60-5 | Inaugurated
212 | USS-146 (E) | Nawada | Kashichak | U.M.S. Vishbnathpur , 9386540972 | 1 | [9 empty] | Retender | Magadh | 2010-11 | USS-177-1 | Inaugurated
213 | USS-147-1 | Nawada | Narhat | M.S. Khanwa, 9905846666 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-177-2 | Inaugurated
214 | USS-147-2 | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-177-3 | Inaugurated
215 | USS-148-1 | Gaya | Bodh Gaya | M.S. Moratala, 9934282506 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-178-1 | Inaugurated
216 | USS-148-2 | Gaya | Bodh Gaya | M.S. Titoiya, 9934672899 | 1 | [9 empty] | Land Problem | Magadh | 2010-11 | USS-179-1 | Inaugurated
217 | USS-148-3 | Gaya | Bodh Gaya | M.S. Bataspur, 9470447309 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-179-2 | Inaugurated
218 | USS-148-4 | Gaya | Bodh Gaya | M.S. Gapha Kala, 9934972678 | 1 | [9 empty] | Not start | Magadh | 2010-11 | USS-179-3 | Inaugurated
219 | USS-149 (A) | Gaya | Dumariya | M.S. Bhangiya, 9472443151 9801769544 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-179-4 | Inaugurated
220 | USS-149 (B) | Gaya | Imamganj | M.S. Karsan Kala, 9199768865, 9199061230 | [8 empty] | 1 |  | . | Magadh | 2010-11 | USS-179-5 | Inaugurated
221 | USS-149 (C) | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-181-1 | Inaugurated
222 | USS-149 (D) | Gaya | Imamganj | M.S. Naudiha, 9135294703, 8235212693 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-182-1 | Inaugurated
223 | USS-149 (E) | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-182-2 | Inaugurated
224 | USS-150 (A) | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-182-3 | Inaugurated
225 | USS-150 (B) | Gaya | Tekari | M.S. Urdu Bishnupur, 9771128251, 9135850031 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-174-1 | Inaugurated
226 | USS-150 (C) | Gaya | Konch | M.S. Goribigha, 9939408167 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-174-3 | Inaugurated
227 | USS-150 (D) | Gaya | Konch | M.S. Ahiyarpur, 9934008030 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-174-4 | Inaugurated
228 | USS-151-1 | Gaya | Bathani | Basic M.S. Radui, 7654409634 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-175-2 | Inaugurated
229 | USS-151-2 | Gaya | Bathani | M.S. Karubigha, 9934427661 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-175-3 | Inaugurated
230 | USS-151-3 | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-175-4 | Inaugurated
231 | USS-152-1 | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-176-1 | Inaugurated
232 | USS-152-2 | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-176-2 | Inaugurated
233 | USS-152-3 | Gaya | Fatehpur | M.S. Khajuri, 8969107991 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-176-3 | Inaugurated
234 | USS-152-4 | Gaya | Fatehpur | M.S. Nagwa, 9798270089 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-212-1 | Inaugurated | SF
235 | USS-152-5 | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-173 (B) | Inaugurated
236 | USS-152-6 | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-46-3 | Inaugurated
237 | USS-153 (A) | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-46-4 | Inaugurated
238 | USS-153 (B) | Gaya | Guraru | M.S. Manjhar, 9572789270 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-47-1 | Inaugurated
239 | USS-153 (C) | Gaya | Amas | M.S. Baliyari, 9570551566, 8294856371, 8051934469 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-47-3 | Inaugurated
240 | USS-153 (D) | Gaya | Sherghatty | M.S. Naknuppa, 9431289085 | 1 | [9 empty] | Land not available | Magadh | 2010-11 | USS-47-4 | Inaugurated
241 | USS-154-1 | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-47-5 | Inaugurated
242 | USS-154-2 | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-162 (B) | Inaugurated
243 | USS-154-3 | Aurangabad | Kutumba | M.S. Darmi, 9955519885, 9931921788 | 1 | [9 empty] | Land not available | Magadh | 2010-11 | USS-162 (C) | Inaugurated
244 | USS-154-4 | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-163 (B) | Inaugurated
245 | USS-154-5 | Aurangabad | Deo | M.S. Vijouli, 9801123435 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-163 (C) | Inaugurated
246 | USS-155-1 | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-75-1 | Inaugurated
247 | USS-155-2 | Aurangabad | Obra | M.S. Ratwar, 9931418907 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-75-2 | Inaugurated
248 | USS-155-3 | Aurangabad | Obra | M.S. Tejpur, 9973299799 | 1 | [9 empty] | Land not available | Magadh | 2010-11 | USS-75-3 | Inaugurated
249 | USS-155-4 | Aurangabad | Obra | M.S. Karsawan, 9470488343 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-76-3 | Inaugurated
250 | USS-156-1 | Aurangabad | Haspura | M.S. Piru, 9135064392 | 1 | [9 empty] | Land Encrochment | Magadh | 2010-11 | USS-76-4 | Inaugurated
251 | USS-156-2 | Aurangabad | Haspura | M.S. Sriwanbhatt, 9939023445 | 1 | [9 empty] | Land not available | Magadh | 2010-11 | USS-77-1 | Ing
252 | USS-156-3 | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-79-1 | Ing
253 | USS-157 (A) | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-29-2 | Ing
254 | USS-157 (B) | Aurangabad | Raphiganj | M.S. Pogar, 9973150471 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-30-2 | Ing
255 | USS-157 (C) | Aurangabad | Madanpur | M.S. Judahi, 9931892284 | [9 empty] | 1 | . | Magadh | 2010-11 | USS-31-1 | Ing
256 | USS-157 (D) | Aurangabad | Madanpur | M.S. Saliya, 9955803641 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-31-2 | Ing
257 | USS-157 (E) | Aurangabad | Raphiganj | M.S. Danai, 9097351245 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-80-1 | Ing
258 | USS-20-1 | Munger | gosyh [kM+xiqj | eŒfoŒj?kqukFkiqj | 1 | [9 empty] | Land Problem | Munger | 2009-10 | USS-80-2 | Ing
259 | USS-20-2 | Munger | eqaxsj lnj | eŒfoŒVhdkjkeiqj 9431612789 | 1 | [9 empty] | Land Problem | Munger | 2009-10 | USS-80-3 | Ing
260 | USS-20-3 | Munger | /kjgjk | eŒfoŒegjuk 9504681361@9852445511 | [6 empty] | 1 |  |  |  |  | Munger | 2009-10 | USS-80-4 | Ing
261 | USS-21-1 | Sheikhpura | 'ks[kiqjk | eŒfoŒckn'kkgiqj 9709066149 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-80-5 | Ing
262 | USS-22-1 | Jamui | pdkbZ | eŒfoŒnqyeiqj 9973390953@9661984491 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-201 | Ing | SF
263 | USS-22-2 | Jamui | >k>k | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-201 | Ing | SF
264 | USS-22-3 | Jamui | lksuks | eŒfoŒiSjk efVgkuk 9801576608 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-201 | Ing | SF
265 | USS-23-1 | Jamui | teqbZ | mRØŒeŒfoŒ HkkVpd 9430818763 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-1 | Ing
266 | USS-23-2 | Jamui | y{ehiqj | eŒfoŒgjyk 9162733763@9006655639 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-2 | In
267 | USS-23-3 | Jamui | [kSjk | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-3 | Ing
268 | USS-23-4 | Jamui | bZŒ vyhxat | eŒfoŒfetkZxat 8292659272 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-4 | Ing
269 | USS-24-1 | Begusarai | cNokM+k | eŒfoŒQrsg 9570919206 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-32-2 | Ing
270 | USS-24-2 | Begusarai | Hkxokuiqj | eŒfoŒeksf[r;kjiqj 9934441250 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-55-1 | Ing
271 | USS-24-3 | Begusarai | psfj;k cfj;kjiqj | eŒfoŒldjoklk 9939576953 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-55-2 | Ing
272 | USS-25-1 | Begusarai | cfy;k | eŒfoŒelwnuiqj 9955252445 | [5 empty] | 1 |  |  |  |  | Roof Casted | Munger | 2009-10 | USS-55-3 | Ing
273 | USS-25-2 | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-55-4 | Ing
274 | USS-25-3 | Begusarai | lkgsciqj deky | eŒfoŒfo".kqiqj vkgksd 9534757293 | 1 | [9 empty] | Objection due to Mukhiya | Munger | 2009-10 | USS-56-1 | Ing
275 | USS-26-1 | Begusarai | cjkSuh | eŒfoŒcFkkSyh 9801572247@9534334080 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-56-2 | Ing
276 | USS-26-2 | Begusarai | efVgkuh | eŒfoŒtxriqjk 9939465778 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-56-3 | Ing
277 | USS-27-1 | Khagaria | ijoÙkk | eŒfoŒdjuk 9939629342@9006237936 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-56-4 | Ing
278 | USS-27-2 | Khagaria | vykSyh | eŒfoŒes?kkSuk 9534870633 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-184-1 | Ing
279 | USS-27-3 | Khagaria | pkSFke | eŒfoŒigkM+pd 9431651745 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-184-2 | Ing
280 | USS-27-4 | Khagaria | xksxjh | eŒfoŒidjSy 9955068112 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-22-1 | Ing
281 | USS-27-5 | Khagaria | [kxfM+;k | eŒfoŒeksjdkgh Fkkuk 9534404397 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-22-2 | Ing
282 | USS-132-1 | Sheikhpura | Barbigha | M.S.Keuti | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-22-3 | Ing
283 | USS-132-2 | Sheikhpura | SheKhpura | M.S.Lodipur | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-23-1 | Ing
284 | USS-132-3 | Sheikhpura | Chewara | M.S.Lahana | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-23-3 | Ing
285 | USS-132-4 | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-23-4 | Ing
286 | USS-132-5 | Sheikhpura | Ariari | M.S.Husainawad | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-28-1 | Ing
287 | USS-133(A) | Lakhisarai | Barahiya | M.S.Pali 9546977875 | [9 empty] | 1 | . | Munger | 2010-11 | USS-28-2 | Ing
288 | USS-133(B) | Lakhisarai | Barahiya | M.S.Lal Diyara 9097688412 | 1 | [9 empty] | Not start | Munger | 2010-11 | USS-28-3 | Ing
289 | USS-133(C) | Lakhisarai | Halsi | M.S. Geruapursanda 8084044144 | 1 | [9 empty] | Not start | Munger | 2010-11 | USS-143-1 | Ing
290 | USS-133(D) | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 | [9 empty] | 1 | . | Munger | 2010-11 | USS-63-1 | Ing
291 | USS-133(E) | Lakhisarai | Suryagarha | U.M.S. Lahasaurwa 9631695175, 8434346388 | [5 empty] | 1 | [5 empty] | Munger | 2010-11 | USS-63-3 | Ing
292 | USS-133(F) | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | [9 empty] | 1 | . | Munger | 2010-11 | USS-66-1 | Ing
293 | USS-134-1 | Jamui | Sono | M.S.Buijhayt 09631584296 |  |  |  |  | 1 | [6 empty] | Munger | 2010-11 | USS-66-3 | Ing
294 | USS-135-1 | Munger | Asarganj | M.S.Chakhand 9135065232 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-35-1 | Ing
295 | USS-135-2 | Munger | Asarganj | M.S. Beran 9204931976 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-36-2 | Ing
296 | USS-135-3 | Munger | Tarapur | M.S. Mahamadpur 9709507263 | [7 empty] | 1 |  |  |  | Munger | 2010-11 | USS-36-3 | Ing
297 | USS-136-1 | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-1-1 | Ing
298 | USS-136-2 | Munger | Sangrampur | M.S.Khapra 9934832035 | 1 | [9 empty] | Land not available | Munger | 2010-11 | USS-1-2 | Ing
299 | USS-136-3 | Munger | Sangrampur | M.S.Katiyari 9199782900 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-1-3 | Ing
300 | USS-137-1 | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-1-4 | Ing
301 | USS-137-2 | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-2-2 | Ing
302 | USS-137-3 | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-2-3 | Ing
303 | USS-137-4 | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-2-4 | Ing
304 | USS-137-5 | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-101-1 | Ing
305 | USS-138-1 | Begusarai | Mansurchak | M.S.Chhabilapur 9771848155 | 1 | [9 empty] | Land not available | Munger | 2010-11 | USS-101-2 | Ing
306 | USS-138-2 | Begusarai | Begusarai | M.S.Bharra 9204202640 | [8 empty] | 1 |  |  | Munger | 2010-11 | USS-101-3 | Ing
307 | USS-138-3 | Begusarai | Begusarai | M.S.Babasudebpur 9934708295, 88777402400 |  |  | 1 | [8 empty] | Munger | 2010-11 | USS-101-5 | Ing
308 | USS-138-4 | Begusarai | Matihani | M.S.Richiyahi Nayartol 9973647476, 9608273410 | [5 empty] | 1 | [5 empty] | Munger | 2010-11 | USS-103-1 | Ing
309 | USS-138-5 | Begusarai | Sahebpur Kamal | M.S.Rajoura 9709067460 | 1 | [9 empty] | Land not available | Munger | 2010-11 | USS-103-3 | Ing
310 | USS-139-1 | Begusarai | Bachhawara | M.S.Dadupur 9801471859 | [8 empty] | 1 |  |  | Munger | 2010-11 | USS-103-4 | Ing
311 | USS-139-2 | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-3-2 | Ing
312 | USS-139-3 | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-3-3 | Ing
313 | USS-139-4 | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-4-1 | Ing
314 | USS-139-5 | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-4-2 | Ing
315 | USS-140-1 | Begusarai | Garhpura | M.S.Kuddhar 9955509070 | [9 empty] | 1 |  | Munger | 2010-11 | USS-5-1 | Ing
316 | USS-140-2 | Begusarai | Dandari | M.S.Katarmala 9709640304 | [9 empty] | 1 |  | Munger | 2010-11 | USS-5-3 | Ing
317 | USS-140-3 | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-37-1 | Ing
318 | USS-141 (A) | Khagaria | Alauli | M.S.Shumbha Ghat 8969741611 |  |  |  |  | 1 | [6 empty] | Munger | 2010-11 | USS-37-2 | Ing
319 | USS-141 (B) | Khagaria | Alauli | M.S.Khairi Khutaha 9471283095 | [7 empty] | 1 |  |  |  | Munger | 2010-11 | USS-37-3 | Ing
320 | USS-141 (C) | Khagaria | Khagaria | M.S.Nanku Mandal Tola 9955646986 |  |  | 1 | [8 empty] | Munger | 2010-11 | USS-37-4 | Ing
321 | USS-141 (D) | Khagaria | Khagaria | M.S.Mathar 9771388437 | [9 empty] | 1 | . | Munger | 2010-11 | USS-38-1 | Ing
322 | USS-142-1 | Khagaria | Beldaur | M.S.Kainjari 7549429234 |  |  | 1 | [7 empty] | Land Dispute | Munger | 2010-11 | USS-38-2 | Ing
323 | USS-142-2 | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-38-3 | Ing
324 | USS-142-3 | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-38-4 | Ing
325 | USS-15-1 | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-81-3 | Ing
326 | USS-15-2 | Bhagalpur | Sultanganj | MS Udadih 9801583582 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-42-1 | Ing
327 | USS-15-3 | Bhagalpur | NathNagar | MS Ajmeribariya 8969037136 | [5 empty] | 1 |  |  |  |  | Ground Floor R.Casted (Stopped From March-14) | Bhagalpur | 2009-10 | USS-42-2 | Ing
328 | USS-15-4 | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-42-3 | Ing
329 | USS-16-1 | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-44-3 | Ing
330 | USS-16-2 | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-44-5 | Ing
331 | USS-16-3 | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-9-1 | Ing
332 | USS-16-4 | Bhagalpur | Goradih | MS Garhotiya 9931865594 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-9-2 | Ing
333 | USS-17-1 | Bhagalpur | Sabaur | MS Shivaydih 9973394344 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-9-3 | Ing
334 | USS-17-2 | Bhagalpur | Kharik | MS Dadpur 8051625862/ 2 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-18-2 | Ing
335 | USS-17-3 | Bhagalpur | Bihpur | MS Kaharour 9934602158 | 1 | [10 empty] | Bhagalpur | 2009-10 | USS-18-3 | Ing
336 | USS-17-4 | Bhagalpur | Ismailpur | MS Laxmipur 9546492998 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-18-4 | Ing
337 | USS-18-1 | Banka | Barahat | MS Saharna 9431689507/ | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-19-1 | Ing
338 | USS-18-2 | Banka | Bounsi | MS Bishanpur 9006554728 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-24-1 | Ing
339 | USS-18-3 | Banka | Dhouriya | MS Bhatuachak 9955916141 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-24-2 | Ing
340 | USS-18-4 | Banka | Rajoun | MS Majhgay 9771243197 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-24-3 | Ing
341 | USS-19-1 | Banka | Amarpur | MS Bhadariya 9939749402 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-26-1 | Ing
342 | USS-19-2 | Banka | Chandan | UMS Asudha-Mukunda 9199722081 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-26-2 | Ing
343 | USS-19-3 | Banka | Katoriya | MS Bhorsar 9304136524 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-11-1 | Ing
344 | USS-19-4 | Banka | Belhar | UMS Nagel 9934928705 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-11-2 | Ing
345 | USS-19-5 | Banka | Shambhuganj | MS Rajghat 9199067916 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-11-3 | Ing
346 | USS-126 (A) | Bhagalpur | Kahalgaon | M.S.Basudeopur Bhaluya 9801295281 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11 | USS-11-4 | Ing
347 | USS-126 (B) | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-12-1 | Ing
348 | USS-126 (C) | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-12-2 | Ing
349 | USS-126 (D) | Bhagalpur | Kahalgaon | M.S. Saur 9430428851 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-15-1 | Ing
350 | USS-127 (A) | Bhagalpur | Pirpainti | M.S.Mahuadhih 9955027709, 7549131650 | 1 | [9 empty] | LAND PROBLEM | Bhagalpur | 2010-11 | USS-15-2 | Ing
351 | USS-127 (B) | Bhagalpur | Pirpainti | M.S. Maultola, 9534766339 | 1 | [9 empty] | LAND PROBLEM | Bhagalpur | 2010-11 | USS-15-4 | Ing
352 | USS-127 (C) | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-16-4 | Ing
353 | USS-127 (D) | Bhagalpur | Pirpainti | M.S.Ekchari Diyara 9507752647, 9934426205 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11 | USS-17-1 | Ing
354 | USS-127 (E) | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | [9 empty] | 1 | . | Bhagalpur | 2010-11 | USS-17-2 | Ing
355 | USS-128 (A) | Bhagalpur | Goradih | M.S.Birnaugha 9955198006 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-17-4 | Ing
356 | USS-128 (B) | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | [9 empty] | 1 | . | Bhagalpur | 2010-11 | USS-7-1 | Ing
357 | USS-128 (C) | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | [9 empty] | 1 | . | Bhagalpur | 2010-11 | USS-61-1 | Ing
358 | USS-128 (D) | Bhagalpur | Sabaur | Govt. M.S.Kurpat 9204660635, 9931729153 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11 | USS-61-2 | Ing
359 | USS-129 (A) | Bhagalpur | Rangrachauk | M.S.Murli 9534523062 | 1 | [9 empty] | Land Dispute | Bhagalpur | 2010-11 | USS-61-3 | Ing
360 | USS-129 (B) | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | [9 empty] | 1 | . | Bhagalpur | 2010-11 | USS-62-1 | Ing
361 | USS-130-1 | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-62-2 | Ing
362 | USS-130-2 | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-62-3 | Ing
363 | USS-130-3 | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-48-1 | Ing
364 | USS-130-4 | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-48-2 | Ing
365 | USS-130-5 | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-48-3 | Ing
366 | USS-131-1 | Banka | Amarpur | M.S.Surihari 9931727384 | [7 empty] | 1 |  |  | Shuttering in Progress | Bhagalpur | 2010-11 | USS-48-4 | Ing
367 | USS-131-2 | Banka | Belhar | M.S.Hatiyadadha 8521126388 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-49-2 | Ing
368 | USS-131-3 | Banka | Dhoraiya | U.M.S.Jharkha 9934883358 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-49-3 | Ing
369 | USS-71-1 | Madhepura | Madhepura | M/S Bharahi Bazar 9852057904 | 1 | [9 empty] | Land Dispute | Kosi | 2009-10 | USS-51-1 | Ing
370 | USS-71-2 | Madhepura | Murliganj | M/S Parsha Navtol 9973625392 | [9 empty] | 1 | Inaugurated. | Kosi | 2009-10 | USS-51-2 | Ing
371 | USS-71-3 | Madhepura | Kumarkhand | M/S Karuvaili 9771194253 | [9 empty] | 1 | Inaugurated. | Kosi | 2009-10 | USS-13-3 | Ing
372 | USS-71-4 | Madhepura | Sigheshwar | M/S Singyon 9430633497 | [9 empty] | 1 | Inaugurated. | Kosi | 2009-10 | USS-13-4 | Ing
373 | USS-72-1 | Madhepura | Uda kishunganj | M/S Barataini 9631850096 | [9 empty] | 1 | . | Kosi | 2009-10 | USS-14-2 | Ing
374 | USS-72-2 | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | [9 empty] | 1 | . | Kosi | 2009-10 | USS-14-3 | Ing
375 | USS-72-3 | Madhepura | Alamnagar | M/S Bargaon 9939489984 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-14-4 | Ing
376 | USS-73-1 | Saharsa | Saur Bazar | M/S Khajuri 9472653157 9430632563 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-52-2 | Ing
377 | USS-73-2 | Saharsa | Navhatta | M/S Kedalpatti 9939942137 8987203752 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-52-3 | Ing
378 | USS-73-3 | Saharsa | Sonbarsa | M/S Pachlakh 7549317375 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-52-4 | Ing
379 | USS-74-1 | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | [9 empty] | 1 | . | Kosi | 2009-10 | USS-53-4 | Ing
380 | USS-74-2 | Saharsa | Simri Bakhtiyarpur | M/S Ghoghsam 9471654377 |  |  |  | 1 | [6 empty] | Work Stopped | Kosi | 2009-10 | USS-54-2 | Ing
381 | USS-74-3 | Saharsa | Mahishi | M/S Jhara 9430696742 | [9 empty] | 1 | . | Kosi | 2009-10 | USS-220 | Ing
382 | USS-75-1 | Supaul | Basantpur | M/S Balbhadrapur 9472034607 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-21-1 | Ing
383 | USS-75-2 | Supaul | Chatapur | M/S Madhubani 9631295927 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-67-2 | Ing
384 | USS-75-3 | Supaul | Marauna | M/S Parikoch 9931662963 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-67-3 | Ing
385 | USS-75-4 | Supaul | Raghopur | Lakhi Chand Sahu M/S Hariraha 9470047275 | [9 empty] | 1 | HANDOVER | Kosi | 2009-10 | USS-67-4 | Ing
386 | USS-76-1 | Supaul | Kishanpur | M/S Phulwaria 8298274284 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-67-5 | Ing
387 | USS-76-2 | Supaul | Pipra | M/S Ramnagar 9472335572 9570603091 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-68-1 | Ing
388 | USS-76-3 | Supaul | Supaul | M/S Kariho 9430029088 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-68-2 | Ing
389 | USS-76-4 | Supaul | Triveniganj | M/S Kumiyahi 8986062906 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-68-3 | Ing
390 | USS-199C | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | [9 empty] | 1 | . | Kosi | 2010-11 | USS-68-4 | Ing
391 | USS-199D-1 | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | [9 empty] | 1 | . | Kosi | 2010-11 | USS-68-5 | Ing
392 | USS-199 D-2 | Madhepura | Singheshwar | Middle School Barhari 9661376885 | [9 empty] | 1 | Inaugurated | Kosi | 2010-11 | USS-68-6 | Ing
393 | USS-199D-3 | Madhepura | Kumarkhand | Middle School Rahta 9631460084 | 1 | [9 empty] | Land not available | Kosi | 2010-11 | USS-69-1 | Ing
394 | USS-77-1 | Araria | Hkjxkek | mRØŒeŒfoŒjgfM+;k 9534388120 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-69-2 | Ing
395 | USS-77-2 | Araria | jkuhxat | ckfydk eŒfoŒxq.korh 9771105449 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-69-3 | Ing
396 | USS-77-3 | Araria | jkuhxat | eŒfoŒijekuaniqj 9631149958 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-69-4 | Ing
397 | USS-77-4 | Araria | ujirxat | eŒfoŒuksfu;k Vksyk pdyk 9973417759 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-70-1 | Ing
398 | USS-78-1 | Araria | Qkjfclxat | eŒfoŒe/kqcuh 9661601762 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-70-2 | Ing
399 | USS-78-2 | Araria | Qkjfclxat | eŒfoŒVs<+h eqlgjh 9801199615 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-1 | Ing
400 | USS-78-3 | Araria | vjfj;k | eŒfoŒiSdVksyk 9431087519@9431471118 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-2 | Ing
401 | USS-78-4 | Araria | vjfj;k | eŒfoŒck¡lckM+h 9430264342 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-3 | Ing
402 | USS-79-1 | Araria | dqlkZdk¡Vk | eŒfoŒdikjQksM+k 9931414194 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-4 | Ing
403 | USS-79-2 | Araria | fldVh | eŒfoŒlksgkxekM+ksa 9661752676@9006316855 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-1 | Ing
404 | USS-79-3 | Araria | tksdhgkV | eŒfoŒHkwuk 9570679546 | 1 | [9 empty] | May be Drop | Purnea | 2009-10 | USS-58-2 | Ing
405 | USS-79-4 | Araria | iyklh | eŒfoŒ:iSy e/kSy 9771866133 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-3 | Ing
406 | USS-80-1 | Kishanganj | fnX?kycSad | eŒfoŒgjokMaxk 8987208103 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-4 | Ing
407 | USS-80-2 | Kishanganj | Bkdqjxat | eŒfoŒtaxyHkhVk 8987254242 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-5 | Ing
408 | USS-80-3 | Kishanganj | dksapk/kkeu | eŒfoŒ/kuiqjk 9470868499 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-47-2 | Ing
409 | USS-80-4 | Kishanganj | iksfB;k | eŒfoŒgfjiks[kj ØkafrxkN 9430677962 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-75 | Ing
410 | USS-80-5 | Kishanganj | cgknqjxat | eŒfoŒgfjHkk"kk 9471834254 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-76-1 | Ing
411 | USS-81-1 | Purnea | dsŒ uxj | vkn'kZ eŒfoŒijksjk 9631003614 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-76-2 | Ing
412 | USS-81-2 | Purnea | dlok | mRØŒ eŒ foŒ dnok 9006717685@9162698638 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 |  |  | 18
413 | USS-81-3 | Purnea | Mx:vk | eŒfoŒeksgEeniqj 8877902279@9852305617 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
414 | USS-82-1 | Purnea | /kenkgk | vkn'kZ eŒfoŒfo'kuiqj 8002692294 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
415 | USS-82-2 | Purnea | Hkokuhiqj | eŒfoŒczãKkuh 9931249419 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
416 | USS-82-3 | Purnea | :ikSyh | eŒfoŒykyxat 9934565697 | [9 empty] | 1 | . | Purnea | 2009-10
417 | USS-82-4 | Purnea | cueu[kh | eŒfoŒtkudh uxj gkV 9430675018 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
418 | USS-83-1 | Purnea | ok;lh | eŒfoŒvkltk ecS;k 9931676786 | 1 | [9 empty] | Avaibility Of land after one year,Contractor not Inauguratedtrested Inaugurated work now. | Purnea | 2009-10
419 | USS-83-2 | Purnea | vekSj | eŒfoŒePNÍk 9470487168@9934622591 | 1 | [10 empty] | Purnea | 2009-10
420 | USS-83-3 | Purnea | oSlk | eŒfoŒekyksikM+k 9939083102 | 1 | [10 empty] | Purnea | 2009-10
421 | USS-84-1 | Katihar | cyjkeiqj | eŒfoŒ>y>yh 9434962404@8986444230 | 1 | [9 empty] | No Land, Proposal for Drop | Purnea | 2009-10
422 | USS-84-2 | Katihar | ckjlksbZ | eŒ foŒ clyxkao 9126846409 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
423 | USS-84-3 | Katihar | ckjlksbZ | eŒ foŒ <ëk 9471674809 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
424 | USS-84-4 | Katihar | vkteuxj | eŒ foŒ tydh 9470423557@ 8877799621 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
425 | USS-85-1 | Katihar | cjkjh | eŒfoŒcfd;k lq[kk; 9572154446 | 1 | [9 empty] | Land not available(E.E letter No.-731/14-15 Dt.28.10.14 | Purnea | 2009-10
426 | USS-85-2 | Katihar | efugkjh | eŒfoŒiVuh ukjk;.kiqj 9430970158 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
427 | USS-85-3 | Katihar | Qydk | eŒfoŒ>x:pd 0431668067 | [9 empty] | 1 |  | Purnea | 2009-10
428 | USS-85-4 | Katihar | dks<+k | eŒfoŒf'kf'k;k 9431625914@ 0430582029 | [9 empty] | 1 |  | Purnea | 2009-10
429 | USS-86-1 | Katihar | venkckn | eŒfoŒfnYyh fnokuxat 9431667161@7631741488 | 1 | [9 empty] | May be Drop | Purnea | 2009-10
430 | USS-86-2 | Katihar | dnok | eŒfoŒvk'k;kuh 8986509086 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
431 | USS-86-3 | Katihar | dnok | eŒfoŒpkSdh 9470208190 | 1 | [9 empty] | May be Drop | Purnea | 2009-10
432 | USS-194-1 | Purnea | Amaur | U. M. S. Bagdar 9939096309 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
433 | USS-194-2 | Purnea | K. Nagar | M S Gauasi 9473124829 | [9 empty] | 1 | . | Purnea | 2010-11
434 | USS-194-3 | Purnea | Purnia East | M S Maranga 9939732346 | [9 empty] | 1 | . | Purnea | 2010-11
435 | USS-194-4 | Purnea | Rupauli | M. S. Bairiya 9434821065 | [9 empty] | 1 | . | Purnea | 2010-11
436 | USS-195-1 | Katihar | Amdabad | M. S. Laxmipur Daiwa 7549854721 | [5 empty] | 1 | [5 empty] | Purnea | 2010-11
437 | USS-195-2 | Katihar | Manihari | Middle School Mirjapur 8084519254 941640318 | 1 | [10 empty] | Purnea | 2010-11
438 | USS-195-3 | Katihar | Mansahi | Middle School Mohanpur 9472890120 |  |  |  | 1 | [7 empty] | Purnea | 2010-11
439 | USS-196(A) | Katihar | Pranpur | Middle School Kast Hawar 8809776384 9162325809 |  |  |  | 1 | [7 empty] | Purnea | 2010-11
440 | USS-196(B) | Katihar | Ajamnagar | Middle School Arihana 8809322797 | [9 empty] | 1 | . | Purnea | 2010-11
441 | USS-196(C) | Katihar | Ajamnagar | Middle School Dhena Baghchhala 9801372634 | [8 empty] | 1 |  |  | Purnea | 2010-11
442 | USS-196(D) | Katihar | Pranpur | Middle School Ghanhar Vighocha 9939688768 | [8 empty] | 1 |  |  | Purnea | 2010-11
443 | USS-197(A) | Katihar | Barsoi | Middle School Barsoi Ghat 9431626189 | [7 empty] | 1 |  |  |  | Purnea | 2010-11
444 | USS-197(B) | Katihar | Dhankhora | Middle School Durgasthan Dhankhora9431869787 | 1 | [9 empty] | Land not available | Purnea | 2010-11
445 | USS-197(C) | Katihar | Kodha | Middle School Marwa Najrachowki 9006363823 | [8 empty] | 1 |  |  | Purnea | 2010-11
446 | USS-197(D) | Katihar | Kadwa | Dukhi Ram Middle School Chandpur9709755452 | [8 empty] | 1 |  | . | Purnea | 2010-11
447 | USS-198-1 | Katihar | Brari | Middle School Laxmipur | 1 | [9 empty] | Tender Process | Purnea | 2010-11
448 | USS-198-2 | Katihar | Brari | Middle School Anarkali | 1 | [9 empty] | Tender Process | Purnea | 2010-11
449 | USS-198-3 | Katihar | Hasanganj | Middle School Hasanganj | 1 | [9 empty] | Tender Process | Purnea | 2010-11
450 | USS-198-4 | Katihar | Phalka | Middle School Morsanda | [7 empty] | 1 |  |  |  | Purnea | 2010-11
451 | USS-198-5 | Katihar | Sameli | Middle School Dumar | [7 empty] | 1 |  |  |  | Purnea | 2010-11
452 | USS-199A (A) | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 | [9 empty] | 1 | . | Purnea | 2010-11
453 | USS-199A (B) | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 | [9 empty] | 1 | . | Purnea | 2010-11
454 | USS-199A (C) | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 | [9 empty] | 1 | . | Purnea | 2010-11
455 | USS-199A (D) | Araria | Narpatganj | Middle School Achra 9801296055 | [9 empty] | 1 | . | Purnea | 2010-11
456 | USS-199 B-1 | Araria | Jokihat | Middle School Jhanpur 9471219710 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
457 | USS-199 B-2 | Araria | Raniganj | Middle School Kosikapur 9199673607 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
458 | USS-199 B-3 | Araria | Araria | Middle School Araria Basti 9661185784 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
459 | USS-46-1 | Sheohar | rfj;kuh | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | [9 empty] | 1 | . | Tirhut East | 2009-10
460 | USS-46-2 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] cyqvk 9771099254 | [9 empty] | 1 | . | Tirhut East | 2009-10
461 | USS-46-3 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] FkqEek 9472379528 | [9 empty] | 1 |  | Tirhut East | 2009-10
462 | USS-46-4 | Sitamarhi | csylaM | eŒ foŒ] ipukSj | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
463 | USS-47-1 | Sitamarhi | jhxk | eŒ foŒ] ;ksxokuk 9534893264 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10 | 157
464 | USS-47-2 | Sitamarhi | cFkukgk | eŒ foŒ] fMgBh 9973981418 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
465 | USS-47-3 | Sitamarhi | ukuiqj | eŒ foŒ] cÙkjk 9931668054 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
466 | USS-47-4 | Sitamarhi | ukuiqj | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
467 | USS-47-5 | Sitamarhi | lksucjlk | eŒ foŒ] bVgjok 9546578977 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
468 | USS-48-1 | Muzaffarpur | vkSjkbZ | eŒ foŒ] cSaxuk 7209905677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
469 | USS-48-2 | Muzaffarpur | ckspgk¡ | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
470 | USS-48-3 | Muzaffarpur | xk; ?kkV | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
471 | USS-48-4 | Muzaffarpur | dVjk | eŒ foŒ] cq/kdkjk 9934016332 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
472 | USS-49-1 | Muzaffarpur | dkaVh | eŒ foŒJ`axkj 8809637605 | 1 | [10 empty] | Tirhut East | 2009-10
473 | USS-49-2 | Muzaffarpur | eM+ou | eŒ foŒ] jsiqjk 8252129824 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
474 | USS-49-3 | Muzaffarpur | ehukiqj | eŒ foŒ] tkfeu efB;k 9934619525 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
475 | USS-50-1 | Muzaffarpur | ik: | eŒ foŒ] HkkstiV~Vh 9931888752 |  |  |  |  | 1 | [6 empty] | Tirhut East | 2009-10
476 | USS-50-2 | Muzaffarpur | ik: | eŒ foŒ] pkaniqj 9801265669 |  |  |  |  | 1 | [6 empty] | Tirhut East | 2009-10
477 | USS-50-3 | Muzaffarpur | lkgscxat | eŒ foŒ] 'kkgiqj iV~Vh 9801128043 |  |  |  |  | 1 | [6 empty] | Tirhut East | 2009-10
478 | USS-50-4 | Muzaffarpur | ljS;k | eŒ foŒ] xksjhxkekMhg 9431615151 | [5 empty] | 1 | [5 empty] | Tirhut East | 2009-10
479 | USS-51-1 | Muzaffarpur | ldjk | eŒ foŒ] ckth cqtqxZ 9572907300 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
480 | USS-51-2 | Muzaffarpur | eq'kgjh | eŒ foŒ] fn?kM+k 9430051489@9304110351 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
481 | USS-51-3 | Muzaffarpur | eksrhiqj | eŒ foŒ] ckjthMhg 9934895236 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
482 | USS-52-1 | Vaishali | lgnsbZ cqtqxZ | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
483 | USS-52-2 | Vaishali | egukj | eŒ foŒ deyk dU;k] djukSrh 8002747546 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
484 | USS-52-3 | Vaishali | tUnkgk | eŒ foŒ] jlqyiqj 8651291731 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
485 | USS-52-4 | Vaishali | fonqiqj | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
486 | USS-53-1 | Vaishali | gkthiqj | eŒ foŒ] yksek 9470638549 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
487 | USS-53-2 | Vaishali | gkthiqj | eŒ foŒ] dqrqciqj 9905099533 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
488 | USS-53-3 | Vaishali | ykyxat | eŒ foŒ] xqjfe;k 8651626851 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
489 | USS-53-4 | Vaishali | xksjkSy | eŒ foŒ] Bhdgk¡ 9431254109 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
490 | USS-54-1 | Vaishali | jktkikdj | eŒ foŒ] csydqaMk 7677785326 | 1 | [9 empty] | Land Dispute | Tirhut East | 2009-10
491 | USS-54-2 | Vaishali | ikrsiqj | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
492 | USS-54-3 | Vaishali | jk?kksiqj | eŒ foŒ] ohjiqj 9931458401 | [9 empty] | 1 |  | Tirhut East | 2009-10
493 | USS-162 (A) | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | [9 empty] | 1 | handover | Tirhut East | 2010-11
494 | USS-162 (B) | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
495 | USS-162 (C) | Sitamarhi | Suppi | M. S. Aktha 9470821881 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
496 | USS-162 (D) | Sitamarhi | Riga | M. S. Ramnagara 9570781314 |  |  | 1 | [8 empty] | Tirhut East | 2010-11
497 | USS-162 (E) | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 | [9 empty] | 1 | . | Tirhut East | 2010-11
498 | USS-162 (F) | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 | [9 empty] | 1 | . | Tirhut East | 2010-11
499 | USS-163 (A) | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 | [9 empty] | 1 | . | Tirhut East | 2010-11
500 | USS-163 (B) | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
501 | USS-163 (C) | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
502 | USS-163 (D) | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 | [9 empty] | 1 | . | Tirhut East | 2010-11
503 | USS-164-1 | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
504 | USS-164-2 | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
505 | USS-164-3 | Vaishali | Bhagwanpur | M. S. Askaranpur | [9 empty] | 1 |  | Tirhut East | 2010-11
506 | USS-164-4 | Vaishali | Bhagwanpur | M. S. Kutubpur 9534509369 | 1 | [9 empty] | Land Dispute | Tirhut East | 2010-11
507 | USS-164-5 | Vaishali | Lalganj | U.M.S. Basanta 9934417163 | 1 | [9 empty] | Land Dispute | Tirhut East | 2010-11
508 | USS-165-1 | Vaishali | Jandaha | U. M.S. Shahpur Rohuya 9934414222 | [7 empty] | 1 |  |  |  | Tirhut East | 2010-11
509 | USS-165-2 | Vaishali | Jandaha | M. S, Mahhisaur 9661844106 | [5 empty] | 1 | [5 empty] | Tirhut East | 2010-11
510 | USS-165-3 | Vaishali | Sahadei Bujurg | M.S, Toimath 9939693675 | [7 empty] | 1 |  |  |  | Tirhut East | 2010-11
511 | USS-165-4 | Vaishali | Sahadei Bujurg | M.S, Nayaganj 9934912623 | 1 | [10 empty] | Tirhut East | 2010-11
512 | USS-165-5 | Vaishali | Jandaha | M.S, Bijrauti 9973922533 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
513 | USS-166 (A) | Vaishali | Raghopur | M. S,Tersiya 9631970772 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
514 | USS-166 (B) | Vaishali | Raghopur | M.S,Paharpur 7654539556 | [9 empty] | 1 | . | Tirhut East | 2010-11
515 | USS-166 (C) | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 | [9 empty] | 1 |  | Tirhut East | 2010-11
516 | USS-166 (D) | Vaishali | Desari | M. S, Bhikhanpura 9973319373 |  |  |  | 1 | [7 empty] | Tirhut East | 2010-11
517 | USS-166 (E) | Vaishali | Rajapakar | M. S, Makhadumpur Pokhraira 9934478747 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
518 | USS-167-1 | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
519 | USS-167-2 | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
520 | USS-167-3 | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
521 | USS-167-4 | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
522 | USS-167-5 | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
523 | USS-168-1 | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
524 | USS-168-2 | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
525 | USS-168-3 | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
526 | USS-168-4 | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
527 | USS-169-1 | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
528 | USS-169-2 | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
529 | USS-169-3 | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
530 | USS-169-4 | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
531 | USS-169-5 | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
532 | USS-170-1 | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
533 | USS-170-2 | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 | [9 empty] | 1 | . | Tirhut East | 2010-11
534 | USS-170-3 | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 | [9 empty] | 1 | . | Tirhut East | 2010-11
535 | USS-170-4 | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | [9 empty] | 1 | . | Tirhut East | 2010-11
536 | USS-170-5 | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
537 | USS-171-1 | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
538 | USS-171-2 | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 | [9 empty] | 1 | . | Tirhut East | 2010-11
539 | USS-171-3 | Muzaffarpur | Gaighat | M. S,Dahila 9973658759 | [8 empty] | 1 |  | . | Tirhut East | 2010-11
540 | USS-171-4 | Muzaffarpur | Katra | M. S, Bakhari 9631173639 | [9 empty] | 1 | . | Tirhut East | 2010-11
541 | USS-171-5 | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | [8 empty] | 1 |  | . | Tirhut East | 2010-11
542 | USS-172-1 | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
543 | USS-172-2 | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
544 | USS-172-3 | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
545 | USS-172-4 | Muzaffarpur | Mushhari | M. S, Dronpur | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
546 | USS-172-5 | Muzaffarpur | Muraul | M. S, Pilkhi | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
547 | USS-37-1 | West Champaran | Manjhauliya | M.S.Aharwar Shekh 9470655463 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
548 | USS-37-2 | West Champaran | Manjhauliya | M.S. Parsa Bahuarwa 9470859628 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
549 | USS-37-3 | West Champaran | Bairiya | M.S. Bathna 9431466192 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
550 | USS-37-4 | West Champaran | Nautan | M.S. Mangalpur 9430691686 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
551 | USS-38-1 | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
552 | USS-38-2 | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
553 | USS-38-3 | West Champaran | Lauriya | M.S.Dhobani 9430571439 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
554 | USS-38-4 | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
555 | USS-39-1 | West Champaran | Mainatand | M.S. Tajpur 8986956152 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
556 | USS-39-2 | West Champaran | Mainatand | M.S. Sukhlahi 9546120109 | [8 empty] | 1 |  |  | Tirhut West | 2009-10
557 | USS-39-3 | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
558 | USS-40-1 | West Champaran | Narkatiaganj | M.S. Shomgarh 9470256119 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
559 | USS-40-2 | West Champaran | Yogapatti | M.S. Kohra 9934686513 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
560 | USS-40-3 | West Champaran | Ramnagar | M.S. Sher Hawa Don 9470860764 |  |  |  | 1 | [7 empty] | Tirhut West | 2009-10
561 | USS-41-1 | East Champaran | Motihari | M.S. Jamla 9934828027 | [8 empty] | 1 |  |  | Tirhut West | 2009-10
562 | USS-41-2 | East Champaran | Banjariya | M.S. Kukurjari 9708975580 | [6 empty] | 1 |  |  |  |  | Tirhut West | 2009-10
563 | USS-41-3 | East Champaran | Turkauliya | M.S. Vishnupurwa 9801485906 | [8 empty] | 1 |  |  | Tirhut West | 2009-10
564 | USS-41-4 | East Champaran | Chiraiya | M.S. Parewa 9386155278 |  |  |  |  | 1 | [6 empty] | Tirhut West | 2009-10
565 | USS-42-1 | East Champaran | Areraj | M.S. Radhiya 9576399366 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
566 | USS-42-2 | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
567 | USS-42-3 | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
568 | USS-42-4 | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
569 | USS-43-1 | East Champaran | Raxaul | M.S. Gonha 9470284937 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
570 | USS-43-2 | East Champaran | Sugauli | M.S. Muswa 9471878742 | [6 empty] | 1 |  |  |  |  | Tirhut West | 2009-10
571 | USS-43-3 | East Champaran | Aadapur | M.S. Beldarwa 9771769291 / 9472911484 |  |  |  |  | 1 | [6 empty] | Tirhut West | 2009-10
572 | USS-43-4 | East Champaran | Chhauradano | M.S. Pakariya Urdu 9470233197 | 1 | [9 empty] | Land not available | Tirhut West | 2009-10
573 | USS-44-1 | East Champaran | Chakiya | M.S. Chintamanpur 9546123872 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
574 | USS-44-2 | East Champaran | kalyanpur | M.S. Mandhwa Urdu 9939516692 | 1 | [9 empty] | Land not available | Tirhut West | 2009-10
575 | USS-44-3 | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
576 | USS-44-4 | East Champaran | Mehshi | M.S. Jhitkahiya 9162250321 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
577 | USS-44-5 | East Champaran | Paharpur | M.S. Siswa Bazar 8809296371 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
578 | USS-45-1 | East Champaran | Dhaka | M.S. Chandanbara Urdu 9931213480 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
579 | USS-45-2 | East Champaran | Patahi | M.S. Betauna 9708717133 |  |  |  |  | 1 | [6 empty] | Tirhut West | 2009-10
580 | USS-45-3 | East Champaran | Madhuban | M.S. Gurmiya |  |  |  | 1 | [7 empty] | Tirhut West | 2009-10
581 | USS-45-4 | East Champaran | Ghorasahan | M.S. Laxmipur Laukhan 9431652891 | [7 empty] | 1 |  |  |  | Tirhut West | 2009-10
582 | USS-158-1 | East Champaran | Turkauliya | M.S. Belwa Ray 9430645457 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
583 | USS-158-2 | East Champaran | Turkauliya | M.S. Jaishinghpur 9430209305 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
584 | USS-158-3 | East Champaran | Motihari | M.S. Basantpur 9576483588 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
585 | USS-159-1 | East Champaran | Pakridayal | M.S. Sishani 9934715029 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
586 | USS-159-2 | East Champaran | chaaiya | M.S. Madhubani 9430565177 | 1 | [9 empty] | Land not available | Tirhut West | 2010-11
587 | USS-159-3 | East Champaran | Tetariya | M.S. Maniyarpur 9471297810 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
588 | USS-159-4 | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
589 | USS-159-5 | East Champaran | Ghorasahan | M.S. Samanpur 9939403946 | [5 empty] | 1 | [5 empty] | Tirhut West | 2010-11
590 | USS-160-1 | West Champaran | Lauriya | Govt.M.S. Phulwariya 9431674559 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
591 | USS-160-2 | West Champaran | Narkatiyaganj | Govt.M.S. Bhadiharwa 8986137181 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
592 | USS-160-3 | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
593 | USS-160-4 | West Champaran | Madhubani | M.S.Pakri Ahawa Khothwa 08002571785 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
594 | USS-160-5 | West Champaran | Nautan | M.S.Sansariya 8757124792 | 1 | [10 empty] | Tirhut West | 2010-11
595 | USS-161-1 | Sheohar | Purnhiya | M.S.Basant Jagivan 9430526421 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
596 | USS-161-2 | Sheohar | Dumri Katsari | M.S.Phulkaha 9631003475 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
597 | USS-61-1 | Madhubani | ?kks?kjMhgk | eŒ foŒ] xax}kj 9934407620 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
598 | USS-61-2 | Madhubani | >a>kjiqj | eŒ foŒ]ykSguk 9430835195 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
599 | USS-61-3 | Madhubani | ykSdgh | eŒ foŒ] dyqvkgh 9572025500 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
600 | USS-62-1 | Madhubani | t;uxj | eŒ foŒflyukFk cjgh 9572618953 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
601 | USS-62-2 | Madhubani | i.MkSy | eŒ foŒ] 'kkgiqj 9973048002 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
602 | USS-62-3 | Madhubani | jktuxj | eŒ foŒ] eaxjkSuh 9931643145 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
603 | USS-63-1 | Darbhanga | guqeku uxj | eŒfoŒ]Fkyokjk 9771791978 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
604 | USS-63-2 | Darbhanga | cgsM+h | eŒfoŒ fctqfy;k 9939521323 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
605 | USS-63-3 | Darbhanga | cgknqjiqj | mRØŒeŒfoŒ dejkSyh 9801391631 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
606 | USS-64-1 | Darbhanga | ?ku';keiqj | eŒfoŒ]rqekSy 9939754496 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
607 | USS-64-2 | Darbhanga | csuhiqj | mRØŒeŒfoŒ jf<+;ke 9770623526 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
608 | USS-64-3 | Darbhanga | euhxkNh | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
609 | USS-64-4 | Darbhanga | rkjMhg | mRØŒeŒfoŒ rkjMhg 9934870957 | 1 | [9 empty] | Land not available | Darbhanga | 2009-10
610 | USS-65-1 | Darbhanga | dq'ks'oj LFkku iwŒ | mRØŒeŒfoŒ egknso eB 9973391579 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
611 | USS-65-2 | Darbhanga | dq'ks'oj LFkku iŒ | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
612 | USS-65-3 | Darbhanga | fojkSy | eŒfoŒ]iVfu;k¡ 9771113614 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
613 | USS-66-1 | Darbhanga | fal?kokM+k | mRØŒeŒfoŒ e/kqiqj 9934911481 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
614 | USS-66-2 | Darbhanga | dsoVh | eŒfoŒ]dks;yk LFkku 9905459110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
615 | USS-66-3 | Darbhanga | njHkaxk xzkeh.k | mRØŒeŒfoŒ cygk 9570479967 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
616 | USS-67-1 | Samastipur | iVksjh | eŒfoŒ]njok 8757084952 | 1 | [9 empty] | Land not available | Darbhanga | 2009-10
617 | USS-67-2 | Samastipur | nyflag ljk; | eŒfoŒ]ekyiqj 9934140121 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
618 | USS-67-3 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]fcUn ckspgk 9939988449 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
619 | USS-67-4 | Samastipur | fo¦kifr uxj | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
620 | USS-67-5 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]efu;kj 7549600801 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
621 | USS-68-1 | Samastipur | foHkwfriqj | eŒfoŒ]nsljh 9939816100 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
622 | USS-68-2 | Samastipur | fcFkku | eŒfoŒ]NsNuh 9934979521 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
623 | USS-68-3 | Samastipur | gluiqj | mRØŒeŒfoŒ egqyh 9801690551 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
624 | USS-68-4 | Samastipur | f'kokth uxj | eŒfoŒ]Jhiqjetjfg;k 9955507715 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
625 | USS-68-5 | Samastipur | foHkwfriqj | eŒfoŒ]irSfy;k 9973163333 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
626 | USS-68-6 | Samastipur | f'kokth uxj | eŒfoŒ]jkuhiêh 9955989162 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
627 | USS-69-1 | Samastipur | dY;k.kiqj | eŒfoŒ]eksjokjk 9162249115 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
628 | USS-69-2 | Samastipur | leLrhiqj | eŒfoŒ][kksM+h 9263781760 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
629 | USS-69-3 | Samastipur | mft;kiqj | eŒfoŒ]vaxkj ?kkV 9204971619 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
630 | USS-69-4 | Samastipur | mft;kiqj | eŒfoŒdksjc)k] irSyh 9263731315 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
631 | USS-70-1 | Samastipur | eksjok | eŒfoŒ iq:"kksreiqj 9973123260 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
632 | USS-70-2 | Samastipur | iwlk | eŒfoŒ]efYydkSj | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
633 | USS-187-1 | Madhubani | Babu Barhi | M. S. Barhara | [8 empty] | 1 |  |  | Darbhanga | 2010-11
634 | USS-187-2 | Madhubani | Lakhanpur | M. S. Belaucha | 1 | [9 empty] | Insufficient Land. (required land 68'x67' avlaible land20'x15') | Darbhanga | 2010-11
635 | USS-187-3 | Madhubani | Jaynagar | Middle School, Dhaniyapatti 9931037199 9661794550 | 1 | [9 empty] | Insufficient Land. (required land 68'x67' avlaible land17'x15') | Darbhanga | 2010-11
636 | USS-187-4 | Madhubani | Rajnagar | Govt. M S, Kewalpatti 9430032594 8051418065 | [7 empty] | 1 |  |  |  | Darbhanga | 2010-11
637 | USS-187-5 | Madhubani | Khutauna | Middle School, Malin Belha 9572178379 | [8 empty] | 1 |  |  | Darbhanga | 2010-11
638 | USS-188-1 | Madhubani | Banipatti | M. S.Ganguli 9431629001 | 1 | [9 empty] | AGREEMENT NOT DONE (CONTRACTOR REFUSED) | Darbhanga | 2010-11
639 | USS-188-2 | Madhubani | Kaluahi | M. S.Kalikapur 9973900631 | 1 | [10 empty] | Darbhanga | 2010-11
640 | USS-188-3 | Madhubani | Bisfi | M. S.Singhaso 9162249674 8051935537 | 1 | [10 empty] | Darbhanga | 2010-11
641 | USS-189-1 | Samastipur | Shivajinagar | M. S. Shripur Bhataura | [6 empty] | 1 |  |  |  |  | Darbhanga | 2010-11
642 | USS-189-2 | Samastipur | Vibhutipur | U. M. S, Mustafapur | 1 | [9 empty] | Low land more than 15' | Darbhanga | 2010-11
643 | USS-190-1 | Darbhanga | Kusheshwarsthan E | U. M. S, Barniya 7870017996 | [5 empty] | 1 | [5 empty] | Darbhanga | 2010-11
644 | USS-190-2 | Darbhanga | Kusheshwarsthan W | U. M. S, Sihariya 8969431987 | [5 empty] | 1 | [5 empty] | Darbhanga | 2010-11
645 | USS-191-1 | Darbhanga | Manigachhi | U. M. S, Dahaura 9431405480 | 1 | [9 empty] | required land 68'x67' avlaible land27'x25' | Darbhanga | 2010-11
646 | USS-191-2 | Darbhanga | Kewati | M. S, Koila Majhigama 9304020023 | 1 | [9 empty] | LAND DISPUTE | Darbhanga | 2010-11
647 | USS-191-3 | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
648 | USS-191-4 | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
649 | USS-191-5 | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
650 | USS-192 A | Darbhanga | Bahadurpur | M. S, Daing 9199229540 | [8 empty] | 1 |  |  | Darbhanga | 2010-11
651 | USS-192 B | Darbhanga | Biraul | M. S, Koilajan 9939650547 | [6 empty] | 1 |  |  |  |  | Darbhanga | 2010-11
652 | USS-192 C | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 | [9 empty] | 1 | . | Darbhanga | 2010-11
653 | USS-192 D | Darbhanga | Biraul | U. M. S, Balha 7631905606 | [9 empty] | 1 | . | Darbhanga | 2010-11
654 | USS-193-1 | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
655 | USS-193-2 | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
656 | USS-193-3 | Darbhanga | Alinagar | U. M. S, Rampur Uday 9546520079 | 1 | [9 empty] | required land 68'x67' avlaible land16'x14' | Darbhanga | 2010-11
657 | USS-193-4 | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
658 | USS-55-1 | Gopalganj | Baikunthapur | M. School, Deokulli, Mob.: 9708861129 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
659 | USS-55-2 | Gopalganj | Baikunthapur | M. School, Maharani, Mob.:9199443900 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
660 | USS-55-3 | Gopalganj | Kuchayakot | M. School, Mahuaba, Hindi, Mob.: 9430055420/9162622220 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
661 | USS-55-4 | Gopalganj | Singhawalia | U. M. School, Dumaria East, Mob.: 9955648224 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
662 | USS-56-1 | Gopalganj | Bhore | M. School, Shivarajpur, Mob.: 9973200939 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
663 | USS-56-2 | Gopalganj | Kattaya | M. School, Rudrapur, Mob.: 9628550100 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
664 | USS-56-3 | Gopalganj | Kuchayakot | M. School, Purkhaus, Mob.: 9955647418 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
665 | USS-56-4 | Gopalganj | Vijayipur | M. School, Mathaulli, Mob.: 9838674751 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
666 | USS-57-1 | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
667 | USS-57-2 | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
668 | USS-57-3 | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
669 | USS-57-4 | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
670 | USS-58-1 | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
671 | USS-58-2 | Siwan | Guddhani | U. M. School, Bangardha, Mob.: 9801180809 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
672 | USS-58-3 | Siwan | Daraulli | M. School, Dumarhar Bujurga, Mob.: 9199854822 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
673 | USS-58-4 | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
674 | USS-58-5 | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
675 | USS-59-1 | Saran | Masharrakha | M. School, Dum Dumma, Mob.: 9006658111 | [6 empty] | 1 |  |  |  |  | Saran | 2009-10
676 | USS-59-2 | Saran | Panapur | U. M. School, Panapur, Mob.: 9199453564 | [5 empty] | 1 | [5 empty] | Saran | 2009-10
677 | USS-59-3 | Saran | Tarraiyan | M. School, Parauna Balak, Mob.: 9931139238 | [7 empty] | 1 |  |  |  | Saran | 2009-10
678 | USS-59-4 | Saran | Jalalpur | M. School, Nawadah, Mob.: 9431630231 | [7 empty] | 1 |  |  |  | Saran | 2009-10
679 | USS-60-1 | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
680 | USS-60-2 | Saran | Manjhi | M. School, Dumari, Mob.: 8083701946/8757054210 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
681 | USS-60-3 | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
682 | USS-60-4 | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
683 | USS-60-5 | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
684 | USS-173 (A) | Siwan | Husainganj | M. S, Hata Tola Chhata 9546660912 |  |  |  | 1 | [6 empty] | Land not available | Saran | 2010-11
685 | USS-173 (B) | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
686 | USS-174-1 | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
687 | USS-174-2 | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 | [9 empty] | 1 |  | Saran | 2010-11
688 | USS-174-3 | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
689 | USS-174-4 | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
690 | USS-175-1 | Siwan | Siswan | M. S, Gyaspur 8809341191 | [9 empty] | 1 | Hand Over | Saran | 2010-11
691 | USS-175-2 | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
692 | USS-175-3 | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
693 | USS-175-4 | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
694 | USS-176-1 | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
695 | USS-176-2 | Siwan | Gudhani | M. S, Belauri 8809165382 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
696 | USS-176-3 | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
697 | USS-177-1 | Saran | Dariyapur | Middle School, Saraiya 9431647901 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
698 | USS-177-2 | Saran | Dariyapur | Middle School, Bhongha 9006298659 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
699 | USS-177-3 | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
700 | USS-177-4 | Saran | Dighwara | Middle School, Malkhachak 9135336330 |  | 1 | [9 empty] | Saran | 2010-11
701 | USS-178-1 | Saran | Sonpur | Middle School, Shikharpur 9631221348 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
702 | USS-179-1 | Saran | Lahaladpur | Middle School, Basahi Urdu | [9 empty] | 1 | Inaugurated | Saran | 2010-11
703 | USS-179-2 | Saran | Ekma | Middle School, Bhodasa | [9 empty] | 1 | Inaugurated | Saran | 2010-11
704 | USS-179-3 | Saran | Ekma | Middle School, Betbaniya 8294839353 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
705 | USS-179-4 | Saran | Ekma | Middle School, Eksar 9572740280 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
706 | USS-179-5 | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
707 | USS-181-1 | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
708 | USS-182-1 | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
709 | USS-182-2 | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
710 | USS-182-3 | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
711 | USS-183-1 | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
712 | USS-183-2 | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
713 | USS-183-3 | Gopalganj | Kuchaikot | Middle School, Balthari 9973181137 | 1 | [9 empty] | Low Land | Saran | 2010-11
714 | USS-183-4 | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
715 | USS-184-1 | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
716 | USS-184-2 | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
717 | USS-184-3 | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
718 | USS-184-4 | Gopalganj | Singhwaliya | Middle School, Amarpura Jagiraha 9801115115 | 1 | [9 empty] | Land Not Available | Saran | 2010-11
719 | USS-185-1 | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
720 | USS-185-2 | Gopalganj | Gopalganj | Middle School, Karariya 9934499260 | 1 | [9 empty] | Land Problem | Saran | 2010-11
721 | USS-185-3 | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
722 | USS-185-4 | Gopalganj | Gopalganj | Middle School, Baraipatti 9955771721 | 1 | [9 empty] | Land Problem | Saran | 2010-11
723 | USS-186-1 | Gopalganj | Hathua | U. M. S, Satai 8757888461 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
724 | USS-186-2 | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
725 | USS-186-3 | Gopalganj | Hathua | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 | 1 | [9 empty] | Land not available | Saran | 2010-11
726 | USS-186-4 | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 | [9 empty] | 1 |  | Saran | 2010-11
| Total No. of Schools-RMSA (USS) |  |  | 726 | 91 | 1 | 6 | 9 | 11 | 33 | 8 | 20 | 77 | 469
Note on P49: Group will closed due dely in land availability.
Note on U62: accord. To div. USS-34-B-2 instead of USS-34-5
Note on B64: ACCORD. TO 475 USS-108-1
Note on U141: Author:
Note on W228: ACCORD. TO DIV. USS-182-2
Note on U229: ACCORD. TO DIV. USS-182-3 INSTEAD OF uss-182-5
Note on E355: Gurudev Const.
Note on E358: Gurudev Const.
Note on U372: according to div. USS-49-1 instead of USS-49-2 & 3
Note on B720: List from 161 & 250 ing list

## Sheet2
Division | (All)
Values
Row Labels | Complete | Layout | Foundation | Plinth | GF-LL | GF-RL | FF-LL | FF-RL | Finishing | Not Start
Araria | 17 | [7 empty] | 1 | 1
Aurangabad | 20 |  |  |  |  | 1 |  | 2 | 1 | 4
Banka | 5 | [6 empty] | 2 | 5
Begusarai | 13 |  |  |  | 1 | 1 |  |  | 2 | 4
Bhagalpur | 19 |  | 1 |  |  | 3 |  |  | 4 | 5
Bhojpur | 19 |  |  | 1 | 1 | 6 | 2 | 4 | 6 | 3
Buxar | 7 |  | 1 |  |  | 2 |  |  | 8 | 6
Darbhanga | 20 |  |  |  |  | 2 | 2 |  |  | 4
East Champaran | 9 |  |  | 1 | 3 | 3 | 2 | 2 | 6 | 3
Gaya | 19 | 1 | 1 |  |  | 3 |  | 5 | 7 | 3
Gopalganj | 19 | [8 empty] | 5
Jamui | 7 |  |  | 1
Jehanabad | 6 |  | 1 | [5 empty] | 1 | 3
Kaimur | 6 |  | 1 |  | 1 | 1 |  |  | 5 | 1
Katihar | 7 |  | 2 | 1 | 1 | 1 |  | 1 | 3 | 11
Khagaria | 8 |  | 2 | [6 empty] | 2
Kishanganj | 5
Lakhisarai | 2 | [7 empty] | 1 | 3
Madhepura | 5 | [6 empty] | 1 | 2 | 2
Madhubani | 6 | [5 empty] | 1 | 1 | 1 | 5
Munger | 9 | 1 |  |  |  |  | 1 |  | 1 | 2
Muzaffarpur | 34 |  |  |  | 3 | 1 |  |  | 4 | 1
Nalanda | 17 |  |  |  | 1 |  |  |  | 1 | 5
Nawada | 10 |  |  |  |  | 3 | 1 |  | 2 | 3
Patna | 16 | [8 empty] | 8
Purnea | 11 | [8 empty] | 3
Rohtas | 17 | [7 empty] | 12 | 2
Saharsa | 5 |  |  | 1 |  |  |  | 2
Samastipur | 16 | [8 empty] | 3
Saran | 18 | 1 |  |  |  | 1 | 1 | 2
Sheikhpura | 6
Sheohar | [8 empty] | 3
Sitamarhi | 13 | [6 empty] | 1 | 3 | 1
Siwan | 21 |  | 1
Supaul | 8
Vaishali | 14 |  |  | 2 |  |  |  | 3 | 2 | 5
West Champaran | 11 |  |  | 1 |  | 2 |  |  | 4 | 1
Grand Total | 445 | 3 | 10 | 8 | 11 | 30 | 10 | 26 | 85 | 99

## USS for District
BSEIDC , Patna
Physical Status of USS (Central Fund) - 2009-10 & 2010-11 31.01.2016
S.N. | Group No. | Name of District | Name of Block | Name of School | Not Start | Layout | Foundation | PL | GF-LL | GF-RL | FF-LL | FF-RL | Finishing | Complete | Remarks | Division | Session | Group No.
1 | USS-1-1 | Nalanda | p.Mh | eŒfoŒlwedk 9931607862 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-77-2 | Inaugurated
2 | USS-1-2 | Nalanda | bLykeiqj | eŒfoŒenkjxat 9631262679 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-77-3 | Inaugurated
3 | USS-1-3 | Nalanda | fgylk | eŒfoŒvdcjiqj 9470085363 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-77-4 | Inaugurated
4 | USS-1-4 | Nalanda | fcgkj 'kjhQ | eŒfoŒflaxFkq 9204881769 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-78-1 | Inaugurated
5 | USS-2-1 | Nalanda | fxfj;d | eŒfoŒblqvk 9934451313 | 1 | [9 empty] | sufficient land not available, work not possible, Proposal for drop | Patna East | 2009-10 | USS-78-2 | Inaugurated
6 | USS-2-2 | Nalanda | drjhljk; | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-78-3 | Inaugurated
7 | USS-2-3 | Nalanda | jktxhj | eŒfoŒygqvkj 9798642205@9504394778 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-78-4 | Inaugurated
8 | USS-2-4 | Nalanda | flyko | eŒfoŒujgj fcxgk 8002186727 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-79-2 | Inaugurated
9 | USS-2-5 | Nalanda | uwjljk; | eŒfoŒdqUnh 9798241195 | 1 | [9 empty] | sufficient land not available, work not possible, Proposal for drop | Patna East | 2009-10 | USS-79-4 | Inaugurated
10 | USS-3-1 | Patna | ck<+ | eŒfoŒngkSj 8804003367 | 1 | [9 empty] | Project Director Inauguratedstruct to DEO to arrange land with corporation of local public work not possible, Proposal for drop | Patna East | 2009-10 | USS-199 B-1 | Inaugurated
11 | USS-3-2 | Patna | ck<+ | eŒfoŒeqckjdiqj 9631978359 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-199 B-2 | Inaugurated
12 | USS-3-3 | Patna | Qrqgk¡ | eŒfoŒMqejh 8521893444 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-199 B-3 | Inaugurated
13 | USS-3-4 | Patna | Qrqgk¡ | mRØŒeŒfoŒip:f[k;k 9801459905 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-29-1 | Inaugurated
14 | USS-3-5 | Patna | [kq'k:iqj | mRØŒeŒfoŒfueZyhpd 9097610852 | 1 | [9 empty] | sufficient land not available work not possible, proposal for drop | Patna East | 2009-10 | USS-29-4 | Inaugurated
15 | USS-4-1 | Patna | nkukiqj | eŒfoŒvdhyiqj 9835490244 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-30-1 | Inaugurated
16 | USS-4-2 | Patna | ukScriqj | eŒfoŒvgqvkjk 9939680617 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-30-3 | Inaugurated
17 | USS-4-3 | Patna | ikyhxat | eŒfoŒHksM+gfj;k 9199997796 | 1 | [9 empty] | dispute, work not possible, Proposal for drop | Patna East | 2009-10 | USS-30-4 | Inaugurated
18 | USS-5-1 | Patna | /ku:vk | eŒfoŒdkslqr 9973270948@9974270948 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-31-3 | Inaugurated
19 | USS-5-2 | Patna | elkS<+h | eŒfoŒNkrk 8084994281 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-154-1 | Inaugurated
20 | USS-5-3 | Patna | lairpd | eŒfoŒyadk dNqvkjk 9162137790 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10 | USS-154-2 | Inaugurated
21 | USS-5-4 | Patna | iquiqu | eŒfoŒdY;k.kiqj 9507549063 | [9 empty] | 1 | Final | Patna East | 2009-10 | USS-154-4 | Inaugurated
22 | USS-6-1 | Bhojpur | ihjks | eŒfoŒrkj 8969213005 | [7 empty] | 1 |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-154-5 | Inaugurated
23 | USS-6-2 | Bhojpur | ihjks | mRØŒeŒfoŒ nsopUnk 9386992853 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-155-1 | Inaugurated
24 | USS-6-3 | Bhojpur | rjkjh | eŒfoŒ[kqVgk¡ 7631530412 | 1 | [9 empty] | low land available, work not possible | Patna East | 2009-10 | USS-155-2 | Inaugurated
25 | USS-7-1 | Bhojpur | fcfg;k¡ | eŒfoŒ:nzuxj 9308401427 | [9 empty] | 1 | Inaugurated. काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-155-4 | Inaugurated
26 | USS-7-2 | Bhojpur | txnh'kiqj | eŒfoŒtaxynkok¡ 9931492812 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-156-3 | Inaugurated
27 | USS-7-3 | Bhojpur | 'kkgiqj | eŒfoŒykyw Msjk 8873932298@9973022234 |  |  |  |  | 1 | [5 empty] | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-84-2 | Inaugurated
28 | USS-8-1 | Bhojpur | vfxvk¡o | eŒfoŒukjk;.kiqj 9852411014 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-84-3 | Inaugurated
29 | USS-8-2 | Bhojpur | cM+gjk | eŒfoŒxqaMh 7739111542 | [6 empty] | 1 |  |  |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-84-4 | Inaugurated
30 | USS-8-3 | Bhojpur | mnoUruxj | eŒfoŒds'kksiqj cdjh 9771242640 |  |  |  | 1 | [6 empty] | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-85-2 | Inaugurated
31 | USS-8-4 | Bhojpur | dksbyoj | mRØŒeŒfoŒ folquiqjk 9334151672 | [8 empty] | 1 |  | काफी दिनों से कार्य बंद | Patna East | 2009-10 | USS-86-2 | Inaugurated
32 | USS-101-1 | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-201-4 | Inaugurated | SF
33 | USS-101-2 | Nalanda | Ben | M.S. Akouna 9570951336 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-202-1 | Inaugurated | SF
34 | USS-101-3 | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-202-2 | Inaugurated | SF
35 | USS-101-4 | Nalanda | Silao | Urdu.M.S. Barakar 9931004916 |  |  |  |  | 1 | [5 empty] | Invalid list | Patna East | 2010-11 | USS-202-4 | Inaugurated | SF
36 | USS-101-5 | Nalanda | Ben | M.S. Ramganj 9135849205 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-202-5 | Inaugurated | SF
37 | USS-102-1 | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-203-1 | Inaugurated | SF
38 | USS-102-2 | Nalanda | Biharsarif | M.S. Majidpur 9570625433 | [8 empty] | 1 |  |  | Patna East | 2010-11 | USS-203-2 | Inaugurated | SF
39 | USS-102-3 | Nalanda | Chandi | M.S. Dariya Bigha 9931236900 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11 | USS-203-3 | Inaugurated | SF
40 | USS-102-4 | Nalanda | Chandi | Urdu.M.S. Baisa 9939043903 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11 | USS-203-4 | Inaugurated | SF
41 | USS-102-5 | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 | [9 empty] | 1 |  | Patna East | 2010-11 | USS-207-1 | Inaugurated | SF
42 | USS-102-6 | Nalanda | Sarmera | M.S.Singhaul 9934212058 | [9 empty] | 1 |  | Patna East | 2010-11 | USS-207-2 | Inaugurated | SF
43 | USS-103-1 | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-207-3 | Inaugurated | SF
44 | USS-103-2 | Nalanda | Hilsa | M.S. Rasai Bigha 9934593683 | 1 | [9 empty] | Retender | Patna East | 2010-11 | USS-207-4 | Inaugurated | SF
45 | USS-103-3 | Nalanda | Islampur | M.S. Bargounw 9279149331 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-27-5 | Inaugurated
46 | USS-103-4 | Nalanda | Islampur | M.S. Banbag 9934487509 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-142-2 | Inaugurated
47 | USS-104-1 | Patna | Khushrupur | M.S. Jagmal Bigha 9771442400 | 1 | [9 empty] | Inaugurated sufficient land, work not possible | Patna East | 2010-11 | USS-142-3 | Inaugurated
48 | USS-104-2 | Patna | Khushrupur | U.M.S. Arrai Benipur 9135748584 | 1 | [10 empty] | Patna East | 2010-11 | USS-32-3 | Inaugurated
49 | USS-104-3 | Patna | Barh | U.M.S. Malahi 7250940590 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-32-4 | Inaugurated
50 | USS-104-4 | Patna | Fatuha | M.S. Gabaspur 9955241716 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-1 | Inaugurated
51 | USS-105-1 | Patna | Patna Sadar | M.S. Khokhna 9135334773 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-2 | Inaugurated
52 | USS-105-2 | Patna | Patna Sadar | M.S. Marchi 9430934711 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-3 | Inaugurated
53 | USS-105-3 | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-33-4 | Inaugurated
54 | USS-105-4 | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-34 A-2 | Inaugurated
55 | USS-106-1 | Patna | Bihta | M.S. Kateshar 7250695245 | 1 | [9 empty] | Low Land about 12'-0", work not possible | Patna East | 2010-11 | USS-34 B-1 | Inaugurated
56 | USS-106-2 | Patna | Bikram | M.S. Barah 8084301353 | 1 | [9 empty] | Land not regitered to school, work not possible | Patna East | 2010-11 | USS-34 A-3 | Inaugurated
57 | USS-106-3 | Patna | Bihta | M.S. Kanhauli 9386873458 | 1 | [10 empty] | Patna East | 2010-11 | USS-34 B-2 | Inaugurated
58 | USS-107-1 | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-151-1 | Inaugurated
59 | USS-108-2 | Bhojpur | Agioan | M.S. Berath 09955434210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-151-2 | Inaugurated
60 | USS-108-3 | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-151-3 | Inaugurated
61 | USS-108-4 | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-152-1 | Inaugurated
62 | USS-108-5 | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 | [9 empty] | 1 |  | Patna East | 2010-11 | USS-152-2 | Inaugurated
63 | USS-108-6 | Bhojpur | Agioan | M.S. Lasarhi 9661399087 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11 | USS-152-5 | Inaugurated
64 | USS-109-1 | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-152-6 | Inaugurated
65 | USS-109-2 | Bhojpur | Garhani | M.S. Kaup 9708602077 | [5 empty] | 1 | [5 empty] | Patna East | 2010-11 | USS-183-1 | Inaugurated
66 | USS-109-3 | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-183-2 | Inaugurated
67 | USS-109-4 | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-183-4 | Inaugurated
68 | USS-109-5 | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-184-1 | Inaugurated
69 | USS-110-1 | Bhojpur | Barhara | U.M.S. Shaligram Singh Ka Tola 8409626973 | [9 empty] | 1 | B/W upto RL, way not available | Patna East | 2010-11 | USS-184-2 | Inaugurated
70 | USS-110-2 | Bhojpur | Barhara | M.S. Pakri 9304856454 | [7 empty] | 1 |  |  | B/W upto RL, way not available | Patna East | 2010-11 | USS-184-3 | Inaugurated
71 | USS-110-3 | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 | [8 empty] | 1 |  |  | Patna East | 2010-11 | USS-185-1 | Inaugurated
72 | USS-110-4 | Bhojpur | Koilwar | M.S. Khesarhiyan 9973554537 | [5 empty] | 1 | [5 empty] | Patna East | 2010-11 | USS-185-3 | Inaugurated
73 | USS-110-5 | Bhojpur | Koilwar | M.S. Khangaown 9631265664 | [8 empty] | 1 |  |  | Patna East | 2010-11 | USS-186-1 | Inaugurated
74 | USS-111-1 | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-186-2 | Inaugurated
75 | USS-111-2 | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-23-2 | Inaugurated
76 | USS-111-3 | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-143-2 | Inaugurated
77 | USS-111-4 | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-143-4 | Inaugurated
78 | USS-112-1 | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 | [9 empty] | 1 |  | Patna East | 2010-11 | USS-63-2 | Inaugurated
79 | USS-112-2 | Bhojpur | Bihiyan | M.S. Kouriya 9431438960 | [7 empty] | 1 |  |  | Inaugurated | Patna East | 2010-11 | USS-64-1 | Inaugurated
80 | USS-112-3 | Bhojpur | Shahpur | M.S. Jawainiya 8083447757 7677504269 | [5 empty] | 1 |  |  |  |  | B/W upto RL | Patna East | 2010-11 | USS-64-2 | Inaugurated
81 | USS-112-4 | Bhojpur | Shahpur | M.S. Suhiya 9471919316 | [6 empty] | 1 |  |  |  |  | Patna East | 2010-11 | USS-64-3 | Inaugurated
82 | USS-113-1 | Bhojpur | Tarari | M.S.Gahruan 9472135231 9162748057 | [8 empty] | 1 |  | RC | Patna East | 2010-11 | USS-65-1 | Inaugurated
83 | USS-113-2 | Bhojpur | Tarari | M.S.Kurmuri 9576176655 | [7 empty] | 1 |  |  | 1st Floor Sill Level | Patna East | 2010-11 | USS-65-2 | Inaugurated
84 | USS-113-3 | Bhojpur | Tarari | M.S. Tarari 9631136009 | [8 empty] | 1 |  |  | Patna East | 2010-11 | USS-65-3 | Inaugurated
85 | USS-113-4 | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-66-2 | Inaugurated
86 | USS-113-5 | Bhojpur | Tarari | M.S.Bagar 9801629878 | [8 empty] | 1 |  | RC | Patna East | 2010-11 | USS-191-3 | Inaugurated
87 | USS-114-1 | Bhojpur | Sandesh | U.M.S.Nasratpur 9334673203 | 1 | [10 empty] | Patna East | 2010-11 | USS-191-4 | Inaugurated
88 | USS-114-2 | Bhojpur | Sahar | M.S. Baruhi 9199571702 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-191-5 | Inaugurated
89 | USS-114-3 | Bhojpur | Ara | M.S. Basantpur 09308735308 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-193-1 | Inaugurated
90 | USS-114-4 | Bhojpur | Sahar | M.S. Nawada 9934483628 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11 | USS-193-2 | Inaugurated
91 | USS-9-1 | Buxar | cDlj | eŒfoŒd`riqjk 9576622685 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-193-4 | Inaugurated
92 | USS-9-2 | Buxar | pkSlk | eŒfoŒcukjiqj 8873946373 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-146 (C) | Inaugurated
93 | USS-9-3 | Buxar | jktiqj | eŒfoŒjlsu 9006272320 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-102-1 | Inaugurated
94 | USS-9-4 | Buxar | bVkM+h | eŒfoŒcSdqUBiqj 9931755863 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-3-4 | Inaugurated
95 | USS-10-1 | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-5-2 | Inaugurated
96 | USS-10-2 | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-104-3 | Inaugurated
97 | USS-10-3 | Buxar | czg~eiqj | eŒfoŒegqvkj 7250949713 | 1 | [10 empty] | Patna West | 2009-10 | USS-104-4 | Inaugurated
98 | USS-10-4 | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-1 | Inaugurated
99 | USS-11-1 | Kaimur | dqnjk | eŒfoŒvojS;k 9973613935 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-2 | Inaugurated
100 | USS-11-2 | Kaimur | eksgfu;k¡ | eŒfoŒdVjkdyk 9006263731 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-3 | Inaugurated
101 | USS-11-3 | Kaimur | jkex<+ | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-105-4 | Inaugurated
102 | USS-11-4 | Kaimur | nqxkZorh | eŒfoŒnqxkZorh 9430340748@9955221828 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-107-1 | Inaugurated
103 | USS-12-1 | Kaimur | HkHkqvk | eŒfoŒdqM+klu 9031437647 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-39-1 | Inaugurated
104 | USS-12-2 | Kaimur | pSuiqj | eŒfoŒdasok 9430026932 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-39-3 | Inaugurated
105 | USS-13-1 | Rohtas | djxgj | eŒfoŒrksjuh 9631253327 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-160-3 | Inaugurated
106 | USS-13-2 | Rohtas | f'kolkxj | eŒfoŒxMqjk 9771022208 | 1 | [9 empty] | Foundation work stopped due to local disturbance (Inaugurated school campus sufficient land available & soil test also done Inaugurated schl. Campus but some local public want to construct this build. Inaugurated other land wich is situated out of campus & no aproach road available & about 800 m(aprox.) away from campus | Patna West | 2009-10 | USS-81-1 | Inaugurated
107 | USS-13-3 | Rohtas | lklkjke | eŒfoŒfldfj;k 9431464894 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-81-2 | Inaugurated
108 | USS-13-4 | Rohtas | dkspl | eŒfoŒegqvkjh 9661222301 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-82-1 | Inaugurated
109 | USS-14-1 | Rohtas | fMgjh | eŒfoŒxaxkSyh 7352200057 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-82-2 | Inaugurated
110 | USS-14-2 | Rohtas | fnukjk | eŒfoŒljuk 9771634397 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-82-4 | Inaugurated
111 | USS-14-3 | Rohtas | dkjkdkV | eŒfoŒeksguiqj 9801296392 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-194-1 | Inaugurated
112 | USS-14-4 | Rohtas | uks[kk | eŒfoŒ?kksjfMgk 9801894133 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10 | USS-42-4 | Inaugurated
113 | USS-115-1 | Buxar | Buxar | M.S.Nadanw 9234866577 9430015496 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-44-1 | Inaugurated
114 | USS-115-2 | Buxar | Buxar | M.S.Manjharia 9472951603 | 1 | [9 empty] | No Way | Patna West | 2010-11 | USS-44-4 | Inaugurated
115 | USS-115-3 | Buxar | Rajpur | M.S. Khiri 9470753325 | [5 empty] | 1 |  |  |  |  | Sill level of GL | Patna West | 2010-11 | USS-159-4 | Inaugurated
116 | USS-115-4 | Buxar | Rajpur | Urdu M.S. Banni 9973105344 | 1 | [9 empty] | No land available | Patna West | 2010-11 | USS-9-4 | Inaugurated
117 | USS-116 (A) | Buxar | Dumraon | M.S.Nuaon 9939391144 | [5 empty] | 1 | [5 empty] | Patna West | 2010-11 | USS-10-1 | Inaugurated
118 | USS-116 (B) | Buxar | Dumraon | M.S. Kanjharua 9955867071 | [8 empty] | 1 |  | Steel bInaugurateddInauguratedg | Patna West | 2010-11 | USS-10-2 | Inaugurated
119 | USS-116 (C) | Buxar | Dumraon | M.S. Mathila 9931890937 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-10-4 | Inaugurated
120 | USS-116 (D) | Buxar | Dumraon | M.S. Karuaj 9931281346 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-18-1 | Inaugurated
121 | USS-116 (E) | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 | [8 empty] | 1 |  | Steel bInaugurateddInauguratedg | Patna West | 2010-11 | USS-25-2 | Inaugurated
122 | USS-117 (A) | Buxar | Nawanagar | M.S.Pramanpur 9386827434 |  |  | 1 | [8 empty] | Patna West | 2010-11 | USS-139-2 | Inaugurated
123 | USS-117 (B) | Buxar | Ithari | M.S. Barkagaon 8651239720 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-139-3 | Inaugurated
124 | USS-117 (C) | Buxar | Ithari | M.S. Harpur 9939590039 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-139-4 | Inaugurated
125 | USS-117 (D) | Buxar | Ithari | M.S. Basawan Kala 7739120173 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-139-5 | Inaugurated
126 | USS-118-1 | Buxar | Simiri | M.S.Dhanpura 9199795834 | 1 | [10 empty] | Patna West | 2010-11 | USS-140-3 | Inaugurated
127 | USS-118-2 | Buxar | Simiri | M.S. Barka Singhnpura 9934740004 | 1 | [10 empty] | Patna West | 2010-11 | USS-16-1 | Inaugurated
128 | USS-118-3 | Buxar | Simiri | M.S. Kharha Tarnh 9199359782 | 1 | [10 empty] | Patna West | 2010-11 | USS-16-2 | Inaugurated
129 | USS-119 (A) | Kaimur | Bhabhua | M.S.Miun | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-16-3 | Inaugurated
130 | USS-119 (B) | Kaimur | Bhabhua | M.S.Piliyan | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-130-1 | Inaugurated
131 | USS-119 (C) | Kaimur | Bhabhua | M.S. Mehsuan | [5 empty] | 1 | [5 empty] | Patna West | 2010-11 | USS-130-2 | Inaugurated
132 | USS-119 (D) | Kaimur | Bhabhua | M.S. Mohan Darwan | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-130-3 | Inaugurated
133 | USS-120 (A) | Kaimur | Ramgarh | M.S.Sijhua | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-130-4 | Inaugurated
134 | USS-120 (B) | Kaimur | Ramgarh | M.S.Upari 9939613033 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-130-5 | Inaugurated
135 | USS-120 (C) | Kaimur | Nuaon | Govt. Basic School Kari Ram Akhili | 1 | [9 empty] | Tender Process | Patna West | 2010-11 | USS-127 (C) | Inaugurated
136 | USS-120 (D) | Kaimur | Nuaon | M.S.Mushiyan 9546505256 |  |  | 1 | [7 empty] | Tender Process | Patna West | 2010-11 | USS-108-2 | Inaugurated
137 | USS-120 (E) | Kaimur | Durgawati | U.M.S Nuaon 9199361709 |  |  |  |  | 1 | [6 empty] | Patna West | 2010-11 | USS-108-3 | Inaugurated
138 | USS-121 (A) | Rohtas | Karakat | M.S.Dewmarkande 8969878557 | [8 empty] | 1 |  | Roof slab casted of GF | Patna West | 2010-11 | USS-108-4 | Inaugurated
139 | USS-121 (B) | Rohtas | Karakat | Girl's M.S.Motha 9162106111 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-109-1 | Inaugurated
140 | USS-121 (C) | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-109-3 | Inaugurated
141 | USS-121 (D) | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-109-4 | Inaugurated
142 | USS-121 (E) | Rohtas | Akorhigola | M.S.Chhapra 9934757484 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-109-5 | Inaugurated
143 | USS-122-1 | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-111-1 | Inaugurated
144 | USS-122-2 | Rohtas | Dinara | M.S.Sarwan ,8084920823 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-111-2 | Inaugurated
145 | USS-122-3 | Rohtas | Dinara | M.S. Baliyan, 9931111475 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-111-3 | Inaugurated
146 | USS-122-4 | Rohtas | Dinara | M.S. Bararhi, 9955083783 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-111-4 | Inaugurated
147 | USS-122-5 | Rohtas | Bikramganj | M.S. Jamorhi, 9955952582 | 1 | [10 empty] | Patna West | 2010-11 | USS-112-2 | Inaugurated
148 | USS-122-6 | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-113-4 | Inaugurated
149 | USS-123-1 | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-114-2 | Inaugurated
150 | USS-123-2 | Rohtas | Kochas | M.S. Ubadhi, 8002578689 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-114-3 | Inaugurated
151 | USS-123-3 | Rohtas | Kochas | M.S. Kuchila, 8002537247 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-114-4 | Inaugurated
152 | USS-123-4 | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 | [9 empty] | 1 |  | Patna West | 2010-11 | USS-219-1 | Inaugurated | SF
153 | USS-123-5 | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | [9 empty] | 1 | Handover | Patna West | 2010-11 | USS-71-2 | Inaugurated
154 | USS-123-6 | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | [9 empty] | 1 | Handover | Patna West | 2010-11 | USS-71-3 | Inaugurated
155 | USS-124-1 | Rohtas | Chenari | M.S. Ramgarh 9771746971 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-71-4 | Inaugurated
156 | USS-124-2 | Rohtas | Chenari | M.S. Chandrakaithi, 9934281842 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-199 D-2 | Inaugurated
157 | USS-124-3 | Rohtas | Sheosagar | M.S. Alampur, 9572407040 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-135-1 | Inaugurated
158 | USS-124-4 | Rohtas | Sheosagar | M.S. Sonhar 9006103550 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-135-2 | Inaugurated
159 | USS-124-5 | Rohtas | Sasaram | M.S. Akasi , 9204460486 | [8 empty] | 1 |  |  | Patna West | 2010-11 | USS-136-1 | Inaugurated
160 | USS-125-1 | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | [9 empty] | 1 | Inaugurated | Patna West | 2010-11 | USS-136-3 | Inaugurated
161 | USS-28-1 | Jehanabad | tgkukckn | eŒfoŒveSu 9473327625 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-1 | Inaugurated
162 | USS-28-2 | Jehanabad | dkdks | eŒfoŒHknljk 9006927848 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-2 | Inaugurated
163 | USS-28-3 | Jehanabad | e[knqeiqj | eŒfoŒdksgjk 9162155024 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-3 | Inaugurated
164 | USS-28-4 | Jehanabad | jruhQjhniqj | mRØŒeŒfoŒyk[kkiqj 9934235714 | 1 | [10 empty] | Magadh | 2009-10 | USS-137-4 | Inaugurated
165 | USS-29-1 | Aurangabad | nso | eŒfoŒcs<+uh 9631266207 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-137-5 | Inaugurated
166 | USS-29-2 | Aurangabad | enuiqj | eŒfoŒfijok¡ 9934340488 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-51-3 | Inaugurated
167 | USS-29-3 | Aurangabad | jQhxat | eŒfoŒ[kjks[kj 9006027690 | [8 empty] | 1 |  |  | Magadh | 2009-10 | USS-167-1 | Inaugurated
168 | USS-29-4 | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-2 | Inaugurated
169 | USS-30-1 | Aurangabad | vkscjk | eŒfoŒ'kadjiqj 7739690373 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-3 | Inaugurated
170 | USS-30-2 | Aurangabad | nkmnuxj | eŒfoŒteqvkok¡ 9801563600 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-4 | Inaugurated
171 | USS-30-3 | Aurangabad | nkmnuxj | eŒfoŒpkSjh 9934434990 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-167-5 | Inaugurated
172 | USS-30-4 | Aurangabad | gliqjk | eŒfoŒdksbyok¡ 9135312996 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-1 | Inaugurated
173 | USS-31-1 | Aurangabad | dqVqEck | eŒfoŒfjfl;i 9955874942 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-2 | Inaugurated
174 | USS-31-2 | Aurangabad | uohuxj | eŒfoŒiM+fj;k 9931622753 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-3 | Inaugurated
175 | USS-31-3 | Aurangabad | ok:.k | eŒfoŒikSFkq 9471060433 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-168-4 | Inaugurated
176 | USS-32-1 | Gaya | cks/k x;k | eŒfoŒchjgqr 9934480418 | [8 empty] | 1 |  | Work Stop due to local problem | Magadh | 2009-10 | USS-169-1 | Inaugurated
177 | USS-32-2 | Gaya | uxj fuxe | eŒfoŒpwjh 9199466924 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-2 | Inaugurated
178 | USS-32-3 | Gaya | osykxat | mRØŒeŒfoŒve>j 9931835374 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-3 | Inaugurated
179 | USS-32-4 | Gaya | fVdkjh | eŒfoŒrkik Qrsgiqj 9430070517 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-4 | Inaugurated
180 | USS-33-1 | Gaya | MksHkh | eŒfoŒihjklhu 9473140628 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-169-5 | Inaugurated
181 | USS-33-2 | Gaya | dksp | eŒfoŒfnX?kh 9576852929 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-170-1 | Inaugurated
182 | USS-33-3 | Gaya | f[ktjljk; | eŒfoŒvkneiqj 9771084118 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-170-5 | Inaugurated
183 | USS-33-4 | Gaya | cthjxat | eŒfoŒikys 9955418354 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-171-1 | Inaugurated
184 | USS-34 A-1 | Gaya | ckjkpV~Vh | mRØŒeŒfoŒ/kuxbZ 9931313425 | 1 | [9 empty] | Approach road unavailable | Magadh | 2009-10 | USS-172-1 | Inaugurated
185 | USS-34 A-2 | Gaya | Qrsgiqj | eŒfoŒckiwxzke 9934840966 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-2 | Inaugurated
186 | USS-34 A-3 | Gaya | eksguiqj | eŒfoŒvedksyk 9955837262 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-3 | Inaugurated
187 | USS-34 B-1 | Gaya | xq:vk | eŒfoŒpk¡lh 9006129640 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-4 | Inaugurated
188 | USS-34 B-2 | Gaya | bekexat | mRØŒeŒfoŒ]dksBh 9931625800 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-172-5 | Inaugurated
189 | USS-35-1 | Nawada | uoknk | eŒfoŒiVok ljk; 9006212577 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-13-1 | Inaugurated
190 | USS-35-2 | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 | [9 empty] | 1 |  | Magadh | 2009-10 | USS-14-1 | Inaugurated
191 | USS-35-3 | Nawada | jksg 1 | mRØŒeŒfoŒf'k[kjiqj 9661237533 | [5 empty] | 1 | [5 empty] | Magadh | 2009-10 | USS-125-1 | Inaugurated
192 | USS-35-4 | Nawada | okfjlyhxat | mRØŒeŒfoŒelwnk 9708007113 | [9 empty] | 1 |  | Magadh | 2009-10 | USS-52-1 | Inaugurated
193 | USS-36-1 | Nawada | vdcjiqj | eŒfoŒrs;kj | 1 | [9 empty] | Approach road unavailable | Magadh | 2009-10 | USS-53-1 | Inaugurated
194 | USS-36-2 | Nawada | jtkSyh | mRØŒeŒfoŒ]ckjkVk¡M loS;k | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-53-2 | Inaugurated
195 | USS-36-3 | Nawada | fljnyk | eŒfoŒlka< 9771960601 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10 | USS-53-3 | Inaugurated
196 | USS-143-1 | Jehanabad | Kako | M.S.Kajisarai 9934814478 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-164-1 | Inaugurated
197 | USS-143-2 | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-164-2 | Inaugurated
198 | USS-143-3 | Jehanabad | Kako | M.S.Pinzour 9931803275 | 1 | [10 empty] | Magadh | 2010-11 | USS-132-1 | Inaugurated
199 | USS-143-4 | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-132-2 | Inaugurated
200 | USS-144 (A) | Jehanabad | Hulasganj | M.S.Vira, 9771693433 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-132-3 | Inaugurated
201 | USS-144 (B) | Jehanabad | Makhdumpur | M.S.Akbarpur, 9934858600 | 1 | [9 empty] | Tender Process | Magadh | 2010-11 | USS-132-4 | Inaugurated
202 | USS-144 (C) | Jehanabad | Jehanabad | M.S.Bazartali, 9955297199 |  |  | 1 | [8 empty] | Magadh | 2010-11 | USS-132-5 | Inaugurated
203 | USS-145-1 | Nawada | Nawada | U.M.S. Jhunathi, 9631172127 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-73-1 | Inaugurated
204 | USS-145-2 | Nawada | Akbarpur | U.M.S. Derma, 9931232692 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-73-2 | Inaugurated
205 | USS-145-3 | Nawada | Akbarpur | M.S. Kuhaila, 9771085197 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-73-3 | Inaugurated
206 | USS-145-4 | Nawada | Akbarpur | M.S. Paharpur, 9771672098 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-72-3 | Inaugurated
207 | USS-145-5 | Nawada | Nawada | M.S. Wermi, 9708857028 | 1 | [9 empty] | Site Changed | Magadh | 2010-11 | USS-60-1 | Inaugurated
208 | USS-146 (A) | Nawada | Govindpur | M.S. Rampur, 9771867218 | [6 empty] | 1 |  |  |  |  | Magadh | 2010-11 | USS-60-2 | Inaugurated
209 | USS-146 (B) | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | [9 empty] | 1 |  | Magadh | 2010-11 | USS-60-3 | Inaugurated
210 | USS-146 (C) | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-60-4 | Inaugurated
211 | USS-146 (D) | Nawada | Pakribarawan | M.S. Ukaorah | [9 empty] | 1 |  | Magadh | 2010-11 | USS-60-5 | Inaugurated
212 | USS-146 (E) | Nawada | Kashichak | U.M.S. Vishbnathpur , 9386540972 | 1 | [9 empty] | Retender | Magadh | 2010-11 | USS-177-1 | Inaugurated
213 | USS-147-1 | Nawada | Narhat | M.S. Khanwa, 9905846666 | [9 empty] | 1 |  | Magadh | 2010-11 | USS-177-2 | Inaugurated
214 | USS-147-2 | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | [9 empty] | 1 |  | Magadh | 2010-11 | USS-177-3 | Inaugurated
215 | USS-148-1 | Gaya | Bodh Gaya | M.S. Moratala, 9934282506 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-178-1 | Inaugurated
216 | USS-148-2 | Gaya | Bodh Gaya | M.S. Titoiya, 9934672899 | 1 | [9 empty] | Land Problem | Magadh | 2010-11 | USS-179-1 | Inaugurated
217 | USS-148-3 | Gaya | Bodh Gaya | M.S. Bataspur, 9470447309 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-179-2 | Inaugurated
218 | USS-148-4 | Gaya | Bodh Gaya | M.S. Gapha Kala, 9934972678 |  | 1 | [8 empty] | Land Problem | Magadh | 2010-11 | USS-179-3 | Inaugurated
219 | USS-149 (A) | Gaya | Dumariya | M.S. Bhangiya, 9472443151 9801769544 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-179-4 | Inaugurated
220 | USS-149 (B) | Gaya | Imamganj | M.S. Karsan Kala, 9199768865, 9199061230 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-179-5 | Inaugurated
221 | USS-149 (C) | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-181-1 | Inaugurated
222 | USS-149 (D) | Gaya | Imamganj | M.S. Naudiha, 9135294703, 8235212693 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-182-1 | Inaugurated
223 | USS-149 (E) | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 | [9 empty] | 1 |  | Magadh | 2010-11 | USS-182-2 | Inaugurated
224 | USS-150 (A) | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-182-3 | Inaugurated
225 | USS-150 (B) | Gaya | Tekari | M.S. Urdu Bishnupur, 9771128251, 9135850031 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-174-1 | Inaugurated
226 | USS-150 (C) | Gaya | Konch | M.S. Goribigha, 9939408167 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-174-3 | Inaugurated
227 | USS-150 (D) | Gaya | Konch | M.S. Ahiyarpur, 9934008030 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-174-4 | Inaugurated
228 | USS-151-1 | Gaya | Bathani | Basic M.S. Radui, 7654409634 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-175-2 | Inaugurated
229 | USS-151-2 | Gaya | Bathani | M.S. Karubigha, 9934427661 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-175-3 | Inaugurated
230 | USS-151-3 | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-175-4 | Inaugurated
231 | USS-152-1 | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-176-1 | Inaugurated
232 | USS-152-2 | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-176-2 | Inaugurated
233 | USS-152-3 | Gaya | Fatehpur | M.S. Khajuri, 8969107991 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-176-3 | Inaugurated
234 | USS-152-4 | Gaya | Fatehpur | M.S. Nagwa, 9798270089 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-212-1 | Inaugurated | SF
235 | USS-152-5 | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-173 (B) | Inaugurated
236 | USS-152-6 | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-46-3 | Inaugurated
237 | USS-153 (A) | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | [8 empty] | 1 |  |  | Magadh | 2010-11 | USS-46-4 | Inaugurated
238 | USS-153 (B) | Gaya | Guraru | M.S. Manjhar, 9572789270 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-47-1 | Inaugurated
239 | USS-153 (C) | Gaya | Amas | M.S. Baliyari, 9570551566, 8294856371, 8051934469 |  |  | 1 | [8 empty] | Magadh | 2010-11 | USS-47-3 | Inaugurated
240 | USS-153 (D) | Gaya | Sherghatty | M.S. Naknuppa, 9431289085 | 1 | [10 empty] | Magadh | 2010-11 | USS-47-4 | Inaugurated
241 | USS-154-1 | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-47-5 | Inaugurated
242 | USS-154-2 | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-162 (B) | Inaugurated
243 | USS-154-3 | Aurangabad | Kutumba | M.S. Darmi, 9955519885, 9931921788 | 1 | [10 empty] | Magadh | 2010-11 | USS-162 (C) | Inaugurated
244 | USS-154-4 | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-163 (B) | Inaugurated
245 | USS-154-5 | Aurangabad | Deo | M.S. Vijouli, 9801123435 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-163 (C) | Inaugurated
246 | USS-155-1 | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-75-1 | Inaugurated
247 | USS-155-2 | Aurangabad | Obra | M.S. Ratwar, 9931418907 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-75-2 | Inaugurated
248 | USS-155-3 | Aurangabad | Obra | M.S. Tejpur, 9973299799 | 1 | [10 empty] | Magadh | 2010-11 | USS-75-3 | Inaugurated
249 | USS-155-4 | Aurangabad | Obra | M.S. Karsawan, 9470488343 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-76-3 | Inaugurated
250 | USS-156-1 | Aurangabad | Haspura | M.S. Piru, 9135064392 | 1 | [9 empty] | Land Encrochment | Magadh | 2010-11 | USS-76-4 | Inaugurated
251 | USS-156-2 | Aurangabad | Haspura | M.S. Sriwanbhatt, 9939023445 | 1 | [9 empty] | Land not available | Magadh | 2010-11 | USS-77-1 | Ing
252 | USS-156-3 | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11 | USS-79-1 | Ing
253 | USS-157 (A) | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 | [9 empty] | 1 |  | Magadh | 2010-11 | USS-29-2 | Ing
254 | USS-157 (B) | Aurangabad | Raphiganj | M.S. Pogar, 9973150471 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-30-2 | Ing
255 | USS-157 (C) | Aurangabad | Madanpur | M.S. Judahi, 9931892284 | [9 empty] | 1 |  | Magadh | 2010-11 | USS-31-1 | Ing
256 | USS-157 (D) | Aurangabad | Madanpur | M.S. Saliya, 9955803641 | [7 empty] | 1 |  |  |  | Magadh | 2010-11 | USS-31-2 | Ing
257 | USS-157 (E) | Aurangabad | Raphiganj | M.S. Danai, 9097351245 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11 | USS-80-1 | Ing
258 | USS-20-1 | Munger | gosyh [kM+xiqj | eŒfoŒj?kqukFkiqj | 1 | [9 empty] | Land Problem | Munger | 2009-10 | USS-80-2 | Ing
259 | USS-20-2 | Munger | eqaxsj lnj | eŒfoŒVhdkjkeiqj 9431612789 |  | 1 | [8 empty] | Lay Out On 14.03.14 | Munger | 2009-10 | USS-80-3 | Ing
260 | USS-20-3 | Munger | /kjgjk | eŒfoŒegjuk 9504681361@9852445511 | [6 empty] | 1 |  |  |  |  | Munger | 2009-10 | USS-80-4 | Ing
261 | USS-21-1 | Sheikhpura | 'ks[kiqjk | eŒfoŒckn'kkgiqj 9709066149 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-80-5 | Ing
262 | USS-22-1 | Jamui | pdkbZ | eŒfoŒnqyeiqj 9973390953@9661984491 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-201 | Ing | SF
263 | USS-22-2 | Jamui | >k>k | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-201 | Ing | SF
264 | USS-22-3 | Jamui | lksuks | eŒfoŒiSjk efVgkuk 9801576608 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-201 | Ing | SF
265 | USS-23-1 | Jamui | teqbZ | mRØŒeŒfoŒ HkkVpd 9430818763 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-1 | Ing
266 | USS-23-2 | Jamui | y{ehiqj | eŒfoŒgjyk 9162733763@9006655639 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-2 | In
267 | USS-23-3 | Jamui | [kSjk | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-3 | Ing
268 | USS-23-4 | Jamui | bZŒ vyhxat | eŒfoŒfetkZxat 8292659272 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-27-4 | Ing
269 | USS-24-1 | Begusarai | cNokM+k | eŒfoŒQrsg 9570919206 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-32-2 | Ing
270 | USS-24-2 | Begusarai | Hkxokuiqj | eŒfoŒeksf[r;kjiqj 9934441250 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-55-1 | Ing
271 | USS-24-3 | Begusarai | psfj;k cfj;kjiqj | eŒfoŒldjoklk 9939576953 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-55-2 | Ing
272 | USS-25-1 | Begusarai | cfy;k | eŒfoŒelwnuiqj 9955252445 | [5 empty] | 1 |  |  |  |  | Roof Casted | Munger | 2009-10 | USS-55-3 | Ing
273 | USS-25-2 | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-55-4 | Ing
274 | USS-25-3 | Begusarai | lkgsciqj deky | eŒfoŒfo".kqiqj vkgksd 9534757293 | 1 | [9 empty] | Objection due to Mukhiya | Munger | 2009-10 | USS-56-1 | Ing
275 | USS-26-1 | Begusarai | cjkSuh | eŒfoŒcFkkSyh 9801572247@9534334080 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-56-2 | Ing
276 | USS-26-2 | Begusarai | efVgkuh | eŒfoŒtxriqjk 9939465778 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-56-3 | Ing
277 | USS-27-1 | Khagaria | ijoÙkk | eŒfoŒdjuk 9939629342@9006237936 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-56-4 | Ing
278 | USS-27-2 | Khagaria | vykSyh | eŒfoŒes?kkSuk 9534870633 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-184-1 | Ing
279 | USS-27-3 | Khagaria | pkSFke | eŒfoŒigkM+pd 9431651745 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-184-2 | Ing
280 | USS-27-4 | Khagaria | xksxjh | eŒfoŒidjSy 9955068112 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-22-1 | Ing
281 | USS-27-5 | Khagaria | [kxfM+;k | eŒfoŒeksjdkgh Fkkuk 9534404397 | [9 empty] | 1 | Inaugurated | Munger | 2009-10 | USS-22-2 | Ing
282 | USS-132-1 | Sheikhpura | Barbigha | M.S.Keuti | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-22-3 | Ing
283 | USS-132-2 | Sheikhpura | SheKhpura | M.S.Lodipur | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-23-1 | Ing
284 | USS-132-3 | Sheikhpura | Chewara | M.S.Lahana | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-23-3 | Ing
285 | USS-132-4 | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-23-4 | Ing
286 | USS-132-5 | Sheikhpura | Ariari | M.S.Husainawad | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-28-1 | Ing
287 | USS-133(A) | Lakhisarai | Barahiya | M.S.Pali 9546977875 | [9 empty] | 1 |  | Munger | 2010-11 | USS-28-2 | Ing
288 | USS-133(B) | Lakhisarai | Barahiya | M.S.Lal Diyara 9097688412 | 1 | [9 empty] | Not start | Munger | 2010-11 | USS-28-3 | Ing
289 | USS-133(C) | Lakhisarai | Halsi | M.S. Geruapursanda 8084044144 | 1 | [10 empty] | Munger | 2010-11 | USS-143-1 | Ing
290 | USS-133(D) | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 | [9 empty] | 1 |  | Munger | 2010-11 | USS-63-1 | Ing
291 | USS-133(E) | Lakhisarai | Suryagarha | U.M.S. Lahasaurwa 9631695175, 8434346388 | 1 | [9 empty] | Retender | Munger | 2010-11 | USS-63-3 | Ing
292 | USS-133(F) | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | [8 empty] | 1 |  |  | Munger | 2010-11 | USS-66-1 | Ing
293 | USS-134-1 | Jamui | Sono | M.S.Buijhayt 09631584296 |  |  |  | 1 | [7 empty] | Munger | 2010-11 | USS-66-3 | Ing
294 | USS-135-1 | Munger | Asarganj | M.S.Chakhand 9135065232 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-35-1 | Ing
295 | USS-135-2 | Munger | Asarganj | M.S. Beran 9204931976 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-36-2 | Ing
296 | USS-135-3 | Munger | Tarapur | M.S. Mahamadpur 9709507263 | [8 empty] | 1 |  |  | Munger | 2010-11 | USS-36-3 | Ing
297 | USS-136-1 | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-1-1 | Ing
298 | USS-136-2 | Munger | Sangrampur | M.S.Khapra 9934832035 | 1 | [9 empty] | No Land | Munger | 2010-11 | USS-1-2 | Ing
299 | USS-136-3 | Munger | Sangrampur | M.S.Katiyari 9199782900 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-1-3 | Ing
300 | USS-137-1 | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-1-4 | Ing
301 | USS-137-2 | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-2-2 | Ing
302 | USS-137-3 | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-2-3 | Ing
303 | USS-137-4 | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-2-4 | Ing
304 | USS-137-5 | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-101-1 | Ing
305 | USS-138-1 | Begusarai | Mansurchak | M.S.Chhabilapur 9771848155 | 1 | [9 empty] | No Land | Munger | 2010-11 | USS-101-2 | Ing
306 | USS-138-2 | Begusarai | Begusarai | M.S.Bharra 9204202640 | [8 empty] | 1 |  |  | Munger | 2010-11 | USS-101-3 | Ing
307 | USS-138-3 | Begusarai | Begusarai | M.S.Babasudebpur 9934708295, 88777402400 | 1 | [9 empty] | No Land | Munger | 2010-11 | USS-101-5 | Ing
308 | USS-138-4 | Begusarai | Matihani | M.S.Richiyahi Nayartol 9973647476, 9608273410 |  |  |  |  | 1 | [6 empty] | Munger | 2010-11 | USS-103-1 | Ing
309 | USS-138-5 | Begusarai | Sahebpur Kamal | M.S.Rajoura 9709067460 | 1 | [9 empty] | No Land | Munger | 2010-11 | USS-103-3 | Ing
310 | USS-139-1 | Begusarai | Bachhawara | M.S.Dadupur 9801471859 | [8 empty] | 1 |  |  | Munger | 2010-11 | USS-103-4 | Ing
311 | USS-139-2 | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-3-2 | Ing
312 | USS-139-3 | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-3-3 | Ing
313 | USS-139-4 | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-4-1 | Ing
314 | USS-139-5 | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-4-2 | Ing
315 | USS-140-1 | Begusarai | Garhpura | M.S.Kuddhar 9955509070 | [9 empty] | 1 |  | Munger | 2010-11 | USS-5-1 | Ing
316 | USS-140-2 | Begusarai | Dandari | M.S.Katarmala 9709640304 | [9 empty] | 1 |  | Munger | 2010-11 | USS-5-3 | Ing
317 | USS-140-3 | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-37-1 | Ing
318 | USS-141 (A) | Khagaria | Alauli | M.S.Shumbha Ghat 8969741611 | 1 | [9 empty] | New Tender | Munger | 2010-11 | USS-37-2 | Ing
319 | USS-141 (B) | Khagaria | Alauli | M.S.Khairi Khutaha 9471283095 |  |  | 1 | [8 empty] | Munger | 2010-11 | USS-37-3 | Ing
320 | USS-141 (C) | Khagaria | Khagaria | M.S.Nanku Mandal Tola 9955646986 | 1 | [9 empty] | New Tender | Munger | 2010-11 | USS-37-4 | Ing
321 | USS-141 (D) | Khagaria | Khagaria | M.S.Mathar 9771388437 | [9 empty] | 1 |  | Munger | 2010-11 | USS-38-1 | Ing
322 | USS-142-1 | Khagaria | Beldaur | M.S.Kainjari 7549429234 |  |  | 1 | [7 empty] | Work stoped due to land dispute | Munger | 2010-11 | USS-38-2 | Ing
323 | USS-142-2 | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-38-3 | Ing
324 | USS-142-3 | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | [9 empty] | 1 | Inaugurated | Munger | 2010-11 | USS-38-4 | Ing
325 | USS-15-1 | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-81-3 | Ing
326 | USS-15-2 | Bhagalpur | Sultanganj | MS Udadih 9801583582 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-42-1 | Ing
327 | USS-15-3 | Bhagalpur | NathNagar | MS Ajmeribariya 8969037136 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2009-10 | USS-42-2 | Ing
328 | USS-15-4 | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-42-3 | Ing
329 | USS-16-1 | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-44-3 | Ing
330 | USS-16-2 | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-44-5 | Ing
331 | USS-16-3 | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-9-1 | Ing
332 | USS-16-4 | Bhagalpur | Goradih | MS Garhotiya 9931865594 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-9-2 | Ing
333 | USS-17-1 | Bhagalpur | Sabaur | MS Shivaydih 9973394344 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-9-3 | Ing
334 | USS-17-2 | Bhagalpur | Kharik | MS Dadpur 8051625862/ 2 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-18-2 | Ing
335 | USS-17-3 | Bhagalpur | Bihpur | MS Kaharour 9934602158 | 1 | [10 empty] | Bhagalpur | 2009-10 | USS-18-3 | Ing
336 | USS-17-4 | Bhagalpur | Ismailpur | MS Laxmipur 9546492998 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-18-4 | Ing
337 | USS-18-1 | Banka | Barahat | MS Saharna 9431689507/ | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-19-1 | Ing
338 | USS-18-2 | Banka | Bounsi | MS Bishanpur 9006554728 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-24-1 | Ing
339 | USS-18-3 | Banka | Dhouriya | MS Bhatuachak 9955916141 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-24-2 | Ing
340 | USS-18-4 | Banka | Rajoun | MS Majhgay 9771243197 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-24-3 | Ing
341 | USS-19-1 | Banka | Amarpur | MS Bhadariya 9939749402 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 | USS-26-1 | Ing
342 | USS-19-2 | Banka | Chandan | UMS Asudha-Mukunda 9199722081 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-26-2 | Ing
343 | USS-19-3 | Banka | Katoriya | MS Bhorsar 9304136524 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-11-1 | Ing
344 | USS-19-4 | Banka | Belhar | UMS Nagel 9934928705 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-11-2 | Ing
345 | USS-19-5 | Banka | Shambhuganj | MS Rajghat 9199067916 | [8 empty] | 1 |  | WORK STOPPED SINCE MANY MONTHS | Bhagalpur | 2009-10 | USS-11-3 | Ing
346 | USS-126 (A) | Bhagalpur | Kahalgaon | M.S.Basudeopur Bhaluya 9801295281 | 1 | [9 empty] | Tender Process | Bhagalpur | 2010-11 | USS-11-4 | Ing
347 | USS-126 (B) | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-12-1 | Ing
348 | USS-126 (C) | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-12-2 | Ing
349 | USS-126 (D) | Bhagalpur | Kahalgaon | M.S. Saur 9430428851 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11 | USS-15-1 | Ing
350 | USS-127 (A) | Bhagalpur | Pirpainti | M.S.Mahuadhih 9955027709, 7549131650 | 1 | [9 empty] | Not start | Bhagalpur | 2010-11 | USS-15-2 | Ing
351 | USS-127 (B) | Bhagalpur | Pirpainti | M.S. Maultola, 9534766339 | 1 | [9 empty] | LAND PROBLEM | Bhagalpur | 2010-11 | USS-15-4 | Ing
352 | USS-127 (C) | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-16-4 | Ing
353 | USS-127 (D) | Bhagalpur | Pirpainti | M.S.Ekchari Diyara 9507752647, 9934426205 |  |  | 1 | [8 empty] | Bhagalpur | 2010-11 | USS-17-1 | Ing
354 | USS-127 (E) | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | [9 empty] | 1 |  | Bhagalpur | 2010-11 | USS-17-2 | Ing
355 | USS-128 (A) | Bhagalpur | Goradih | M.S.Birnaugha 9955198006 | [8 empty] | 1 |  | F.F.R.C. | Bhagalpur | 2010-11 | USS-17-4 | Ing
356 | USS-128 (B) | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | [9 empty] | 1 |  | Bhagalpur | 2010-11 | USS-7-1 | Ing
357 | USS-128 (C) | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11 | USS-61-1 | Ing
358 | USS-128 (D) | Bhagalpur | Sabaur | Govt. M.S.Kurpat 9204660635, 9931729153 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11 | USS-61-2 | Ing
359 | USS-129 (A) | Bhagalpur | Rangrachauk | M.S.Murli 9534523062 | 1 | [9 empty] | Land Dispute | Bhagalpur | 2010-11 | USS-61-3 | Ing
360 | USS-129 (B) | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | [9 empty] | 1 |  | Bhagalpur | 2010-11 | USS-62-1 | Ing
361 | USS-130-1 | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-62-2 | Ing
362 | USS-130-2 | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-62-3 | Ing
363 | USS-130-3 | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-48-1 | Ing
364 | USS-130-4 | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-48-2 | Ing
365 | USS-130-5 | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 | USS-48-3 | Ing
366 | USS-131-1 | Banka | Amarpur | M.S.Surihari 9931727384 | [7 empty] | 1 |  |  | Shuttering in Progress | Bhagalpur | 2010-11 | USS-48-4 | Ing
367 | USS-131-2 | Banka | Belhar | M.S.Hatiyadadha 8521126388 | [7 empty] | . | 1 |  | In Progress | Bhagalpur | 2010-11 | USS-49-2 | Ing
368 | USS-131-3 | Banka | Dhoraiya | U.M.S.Jharkha 9934883358 | [7 empty] | 1 |  |  | F.F.R.C. | Bhagalpur | 2010-11 | USS-49-3 | Ing
369 | USS-71-1 | Madhepura | Madhepura | M/S Bharahi Bazar 9852057904 | 1 | [9 empty] | LAND DISPUTE | Kosi | 2009-10 | USS-51-1 | Ing
370 | USS-71-2 | Madhepura | Murliganj | M/S Parsha Navtol 9973625392 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-51-2 | Ing
371 | USS-71-3 | Madhepura | Kumarkhand | M/S Karuvaili 9771194253 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-13-3 | Ing
372 | USS-71-4 | Madhepura | Sigheshwar | M/S Singyon 9430633497 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-13-4 | Ing
373 | USS-72-1 | Madhepura | Uda kishunganj | M/S Barataini 9631850096 | [7 empty] | 1 |  |  | Work Inaugurated Progress | Kosi | 2009-10 | USS-14-2 | Ing
374 | USS-72-2 | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | [8 empty] | 1 |  | Work Inaugurated progress | Kosi | 2009-10 | USS-14-3 | Ing
375 | USS-72-3 | Madhepura | Alamnagar | M/S Bargaon 9939489984 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-14-4 | Ing
376 | USS-73-1 | Saharsa | Saur Bazar | M/S Khajuri 9472653157 9430632563 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-52-2 | Ing
377 | USS-73-2 | Saharsa | Navhatta | M/S Kedalpatti 9939942137 8987203752 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-52-3 | Ing
378 | USS-73-3 | Saharsa | Sonbarsa | M/S Pachlakh 7549317375 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-52-4 | Ing
379 | USS-74-1 | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | [9 empty] | 1 | Work Inaugurated Progress | Kosi | 2009-10 | USS-53-4 | Ing
380 | USS-74-2 | Saharsa | Simri Bakhtiyarpur | M/S Ghoghsam 9471654377 |  |  |  | 1 | [6 empty] | Work Stopped | Kosi | 2009-10 | USS-54-2 | Ing
381 | USS-74-3 | Saharsa | Mahishi | M/S Jhara 9430696742 | [7 empty] | 1 |  |  | Work Stopped | Kosi | 2009-10 | USS-220 | Ing
382 | USS-75-1 | Supaul | Basantpur | M/S Balbhadrapur 9472034607 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-21-1 | Ing
383 | USS-75-2 | Supaul | Chatapur | M/S Madhubani 9631295927 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-67-2 | Ing
384 | USS-75-3 | Supaul | Marauna | M/S Parikoch 9931662963 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-67-3 | Ing
385 | USS-75-4 | Supaul | Raghopur | Lakhi Chand Sahu M/S Hariraha 9470047275 | [9 empty] | 1 | HANDOVER | Kosi | 2009-10 | USS-67-4 | Ing
386 | USS-76-1 | Supaul | Kishanpur | M/S Phulwaria 8298274284 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-67-5 | Ing
387 | USS-76-2 | Supaul | Pipra | M/S Ramnagar 9472335572 9570603091 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-68-1 | Ing
388 | USS-76-3 | Supaul | Supaul | M/S Kariho 9430029088 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-68-2 | Ing
389 | USS-76-4 | Supaul | Triveniganj | M/S Kumiyahi 8986062906 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10 | USS-68-3 | Ing
390 | USS-199C | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | [7 empty] | 1 |  | 1 | FF Roof Comp | Kosi | 2010-11 | USS-68-4 | Ing
391 | USS-199D-1 | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | [8 empty] | 1 |  | Work in Progress | Kosi | 2010-11 | USS-68-5 | Ing
392 | USS-199 D-2 | Madhepura | Singheshwar | Middle School Barhari 9661376885 | [9 empty] | 1 | Inaugurated | Kosi | 2010-11 | USS-68-6 | Ing
393 | USS-199D-3 | Madhepura | Kumarkhand | Middle School Rahta 9631460084 | 1 | [9 empty] | No Land | Kosi | 2010-11 | USS-69-1 | Ing
394 | USS-77-1 | Araria | Hkjxkek | mRØŒeŒfoŒjgfM+;k 9534388120 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-69-2 | Ing
395 | USS-77-2 | Araria | jkuhxat | ckfydk eŒfoŒxq.korh 9771105449 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-69-3 | Ing
396 | USS-77-3 | Araria | jkuhxat | eŒfoŒijekuaniqj 9631149958 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-69-4 | Ing
397 | USS-77-4 | Araria | ujirxat | eŒfoŒuksfu;k Vksyk pdyk 9973417759 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-70-1 | Ing
398 | USS-78-1 | Araria | Qkjfclxat | eŒfoŒe/kqcuh 9661601762 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-70-2 | Ing
399 | USS-78-2 | Araria | Qkjfclxat | eŒfoŒVs<+h eqlgjh 9801199615 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-1 | Ing
400 | USS-78-3 | Araria | vjfj;k | eŒfoŒiSdVksyk 9431087519@9431471118 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-2 | Ing
401 | USS-78-4 | Araria | vjfj;k | eŒfoŒck¡lckM+h 9430264342 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-3 | Ing
402 | USS-79-1 | Araria | dqlkZdk¡Vk | eŒfoŒdikjQksM+k 9931414194 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-57-4 | Ing
403 | USS-79-2 | Araria | fldVh | eŒfoŒlksgkxekM+ksa 9661752676@9006316855 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-1 | Ing
404 | USS-79-3 | Araria | tksdhgkV | eŒfoŒHkwuk 9570679546 | 1 | [9 empty] | May be Drop | Purnea | 2009-10 | USS-58-2 | Ing
405 | USS-79-4 | Araria | iyklh | eŒfoŒ:iSy e/kSy 9771866133 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-3 | Ing
406 | USS-80-1 | Kishanganj | fnX?kycSad | eŒfoŒgjokMaxk 8987208103 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-4 | Ing
407 | USS-80-2 | Kishanganj | Bkdqjxat | eŒfoŒtaxyHkhVk 8987254242 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-58-5 | Ing
408 | USS-80-3 | Kishanganj | dksapk/kkeu | eŒfoŒ/kuiqjk 9470868499 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-47-2 | Ing
409 | USS-80-4 | Kishanganj | iksfB;k | eŒfoŒgfjiks[kj ØkafrxkN 9430677962 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-75 | Ing
410 | USS-80-5 | Kishanganj | cgknqjxat | eŒfoŒgfjHkk"kk 9471834254 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-76-1 | Ing
411 | USS-81-1 | Purnea | dsŒ uxj | vkn'kZ eŒfoŒijksjk 9631003614 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 | USS-76-2 | Ing
412 | USS-81-2 | Purnea | dlok | mRØŒ eŒ foŒ dnok 9006717685@9162698638 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10 |  |  | 18
413 | USS-81-3 | Purnea | Mx:vk | eŒfoŒeksgEeniqj 8877902279@9852305617 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
414 | USS-82-1 | Purnea | /kenkgk | vkn'kZ eŒfoŒfo'kuiqj 8002692294 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
415 | USS-82-2 | Purnea | Hkokuhiqj | eŒfoŒczãKkuh 9931249419 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
416 | USS-82-3 | Purnea | :ikSyh | eŒfoŒykyxat 9934565697 | [9 empty] | 1 |  | Purnea | 2009-10
417 | USS-82-4 | Purnea | cueu[kh | eŒfoŒtkudh uxj gkV 9430675018 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
418 | USS-83-1 | Purnea | ok;lh | eŒfoŒvkltk ecS;k 9931676786 | 1 | [9 empty] | Avaibility Of land after one year,Contractor not Inauguratedtrested Inaugurated work now. | Purnea | 2009-10
419 | USS-83-2 | Purnea | vekSj | eŒfoŒePNÍk 9470487168@9934622591 | 1 | [10 empty] | Purnea | 2009-10
420 | USS-83-3 | Purnea | oSlk | eŒfoŒekyksikM+k 9939083102 | 1 | [10 empty] | Purnea | 2009-10
421 | USS-84-1 | Katihar | cyjkeiqj | eŒfoŒ>y>yh 9434962404@8986444230 | 1 | [9 empty] | No Land, Proposal for Drop | Purnea | 2009-10
422 | USS-84-2 | Katihar | ckjlksbZ | eŒ foŒ clyxkao 9126846409 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
423 | USS-84-3 | Katihar | ckjlksbZ | eŒ foŒ <ëk 9471674809 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
424 | USS-84-4 | Katihar | vkteuxj | eŒ foŒ tydh 9470423557@ 8877799621 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
425 | USS-85-1 | Katihar | cjkjh | eŒfoŒcfd;k lq[kk; 9572154446 | 1 | [9 empty] | Land not available(E.E letter No.-731/14-15 Dt.28.10.14 | Purnea | 2009-10
426 | USS-85-2 | Katihar | efugkjh | eŒfoŒiVuh ukjk;.kiqj 9430970158 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
427 | USS-85-3 | Katihar | Qydk | eŒfoŒ>x:pd 0431668067 | [9 empty] | 1 |  | Purnea | 2009-10
428 | USS-85-4 | Katihar | dks<+k | eŒfoŒf'kf'k;k 9431625914@ 0430582029 | [9 empty] | 1 |  | Purnea | 2009-10
429 | USS-86-1 | Katihar | venkckn | eŒfoŒfnYyh fnokuxat 9431667161@7631741488 | 1 | [9 empty] | May be Drop | Purnea | 2009-10
430 | USS-86-2 | Katihar | dnok | eŒfoŒvk'k;kuh 8986509086 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
431 | USS-86-3 | Katihar | dnok | eŒfoŒpkSdh 9470208190 | 1 | [9 empty] | May be Drop | Purnea | 2009-10
432 | USS-194-1 | Purnea | Amaur | U. M. S. Bagdar 9939096309 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
433 | USS-194-2 | Purnea | K. Nagar | M S Gauasi 9473124829 | [9 empty] | 1 |  | Purnea | 2010-11
434 | USS-194-3 | Purnea | Purnia East | M S Maranga 9939732346 | [9 empty] | 1 |  | Purnea | 2010-11
435 | USS-194-4 | Purnea | Rupauli | M. S. Bairiya 9434821065 | [9 empty] | 1 |  | Purnea | 2010-11
436 | USS-195-1 | Katihar | Amdabad | M. S. Laxmipur Daiwa 7549854721 | 1 | [10 empty] | Purnea | 2010-11
437 | USS-195-2 | Katihar | Manihari | Middle School Mirjapur 8084519254 941640318 | 1 | [10 empty] | Purnea | 2010-11
438 | USS-195-3 | Katihar | Mansahi | Middle School Mohanpur 9472890120 | 1 | [10 empty] | Purnea | 2010-11
439 | USS-196(A) | Katihar | Pranpur | Middle School Kast Hawar 8809776384 9162325809 |  |  |  | 1 | [7 empty] | Purnea | 2010-11
440 | USS-196(B) | Katihar | Ajamnagar | Middle School Arihana 8809322797 | [8 empty] | 1 |  |  | Purnea | 2010-11
441 | USS-196(C) | Katihar | Ajamnagar | Middle School Dhena Baghchhala 9801372634 | [8 empty] | 1 |  |  | Purnea | 2010-11
442 | USS-196(D) | Katihar | Pranpur | Middle School Ghanhar Vighocha 9939688768 | [7 empty] | 1 |  |  |  | Purnea | 2010-11
443 | USS-197(A) | Katihar | Barsoi | Middle School Barsoi Ghat 9431626189 |  |  |  |  | 1 | [6 empty] | Purnea | 2010-11
444 | USS-197(B) | Katihar | Dhankhora | Middle School Durgasthan Dhankhora9431869787 | 1 | [10 empty] | Purnea | 2010-11
445 | USS-197(C) | Katihar | Kodha | Middle School Marwa Najrachowki 9006363823 | [5 empty] | 1 | [5 empty] | Purnea | 2010-11
446 | USS-197(D) | Katihar | Kadwa | Dukhi Ram Middle School Chandpur9709755452 | [8 empty] | 1 |  |  | Purnea | 2010-11
447 | USS-198-1 | Katihar | Brari | Middle School Laxmipur | 1 | [9 empty] | Tender Process | Purnea | 2010-11
448 | USS-198-2 | Katihar | Brari | Middle School Anarkali | 1 | [9 empty] | Tender Process | Purnea | 2010-11
449 | USS-198-3 | Katihar | Hasanganj | Middle School Hasanganj | 1 | [9 empty] | Tender Process | Purnea | 2010-11
450 | USS-198-4 | Katihar | Phalka | Middle School Morsanda |  |  | 1 | [7 empty] | Tender Process | Purnea | 2010-11
451 | USS-198-5 | Katihar | Sameli | Middle School Dumar |  |  | 1 | [7 empty] | Tender Process | Purnea | 2010-11
452 | USS-199A (A) | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 | [9 empty] | 1 |  | Purnea | 2010-11
453 | USS-199A (B) | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 | [9 empty] | 1 |  | Purnea | 2010-11
454 | USS-199A (C) | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 | [8 empty] | 1 |  |  | Purnea | 2010-11
455 | USS-199A (D) | Araria | Narpatganj | Middle School Achra 9801296055 | [9 empty] | 1 |  | Purnea | 2010-11
456 | USS-199 B-1 | Araria | Jokihat | Middle School Jhanpur 9471219710 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
457 | USS-199 B-2 | Araria | Raniganj | Middle School Kosikapur 9199673607 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
458 | USS-199 B-3 | Araria | Araria | Middle School Araria Basti 9661185784 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
459 | USS-46-1 | Sheohar | rfj;kuh | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | [8 empty] | 1 |  |  | Tirhut East | 2009-10
460 | USS-46-2 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] cyqvk 9771099254 | [8 empty] | 1 |  |  | Tirhut East | 2009-10
461 | USS-46-3 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] FkqEek 9472379528 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
462 | USS-46-4 | Sitamarhi | csylaM | eŒ foŒ] ipukSj | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
463 | USS-47-1 | Sitamarhi | jhxk | eŒ foŒ] ;ksxokuk 9534893264 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10 | 157
464 | USS-47-2 | Sitamarhi | cFkukgk | eŒ foŒ] fMgBh 9973981418 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
465 | USS-47-3 | Sitamarhi | ukuiqj | eŒ foŒ] cÙkjk 9931668054 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
466 | USS-47-4 | Sitamarhi | ukuiqj | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
467 | USS-47-5 | Sitamarhi | lksucjlk | eŒ foŒ] bVgjok 9546578977 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
468 | USS-48-1 | Muzaffarpur | vkSjkbZ | eŒ foŒ] cSaxuk 7209905677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
469 | USS-48-2 | Muzaffarpur | ckspgk¡ | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
470 | USS-48-3 | Muzaffarpur | xk; ?kkV | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
471 | USS-48-4 | Muzaffarpur | dVjk | eŒ foŒ] cq/kdkjk 9934016332 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
472 | USS-49-1 | Muzaffarpur | dkaVh | eŒ foŒJ`axkj 8809637605 | 1 | [10 empty] | Tirhut East | 2009-10
473 | USS-49-2 | Muzaffarpur | eM+ou | eŒ foŒ] jsiqjk 8252129824 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
474 | USS-49-3 | Muzaffarpur | ehukiqj | eŒ foŒ] tkfeu efB;k 9934619525 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
475 | USS-50-1 | Muzaffarpur | ik: | eŒ foŒ] HkkstiV~Vh 9931888752 |  |  |  |  | 1 | [6 empty] | Tirhut East | 2009-10
476 | USS-50-2 | Muzaffarpur | ik: | eŒ foŒ] pkaniqj 9801265669 |  |  |  |  | 1 | [6 empty] | Tirhut East | 2009-10
477 | USS-50-3 | Muzaffarpur | lkgscxat | eŒ foŒ] 'kkgiqj iV~Vh 9801128043 |  |  |  |  | 1 | [6 empty] | Tirhut East | 2009-10
478 | USS-50-4 | Muzaffarpur | ljS;k | eŒ foŒ] xksjhxkekMhg 9431615151 | [5 empty] | 1 | [5 empty] | Tirhut East | 2009-10
479 | USS-51-1 | Muzaffarpur | ldjk | eŒ foŒ] ckth cqtqxZ 9572907300 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
480 | USS-51-2 | Muzaffarpur | eq'kgjh | eŒ foŒ] fn?kM+k 9430051489@9304110351 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
481 | USS-51-3 | Muzaffarpur | eksrhiqj | eŒ foŒ] ckjthMhg 9934895236 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
482 | USS-52-1 | Vaishali | lgnsbZ cqtqxZ | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
483 | USS-52-2 | Vaishali | egukj | eŒ foŒ deyk dU;k] djukSrh 8002747546 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
484 | USS-52-3 | Vaishali | tUnkgk | eŒ foŒ] jlqyiqj 8651291731 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
485 | USS-52-4 | Vaishali | fonqiqj | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
486 | USS-53-1 | Vaishali | gkthiqj | eŒ foŒ] yksek 9470638549 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
487 | USS-53-2 | Vaishali | gkthiqj | eŒ foŒ] dqrqciqj 9905099533 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
488 | USS-53-3 | Vaishali | ykyxat | eŒ foŒ] xqjfe;k 8651626851 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
489 | USS-53-4 | Vaishali | xksjkSy | eŒ foŒ] Bhdgk¡ 9431254109 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
490 | USS-54-1 | Vaishali | jktkikdj | eŒ foŒ] csydqaMk 7677785326 | 1 | [10 empty] | Tirhut East | 2009-10
491 | USS-54-2 | Vaishali | ikrsiqj | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
492 | USS-54-3 | Vaishali | jk?kksiqj | eŒ foŒ] ohjiqj 9931458401 | [9 empty] | 1 |  | Tirhut East | 2009-10
493 | USS-162 (A) | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | [8 empty] | 1 |  | Plaster Done , Flooring in Progress | Tirhut East | 2010-11
494 | USS-162 (B) | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
495 | USS-162 (C) | Sitamarhi | Suppi | M. S. Aktha 9470821881 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
496 | USS-162 (D) | Sitamarhi | Riga | M. S. Ramnagara 9570781314 | 1 | [10 empty] | Tirhut East | 2010-11
497 | USS-162 (E) | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 | [8 empty] | 1 |  | G.f Electric, Internal Plaster In Progress Plumbing Start | Tirhut East | 2010-11
498 | USS-162 (F) | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 | [9 empty] | 1 |  | Tirhut East | 2010-11
499 | USS-163 (A) | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 | [9 empty] | 1 |  | Tirhut East | 2010-11
500 | USS-163 (B) | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
501 | USS-163 (C) | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
502 | USS-163 (D) | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 | [7 empty] | 1 |  |  | Roof Casted 23.12.15 | Tirhut East | 2010-11
503 | USS-164-1 | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
504 | USS-164-2 | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
505 | USS-164-3 | Vaishali | Bhagwanpur | M. S. Askaranpur | [9 empty] | 1 |  | Tirhut East | 2010-11
506 | USS-164-4 | Vaishali | Bhagwanpur | M. S. Kutubpur 9534509369 | 1 | [9 empty] | No Land | Tirhut East | 2010-11
507 | USS-164-5 | Vaishali | Lalganj | U.M.S. Basanta 9934417163 | 1 | [9 empty] | No Land | Tirhut East | 2010-11
508 | USS-165-1 | Vaishali | Jandaha | U. M.S. Shahpur Rohuya 9934414222 | [7 empty] | 1 |  |  | Work stoped by Contractor without any reason | Tirhut East | 2010-11
509 | USS-165-2 | Vaishali | Jandaha | M. S, Mahhisaur 9661844106 |  |  |  | 1 | [7 empty] | Tirhut East | 2010-11
510 | USS-165-3 | Vaishali | Sahadei Bujurg | M.S, Toimath 9939693675 | [7 empty] | 1 |  |  |  | Tirhut East | 2010-11
511 | USS-165-4 | Vaishali | Sahadei Bujurg | M.S, Nayaganj 9934912623 | 1 | [10 empty] | Tirhut East | 2010-11
512 | USS-165-5 | Vaishali | Jandaha | M.S, Bijrauti 9973922533 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
513 | USS-166 (A) | Vaishali | Raghopur | M. S,Tersiya 9631970772 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
514 | USS-166 (B) | Vaishali | Raghopur | M.S,Paharpur 7654539556 | [9 empty] | 1 | handover | Tirhut East | 2010-11
515 | USS-166 (C) | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 | 1 | [10 empty] | Tirhut East | 2010-11
516 | USS-166 (D) | Vaishali | Desari | M. S, Bhikhanpura 9973319373 |  |  |  | 1 | [6 empty] | Exavation | Tirhut East | 2010-11
517 | USS-166 (E) | Vaishali | Rajapakar | M. S, Makhadumpur Pokhraira 9934478747 | [7 empty] | 1 |  |  |  | Tirhut East | 2010-11
518 | USS-167-1 | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
519 | USS-167-2 | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
520 | USS-167-3 | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
521 | USS-167-4 | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
522 | USS-167-5 | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
523 | USS-168-1 | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
524 | USS-168-2 | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
525 | USS-168-3 | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
526 | USS-168-4 | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
527 | USS-169-1 | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
528 | USS-169-2 | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
529 | USS-169-3 | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
530 | USS-169-4 | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
531 | USS-169-5 | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
532 | USS-170-1 | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
533 | USS-170-2 | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 | [9 empty] | 1 |  | Tirhut East | 2010-11
534 | USS-170-3 | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
535 | USS-170-4 | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | [9 empty] | 1 | Internal Plaster ELECTRIC Plumbing In Progress, | Tirhut East | 2010-11
536 | USS-170-5 | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
537 | USS-171-1 | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
538 | USS-171-2 | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 | [9 empty] | 1 |  | Tirhut East | 2010-11
539 | USS-171-3 | Muzaffarpur | Gaighat | M. S,Dahila 9973658759 | [8 empty] | 1 |  | Plaster , flooring Just Done | Tirhut East | 2010-11
540 | USS-171-4 | Muzaffarpur | Katra | M. S, Bakhari 9631173639 | [8 empty] | 1 |  | Flooring , Done sanitary , electric Painting Running | Tirhut East | 2010-11
541 | USS-171-5 | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | [8 empty] | 1 |  | Outer Plaster Start | Tirhut East | 2010-11
542 | USS-172-1 | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
543 | USS-172-2 | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
544 | USS-172-3 | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
545 | USS-172-4 | Muzaffarpur | Mushhari | M. S, Dronpur | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
546 | USS-172-5 | Muzaffarpur | Muraul | M. S, Pilkhi | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
547 | USS-37-1 | West Champaran | Manjhauliya | M.S.Aharwar Shekh 9470655463 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
548 | USS-37-2 | West Champaran | Manjhauliya | M.S. Parsa Bahuarwa 9470859628 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
549 | USS-37-3 | West Champaran | Bairiya | M.S. Bathna 9431466192 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
550 | USS-37-4 | West Champaran | Nautan | M.S. Mangalpur 9430691686 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
551 | USS-38-1 | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
552 | USS-38-2 | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
553 | USS-38-3 | West Champaran | Lauriya | M.S.Dhobani 9430571439 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
554 | USS-38-4 | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
555 | USS-39-1 | West Champaran | Mainatand | M.S. Tajpur 8986956152 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
556 | USS-39-2 | West Champaran | Mainatand | M.S. Sukhlahi 9546120109 | [8 empty] | 1 |  |  | Tirhut West | 2009-10
557 | USS-39-3 | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
558 | USS-40-1 | West Champaran | Narkatiaganj | M.S. Shomgarh 9470256119 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
559 | USS-40-2 | West Champaran | Yogapatti | M.S. Kohra 9934686513 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
560 | USS-40-3 | West Champaran | Ramnagar | M.S. Sher Hawa Don 9470860764 |  |  |  | 1 | [7 empty] | Tirhut West | 2009-10
561 | USS-41-1 | East Champaran | Motihari | M.S. Jamla 9934828027 | [8 empty] | 1 |  |  | Tirhut West | 2009-10
562 | USS-41-2 | East Champaran | Banjariya | M.S. Kukurjari 9708975580 | [6 empty] | 1 |  |  |  |  | Tirhut West | 2009-10
563 | USS-41-3 | East Champaran | Turkauliya | M.S. Vishnupurwa 9801485906 | [8 empty] | 1 |  |  | Tirhut West | 2009-10
564 | USS-41-4 | East Champaran | Chiraiya | M.S. Parewa 9386155278 |  |  |  |  | 1 | [6 empty] | Tirhut West | 2009-10
565 | USS-42-1 | East Champaran | Areraj | M.S. Radhiya 9576399366 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
566 | USS-42-2 | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
567 | USS-42-3 | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
568 | USS-42-4 | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
569 | USS-43-1 | East Champaran | Raxaul | M.S. Gonha 9470284937 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
570 | USS-43-2 | East Champaran | Sugauli | M.S. Muswa 9471878742 | [6 empty] | 1 |  |  |  |  | Tirhut West | 2009-10
571 | USS-43-3 | East Champaran | Aadapur | M.S. Beldarwa 9771769291 / 9472911484 |  |  |  |  | 1 | [6 empty] | Tirhut West | 2009-10
572 | USS-43-4 | East Champaran | Chhauradano | M.S. Pakariya Urdu 9470233197 | 1 | [10 empty] | Tirhut West | 2009-10
573 | USS-44-1 | East Champaran | Chakiya | M.S. Chintamanpur 9546123872 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
574 | USS-44-2 | East Champaran | kalyanpur | M.S. Mandhwa Urdu 9939516692 | 1 | [10 empty] | Tirhut West | 2009-10
575 | USS-44-3 | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
576 | USS-44-4 | East Champaran | Mehshi | M.S. Jhitkahiya 9162250321 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
577 | USS-44-5 | East Champaran | Paharpur | M.S. Siswa Bazar 8809296371 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
578 | USS-45-1 | East Champaran | Dhaka | M.S. Chandanbara Urdu 9931213480 | [5 empty] | 1 | [5 empty] | Tirhut West | 2009-10
579 | USS-45-2 | East Champaran | Patahi | M.S. Betauna 9708717133 |  |  |  |  | 1 | [6 empty] | Tirhut West | 2009-10
580 | USS-45-3 | East Champaran | Madhuban | M.S. Gurmiya |  |  |  | 1 | [7 empty] | Tirhut West | 2009-10
581 | USS-45-4 | East Champaran | Ghorasahan | M.S. Laxmipur Laukhan 9431652891 | [7 empty] | 1 |  |  |  | Tirhut West | 2009-10
582 | USS-158-1 | East Champaran | Turkauliya | M.S. Belwa Ray 9430645457 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
583 | USS-158-2 | East Champaran | Turkauliya | M.S. Jaishinghpur 9430209305 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
584 | USS-158-3 | East Champaran | Motihari | M.S. Basantpur 9576483588 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
585 | USS-159-1 | East Champaran | Pakridayal | M.S. Sishani 9934715029 | [7 empty] | 1 |  |  |  | Tirhut West | 2010-11
586 | USS-159-2 | East Champaran | chaaiya | M.S. Madhubani 9430565177 | 1 | [10 empty] | Tirhut West | 2010-11
587 | USS-159-3 | East Champaran | Tetariya | M.S. Maniyarpur 9471297810 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
588 | USS-159-4 | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
589 | USS-159-5 | East Champaran | Ghorasahan | M.S. Samanpur 9939403946 | [5 empty] | 1 | [5 empty] | Tirhut West | 2010-11
590 | USS-160-1 | West Champaran | Lauriya | Govt.M.S. Phulwariya 9431674559 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
591 | USS-160-2 | West Champaran | Narkatiyaganj | Govt.M.S. Bhadiharwa 8986137181 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
592 | USS-160-3 | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
593 | USS-160-4 | West Champaran | Madhubani | M.S.Pakri Ahawa Khothwa 08002571785 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
594 | USS-160-5 | West Champaran | Nautan | M.S.Sansariya 8757124792 | 1 | [10 empty] | Tirhut West | 2010-11
595 | USS-161-1 | Sheohar | Purnhiya | M.S.Basant Jagivan 9430526421 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
596 | USS-161-2 | Sheohar | Dumri Katsari | M.S.Phulkaha 9631003475 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
597 | USS-61-1 | Madhubani | ?kks?kjMhgk | eŒ foŒ] xax}kj 9934407620 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
598 | USS-61-2 | Madhubani | >a>kjiqj | eŒ foŒ]ykSguk 9430835195 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
599 | USS-61-3 | Madhubani | ykSdgh | eŒ foŒ] dyqvkgh 9572025500 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
600 | USS-62-1 | Madhubani | t;uxj | eŒ foŒflyukFk cjgh 9572618953 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
601 | USS-62-2 | Madhubani | i.MkSy | eŒ foŒ] 'kkgiqj 9973048002 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
602 | USS-62-3 | Madhubani | jktuxj | eŒ foŒ] eaxjkSuh 9931643145 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
603 | USS-63-1 | Darbhanga | guqeku uxj | eŒfoŒ]Fkyokjk 9771791978 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
604 | USS-63-2 | Darbhanga | cgsM+h | eŒfoŒ fctqfy;k 9939521323 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
605 | USS-63-3 | Darbhanga | cgknqjiqj | mRØŒeŒfoŒ dejkSyh 9801391631 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
606 | USS-64-1 | Darbhanga | ?ku';keiqj | eŒfoŒ]rqekSy 9939754496 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
607 | USS-64-2 | Darbhanga | csuhiqj | mRØŒeŒfoŒ jf<+;ke 9770623526 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
608 | USS-64-3 | Darbhanga | euhxkNh | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
609 | USS-64-4 | Darbhanga | rkjMhg | mRØŒeŒfoŒ rkjMhg 9934870957 | 1 | [9 empty] | L.N.A. | Darbhanga | 2009-10
610 | USS-65-1 | Darbhanga | dq'ks'oj LFkku iwŒ | mRØŒeŒfoŒ egknso eB 9973391579 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
611 | USS-65-2 | Darbhanga | dq'ks'oj LFkku iŒ | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
612 | USS-65-3 | Darbhanga | fojkSy | eŒfoŒ]iVfu;k¡ 9771113614 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
613 | USS-66-1 | Darbhanga | fal?kokM+k | mRØŒeŒfoŒ e/kqiqj 9934911481 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
614 | USS-66-2 | Darbhanga | dsoVh | eŒfoŒ]dks;yk LFkku 9905459110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
615 | USS-66-3 | Darbhanga | njHkaxk xzkeh.k | mRØŒeŒfoŒ cygk 9570479967 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
616 | USS-67-1 | Samastipur | iVksjh | eŒfoŒ]njok 8757084952 | 1 | [9 empty] | L.N.A. | Darbhanga | 2009-10
617 | USS-67-2 | Samastipur | nyflag ljk; | eŒfoŒ]ekyiqj 9934140121 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
618 | USS-67-3 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]fcUn ckspgk 9939988449 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
619 | USS-67-4 | Samastipur | fo¦kifr uxj | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
620 | USS-67-5 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]efu;kj 7549600801 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
621 | USS-68-1 | Samastipur | foHkwfriqj | eŒfoŒ]nsljh 9939816100 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
622 | USS-68-2 | Samastipur | fcFkku | eŒfoŒ]NsNuh 9934979521 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
623 | USS-68-3 | Samastipur | gluiqj | mRØŒeŒfoŒ egqyh 9801690551 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
624 | USS-68-4 | Samastipur | f'kokth uxj | eŒfoŒ]Jhiqjetjfg;k 9955507715 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
625 | USS-68-5 | Samastipur | foHkwfriqj | eŒfoŒ]irSfy;k 9973163333 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
626 | USS-68-6 | Samastipur | f'kokth uxj | eŒfoŒ]jkuhiêh 9955989162 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
627 | USS-69-1 | Samastipur | dY;k.kiqj | eŒfoŒ]eksjokjk 9162249115 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
628 | USS-69-2 | Samastipur | leLrhiqj | eŒfoŒ][kksM+h 9263781760 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
629 | USS-69-3 | Samastipur | mft;kiqj | eŒfoŒ]vaxkj ?kkV 9204971619 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
630 | USS-69-4 | Samastipur | mft;kiqj | eŒfoŒdksjc)k] irSyh 9263731315 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
631 | USS-70-1 | Samastipur | eksjok | eŒfoŒ iq:"kksreiqj 9973123260 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
632 | USS-70-2 | Samastipur | iwlk | eŒfoŒ]efYydkSj | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
633 | USS-187-1 | Madhubani | Babu Barhi | M. S. Barhara | [8 empty] | 1 |  |  | Darbhanga | 2010-11
634 | USS-187-2 | Madhubani | Lakhanpur | M. S. Belaucha | 1 | [9 empty] | Land Not Avilabl e | Darbhanga | 2010-11
635 | USS-187-3 | Madhubani | Jaynagar | Middle School, Dhaniyapatti 9931037199 9661794550 | 1 | [9 empty] | Land Not Avilabl e | Darbhanga | 2010-11
636 | USS-187-4 | Madhubani | Rajnagar | Govt. M S, Kewalpatti 9430032594 8051418065 | [7 empty] | 1 |  |  |  | Darbhanga | 2010-11
637 | USS-187-5 | Madhubani | Khutauna | Middle School, Malin Belha 9572178379 | [6 empty] | 1 |  |  |  |  | Darbhanga | 2010-11
638 | USS-188-1 | Madhubani | Banipatti | M. S.Ganguli 9431629001 | 1 | [9 empty] | AGREEMENT NOT DONE (CONTRACTOR REFUSED) | Darbhanga | 2010-11
639 | USS-188-2 | Madhubani | Kaluahi | M. S.Kalikapur 9973900631 | 1 | [10 empty] | Darbhanga | 2010-11
640 | USS-188-3 | Madhubani | Bisfi | M. S.Singhaso 9162249674 8051935537 | 1 | [10 empty] | Darbhanga | 2010-11
641 | USS-189-1 | Samastipur | Shivajinagar | M. S. Shripur Bhataura | 1 | [9 empty] | Land Not Avilabl e | Darbhanga | 2010-11
642 | USS-189-2 | Samastipur | Vibhutipur | U. M. S, Mustafapur | 1 | [9 empty] | LOW LAND | Darbhanga | 2010-11
643 | USS-190-1 | Darbhanga | Kusheshwarsthan E | U. M. S, Barniya 7870017996 | [5 empty] | 1 | [5 empty] | Darbhanga | 2010-11
644 | USS-190-2 | Darbhanga | Kusheshwarsthan W | U. M. S, Sihariya 8969431987 | [5 empty] | 1 | [5 empty] | Darbhanga | 2010-11
645 | USS-191-1 | Darbhanga | Manigachhi | U. M. S, Dahaura 9431405480 | 1 | [9 empty] | Land Not Avilabl e | Darbhanga | 2010-11
646 | USS-191-2 | Darbhanga | Kewati | M. S, Koila Majhigama 9304020023 | 1 | [9 empty] | LAND DISPUTE | Darbhanga | 2010-11
647 | USS-191-3 | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
648 | USS-191-4 | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
649 | USS-191-5 | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
650 | USS-192 A | Darbhanga | Bahadurpur | M. S, Daing 9199229540 | [6 empty] | 1 |  |  |  |  | Darbhanga | 2010-11
651 | USS-192 B | Darbhanga | Biraul | M. S, Koilajan 9939650547 | [6 empty] | 1 |  |  |  |  | Darbhanga | 2010-11
652 | USS-192 C | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 | [9 empty] | 1 |  | Darbhanga | 2010-11
653 | USS-192 D | Darbhanga | Biraul | U. M. S, Balha 7631905606 | [9 empty] | 1 |  | Darbhanga | 2010-11
654 | USS-193-1 | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
655 | USS-193-2 | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
656 | USS-193-3 | Darbhanga | Alinagar | U. M. S, Rampur Uday 9546520079 | 1 | [9 empty] | L.N.A. | Darbhanga | 2010-11
657 | USS-193-4 | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
658 | USS-55-1 | Gopalganj | Baikunthapur | M. School, Deokulli, Mob.: 9708861129 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
659 | USS-55-2 | Gopalganj | Baikunthapur | M. School, Maharani, Mob.:9199443900 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
660 | USS-55-3 | Gopalganj | Kuchayakot | M. School, Mahuaba, Hindi, Mob.: 9430055420/9162622220 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
661 | USS-55-4 | Gopalganj | Singhawalia | U. M. School, Dumaria East, Mob.: 9955648224 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
662 | USS-56-1 | Gopalganj | Bhore | M. School, Shivarajpur, Mob.: 9973200939 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
663 | USS-56-2 | Gopalganj | Kattaya | M. School, Rudrapur, Mob.: 9628550100 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
664 | USS-56-3 | Gopalganj | Kuchayakot | M. School, Purkhaus, Mob.: 9955647418 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
665 | USS-56-4 | Gopalganj | Vijayipur | M. School, Mathaulli, Mob.: 9838674751 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
666 | USS-57-1 | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
667 | USS-57-2 | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
668 | USS-57-3 | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
669 | USS-57-4 | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
670 | USS-58-1 | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
671 | USS-58-2 | Siwan | Guddhani | U. M. School, Bangardha, Mob.: 9801180809 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
672 | USS-58-3 | Siwan | Daraulli | M. School, Dumarhar Bujurga, Mob.: 9199854822 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
673 | USS-58-4 | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
674 | USS-58-5 | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
675 | USS-59-1 | Saran | Masharrakha | M. School, Dum Dumma, Mob.: 9006658111 | [6 empty] | 1 |  |  |  |  | Saran | 2009-10
676 | USS-59-2 | Saran | Panapur | U. M. School, Panapur, Mob.: 9199453564 | [5 empty] | 1 | [5 empty] | Saran | 2009-10
677 | USS-59-3 | Saran | Tarraiyan | M. School, Parauna Balak, Mob.: 9931139238 | [7 empty] | 1 |  |  |  | Saran | 2009-10
678 | USS-59-4 | Saran | Jalalpur | M. School, Nawadah, Mob.: 9431630231 | [7 empty] | 1 |  |  |  | Saran | 2009-10
679 | USS-60-1 | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
680 | USS-60-2 | Saran | Manjhi | M. School, Dumari, Mob.: 8083701946/8757054210 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
681 | USS-60-3 | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
682 | USS-60-4 | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
683 | USS-60-5 | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
684 | USS-173 (A) | Siwan | Husainganj | M. S, Hata Tola Chhata 9546660912 |  |  | 1 | [8 empty] | Saran | 2010-11
685 | USS-173 (B) | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
686 | USS-174-1 | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
687 | USS-174-2 | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 | [9 empty] | 1 |  | Saran | 2010-11
688 | USS-174-3 | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
689 | USS-174-4 | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
690 | USS-175-1 | Siwan | Siswan | M. S, Gyaspur 8809341191 | [9 empty] | 1 | Hand Over | Saran | 2010-11
691 | USS-175-2 | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
692 | USS-175-3 | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
693 | USS-175-4 | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
694 | USS-176-1 | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
695 | USS-176-2 | Siwan | Gudhani | M. S, Belauri 8809165382 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
696 | USS-176-3 | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
697 | USS-177-1 | Saran | Dariyapur | Middle School, Saraiya 9431647901 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
698 | USS-177-2 | Saran | Dariyapur | Middle School, Bhongha 9006298659 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
699 | USS-177-3 | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
700 | USS-177-4 | Saran | Dighwara | Middle School, Malkhachak 9135336330 |  | 1 | [9 empty] | Saran | 2010-11
701 | USS-178-1 | Saran | Sonpur | Middle School, Shikharpur 9631221348 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
702 | USS-179-1 | Saran | Lahaladpur | Middle School, Basahi Urdu | [9 empty] | 1 | Inaugurated | Saran | 2010-11
703 | USS-179-2 | Saran | Ekma | Middle School, Bhodasa | [9 empty] | 1 | Inaugurated | Saran | 2010-11
704 | USS-179-3 | Saran | Ekma | Middle School, Betbaniya 8294839353 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
705 | USS-179-4 | Saran | Ekma | Middle School, Eksar 9572740280 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
706 | USS-179-5 | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
707 | USS-181-1 | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
708 | USS-182-1 | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
709 | USS-182-2 | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
710 | USS-182-3 | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
711 | USS-183-1 | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
712 | USS-183-2 | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
713 | USS-183-3 | Gopalganj | Kuchaikot | Middle School, Balthari 9973181137 | 1 | [9 empty] | Low Land | Saran | 2010-11
714 | USS-183-4 | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
715 | USS-184-1 | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
716 | USS-184-2 | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
717 | USS-184-3 | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
718 | USS-184-4 | Gopalganj | Singhwaliya | Middle School, Amarpura Jagiraha 9801115115 | 1 | [9 empty] | Land Not Available | Saran | 2010-11
719 | USS-185-1 | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
720 | USS-185-2 | Gopalganj | Gopalganj | Middle School, Karariya 9934499260 | 1 | [9 empty] | Land Problem | Saran | 2010-11
721 | USS-185-3 | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
722 | USS-185-4 | Gopalganj | Gopalganj | Middle School, Baraipatti 9955771721 | 1 | [9 empty] | Land Problem | Saran | 2010-11
723 | USS-186-1 | Gopalganj | Hathua | U. M. S, Satai 8757888461 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
724 | USS-186-2 | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
725 | USS-186-3 | Gopalganj | Hathua | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 | 1 | [9 empty] | Land Problem | Saran | 2010-11
726 | USS-186-4 | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 | [9 empty] | 1 |  | Saran | 2010-11
| Total No. of Schools-RMSA (USS) |  |  | 726 | 99 | 3 | 10 | 8 | 11 | 30 | 10 | 26 | 85 | 445 | 387
| Retender |  |  | 3
| Tender Process |  |  | 9
| Contract Award (2009-10) CF |  |  | 323
| Contract Award (2010-11) CF |  |  | 400
| Inaugurated (2009-10) & (2010-11) |  |  | 387
Note on P47: Group will closed due dely in land availability.
Note on U60: accord. To div. USS-34-B-2 instead of USS-34-5
Note on B62: ACCORD. TO 475 USS-108-1
Note on U139: Author:
Note on W226: ACCORD. TO DIV. USS-182-2
Note on U227: ACCORD. TO DIV. USS-182-3 INSTEAD OF uss-182-5
Note on E353: Gurudev Const.
Note on E356: Gurudev Const.
Note on U370: according to div. USS-49-1 instead of USS-49-2 & 3
Note on B718: List from 161 & 250 ing list

## Completed 2009-10
BSEIDC , Patna
Completed List of USS 2009-10
S.N. | Group No. | Name of District | Name of Block | Name of School | Remarks | Division | Session | Division
1 | USS-1-1 | Nalanda | p.Mh | eŒfoŒlwedk 9931607862 | Inaugurated |  |  | Patna East
2 | USS-1-2 | Nalanda | bLykeiqj | eŒfoŒenkjxat 9631262679 | Inaugurated |  |  | Patna East
3 | USS-1-3 | Nalanda | fgylk | eŒfoŒvdcjiqj 9470085363 | Inaugurated |  |  | Patna East
4 | USS-1-4 | Nalanda | fcgkj 'kjhQ | eŒfoŒflaxFkq 9204881769 | Inaugurated |  |  | Patna East
5 | USS-2-2 | Nalanda | drjhljk; | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | Inaugurated |  |  | Patna East
6 | USS-2-3 | Nalanda | jktxhj | eŒfoŒygqvkj 9798642205@9504394778 | Inaugurated |  |  | Patna East
7 | USS-2-4 | Nalanda | flyko | eŒfoŒujgj fcxgk 8002186727 | Inaugurated |  |  | Patna East
8 | USS-3-2 | Patna | ck<+ | eŒfoŒeqckjdiqj 9631978359 | Inaugurated |  |  | Patna East
9 | USS-3-3 | Patna | Qrqgk¡ | eŒfoŒMqejh 8521893444 | Inaugurated |  |  | Patna East
10 | USS-3-4 | Patna | Qrqgk¡ | mRØŒeŒfoŒip:f[k;k 9801459905 | Inaugurated |  |  | Patna East
11 | USS-4-1 | Patna | nkukiqj | eŒfoŒvdhyiqj 9835490244 | Inaugurated |  |  | Patna East
12 | USS-4-2 | Patna | ukScriqj | eŒfoŒvgqvkjk 9939680617 | Inaugurated |  |  | Patna East
13 | USS-5-1 | Patna | /ku:vk | eŒfoŒdkslqr 9973270948@9974270948 | Inaugurated |  |  | Patna East
14 | USS-5-2 | Patna | elkS<+h | eŒfoŒNkrk 8084994281 | Inaugurated |  |  | Patna East
15 | USS-5-3 | Patna | lairpd | eŒfoŒyadk dNqvkjk 9162137790 | Inaugurated |  |  | Patna East
16 | USS-5-4 | Patna | iquiqu | eŒfoŒdY;k.kiqj 9507549063 | Final |  |  | Patna East
17 | USS-9-1 | Buxar | cDlj | eŒfoŒd`riqjk 9576622685 | Inaugurated |  |  | Patna West
18 | USS-9-2 | Buxar | pkSlk | eŒfoŒcukjiqj 8873946373 | Inaugurated |  |  | Patna West
19 | USS-9-3 | Buxar | jktiqj | eŒfoŒjlsu 9006272320 | Inaugurated |  |  | Patna West
20 | USS-9-4 | Buxar | bVkM+h | eŒfoŒcSdqUBiqj 9931755863 | Inaugurated |  |  | Patna West
21 | USS-10-1 | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | Inaugurated |  |  | Patna West
22 | USS-10-2 | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | Inaugurated |  |  | Patna West
23 | USS-10-4 | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | Inaugurated |  |  | Patna West
24 | USS-11-1 | Kaimur | dqnjk | eŒfoŒvojS;k 9973613935 | Inaugurated |  |  | Patna West
25 | USS-11-2 | Kaimur | eksgfu;k¡ | eŒfoŒdVjkdyk 9006263731 | Inaugurated |  |  | Patna West
26 | USS-11-3 | Kaimur | jkex<+ | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | Inaugurated |  |  | Patna West
27 | USS-11-4 | Kaimur | nqxkZorh | eŒfoŒnqxkZorh 9430340748@9955221828 | Inaugurated |  |  | Patna West
28 | USS-12-1 | Kaimur | HkHkqvk | eŒfoŒdqM+klu 9031437647 | Inaugurated |  |  | Patna West
29 | USS-12-2 | Kaimur | pSuiqj | eŒfoŒdasok 9430026932 | Inaugurated |  |  | Patna West
30 | USS-13-1 | Rohtas | djxgj | eŒfoŒrksjuh 9631253327 | Inaugurated |  |  | Patna West
31 | USS-13-3 | Rohtas | lklkjke | eŒfoŒfldfj;k 9431464894 | Inaugurated |  |  | Patna West
32 | USS-13-4 | Rohtas | dkspl | eŒfoŒegqvkjh 9661222301 | Inaugurated |  |  | Patna West
33 | USS-14-1 | Rohtas | fMgjh | eŒfoŒxaxkSyh 7352200057 | Inaugurated |  |  | Patna West
34 | USS-14-2 | Rohtas | fnukjk | eŒfoŒljuk 9771634397 | Inaugurated |  |  | Patna West
35 | USS-14-3 | Rohtas | dkjkdkV | eŒfoŒeksguiqj 9801296392 | Inaugurated |  |  | Patna West
36 | USS-14-4 | Rohtas | uks[kk | eŒfoŒ?kksjfMgk 9801894133 | Inaugurated |  |  | Patna West
37 | USS-28-1 | Jehanabad | tgkukckn | eŒfoŒveSu 9473327625 | Inaugurated |  |  | Magadh
38 | USS-28-2 | Jehanabad | dkdks | eŒfoŒHknljk 9006927848 | Inaugurated |  |  | Magadh
39 | USS-28-3 | Jehanabad | e[knqeiqj | eŒfoŒdksgjk 9162155024 | Inaugurated |  |  | Magadh
40 | USS-29-1 | Aurangabad | nso | eŒfoŒcs<+uh 9631266207 | Inaugurated |  |  | Magadh
41 | USS-29-2 | Aurangabad | enuiqj | eŒfoŒfijok¡ 9934340488 | Inaugurated |  |  | Magadh
42 | USS-29-4 | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | Inaugurated |  |  | Magadh
43 | USS-30-1 | Aurangabad | vkscjk | eŒfoŒ'kadjiqj 7739690373 | Inaugurated |  |  | Magadh
44 | USS-30-2 | Aurangabad | nkmnuxj | eŒfoŒteqvkok¡ 9801563600 | Inaugurated |  |  | Magadh
45 | USS-30-3 | Aurangabad | nkmnuxj | eŒfoŒpkSjh 9934434990 | Inaugurated |  |  | Magadh
46 | USS-30-4 | Aurangabad | gliqjk | eŒfoŒdksbyok¡ 9135312996 | Inaugurated |  |  | Magadh
47 | USS-31-1 | Aurangabad | dqVqEck | eŒfoŒfjfl;i 9955874942 | Inaugurated |  |  | Magadh
48 | USS-31-2 | Aurangabad | uohuxj | eŒfoŒiM+fj;k 9931622753 | Inaugurated |  |  | Magadh
49 | USS-31-3 | Aurangabad | ok:.k | eŒfoŒikSFkq 9471060433 | Inaugurated |  |  | Magadh
50 | USS-32-1 | Gaya | cks/k x;k | eŒfoŒchjgqr 9934480418 |  |  |  | Magadh
51 | USS-32-2 | Gaya | uxj fuxe | eŒfoŒpwjh 9199466924 | Inaugurated |  |  | Magadh
52 | USS-32-3 | Gaya | osykxat | mRØŒeŒfoŒve>j 9931835374 | Inaugurated |  |  | Magadh
53 | USS-32-4 | Gaya | fVdkjh | eŒfoŒrkik Qrsgiqj 9430070517 | Inaugurated |  |  | Magadh
54 | USS-33-1 | Gaya | MksHkh | eŒfoŒihjklhu 9473140628 | Inaugurated |  |  | Magadh
55 | USS-33-2 | Gaya | dksp | eŒfoŒfnX?kh 9576852929 | Inaugurated |  |  | Magadh
56 | USS-33-3 | Gaya | f[ktjljk; | eŒfoŒvkneiqj 9771084118 | Inaugurated |  |  | Magadh
57 | USS-33-4 | Gaya | cthjxat | eŒfoŒikys 9955418354 | Inaugurated |  |  | Magadh
58 | USS-34 A-2 | Gaya | Qrsgiqj | eŒfoŒckiwxzke 9934840966 | Inaugurated |  |  | Magadh
59 | USS-34 A-3 | Gaya | eksguiqj | eŒfoŒvedksyk 9955837262 | Inaugurated |  |  | Magadh
60 | USS-34 B-1 | Gaya | xq:vk | eŒfoŒpk¡lh 9006129640 | Inaugurated |  |  | Magadh
61 | USS-34 B-2 | Gaya | bekexat | mRØŒeŒfoŒ]dksBh 9931625800 | Inaugurated |  |  | Magadh
62 | USS-35-2 | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 |  |  |  | Magadh
63 | USS-36-2 | Nawada | jtkSyh | mRØŒeŒfoŒ]ckjkVk¡M loS;k | Inaugurated |  |  | Magadh
64 | USS-36-3 | Nawada | fljnyk | eŒfoŒlka< 9771960601 | Inaugurated |  |  | Magadh
65 | USS-21-1 | Sheikhpura | 'ks[kiqjk | eŒfoŒckn'kkgiqj 9709066149 | Inaugurated |  |  | Munger
66 | USS-22-1 | Jamui | pdkbZ | eŒfoŒnqyeiqj 9973390953@9661984491 | Inaugurated |  |  | Munger
67 | USS-22-2 | Jamui | >k>k | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | Inaugurated |  |  | Munger
68 | USS-22-3 | Jamui | lksuks | eŒfoŒiSjk efVgkuk 9801576608 | Inaugurated |  |  | Munger
69 | USS-23-1 | Jamui | teqbZ | mRØŒeŒfoŒ HkkVpd 9430818763 | Inaugurated |  |  | Munger
70 | USS-23-2 | Jamui | y{ehiqj | eŒfoŒgjyk 9162733763@9006655639 | Inaugurated |  |  | Munger
71 | USS-23-3 | Jamui | [kSjk | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | Inaugurated |  |  | Munger
72 | USS-23-4 | Jamui | bZŒ vyhxat | eŒfoŒfetkZxat 8292659272 | Inaugurated |  |  | Munger
73 | USS-24-1 | Begusarai | cNokM+k | eŒfoŒQrsg 9570919206 | Inaugurated |  |  | Munger
74 | USS-24-2 | Begusarai | Hkxokuiqj | eŒfoŒeksf[r;kjiqj 9934441250 | Inaugurated |  |  | Munger
75 | USS-24-3 | Begusarai | psfj;k cfj;kjiqj | eŒfoŒldjoklk 9939576953 | Inaugurated |  |  | Munger
76 | USS-25-2 | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | Inaugurated |  |  | Munger
77 | USS-26-1 | Begusarai | cjkSuh | eŒfoŒcFkkSyh 9801572247@9534334080 | Inaugurated |  |  | Munger
78 | USS-26-2 | Begusarai | efVgkuh | eŒfoŒtxriqjk 9939465778 | Inaugurated |  |  | Munger
79 | USS-27-1 | Khagaria | ijoÙkk | eŒfoŒdjuk 9939629342@9006237936 | Inaugurated |  |  | Munger
80 | USS-27-2 | Khagaria | vykSyh | eŒfoŒes?kkSuk 9534870633 | Inaugurated |  |  | Munger
81 | USS-27-3 | Khagaria | pkSFke | eŒfoŒigkM+pd 9431651745 | Inaugurated |  |  | Munger
82 | USS-27-4 | Khagaria | xksxjh | eŒfoŒidjSy 9955068112 | Inaugurated |  |  | Munger
83 | USS-27-5 | Khagaria | [kxfM+;k | eŒfoŒeksjdkgh Fkkuk 9534404397 | Inaugurated |  |  | Munger
84 | USS-15-1 | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | Inaugurated |  |  | Bhagalpur
85 | USS-15-2 | Bhagalpur | Sultanganj | MS Udadih 9801583582 | Inaugurated |  |  | Bhagalpur
86 | USS-15-4 | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | Inaugurated |  |  | Bhagalpur
87 | USS-16-1 | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | Inaugurated |  |  | Bhagalpur
88 | USS-16-2 | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | Inaugurated |  |  | Bhagalpur
89 | USS-16-3 | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | Inaugurated |  |  | Bhagalpur
90 | USS-16-4 | Bhagalpur | Goradih | MS Garhotiya 9931865594 | Inaugurated |  |  | Bhagalpur
91 | USS-17-1 | Bhagalpur | Sabaur | MS Shivaydih 9973394344 | Inaugurated |  |  | Bhagalpur
92 | USS-17-2 | Bhagalpur | Kharik | MS Dadpur 8051625862/ 2 | Inaugurated |  |  | Bhagalpur
93 | USS-17-4 | Bhagalpur | Ismailpur | MS Laxmipur 9546492998 | Inaugurated |  |  | Bhagalpur
94 | USS-18-1 | Banka | Barahat | MS Saharna 9431689507/ | Inaugurated |  |  | Bhagalpur
95 | USS-18-2 | Banka | Bounsi | MS Bishanpur 9006554728 | Inaugurated |  |  | Bhagalpur
96 | USS-18-3 | Banka | Dhouriya | MS Bhatuachak 9955916141 | Inaugurated |  |  | Bhagalpur
97 | USS-18-4 | Banka | Rajoun | MS Majhgay 9771243197 | Inaugurated |  |  | Bhagalpur
98 | USS-19-1 | Banka | Amarpur | MS Bhadariya 9939749402 | Inaugurated |  |  | Bhagalpur
99 | USS-71-2 | Madhepura | Murliganj | M/S Parsha Navtol 9973625392 | Inaugurated. |  |  | Kosi
100 | USS-71-3 | Madhepura | Kumarkhand | M/S Karuvaili 9771194253 | Inaugurated. |  |  | Kosi
101 | USS-71-4 | Madhepura | Sigheshwar | M/S Singyon 9430633497 | Inaugurated. |  |  | Kosi
102 | USS-72-1 | Madhepura | Uda kishunganj | M/S Barataini 9631850096 |  |  |  | Kosi
103 | USS-72-2 | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | Inaugurated |  |  | Kosi
104 | USS-72-3 | Madhepura | Alamnagar | M/S Bargaon 9939489984 | Inaugurated |  |  | Kosi
105 | USS-73-1 | Saharsa | Saur Bazar | M/S Khajuri 9472653157 9430632563 | Inaugurated |  |  | Kosi
106 | USS-73-2 | Saharsa | Navhatta | M/S Kedalpatti 9939942137 8987203752 | Inaugurated |  |  | Kosi
107 | USS-73-3 | Saharsa | Sonbarsa | M/S Pachlakh 7549317375 | Inaugurated |  |  | Kosi
108 | USS-74-1 | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | Inaugurated |  |  | Kosi
109 | USS-74-3 | Saharsa | Mahishi | M/S Jhara 9430696742 |  |  |  | Kosi
110 | USS-75-1 | Supaul | Basantpur | M/S Balbhadrapur 9472034607 | Inaugurated |  |  | Kosi
111 | USS-75-2 | Supaul | Chatapur | M/S Madhubani 9631295927 | Inaugurated |  |  | Kosi
112 | USS-75-3 | Supaul | Marauna | M/S Parikoch 9931662963 | Inaugurated |  |  | Kosi
113 | USS-75-4 | Supaul | Raghopur | Lakhi Chand Sahu M/S Hariraha 9470047275 | HANDOVER |  |  | Kosi
114 | USS-76-1 | Supaul | Kishanpur | M/S Phulwaria 8298274284 | Inaugurated |  |  | Kosi
115 | USS-76-2 | Supaul | Pipra | M/S Ramnagar 9472335572 9570603091 | Inaugurated |  |  | Kosi
116 | USS-76-3 | Supaul | Supaul | M/S Kariho 9430029088 | Inaugurated |  |  | Kosi
117 | USS-76-4 | Supaul | Triveniganj | M/S Kumiyahi 8986062906 | Inaugurated |  |  | Kosi
118 | USS-77-1 | Araria | Hkjxkek | mRØŒeŒfoŒjgfM+;k 9534388120 | Inaugurated |  |  | Purnea
119 | USS-77-2 | Araria | jkuhxat | ckfydk eŒfoŒxq.korh 9771105449 | Inaugurated |  |  | Purnea
120 | USS-77-3 | Araria | jkuhxat | eŒfoŒijekuaniqj 9631149958 | Inaugurated |  |  | Purnea
121 | USS-77-4 | Araria | ujirxat | eŒfoŒuksfu;k Vksyk pdyk 9973417759 | Inaugurated |  |  | Purnea
122 | USS-78-1 | Araria | Qkjfclxat | eŒfoŒe/kqcuh 9661601762 | Inaugurated |  |  | Purnea
123 | USS-78-2 | Araria | Qkjfclxat | eŒfoŒVs<+h eqlgjh 9801199615 | Inaugurated |  |  | Purnea
124 | USS-78-3 | Araria | vjfj;k | eŒfoŒiSdVksyk 9431087519@9431471118 | Inaugurated |  |  | Purnea
125 | USS-78-4 | Araria | vjfj;k | eŒfoŒck¡lckM+h 9430264342 | Inaugurated |  |  | Purnea
126 | USS-79-1 | Araria | dqlkZdk¡Vk | eŒfoŒdikjQksM+k 9931414194 | Inaugurated |  |  | Purnea
127 | USS-79-2 | Araria | fldVh | eŒfoŒlksgkxekM+ksa 9661752676@9006316855 | Inaugurated |  |  | Purnea
128 | USS-79-4 | Araria | iyklh | eŒfoŒ:iSy e/kSy 9771866133 | Inaugurated |  |  | Purnea
129 | USS-80-1 | Kishanganj | fnX?kycSad | eŒfoŒgjokMaxk 8987208103 | Inaugurated |  |  | Purnea
130 | USS-80-2 | Kishanganj | Bkdqjxat | eŒfoŒtaxyHkhVk 8987254242 | Inaugurated |  |  | Purnea
131 | USS-80-3 | Kishanganj | dksapk/kkeu | eŒfoŒ/kuiqjk 9470868499 | Inaugurated |  |  | Purnea
132 | USS-80-4 | Kishanganj | iksfB;k | eŒfoŒgfjiks[kj ØkafrxkN 9430677962 | Inaugurated |  |  | Purnea
133 | USS-80-5 | Kishanganj | cgknqjxat | eŒfoŒgfjHkk"kk 9471834254 | Inaugurated |  |  | Purnea
134 | USS-81-1 | Purnea | dsŒ uxj | vkn'kZ eŒfoŒijksjk 9631003614 | Inaugurated |  |  | Purnea
135 | USS-81-2 | Purnea | dlok | mRØŒ eŒ foŒ dnok 9006717685@9162698638 | Inaugurated |  |  | Purnea
136 | USS-81-3 | Purnea | Mx:vk | eŒfoŒeksgEeniqj 8877902279@9852305617 | Inaugurated |  |  | Purnea
137 | USS-82-1 | Purnea | /kenkgk | vkn'kZ eŒfoŒfo'kuiqj 8002692294 | Inaugurated |  |  | Purnea
138 | USS-82-2 | Purnea | Hkokuhiqj | eŒfoŒczãKkuh 9931249419 | Inaugurated |  |  | Purnea
139 | USS-82-3 | Purnea | :ikSyh | eŒfoŒykyxat 9934565697 |  |  |  | Purnea
140 | USS-82-4 | Purnea | cueu[kh | eŒfoŒtkudh uxj gkV 9430675018 | Inaugurated |  |  | Purnea
141 | USS-84-2 | Katihar | ckjlksbZ | eŒ foŒ clyxkao 9126846409 | Inaugurated |  |  | Purnea
142 | USS-84-3 | Katihar | ckjlksbZ | eŒ foŒ <ëk 9471674809 | Inaugurated |  |  | Purnea
143 | USS-84-4 | Katihar | vkteuxj | eŒ foŒ tydh 9470423557@ 8877799621 | Inaugurated |  |  | Purnea
144 | USS-85-2 | Katihar | efugkjh | eŒfoŒiVuh ukjk;.kiqj 9430970158 | Inaugurated |  |  | Purnea
145 | USS-85-3 | Katihar | Qydk | eŒfoŒ>x:pd 0431668067 |  |  |  | Purnea
146 | USS-85-4 | Katihar | dks<+k | eŒfoŒf'kf'k;k 9431625914@ 0430582029 |  |  |  | Purnea
147 | USS-86-2 | Katihar | dnok | eŒfoŒvk'k;kuh 8986509086 | Inaugurated |  |  | Purnea
148 | USS-46-1 | Sheohar | rfj;kuh | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | handover |  |  | Tirhut East
149 | USS-46-2 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] cyqvk 9771099254 | handover |  |  | Tirhut East
150 | USS-46-3 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] FkqEek 9472379528 |  |  |  | Tirhut East
151 | USS-46-4 | Sitamarhi | csylaM | eŒ foŒ] ipukSj | Inaugurated |  |  | Tirhut East
152 | USS-47-1 | Sitamarhi | jhxk | eŒ foŒ] ;ksxokuk 9534893264 | Inaugurated |  |  | Tirhut East
153 | USS-47-2 | Sitamarhi | cFkukgk | eŒ foŒ] fMgBh 9973981418 | Inaugurated |  |  | Tirhut East
154 | USS-47-3 | Sitamarhi | ukuiqj | eŒ foŒ] cÙkjk 9931668054 | Inaugurated |  |  | Tirhut East
155 | USS-47-4 | Sitamarhi | ukuiqj | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | Inaugurated |  |  | Tirhut East
156 | USS-47-5 | Sitamarhi | lksucjlk | eŒ foŒ] bVgjok 9546578977 | Inaugurated |  |  | Tirhut East
157 | USS-48-1 | Muzaffarpur | vkSjkbZ | eŒ foŒ] cSaxuk 7209905677 | Inaugurated |  |  | Tirhut East
158 | USS-48-2 | Muzaffarpur | ckspgk¡ | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | Inaugurated |  |  | Tirhut East
159 | USS-48-3 | Muzaffarpur | xk; ?kkV | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | Inaugurated |  |  | Tirhut East
160 | USS-48-4 | Muzaffarpur | dVjk | eŒ foŒ] cq/kdkjk 9934016332 | Inaugurated |  |  | Tirhut East
161 | USS-49-2 | Muzaffarpur | eM+ou | eŒ foŒ] jsiqjk 8252129824 | Inaugurated |  |  | Tirhut East
162 | USS-49-3 | Muzaffarpur | ehukiqj | eŒ foŒ] tkfeu efB;k 9934619525 | Inaugurated |  |  | Tirhut East
163 | USS-51-1 | Muzaffarpur | ldjk | eŒ foŒ] ckth cqtqxZ 9572907300 | Inaugurated |  |  | Tirhut East
164 | USS-51-2 | Muzaffarpur | eq'kgjh | eŒ foŒ] fn?kM+k 9430051489@9304110351 | Inaugurated |  |  | Tirhut East
165 | USS-51-3 | Muzaffarpur | eksrhiqj | eŒ foŒ] ckjthMhg 9934895236 | Inaugurated |  |  | Tirhut East
166 | USS-52-1 | Vaishali | lgnsbZ cqtqxZ | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | Inaugurated |  |  | Tirhut East
167 | USS-52-2 | Vaishali | egukj | eŒ foŒ deyk dU;k] djukSrh 8002747546 | Inaugurated |  |  | Tirhut East
168 | USS-52-3 | Vaishali | tUnkgk | eŒ foŒ] jlqyiqj 8651291731 | Inaugurated |  |  | Tirhut East
169 | USS-52-4 | Vaishali | fonqiqj | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | Inaugurated |  |  | Tirhut East
170 | USS-53-1 | Vaishali | gkthiqj | eŒ foŒ] yksek 9470638549 | Inaugurated |  |  | Tirhut East
171 | USS-53-2 | Vaishali | gkthiqj | eŒ foŒ] dqrqciqj 9905099533 | Inaugurated |  |  | Tirhut East
172 | USS-53-3 | Vaishali | ykyxat | eŒ foŒ] xqjfe;k 8651626851 | Inaugurated |  |  | Tirhut East
173 | USS-53-4 | Vaishali | xksjkSy | eŒ foŒ] Bhdgk¡ 9431254109 | Inaugurated |  |  | Tirhut East
174 | USS-54-2 | Vaishali | ikrsiqj | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | Inaugurated |  |  | Tirhut East
175 | USS-54-3 | Vaishali | jk?kksiqj | eŒ foŒ] ohjiqj 9931458401 |  |  |  | Tirhut East
176 | USS-37-1 | West Champaran | Manjhauliya | M.S.Aharwar Shekh 9470655463 | Inaugurated |  |  | Tirhut West
177 | USS-37-2 | West Champaran | Manjhauliya | M.S. Parsa Bahuarwa 9470859628 | Inaugurated |  |  | Tirhut West
178 | USS-37-3 | West Champaran | Bairiya | M.S. Bathna 9431466192 | Inaugurated |  |  | Tirhut West
179 | USS-37-4 | West Champaran | Nautan | M.S. Mangalpur 9430691686 | Inaugurated |  |  | Tirhut West
180 | USS-38-1 | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | Inaugurated |  |  | Tirhut West
181 | USS-38-2 | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | Inaugurated |  |  | Tirhut West
182 | USS-38-3 | West Champaran | Lauriya | M.S.Dhobani 9430571439 | Inaugurated |  |  | Tirhut West
183 | USS-38-4 | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | Inaugurated |  |  | Tirhut West
184 | USS-39-1 | West Champaran | Mainatand | M.S. Tajpur 8986956152 | Inaugurated |  |  | Tirhut West
185 | USS-39-3 | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | Inaugurated |  |  | Tirhut West
186 | USS-42-1 | East Champaran | Areraj | M.S. Radhiya 9576399366 | Inaugurated |  |  | Tirhut West
187 | USS-42-2 | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | Inaugurated |  |  | Tirhut West
188 | USS-42-3 | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | Inaugurated |  |  | Tirhut West
189 | USS-42-4 | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | Inaugurated |  |  | Tirhut West
190 | USS-44-1 | East Champaran | Chakiya | M.S. Chintamanpur 9546123872 | Inaugurated |  |  | Tirhut West
191 | USS-44-3 | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | Inaugurated |  |  | Tirhut West
192 | USS-44-4 | East Champaran | Mehshi | M.S. Jhitkahiya 9162250321 | Inaugurated |  |  | Tirhut West
193 | USS-44-5 | East Champaran | Paharpur | M.S. Siswa Bazar 8809296371 | Inaugurated |  |  | Tirhut West
194 | USS-61-1 | Madhubani | ?kks?kjMhgk | eŒ foŒ] xax}kj 9934407620 | Inaugurated |  |  | Darbhanga
195 | USS-61-2 | Madhubani | >a>kjiqj | eŒ foŒ]ykSguk 9430835195 | Inaugurated |  |  | Darbhanga
196 | USS-61-3 | Madhubani | ykSdgh | eŒ foŒ] dyqvkgh 9572025500 | Inaugurated |  |  | Darbhanga
197 | USS-62-1 | Madhubani | t;uxj | eŒ foŒflyukFk cjgh 9572618953 | Inaugurated |  |  | Darbhanga
198 | USS-62-2 | Madhubani | i.MkSy | eŒ foŒ] 'kkgiqj 9973048002 | Inaugurated |  |  | Darbhanga
199 | USS-62-3 | Madhubani | jktuxj | eŒ foŒ] eaxjkSuh 9931643145 | Inaugurated |  |  | Darbhanga
200 | USS-63-1 | Darbhanga | guqeku uxj | eŒfoŒ]Fkyokjk 9771791978 | Inaugurated |  |  | Darbhanga
201 | USS-63-2 | Darbhanga | cgsM+h | eŒfoŒ fctqfy;k 9939521323 | Inaugurated |  |  | Darbhanga
202 | USS-63-3 | Darbhanga | cgknqjiqj | mRØŒeŒfoŒ dejkSyh 9801391631 | Inaugurated |  |  | Darbhanga
203 | USS-64-1 | Darbhanga | ?ku';keiqj | eŒfoŒ]rqekSy 9939754496 | Inaugurated |  |  | Darbhanga
204 | USS-64-2 | Darbhanga | csuhiqj | mRØŒeŒfoŒ jf<+;ke 9770623526 | Inaugurated |  |  | Darbhanga
205 | USS-64-3 | Darbhanga | euhxkNh | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | Inaugurated |  |  | Darbhanga
206 | USS-65-1 | Darbhanga | dq'ks'oj LFkku iwŒ | mRØŒeŒfoŒ egknso eB 9973391579 | Inaugurated |  |  | Darbhanga
207 | USS-65-2 | Darbhanga | dq'ks'oj LFkku iŒ | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | Inaugurated |  |  | Darbhanga
208 | USS-65-3 | Darbhanga | fojkSy | eŒfoŒ]iVfu;k¡ 9771113614 | Inaugurated |  |  | Darbhanga
209 | USS-66-1 | Darbhanga | fal?kokM+k | mRØŒeŒfoŒ e/kqiqj 9934911481 | Inaugurated |  |  | Darbhanga
210 | USS-66-2 | Darbhanga | dsoVh | eŒfoŒ]dks;yk LFkku 9905459110 | Inaugurated |  |  | Darbhanga
211 | USS-66-3 | Darbhanga | njHkaxk xzkeh.k | mRØŒeŒfoŒ cygk 9570479967 | Inaugurated |  |  | Darbhanga
212 | USS-67-2 | Samastipur | nyflag ljk; | eŒfoŒ]ekyiqj 9934140121 | Inaugurated |  |  | Darbhanga
213 | USS-67-3 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]fcUn ckspgk 9939988449 | Inaugurated |  |  | Darbhanga
214 | USS-67-4 | Samastipur | fo¦kifr uxj | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | Inaugurated |  |  | Darbhanga
215 | USS-67-5 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]efu;kj 7549600801 | Inaugurated |  |  | Darbhanga
216 | USS-68-1 | Samastipur | foHkwfriqj | eŒfoŒ]nsljh 9939816100 | Inaugurated |  |  | Darbhanga
217 | USS-68-2 | Samastipur | fcFkku | eŒfoŒ]NsNuh 9934979521 | Inaugurated |  |  | Darbhanga
218 | USS-68-3 | Samastipur | gluiqj | mRØŒeŒfoŒ egqyh 9801690551 | Inaugurated |  |  | Darbhanga
219 | USS-68-4 | Samastipur | f'kokth uxj | eŒfoŒ]Jhiqjetjfg;k 9955507715 | Inaugurated |  |  | Darbhanga
220 | USS-68-5 | Samastipur | foHkwfriqj | eŒfoŒ]irSfy;k 9973163333 | Inaugurated |  |  | Darbhanga
221 | USS-68-6 | Samastipur | f'kokth uxj | eŒfoŒ]jkuhiêh 9955989162 | Inaugurated |  |  | Darbhanga
222 | USS-69-1 | Samastipur | dY;k.kiqj | eŒfoŒ]eksjokjk 9162249115 | Inaugurated |  |  | Darbhanga
223 | USS-69-2 | Samastipur | leLrhiqj | eŒfoŒ][kksM+h 9263781760 | Inaugurated |  |  | Darbhanga
224 | USS-69-3 | Samastipur | mft;kiqj | eŒfoŒ]vaxkj ?kkV 9204971619 | Inaugurated |  |  | Darbhanga
225 | USS-69-4 | Samastipur | mft;kiqj | eŒfoŒdksjc)k] irSyh 9263731315 | Inaugurated |  |  | Darbhanga
226 | USS-70-1 | Samastipur | eksjok | eŒfoŒ iq:"kksreiqj 9973123260 | Inaugurated |  |  | Darbhanga
227 | USS-70-2 | Samastipur | iwlk | eŒfoŒ]efYydkSj | Inaugurated |  |  | Darbhanga
228 | USS-55-1 | Gopalganj | Baikunthapur | M. School, Deokulli, Mob.: 9708861129 | Inaugurated |  |  | Saran
229 | USS-55-2 | Gopalganj | Baikunthapur | M. School, Maharani, Mob.:9199443900 | Inaugurated |  |  | Saran
230 | USS-55-3 | Gopalganj | Kuchayakot | M. School, Mahuaba, Hindi, Mob.: 9430055420/9162622220 | Inaugurated |  |  | Saran
231 | USS-55-4 | Gopalganj | Singhawalia | U. M. School, Dumaria East, Mob.: 9955648224 | Inaugurated |  |  | Saran
232 | USS-56-1 | Gopalganj | Bhore | M. School, Shivarajpur, Mob.: 9973200939 | Inaugurated |  |  | Saran
233 | USS-56-2 | Gopalganj | Kattaya | M. School, Rudrapur, Mob.: 9628550100 | Inaugurated |  |  | Saran
234 | USS-56-3 | Gopalganj | Kuchayakot | M. School, Purkhaus, Mob.: 9955647418 | Inaugurated |  |  | Saran
235 | USS-56-4 | Gopalganj | Vijayipur | M. School, Mathaulli, Mob.: 9838674751 | Inaugurated |  |  | Saran
236 | USS-57-1 | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | Inaugurated |  |  | Saran
237 | USS-57-2 | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | Inaugurated |  |  | Saran
238 | USS-57-3 | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | Inaugurated |  |  | Saran
239 | USS-57-4 | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | Inaugurated |  |  | Saran
240 | USS-58-1 | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | Inaugurated |  |  | Saran
241 | USS-58-2 | Siwan | Guddhani | U. M. School, Bangardha, Mob.: 9801180809 | Inaugurated |  |  | Saran
242 | USS-58-3 | Siwan | Daraulli | M. School, Dumarhar Bujurga, Mob.: 9199854822 | Inaugurated |  |  | Saran
243 | USS-58-4 | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | Inaugurated |  |  | Saran
244 | USS-58-5 | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | Inaugurated |  |  | Saran
245 | USS-60-1 | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | Inaugurated |  |  | Saran
246 | USS-60-2 | Saran | Manjhi | M. School, Dumari, Mob.: 8083701946/8757054210 | Inaugurated |  |  | Saran
247 | USS-60-3 | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | Inaugurated |  |  | Saran
248 | USS-60-4 | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | Inaugurated |  |  | Saran
249 | USS-60-5 | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | Inaugurated |  |  | Saran

## USS 2010-11
[5 empty] | Not Start | [8 empty] | Completed |  | Division
1 | USS-101-1 | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
2 | USS-101-2 | Nalanda | Ben | M.S. Akouna 9570951336 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
3 | USS-101-3 | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
4 | USS-101-4 | Nalanda | Silao | Urdu.M.S. Barakar 9931004916 |  |  |  |  | 1 | [5 empty] | Invalid list | Patna East | 2010-11
5 | USS-101-5 | Nalanda | Ben | M.S. Ramganj 9135849205 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
6 | USS-102-1 | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
7 | USS-102-2 | Nalanda | Biharsarif | M.S. Majidpur 9570625433 | [8 empty] | 1 |  |  | Patna East | 2010-11
8 | USS-102-3 | Nalanda | Chandi | M.S. Dariya Bigha 9931236900 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11
9 | USS-102-4 | Nalanda | Chandi | Urdu.M.S. Baisa 9939043903 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11
10 | USS-102-5 | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 | [9 empty] | 1 |  | Patna East | 2010-11
11 | USS-102-6 | Nalanda | Sarmera | M.S.Singhaul 9934212058 | [9 empty] | 1 |  | Patna East | 2010-11
12 | USS-103-1 | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
13 | USS-103-2 | Nalanda | Hilsa | M.S. Rasai Bigha 9934593683 | 1 | [9 empty] | Retender | Patna East | 2010-11
14 | USS-103-3 | Nalanda | Islampur | M.S. Bargounw 9279149331 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
15 | USS-103-4 | Nalanda | Islampur | M.S. Banbag 9934487509 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
16 | USS-104-1 | Patna | Khushrupur | M.S. Jagmal Bigha 9771442400 | 1 | [9 empty] | Insufficient land | Patna East | 2010-11
17 | USS-104-2 | Patna | Khushrupur | U.M.S. Arrai Benipur 9135748584 | 1 | [9 empty] | Insufficient land | Patna East | 2010-11
18 | USS-104-3 | Patna | Barh | U.M.S. Malahi 7250940590 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
19 | USS-104-4 | Patna | Fatuha | M.S. Gabaspur 9955241716 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
20 | USS-105-1 | Patna | Patna Sadar | M.S. Khokhna 9135334773 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
21 | USS-105-2 | Patna | Patna Sadar | M.S. Marchi 9430934711 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
22 | USS-105-3 | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
23 | USS-105-4 | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
24 | USS-106-1 | Patna | Bihta | M.S. Kateshar 7250695245 | 1 | [9 empty] | Low Land about 12'-0", work not possible | Patna East | 2010-11
25 | USS-106-2 | Patna | Bikram | M.S. Barah 8084301353 | 1 | [9 empty] | Land not regitered to school, work not possible | Patna East | 2010-11
26 | USS-106-3 | Patna | Bihta | M.S. Kanhauli 9386873458 | 1 | [9 empty] | Land dispute between School & college, work not possible | Patna East | 2010-11
27 | USS-107-1 | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
28 | USS-108-2 | Bhojpur | Agioan | M.S. Berath 09955434210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
29 | USS-108-3 | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
30 | USS-108-4 | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
31 | USS-108-5 | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 | [9 empty] | 1 |  | Patna East | 2010-11
32 | USS-108-6 | Bhojpur | Agioan | M.S. Lasarhi 9661399087 | 1 | [9 empty] | Land not available, work not possible | Patna East | 2010-11
33 | USS-109-1 | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
34 | USS-109-2 | Bhojpur | Garhani | M.S. Kaup 9708602077 | [5 empty] | 1 | [5 empty] | Patna East | 2010-11
35 | USS-109-3 | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
36 | USS-109-4 | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
37 | USS-109-5 | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
38 | USS-110-1 | Bhojpur | Barhara | U.M.S. Shaligram Singh Ka Tola 8409626973 | [8 empty] | 1 |  |  | Patna East | 2010-11
39 | USS-110-2 | Bhojpur | Barhara | M.S. Pakri 9304856454 | [7 empty] | 1 |  |  |  | Patna East | 2010-11
40 | USS-110-3 | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 | [9 empty] | 1 |  | Patna East | 2010-11
41 | USS-110-4 | Bhojpur | Koilwar | M.S. Khesarhiyan 9973554537 | [5 empty] | 1 | [5 empty] | Patna East | 2010-11
42 | USS-110-5 | Bhojpur | Koilwar | M.S. Khangaown 9631265664 | [8 empty] | 1 |  |  | Patna East | 2010-11
43 | USS-111-1 | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
44 | USS-111-2 | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
45 | USS-111-3 | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
46 | USS-111-4 | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
47 | USS-112-1 | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 | [9 empty] | 1 |  | Patna East | 2010-11
48 | USS-112-2 | Bhojpur | Bihiyan | M.S. Kouriya 9431438960 | [7 empty] | 1 |  |  | Inaugurated | Patna East | 2010-11
49 | USS-112-3 | Bhojpur | Shahpur | M.S. Jawainiya 8083447757 7677504269 |  |  |  | 1 | [6 empty] | B/W upto RL | Patna East | 2010-11
50 | USS-112-4 | Bhojpur | Shahpur | M.S. Suhiya 9471919316 | [7 empty] | 1 |  |  |  | Patna East | 2010-11
51 | USS-113-1 | Bhojpur | Tarari | M.S.Gahruan 9472135231 9162748057 | [8 empty] | 1 |  | RC | Patna East | 2010-11
52 | USS-113-2 | Bhojpur | Tarari | M.S.Kurmuri 9576176655 | [7 empty] | 1 |  |  | 1st Floor Sill Level | Patna East | 2010-11
53 | USS-113-3 | Bhojpur | Tarari | M.S. Tarari 9631136009 | [8 empty] | 1 |  |  | Patna East | 2010-11
54 | USS-113-4 | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
55 | USS-113-5 | Bhojpur | Tarari | M.S.Bagar 9801629878 | [8 empty] | 1 |  | RC | Patna East | 2010-11
56 | USS-114-1 | Bhojpur | Sandesh | U.M.S.Nasratpur 9334673203 | 1 | [9 empty] | Land Dispute | Patna East | 2010-11
57 | USS-114-2 | Bhojpur | Sahar | M.S. Baruhi 9199571702 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
58 | USS-114-3 | Bhojpur | Ara | M.S. Basantpur 09308735308 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
59 | USS-114-4 | Bhojpur | Sahar | M.S. Nawada 9934483628 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
60 | USS-115-1 | Buxar | Buxar | M.S.Nadanw 9234866577 9430015496 | [8 empty] | 1 |  |  | Patna West | 2010-11
61 | USS-115-2 | Buxar | Buxar | M.S.Manjharia 9472951603 | 1 | [9 empty] | No Way | Patna West | 2010-11
62 | USS-115-3 | Buxar | Rajpur | M.S. Khiri 9470753325 | [5 empty] | 1 |  |  |  |  | Sill level of GL | Patna West | 2010-11
63 | USS-115-4 | Buxar | Rajpur | Urdu M.S. Banni 9973105344 | 1 | [9 empty] | Land not available | Patna West | 2010-11
64 | USS-116 (A) | Buxar | Dumraon | M.S.Nuaon 9939391144 | [6 empty] | 1 |  |  |  |  | Patna West | 2010-11
65 | USS-116 (B) | Buxar | Dumraon | M.S. Kanjharua 9955867071 | [9 empty] | 1 |  | Patna West | 2010-11
66 | USS-116 (C) | Buxar | Dumraon | M.S. Mathila 9931890937 | [8 empty] | 1 |  |  | Patna West | 2010-11
67 | USS-116 (D) | Buxar | Dumraon | M.S. Karuaj 9931281346 | [9 empty] | 1 |  | Patna West | 2010-11
68 | USS-116 (E) | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 | [9 empty] | 1 |  | Patna West | 2010-11
69 | USS-117 (A) | Buxar | Nawanagar | M.S.Pramanpur 9386827434 |  |  | 1 | [8 empty] | Patna West | 2010-11
70 | USS-117 (B) | Buxar | Ithari | M.S. Barkagaon 8651239720 | [8 empty] | 1 |  |  | Patna West | 2010-11
71 | USS-117 (C) | Buxar | Ithari | M.S. Harpur 9939590039 | [8 empty] | 1 |  |  | Patna West | 2010-11
72 | USS-117 (D) | Buxar | Ithari | M.S. Basawan Kala 7739120173 | [8 empty] | 1 |  |  | Patna West | 2010-11
73 | USS-118-1 | Buxar | Simiri | M.S.Dhanpura 9199795834 | 1 | [10 empty] | Patna West | 2010-11
74 | USS-118-2 | Buxar | Simiri | M.S. Barka Singhnpura 9934740004 | 1 | [10 empty] | Patna West | 2010-11
75 | USS-118-3 | Buxar | Simiri | M.S. Kharha Tarnh 9199359782 | 1 | [10 empty] | Patna West | 2010-11
76 | USS-119 (A) | Kaimur | Bhabhua | M.S.Miun | [8 empty] | 1 |  |  | Patna West | 2010-11
77 | USS-119 (B) | Kaimur | Bhabhua | M.S.Piliyan | [9 empty] | 1 |  | Patna West | 2010-11
78 | USS-119 (C) | Kaimur | Bhabhua | M.S. Mehsuan | [5 empty] | 1 | [5 empty] | Patna West | 2010-11
79 | USS-119 (D) | Kaimur | Bhabhua | M.S. Mohan Darwan | [9 empty] | 1 |  | Patna West | 2010-11
80 | USS-120 (A) | Kaimur | Ramgarh | M.S.Sijhua | [8 empty] | 1 |  |  | Patna West | 2010-11
81 | USS-120 (B) | Kaimur | Ramgarh | M.S.Upari 9939613033 | [8 empty] | 1 |  |  | Patna West | 2010-11
82 | USS-120 (C) | Kaimur | Nuaon | Govt. Basic School Kari Ram Akhili | 1 | [9 empty] | Tender Process | Patna West | 2010-11
83 | USS-120 (D) | Kaimur | Nuaon | M.S.Mushiyan 9546505256 |  |  |  |  | 1 | [6 empty] | Patna West | 2010-11
84 | USS-120 (E) | Kaimur | Durgawati | U.M.S Nuaon 9199361709 | [5 empty] | 1 | [5 empty] | Patna West | 2010-11
85 | USS-121 (A) | Rohtas | Karakat | M.S.Dewmarkande 8969878557 | [8 empty] | 1 |  | Roof slab casted of GF | Patna West | 2010-11
86 | USS-121 (B) | Rohtas | Karakat | Girl's M.S.Motha 9162106111 | [9 empty] | 1 |  | Patna West | 2010-11
87 | USS-121 (C) | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 | [9 empty] | 1 |  | Patna West | 2010-11
88 | USS-121 (D) | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | [8 empty] | 1 |  |  | Patna West | 2010-11
89 | USS-121 (E) | Rohtas | Akorhigola | M.S.Chhapra 9934757484 | [9 empty] | 1 |  | Patna West | 2010-11
90 | USS-122-1 | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | [8 empty] | 1 |  |  | Patna West | 2010-11
91 | USS-122-2 | Rohtas | Dinara | M.S.Sarwan ,8084920823 | [8 empty] | 1 |  |  | Patna West | 2010-11
92 | USS-122-3 | Rohtas | Dinara | M.S. Baliyan, 9931111475 | [8 empty] | 1 |  |  | Patna West | 2010-11
93 | USS-122-4 | Rohtas | Dinara | M.S. Bararhi, 9955083783 | [8 empty] | 1 |  |  | Patna West | 2010-11
94 | USS-122-5 | Rohtas | Bikramganj | M.S. Jamorhi, 9955952582 | 1 | [10 empty] | Patna West | 2010-11
95 | USS-122-6 | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 | [9 empty] | 1 |  | Patna West | 2010-11
96 | USS-123-1 | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 | [9 empty] | 1 |  | Patna West | 2010-11
97 | USS-123-2 | Rohtas | Kochas | M.S. Ubadhi, 8002578689 | [9 empty] | 1 |  | Patna West | 2010-11
98 | USS-123-3 | Rohtas | Kochas | M.S. Kuchila, 8002537247 | [9 empty] | 1 |  | Patna West | 2010-11
99 | USS-123-4 | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 | [9 empty] | 1 |  | Patna West | 2010-11
100 | USS-123-5 | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | [9 empty] | 1 | Handover | Patna West | 2010-11
101 | USS-123-6 | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | [9 empty] | 1 | Handover | Patna West | 2010-11
102 | USS-124-1 | Rohtas | Chenari | M.S. Ramgarh 9771746971 | [8 empty] | 1 |  |  | Patna West | 2010-11
103 | USS-124-2 | Rohtas | Chenari | M.S. Chandrakaithi, 9934281842 | [8 empty] | 1 |  |  | Patna West | 2010-11
104 | USS-124-3 | Rohtas | Sheosagar | M.S. Alampur, 9572407040 | [8 empty] | 1 |  |  | Patna West | 2010-11
105 | USS-124-4 | Rohtas | Sheosagar | M.S. Sonhar 9006103550 | [8 empty] | 1 |  |  | Patna West | 2010-11
106 | USS-124-5 | Rohtas | Sasaram | M.S. Akasi , 9204460486 | [8 empty] | 1 |  |  | Patna West | 2010-11
107 | USS-125-1 | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | [9 empty] | 1 | Inaugurated | Patna West | 2010-11
108 | USS-143-1 | Jehanabad | Kako | M.S.Kajisarai 9934814478 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
109 | USS-143-2 | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
110 | USS-143-3 | Jehanabad | Kako | M.S.Pinzour 9931803275 | 1 | [9 empty] | Insufficient Land | Magadh | 2010-11
111 | USS-143-4 | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
112 | USS-144 (A) | Jehanabad | Hulasganj | M.S.Vira, 9771693433 | [8 empty] | 1 |  |  | Magadh | 2010-11
113 | USS-144 (B) | Jehanabad | Makhdumpur | M.S.Akbarpur, 9934858600 | 1 | [9 empty] | Tender Process | Magadh | 2010-11
114 | USS-144 (C) | Jehanabad | Jehanabad | M.S.Bazartali, 9955297199 |  |  |  | 1 | [7 empty] | Magadh | 2010-11
115 | USS-145-1 | Nawada | Nawada | U.M.S. Jhunathi, 9631172127 | [7 empty] | 1 |  |  |  | Magadh | 2010-11
116 | USS-145-2 | Nawada | Akbarpur | U.M.S. Derma, 9931232692 | [8 empty] | 1 |  |  | Magadh | 2010-11
117 | USS-145-3 | Nawada | Akbarpur | M.S. Kuhaila, 9771085197 | [8 empty] | 1 |  |  | Magadh | 2010-11
118 | USS-145-4 | Nawada | Akbarpur | M.S. Paharpur, 9771672098 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11
119 | USS-145-5 | Nawada | Nawada | M.S. Wermi, 9708857028 | 1 | [9 empty] | Land not available | Magadh | 2010-11
120 | USS-146 (A) | Nawada | Govindpur | M.S. Rampur, 9771867218 | [7 empty] | 1 |  |  |  | Magadh | 2010-11
121 | USS-146 (B) | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | [9 empty] | 1 |  | Magadh | 2010-11
122 | USS-146 (C) | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
123 | USS-146 (D) | Nawada | Pakribarawan | M.S. Ukaorah | [9 empty] | 1 |  | Magadh | 2010-11
124 | USS-146 (E) | Nawada | Kashichak | U.M.S. Vishbnathpur , 9386540972 | 1 | [9 empty] | Retender | Magadh | 2010-11
125 | USS-147-1 | Nawada | Narhat | M.S. Khanwa, 9905846666 | [9 empty] | 1 |  | Magadh | 2010-11
126 | USS-147-2 | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | [9 empty] | 1 |  | Magadh | 2010-11
127 | USS-148-1 | Gaya | Bodh Gaya | M.S. Moratala, 9934282506 | [8 empty] | 1 |  |  | Magadh | 2010-11
128 | USS-148-2 | Gaya | Bodh Gaya | M.S. Titoiya, 9934672899 | 1 | [9 empty] | Land Problem | Magadh | 2010-11
129 | USS-148-3 | Gaya | Bodh Gaya | M.S. Bataspur, 9470447309 | [8 empty] | 1 |  |  | Magadh | 2010-11
130 | USS-148-4 | Gaya | Bodh Gaya | M.S. Gapha Kala, 9934972678 | 1 | [9 empty] | Not start | Magadh | 2010-11
131 | USS-149 (A) | Gaya | Dumariya | M.S. Bhangiya, 9472443151 9801769544 | [8 empty] | 1 |  |  | Magadh | 2010-11
132 | USS-149 (B) | Gaya | Imamganj | M.S. Karsan Kala, 9199768865, 9199061230 | [7 empty] | 1 |  |  |  | Magadh | 2010-11
133 | USS-149 (C) | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 | [9 empty] | 1 |  | Magadh | 2010-11
134 | USS-149 (D) | Gaya | Imamganj | M.S. Naudiha, 9135294703, 8235212693 | [8 empty] | 1 |  |  | Magadh | 2010-11
135 | USS-149 (E) | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 | [9 empty] | 1 |  | Magadh | 2010-11
136 | USS-150 (A) | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 | [9 empty] | 1 |  | Magadh | 2010-11
137 | USS-150 (B) | Gaya | Tekari | M.S. Urdu Bishnupur, 9771128251, 9135850031 | [8 empty] | 1 |  |  | Magadh | 2010-11
138 | USS-150 (C) | Gaya | Konch | M.S. Goribigha, 9939408167 | [6 empty] | 1 |  |  |  |  | Magadh | 2010-11
139 | USS-150 (D) | Gaya | Konch | M.S. Ahiyarpur, 9934008030 | [7 empty] | 1 |  |  |  | Magadh | 2010-11
140 | USS-151-1 | Gaya | Bathani | Basic M.S. Radui, 7654409634 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
141 | USS-151-2 | Gaya | Bathani | M.S. Karubigha, 9934427661 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
142 | USS-151-3 | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
143 | USS-152-1 | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
144 | USS-152-2 | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
145 | USS-152-3 | Gaya | Fatehpur | M.S. Khajuri, 8969107991 | [8 empty] | 1 |  |  | Magadh | 2010-11
146 | USS-152-4 | Gaya | Fatehpur | M.S. Nagwa, 9798270089 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11
147 | USS-152-5 | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
148 | USS-152-6 | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
149 | USS-153 (A) | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | [8 empty] | 1 |  |  | Magadh | 2010-11
150 | USS-153 (B) | Gaya | Guraru | M.S. Manjhar, 9572789270 | [7 empty] | 1 |  |  |  | Magadh | 2010-11
151 | USS-153 (C) | Gaya | Amas | M.S. Baliyari, 9570551566, 8294856371, 8051934469 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11
152 | USS-153 (D) | Gaya | Sherghatty | M.S. Naknuppa, 9431289085 | 1 | [9 empty] | Land not available | Magadh | 2010-11
153 | USS-154-1 | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
154 | USS-154-2 | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
155 | USS-154-3 | Aurangabad | Kutumba | M.S. Darmi, 9955519885, 9931921788 | 1 | [9 empty] | Land not available | Magadh | 2010-11
156 | USS-154-4 | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
157 | USS-154-5 | Aurangabad | Deo | M.S. Vijouli, 9801123435 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
158 | USS-155-1 | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
159 | USS-155-2 | Aurangabad | Obra | M.S. Ratwar, 9931418907 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
160 | USS-155-3 | Aurangabad | Obra | M.S. Tejpur, 9973299799 | 1 | [9 empty] | Land not available | Magadh | 2010-11
161 | USS-155-4 | Aurangabad | Obra | M.S. Karsawan, 9470488343 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
162 | USS-156-1 | Aurangabad | Haspura | M.S. Piru, 9135064392 | 1 | [9 empty] | Land Encrochment | Magadh | 2010-11
163 | USS-156-2 | Aurangabad | Haspura | M.S. Sriwanbhatt, 9939023445 | 1 | [9 empty] | Land not available | Magadh | 2010-11
164 | USS-156-3 | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
165 | USS-157 (A) | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 | [9 empty] | 1 |  | Magadh | 2010-11
166 | USS-157 (B) | Aurangabad | Raphiganj | M.S. Pogar, 9973150471 | [8 empty] | 1 |  |  | Magadh | 2010-11
167 | USS-157 (C) | Aurangabad | Madanpur | M.S. Judahi, 9931892284 | [9 empty] | 1 |  | Magadh | 2010-11
168 | USS-157 (D) | Aurangabad | Madanpur | M.S. Saliya, 9955803641 | [7 empty] | 1 |  |  |  | Magadh | 2010-11
169 | USS-157 (E) | Aurangabad | Raphiganj | M.S. Danai, 9097351245 | [5 empty] | 1 | [5 empty] | Magadh | 2010-11
170 | USS-132-1 | Sheikhpura | Barbigha | M.S.Keuti | [9 empty] | 1 | Inaugurated | Munger | 2010-11
171 | USS-132-2 | Sheikhpura | SheKhpura | M.S.Lodipur | [9 empty] | 1 | Inaugurated | Munger | 2010-11
172 | USS-132-3 | Sheikhpura | Chewara | M.S.Lahana | [9 empty] | 1 | Inaugurated | Munger | 2010-11
173 | USS-132-4 | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | [9 empty] | 1 | Inaugurated | Munger | 2010-11
174 | USS-132-5 | Sheikhpura | Ariari | M.S.Husainawad | [9 empty] | 1 | Inaugurated | Munger | 2010-11
175 | USS-133(A) | Lakhisarai | Barahiya | M.S.Pali 9546977875 | [9 empty] | 1 |  | Munger | 2010-11
176 | USS-133(B) | Lakhisarai | Barahiya | M.S.Lal Diyara 9097688412 | 1 | [9 empty] | Not start | Munger | 2010-11
177 | USS-133(C) | Lakhisarai | Halsi | M.S. Geruapursanda 8084044144 | 1 | [9 empty] | Not start | Munger | 2010-11
178 | USS-133(D) | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 | [9 empty] | 1 |  | Munger | 2010-11
179 | USS-133(E) | Lakhisarai | Suryagarha | U.M.S. Lahasaurwa 9631695175, 8434346388 | [5 empty] | 1 | [5 empty] | Munger | 2010-11
180 | USS-133(F) | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | [9 empty] | 1 |  | Munger | 2010-11
181 | USS-134-1 | Jamui | Sono | M.S.Buijhayt 09631584296 |  |  |  |  | 1 | [6 empty] | Munger | 2010-11
182 | USS-135-1 | Munger | Asarganj | M.S.Chakhand 9135065232 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
183 | USS-135-2 | Munger | Asarganj | M.S. Beran 9204931976 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
184 | USS-135-3 | Munger | Tarapur | M.S. Mahamadpur 9709507263 | [8 empty] | 1 |  |  | Munger | 2010-11
185 | USS-136-1 | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
186 | USS-136-2 | Munger | Sangrampur | M.S.Khapra 9934832035 | 1 | [9 empty] | Land not available | Munger | 2010-11
187 | USS-136-3 | Munger | Sangrampur | M.S.Katiyari 9199782900 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
188 | USS-137-1 | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
189 | USS-137-2 | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
190 | USS-137-3 | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
191 | USS-137-4 | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
192 | USS-137-5 | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
193 | USS-138-1 | Begusarai | Mansurchak | M.S.Chhabilapur 9771848155 | 1 | [9 empty] | Land not available | Munger | 2010-11
194 | USS-138-2 | Begusarai | Begusarai | M.S.Bharra 9204202640 | [8 empty] | 1 |  |  | Munger | 2010-11
195 | USS-138-3 | Begusarai | Begusarai | M.S.Babasudebpur 9934708295, 88777402400 |  |  | 1 | [8 empty] | Munger | 2010-11
196 | USS-138-4 | Begusarai | Matihani | M.S.Richiyahi Nayartol 9973647476, 9608273410 |  |  |  |  | 1 | [6 empty] | Munger | 2010-11
197 | USS-138-5 | Begusarai | Sahebpur Kamal | M.S.Rajoura 9709067460 | 1 | [9 empty] | Land not available | Munger | 2010-11
198 | USS-139-1 | Begusarai | Bachhawara | M.S.Dadupur 9801471859 | [8 empty] | 1 |  |  | Munger | 2010-11
199 | USS-139-2 | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
200 | USS-139-3 | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
201 | USS-139-4 | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
202 | USS-139-5 | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
203 | USS-140-1 | Begusarai | Garhpura | M.S.Kuddhar 9955509070 | [9 empty] | 1 |  | Munger | 2010-11
204 | USS-140-2 | Begusarai | Dandari | M.S.Katarmala 9709640304 | [9 empty] | 1 |  | Munger | 2010-11
205 | USS-140-3 | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
206 | USS-141 (A) | Khagaria | Alauli | M.S.Shumbha Ghat 8969741611 |  |  |  | 1 | [7 empty] | Munger | 2010-11
207 | USS-141 (B) | Khagaria | Alauli | M.S.Khairi Khutaha 9471283095 | [5 empty] | 1 | [5 empty] | Munger | 2010-11
208 | USS-141 (C) | Khagaria | Khagaria | M.S.Nanku Mandal Tola 9955646986 |  |  | 1 | [8 empty] | Munger | 2010-11
209 | USS-141 (D) | Khagaria | Khagaria | M.S.Mathar 9771388437 | [9 empty] | 1 |  | Munger | 2010-11
210 | USS-142-1 | Khagaria | Beldaur | M.S.Kainjari 7549429234 |  |  | 1 | [7 empty] | Work stoped due to land dispute | Munger | 2010-11
211 | USS-142-2 | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
212 | USS-142-3 | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
213 | USS-126 (A) | Bhagalpur | Kahalgaon | M.S.Basudeopur Bhaluya 9801295281 |  | 1 | [9 empty] | Bhagalpur | 2010-11
214 | USS-126 (B) | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11
215 | USS-126 (C) | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11
216 | USS-126 (D) | Bhagalpur | Kahalgaon | M.S. Saur 9430428851 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11
217 | USS-127 (A) | Bhagalpur | Pirpainti | M.S.Mahuadhih 9955027709, 7549131650 | 1 | [9 empty] | LAND PROBLEM | Bhagalpur | 2010-11
218 | USS-127 (B) | Bhagalpur | Pirpainti | M.S. Maultola, 9534766339 | 1 | [9 empty] | LAND PROBLEM | Bhagalpur | 2010-11
219 | USS-127 (C) | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
220 | USS-127 (D) | Bhagalpur | Pirpainti | M.S.Ekchari Diyara 9507752647, 9934426205 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11
221 | USS-127 (E) | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | [9 empty] | 1 | HANDOVER | Bhagalpur | 2010-11
222 | USS-128 (A) | Bhagalpur | Goradih | M.S.Birnaugha 9955198006 | [8 empty] | 1 |  |  | Bhagalpur | 2010-11
223 | USS-128 (B) | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | [9 empty] | 1 | HANDOVER | Bhagalpur | 2010-11
224 | USS-128 (C) | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | [9 empty] | 1 |  | Bhagalpur | 2010-11
225 | USS-128 (D) | Bhagalpur | Sabaur | Govt. M.S.Kurpat 9204660635, 9931729153 | [5 empty] | 1 | [5 empty] | Bhagalpur | 2010-11
226 | USS-129 (A) | Bhagalpur | Rangrachauk | M.S.Murli 9534523062 | 1 | [9 empty] | Land Dispute | Bhagalpur | 2010-11
227 | USS-129 (B) | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | [9 empty] | 1 |  | Bhagalpur | 2010-11
228 | USS-130-1 | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
229 | USS-130-2 | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
230 | USS-130-3 | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
231 | USS-130-4 | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
232 | USS-130-5 | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
233 | USS-131-1 | Banka | Amarpur | M.S.Surihari 9931727384 | [7 empty] | 1 |  |  | Shuttering in Progress | Bhagalpur | 2010-11
234 | USS-131-2 | Banka | Belhar | M.S.Hatiyadadha 8521126388 | [8 empty] | 1 |  | In Progress | Bhagalpur | 2010-11
235 | USS-131-3 | Banka | Dhoraiya | U.M.S.Jharkha 9934883358 | [8 empty] | 1 |  | F.F.R.C. | Bhagalpur | 2010-11
236 | USS-199C | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | [9 empty] | 1 | HANDOVER | Kosi | 2010-11
237 | USS-199D-1 | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | [8 empty] | 1 |  | Work in Progress | Kosi | 2010-11
238 | USS-199 D-2 | Madhepura | Singheshwar | Middle School Barhari 9661376885 | [9 empty] | 1 | Inaugurated | Kosi | 2010-11
239 | USS-199D-3 | Madhepura | Kumarkhand | Middle School Rahta 9631460084 | 1 | [9 empty] | Land not available | Kosi | 2010-11
240 | USS-194-1 | Purnea | Amaur | U. M. S. Bagdar 9939096309 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
241 | USS-194-2 | Purnea | K. Nagar | M S Gauasi 9473124829 | [9 empty] | 1 |  | Purnea | 2010-11
242 | USS-194-3 | Purnea | Purnia East | M S Maranga 9939732346 | [9 empty] | 1 |  | Purnea | 2010-11
243 | USS-194-4 | Purnea | Rupauli | M. S. Bairiya 9434821065 | [9 empty] | 1 |  | Purnea | 2010-11
244 | USS-195-1 | Katihar | Amdabad | M. S. Laxmipur Daiwa 7549854721 |  |  |  |  | 1 | [6 empty] | Purnea | 2010-11
245 | USS-195-2 | Katihar | Manihari | Middle School Mirjapur 8084519254 941640318 | 1 | [10 empty] | Purnea | 2010-11
246 | USS-195-3 | Katihar | Mansahi | Middle School Mohanpur 9472890120 |  |  | 1 | [8 empty] | Purnea | 2010-11
247 | USS-196(A) | Katihar | Pranpur | Middle School Kast Hawar 8809776384 9162325809 |  |  |  | 1 | [6 empty] | work stoped by villegers due to land dispute | Purnea | 2010-11
248 | USS-196(B) | Katihar | Ajamnagar | Middle School Arihana 8809322797 | [8 empty] | 1 |  |  | Purnea | 2010-11
249 | USS-196(C) | Katihar | Ajamnagar | Middle School Dhena Baghchhala 9801372634 | [8 empty] | 1 |  |  | Purnea | 2010-11
250 | USS-196(D) | Katihar | Pranpur | Middle School Ghanhar Vighocha 9939688768 | [8 empty] | 1 |  |  | Purnea | 2010-11
251 | USS-197(A) | Katihar | Barsoi | Middle School Barsoi Ghat 9431626189 | [5 empty] | 1 | [5 empty] | Purnea | 2010-11
252 | USS-197(B) | Katihar | Dhankhora | Middle School Durgasthan Dhankhora9431869787 | 1 | [9 empty] | Land not available | Purnea | 2010-11
253 | USS-197(C) | Katihar | Kodha | Middle School Marwa Najrachowki 9006363823 | [8 empty] | 1 |  |  | Purnea | 2010-11
254 | USS-197(D) | Katihar | Kadwa | Dukhi Ram Middle School Chandpur9709755452 | [8 empty] | 1 |  |  | Purnea | 2010-11
255 | USS-198-1 | Katihar | Brari | Middle School Laxmipur | 1 | [9 empty] | Tender Process | Purnea | 2010-11
256 | USS-198-2 | Katihar | Brari | Middle School Anarkali | 1 | [9 empty] | Tender Process | Purnea | 2010-11
257 | USS-198-3 | Katihar | Hasanganj | Middle School Hasanganj | 1 | [9 empty] | Tender Process | Purnea | 2010-11
258 | USS-198-4 | Katihar | Phalka | Middle School Morsanda | [5 empty] | 1 | [5 empty] | Purnea | 2010-11
259 | USS-198-5 | Katihar | Sameli | Middle School Dumar | [5 empty] | 1 | [5 empty] | Purnea | 2010-11
260 | USS-199A (A) | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 | [9 empty] | 1 |  | Purnea | 2010-11
261 | USS-199A (B) | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 | [9 empty] | 1 |  | Purnea | 2010-11
262 | USS-199A (C) | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 | [9 empty] | 1 |  | Purnea | 2010-11
263 | USS-199A (D) | Araria | Narpatganj | Middle School Achra 9801296055 | [9 empty] | 1 |  | Purnea | 2010-11
264 | USS-199 B-1 | Araria | Jokihat | Middle School Jhanpur 9471219710 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
265 | USS-199 B-2 | Araria | Raniganj | Middle School Kosikapur 9199673607 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
266 | USS-199 B-3 | Araria | Araria | Middle School Araria Basti 9661185784 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
267 | USS-162 (A) | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
268 | USS-162 (B) | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
269 | USS-162 (C) | Sitamarhi | Suppi | M. S. Aktha 9470821881 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
270 | USS-162 (D) | Sitamarhi | Riga | M. S. Ramnagara 9570781314 | 1 | [10 empty] | Tirhut East | 2010-11
271 | USS-162 (E) | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 | [8 empty] | 1 |  | G.f Electric, Internal Plaster In Progress Plumbing Start | Tirhut East | 2010-11
272 | USS-162 (F) | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 | [9 empty] | 1 |  | Tirhut East | 2010-11
273 | USS-163 (A) | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 | [9 empty] | 1 |  | Tirhut East | 2010-11
274 | USS-163 (B) | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
275 | USS-163 (C) | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
276 | USS-163 (D) | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 | [8 empty] | 1 |  | Roof Casted 23.12.15 | Tirhut East | 2010-11
277 | USS-164-1 | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
278 | USS-164-2 | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
279 | USS-164-3 | Vaishali | Bhagwanpur | M. S. Askaranpur | [9 empty] | 1 |  | Tirhut East | 2010-11
280 | USS-164-4 | Vaishali | Bhagwanpur | M. S. Kutubpur 9534509369 | 1 | [9 empty] | No Land | Tirhut East | 2010-11
281 | USS-164-5 | Vaishali | Lalganj | U.M.S. Basanta 9934417163 | 1 | [9 empty] | No Land | Tirhut East | 2010-11
282 | USS-165-1 | Vaishali | Jandaha | U. M.S. Shahpur Rohuya 9934414222 | [7 empty] | 1 |  |  | Work stoped by Contractor without any reason | Tirhut East | 2010-11
283 | USS-165-2 | Vaishali | Jandaha | M. S, Mahhisaur 9661844106 | [5 empty] | 1 | [5 empty] | Tirhut East | 2010-11
284 | USS-165-3 | Vaishali | Sahadei Bujurg | M.S, Toimath 9939693675 | [7 empty] | 1 |  |  |  | Tirhut East | 2010-11
285 | USS-165-4 | Vaishali | Sahadei Bujurg | M.S, Nayaganj 9934912623 | 1 | [10 empty] | Tirhut East | 2010-11
286 | USS-165-5 | Vaishali | Jandaha | M.S, Bijrauti 9973922533 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
287 | USS-166 (A) | Vaishali | Raghopur | M. S,Tersiya 9631970772 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
288 | USS-166 (B) | Vaishali | Raghopur | M.S,Paharpur 7654539556 | [9 empty] | 1 | handover | Tirhut East | 2010-11
289 | USS-166 (C) | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 | 1 | [10 empty] | Tirhut East | 2010-11
290 | USS-166 (D) | Vaishali | Desari | M. S, Bhikhanpura 9973319373 |  |  |  | 1 | [6 empty] | Exavation | Tirhut East | 2010-11
291 | USS-166 (E) | Vaishali | Rajapakar | M. S, Makhadumpur Pokhraira 9934478747 | [7 empty] | 1 |  |  |  | Tirhut East | 2010-11
292 | USS-167-1 | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
293 | USS-167-2 | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
294 | USS-167-3 | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
295 | USS-167-4 | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
296 | USS-167-5 | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
297 | USS-168-1 | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
298 | USS-168-2 | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
299 | USS-168-3 | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
300 | USS-168-4 | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
301 | USS-169-1 | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
302 | USS-169-2 | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
303 | USS-169-3 | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
304 | USS-169-4 | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
305 | USS-169-5 | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
306 | USS-170-1 | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
307 | USS-170-2 | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 | [9 empty] | 1 |  | Tirhut East | 2010-11
308 | USS-170-3 | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 | [9 empty] | 1 |  | Tirhut East | 2010-11
309 | USS-170-4 | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | [9 empty] | 1 |  | Tirhut East | 2010-11
310 | USS-170-5 | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
311 | USS-171-1 | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
312 | USS-171-2 | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 | [9 empty] | 1 |  | Tirhut East | 2010-11
313 | USS-171-3 | Muzaffarpur | Gaighat | M. S,Dahila 9973658759 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
314 | USS-171-4 | Muzaffarpur | Katra | M. S, Bakhari 9631173639 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
315 | USS-171-5 | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | [8 empty] | 1 |  |  | Tirhut East | 2010-11
316 | USS-172-1 | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
317 | USS-172-2 | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
318 | USS-172-3 | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
319 | USS-172-4 | Muzaffarpur | Mushhari | M. S, Dronpur | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
320 | USS-172-5 | Muzaffarpur | Muraul | M. S, Pilkhi | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
321 | USS-158-1 | East Champaran | Turkauliya | M.S. Belwa Ray 9430645457 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
322 | USS-158-2 | East Champaran | Turkauliya | M.S. Jaishinghpur 9430209305 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
323 | USS-158-3 | East Champaran | Motihari | M.S. Basantpur 9576483588 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
324 | USS-159-1 | East Champaran | Pakridayal | M.S. Sishani 9934715029 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
325 | USS-159-2 | East Champaran | chaaiya | M.S. Madhubani 9430565177 | 1 | [10 empty] | Tirhut West | 2010-11
326 | USS-159-3 | East Champaran | Tetariya | M.S. Maniyarpur 9471297810 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
327 | USS-159-4 | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
328 | USS-159-5 | East Champaran | Ghorasahan | M.S. Samanpur 9939403946 | [5 empty] | 1 | [5 empty] | Tirhut West | 2010-11
329 | USS-160-1 | West Champaran | Lauriya | Govt.M.S. Phulwariya 9431674559 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
330 | USS-160-2 | West Champaran | Narkatiyaganj | Govt.M.S. Bhadiharwa 8986137181 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
331 | USS-160-3 | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
332 | USS-160-4 | West Champaran | Madhubani | M.S.Pakri Ahawa Khothwa 08002571785 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
333 | USS-160-5 | West Champaran | Nautan | M.S.Sansariya 8757124792 | 1 | [10 empty] | Tirhut West | 2010-11
334 | USS-161-1 | Sheohar | Purnhiya | M.S.Basant Jagivan 9430526421 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
335 | USS-161-2 | Sheohar | Dumri Katsari | M.S.Phulkaha 9631003475 | [8 empty] | 1 |  |  | Tirhut West | 2010-11
336 | USS-187-1 | Madhubani | Babu Barhi | M. S. Barhara | [8 empty] | 1 |  |  | Darbhanga | 2010-11
337 | USS-187-2 | Madhubani | Lakhanpur | M. S. Belaucha | 1 | [9 empty] | Land Not Avilable | Darbhanga | 2010-11
338 | USS-187-3 | Madhubani | Jaynagar | Middle School, Dhaniyapatti 9931037199 9661794550 | 1 | [9 empty] | Land Not Avilable | Darbhanga | 2010-11
339 | USS-187-4 | Madhubani | Rajnagar | Govt. M S, Kewalpatti 9430032594 8051418065 | [7 empty] | 1 |  |  |  | Darbhanga | 2010-11
340 | USS-187-5 | Madhubani | Khutauna | Middle School, Malin Belha 9572178379 | [8 empty] | 1 |  |  | Darbhanga | 2010-11
341 | USS-188-1 | Madhubani | Banipatti | M. S.Ganguli 9431629001 | 1 | [9 empty] | AGREEMENT NOT DONE (CONTRACTOR REFUSED) | Darbhanga | 2010-11
342 | USS-188-2 | Madhubani | Kaluahi | M. S.Kalikapur 9973900631 | 1 | [10 empty] | Darbhanga | 2010-11
343 | USS-188-3 | Madhubani | Bisfi | M. S.Singhaso 9162249674 8051935537 | 1 | [10 empty] | Darbhanga | 2010-11
344 | USS-189-1 | Samastipur | Shivajinagar | M. S. Shripur Bhataura |  |  |  |  | 1 | [6 empty] | Darbhanga | 2010-11
345 | USS-189-2 | Samastipur | Vibhutipur | U. M. S, Mustafapur | 1 | [9 empty] | LOW LAND | Darbhanga | 2010-11
346 | USS-190-1 | Darbhanga | Kusheshwarsthan E | U. M. S, Barniya 7870017996 | [5 empty] | 1 | [5 empty] | Darbhanga | 2010-11
347 | USS-190-2 | Darbhanga | Kusheshwarsthan W | U. M. S, Sihariya 8969431987 | [5 empty] | 1 | [5 empty] | Darbhanga | 2010-11
348 | USS-191-1 | Darbhanga | Manigachhi | U. M. S, Dahaura 9431405480 | 1 | [9 empty] | required land 68'x67' avlaible land27'x25' | Darbhanga | 2010-11
349 | USS-191-2 | Darbhanga | Kewati | M. S, Koila Majhigama 9304020023 | 1 | [9 empty] | LAND DISPUTE | Darbhanga | 2010-11
350 | USS-191-3 | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
351 | USS-191-4 | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
352 | USS-191-5 | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
353 | USS-192 A | Darbhanga | Bahadurpur | M. S, Daing 9199229540 | [8 empty] | 1 |  |  | Darbhanga | 2010-11
354 | USS-192 B | Darbhanga | Biraul | M. S, Koilajan 9939650547 | [6 empty] | 1 |  |  |  |  | Darbhanga | 2010-11
355 | USS-192 C | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 | [9 empty] | 1 |  | Darbhanga | 2010-11
356 | USS-192 D | Darbhanga | Biraul | U. M. S, Balha 7631905606 | [9 empty] | 1 |  | Darbhanga | 2010-11
357 | USS-193-1 | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
358 | USS-193-2 | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
359 | USS-193-3 | Darbhanga | Alinagar | U. M. S, Rampur Uday 9546520079 | 1 | [9 empty] | required land 68'x67' avlaible land16'x14' | Darbhanga | 2010-11
360 | USS-193-4 | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
361 | USS-173 (A) | Siwan | Husainganj | M. S, Hata Tola Chhata 9546660912 |  |  | 1 | [7 empty] | Land not available | Saran | 2010-11
362 | USS-173 (B) | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
363 | USS-174-1 | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
364 | USS-174-2 | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 | [9 empty] | 1 |  | Saran | 2010-11
365 | USS-174-3 | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
366 | USS-174-4 | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
367 | USS-175-1 | Siwan | Siswan | M. S, Gyaspur 8809341191 | [9 empty] | 1 | Hand Over | Saran | 2010-11
368 | USS-175-2 | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
369 | USS-175-3 | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
370 | USS-175-4 | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
371 | USS-176-1 | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
372 | USS-176-2 | Siwan | Gudhani | M. S, Belauri 8809165382 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
373 | USS-176-3 | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
374 | USS-177-1 | Saran | Dariyapur | Middle School, Saraiya 9431647901 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
375 | USS-177-2 | Saran | Dariyapur | Middle School, Bhongha 9006298659 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
376 | USS-177-3 | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
377 | USS-177-4 | Saran | Dighwara | Middle School, Malkhachak 9135336330 |  | 1 | [9 empty] | Saran | 2010-11
378 | USS-178-1 | Saran | Sonpur | Middle School, Shikharpur 9631221348 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
379 | USS-179-1 | Saran | Lahaladpur | Middle School, Basahi Urdu | [9 empty] | 1 | Inaugurated | Saran | 2010-11
380 | USS-179-2 | Saran | Ekma | Middle School, Bhodasa | [9 empty] | 1 | Inaugurated | Saran | 2010-11
381 | USS-179-3 | Saran | Ekma | Middle School, Betbaniya 8294839353 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
382 | USS-179-4 | Saran | Ekma | Middle School, Eksar 9572740280 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
383 | USS-179-5 | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
384 | USS-181-1 | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
385 | USS-182-1 | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
386 | USS-182-2 | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
387 | USS-182-3 | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
388 | USS-183-1 | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
389 | USS-183-2 | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
390 | USS-183-3 | Gopalganj | Kuchaikot | Middle School, Balthari 9973181137 | 1 | [9 empty] | Low Land | Saran | 2010-11
391 | USS-183-4 | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
392 | USS-184-1 | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
393 | USS-184-2 | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
394 | USS-184-3 | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
395 | USS-184-4 | Gopalganj | Singhwaliya | Middle School, Amarpura Jagiraha 9801115115 | 1 | [9 empty] | Land Not Available | Saran | 2010-11
396 | USS-185-1 | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
397 | USS-185-2 | Gopalganj | Gopalganj | Middle School, Karariya 9934499260 | 1 | [9 empty] | Land Problem | Saran | 2010-11
398 | USS-185-3 | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
399 | USS-185-4 | Gopalganj | Gopalganj | Middle School, Baraipatti 9955771721 | 1 | [9 empty] | Land Problem | Saran | 2010-11
400 | USS-186-1 | Gopalganj | Hathua | U. M. S, Satai 8757888461 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
401 | USS-186-2 | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
402 | USS-186-3 | Gopalganj | Hathua | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 | 1 | [9 empty] | Land Problem | Saran | 2010-11
403 | USS-186-4 | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 | [9 empty] | 1 |  | Saran | 2010-11
Note on P20: Group will closed due dely in land availability.
Note on B35: ACCORD. TO 475 USS-108-1
Note on E224: Gurudev Const.
Note on E227: Gurudev Const.
Note on B399: List from 161 & 250 ing list

## Completed
BSEIDC , Patna
Completed List of USS 2010-11
S.N. | Group No. | Name of District | Name of Block | Name of School | Remarks | Division
1 | USS-101-1 | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | Inaugurated | Patna East
2 | USS-101-2 | Nalanda | Ben | M.S. Akouna 9570951336 | Inaugurated | Patna East
3 | USS-101-3 | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | Inaugurated | Patna East
4 | USS-101-5 | Nalanda | Ben | M.S. Ramganj 9135849205 | Inaugurated | Patna East
5 | USS-102-1 | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | Inaugurated | Patna East
6 | USS-102-5 | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 |  | Patna East
7 | USS-102-6 | Nalanda | Sarmera | M.S.Singhaul 9934212058 |  | Patna East
8 | USS-103-1 | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | Inaugurated | Patna East
9 | USS-103-3 | Nalanda | Islampur | M.S. Bargounw 9279149331 | Inaugurated | Patna East
10 | USS-103-4 | Nalanda | Islampur | M.S. Banbag 9934487509 | Inaugurated | Patna East
11 | USS-104-3 | Patna | Barh | U.M.S. Malahi 7250940590 | Inaugurated | Patna East
12 | USS-104-4 | Patna | Fatuha | M.S. Gabaspur 9955241716 | Inaugurated | Patna East
13 | USS-105-1 | Patna | Patna Sadar | M.S. Khokhna 9135334773 | Inaugurated | Patna East
14 | USS-105-2 | Patna | Patna Sadar | M.S. Marchi 9430934711 | Inaugurated | Patna East
15 | USS-105-3 | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | Inaugurated | Patna East
16 | USS-105-4 | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | Inaugurated | Patna East
17 | USS-107-1 | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | Inaugurated | Patna East
18 | USS-108-2 | Bhojpur | Agioan | M.S. Berath 09955434210 | Inaugurated | Patna East
19 | USS-108-3 | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | Inaugurated | Patna East
20 | USS-108-4 | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | Inaugurated | Patna East
21 | USS-108-5 | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 |  | Patna East
22 | USS-109-1 | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | Inaugurated | Patna East
23 | USS-109-3 | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | Inaugurated | Patna East
24 | USS-109-4 | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | Inaugurated | Patna East
25 | USS-109-5 | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | Inaugurated | Patna East
26 | USS-110-3 | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 |  | Patna East
27 | USS-111-1 | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | Inaugurated | Patna East
28 | USS-111-2 | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | Inaugurated | Patna East
29 | USS-111-3 | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | Inaugurated | Patna East
30 | USS-111-4 | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | Inaugurated | Patna East
31 | USS-112-1 | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 |  | Patna East
32 | USS-113-4 | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | Inaugurated | Patna East
33 | USS-114-2 | Bhojpur | Sahar | M.S. Baruhi 9199571702 | Inaugurated | Patna East
34 | USS-114-3 | Bhojpur | Ara | M.S. Basantpur 09308735308 | Inaugurated | Patna East
35 | USS-114-4 | Bhojpur | Sahar | M.S. Nawada 9934483628 | Inaugurated | Patna East
36 | USS-116 (B) | Buxar | Dumraon | M.S. Kanjharua 9955867071 |  | Patna West
37 | USS-116 (D) | Buxar | Dumraon | M.S. Karuaj 9931281346 |  | Patna West
38 | USS-116 (E) | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 |  | Patna West
39 | USS-119 (B) | Kaimur | Bhabhua | M.S.Piliyan |  | Patna West
40 | USS-119 (D) | Kaimur | Bhabhua | M.S. Mohan Darwan |  | Patna West
41 | USS-121 (B) | Rohtas | Karakat | Girl's M.S.Motha 9162106111 |  | Patna West
42 | USS-121 (C) | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 |  | Patna West
43 | USS-121 (E) | Rohtas | Akorhigola | M.S.Chhapra 9934757484 |  | Patna West
44 | USS-122-4 | Rohtas | Dinara | M.S. Bararhi, 9955083783 |  | Patna West
45 | USS-122-6 | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 |  | Patna West
46 | USS-123-1 | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 |  | Patna West
47 | USS-123-2 | Rohtas | Kochas | M.S. Ubadhi, 8002578689 |  | Patna West
48 | USS-123-3 | Rohtas | Kochas | M.S. Kuchila, 8002537247 |  | Patna West
49 | USS-123-4 | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 |  | Patna West
50 | USS-123-5 | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | Handover | Patna West
51 | USS-123-6 | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | Handover | Patna West
52 | USS-125-1 | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | Inaugurated | Patna West
53 | USS-143-1 | Jehanabad | Kako | M.S.Kajisarai 9934814478 | Inaugurated | Magadh
54 | USS-143-2 | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | Inaugurated | Magadh
55 | USS-143-4 | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | Inaugurated | Magadh
56 | USS-146 (B) | Nawada | Roh 3 | M.S. Wara panday, 9931630318 |  | Magadh
57 | USS-146 (C) | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | Inaugurated | Magadh
58 | USS-146 (D) | Nawada | Pakribarawan | M.S. Ukaorah |  | Magadh
59 | USS-147-1 | Nawada | Narhat | M.S. Khanwa, 9905846666 |  | Magadh
60 | USS-147-2 | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 |  | Magadh
61 | USS-149 (C) | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 |  | Magadh
62 | USS-149 (E) | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 |  | Magadh
63 | USS-150 (A) | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 |  | Magadh
64 | USS-151-1 | Gaya | Bathani | Basic M.S. Radui, 7654409634 | Inaugurated | Magadh
65 | USS-151-2 | Gaya | Bathani | M.S. Karubigha, 9934427661 | Inaugurated | Magadh
66 | USS-151-3 | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | Inaugurated | Magadh
67 | USS-152-1 | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | Inaugurated | Magadh
68 | USS-152-2 | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | Inaugurated | Magadh
69 | USS-152-5 | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | Inaugurated | Magadh
70 | USS-152-6 | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | Inaugurated | Magadh
71 | USS-153 (A) | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 |  | Magadh
72 | USS-154-1 | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | Inaugurated | Magadh
73 | USS-154-2 | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | Inaugurated | Magadh
74 | USS-154-4 | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | Inaugurated | Magadh
75 | USS-154-5 | Aurangabad | Deo | M.S. Vijouli, 9801123435 | Inaugurated | Magadh
76 | USS-155-1 | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | Inaugurated | Magadh
77 | USS-155-2 | Aurangabad | Obra | M.S. Ratwar, 9931418907 | Inaugurated | Magadh
78 | USS-155-4 | Aurangabad | Obra | M.S. Karsawan, 9470488343 | Inaugurated | Magadh
79 | USS-156-3 | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | Inaugurated | Magadh
80 | USS-157 (A) | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 |  | Magadh
81 | USS-157 (C) | Aurangabad | Madanpur | M.S. Judahi, 9931892284 |  | Magadh
82 | USS-132-1 | Sheikhpura | Barbigha | M.S.Keuti | Inaugurated | Munger
83 | USS-132-2 | Sheikhpura | SheKhpura | M.S.Lodipur | Inaugurated | Munger
84 | USS-132-3 | Sheikhpura | Chewara | M.S.Lahana | Inaugurated | Munger
85 | USS-132-4 | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | Inaugurated | Munger
86 | USS-132-5 | Sheikhpura | Ariari | M.S.Husainawad | Inaugurated | Munger
87 | USS-133(A) | Lakhisarai | Barahiya | M.S.Pali 9546977875 |  | Munger
88 | USS-133(D) | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 |  | Munger
89 | USS-133(F) | Lakhisarai | Pipariya | M.S. Pawai 9263032826 |  | Munger
90 | USS-135-1 | Munger | Asarganj | M.S.Chakhand 9135065232 | Inaugurated | Munger
91 | USS-135-2 | Munger | Asarganj | M.S. Beran 9204931976 | Inaugurated | Munger
92 | USS-136-1 | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | Inaugurated | Munger
93 | USS-136-3 | Munger | Sangrampur | M.S.Katiyari 9199782900 | Inaugurated | Munger
94 | USS-137-1 | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | Inaugurated | Munger
95 | USS-137-2 | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | Inaugurated | Munger
96 | USS-137-3 | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | Inaugurated | Munger
97 | USS-137-4 | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | Inaugurated | Munger
98 | USS-137-5 | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | Inaugurated | Munger
99 | USS-139-2 | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | Inaugurated | Munger
100 | USS-139-3 | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | Inaugurated | Munger
101 | USS-139-4 | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | Inaugurated | Munger
102 | USS-139-5 | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | Inaugurated | Munger
103 | USS-140-1 | Begusarai | Garhpura | M.S.Kuddhar 9955509070 |  | Munger
104 | USS-140-2 | Begusarai | Dandari | M.S.Katarmala 9709640304 |  | Munger
105 | USS-140-3 | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | Inaugurated | Munger
106 | USS-141 (D) | Khagaria | Khagaria | M.S.Mathar 9771388437 |  | Munger
107 | USS-142-2 | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | Inaugurated | Munger
108 | USS-142-3 | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | Inaugurated | Munger
109 | USS-127 (C) | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | Inaugurated | Bhagalpur
110 | USS-127 (E) | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | HANDOVER | Bhagalpur
111 | USS-128 (B) | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | HANDOVER | Bhagalpur
112 | USS-128 (C) | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 |  | Bhagalpur
113 | USS-129 (B) | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 |  | Bhagalpur
114 | USS-130-1 | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | Inaugurated | Bhagalpur
115 | USS-130-2 | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | Inaugurated | Bhagalpur
116 | USS-130-3 | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | Inaugurated | Bhagalpur
117 | USS-130-4 | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | Inaugurated | Bhagalpur
118 | USS-130-5 | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | Inaugurated | Bhagalpur
119 | USS-199C | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | HANDOVER | Kosi
120 | USS-199D-1 | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 |  | Kosi
121 | USS-199 D-2 | Madhepura | Singheshwar | Middle School Barhari 9661376885 | Inaugurated | Kosi
122 | USS-194-1 | Purnea | Amaur | U. M. S. Bagdar 9939096309 | Inaugurated | Purnea
123 | USS-194-2 | Purnea | K. Nagar | M S Gauasi 9473124829 |  | Purnea
124 | USS-194-3 | Purnea | Purnia East | M S Maranga 9939732346 |  | Purnea
125 | USS-194-4 | Purnea | Rupauli | M. S. Bairiya 9434821065 |  | Purnea
126 | USS-196(B) | Katihar | Ajamnagar | Middle School Arihana 8809322797 |  | Purnea
127 | USS-199A (A) | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 |  | Purnea
128 | USS-199A (B) | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 |  | Purnea
129 | USS-199A (C) | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 |  | Purnea
130 | USS-199A (D) | Araria | Narpatganj | Middle School Achra 9801296055 |  | Purnea
131 | USS-199 B-1 | Araria | Jokihat | Middle School Jhanpur 9471219710 | Inaugurated | Purnea
132 | USS-199 B-2 | Araria | Raniganj | Middle School Kosikapur 9199673607 | Inaugurated | Purnea
133 | USS-199 B-3 | Araria | Araria | Middle School Araria Basti 9661185784 | Inaugurated | Purnea
134 | USS-162 (A) | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | handover | Tirhut East
135 | USS-162 (B) | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | Inaugurated | Tirhut East
136 | USS-162 (C) | Sitamarhi | Suppi | M. S. Aktha 9470821881 | Inaugurated | Tirhut East
137 | USS-162 (E) | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 |  | Tirhut East
138 | USS-162 (F) | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 |  | Tirhut East
139 | USS-163 (A) | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 |  | Tirhut East
140 | USS-163 (B) | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | Inaugurated | Tirhut East
141 | USS-163 (C) | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | Inaugurated | Tirhut East
142 | USS-163 (D) | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 |  | Tirhut East
143 | USS-164-1 | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | Inaugurated | Tirhut East
144 | USS-164-2 | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | Inaugurated | Tirhut East
145 | USS-164-3 | Vaishali | Bhagwanpur | M. S. Askaranpur |  | Tirhut East
146 | USS-166 (B) | Vaishali | Raghopur | M.S,Paharpur 7654539556 | handover | Tirhut East
147 | USS-166 (C) | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 |  | Tirhut East
148 | USS-167-1 | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | Inaugurated | Tirhut East
149 | USS-167-2 | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | Inaugurated | Tirhut East
150 | USS-167-3 | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | Inaugurated | Tirhut East
151 | USS-167-4 | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | Inaugurated | Tirhut East
152 | USS-167-5 | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | Inaugurated | Tirhut East
153 | USS-168-1 | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | Inaugurated | Tirhut East
154 | USS-168-2 | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | Inaugurated | Tirhut East
155 | USS-168-3 | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | Inaugurated | Tirhut East
156 | USS-168-4 | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | Inaugurated | Tirhut East
157 | USS-169-1 | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | Inaugurated | Tirhut East
158 | USS-169-2 | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | Inaugurated | Tirhut East
159 | USS-169-3 | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | Inaugurated | Tirhut East
160 | USS-169-4 | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | Inaugurated | Tirhut East
161 | USS-169-5 | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | Inaugurated | Tirhut East
162 | USS-170-1 | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | Inaugurated | Tirhut East
163 | USS-170-2 | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 |  | Tirhut East
164 | USS-170-3 | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 |  | Tirhut East
165 | USS-170-4 | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 |  | Tirhut East
166 | USS-170-5 | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | Inaugurated | Tirhut East
167 | USS-171-1 | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | Inaugurated | Tirhut East
168 | USS-171-2 | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 |  | Tirhut East
169 | USS-171-4 | Muzaffarpur | Katra | M. S, Bakhari 9631173639 |  | Tirhut East
170 | USS-172-1 | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | Inaugurated | Tirhut East
171 | USS-172-2 | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | Inaugurated | Tirhut East
172 | USS-172-3 | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | Inaugurated | Tirhut East
173 | USS-172-4 | Muzaffarpur | Mushhari | M. S, Dronpur | Inaugurated | Tirhut East
174 | USS-172-5 | Muzaffarpur | Muraul | M. S, Pilkhi | Inaugurated | Tirhut East
175 | USS-159-4 | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | Inaugurated | Tirhut West
176 | USS-160-3 | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | Inaugurated | Tirhut West
177 | USS-191-3 | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | Inaugurated | Darbhanga
178 | USS-191-4 | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | Inaugurated | Darbhanga
179 | USS-191-5 | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | Inaugurated | Darbhanga
180 | USS-192 C | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 |  | Darbhanga
181 | USS-192 D | Darbhanga | Biraul | U. M. S, Balha 7631905606 |  | Darbhanga
182 | USS-193-1 | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | Inaugurated | Darbhanga
183 | USS-193-2 | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | Inaugurated | Darbhanga
184 | USS-193-4 | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | Inaugurated | Darbhanga
185 | USS-173 (B) | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | Inaugurated | Saran
186 | USS-174-1 | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | Inaugurated | Saran
187 | USS-174-2 | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 |  | Saran
188 | USS-174-3 | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | Inaugurated | Saran
189 | USS-174-4 | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | Inaugurated | Saran
190 | USS-175-1 | Siwan | Siswan | M. S, Gyaspur 8809341191 | Hand Over | Saran
191 | USS-175-2 | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | Inaugurated | Saran
192 | USS-175-3 | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | Inaugurated | Saran
193 | USS-175-4 | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | Inaugurated | Saran
194 | USS-176-1 | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | Inaugurated | Saran
195 | USS-176-2 | Siwan | Gudhani | M. S, Belauri 8809165382 | Inaugurated | Saran
196 | USS-176-3 | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | Inaugurated | Saran
197 | USS-177-1 | Saran | Dariyapur | Middle School, Saraiya 9431647901 | Inaugurated | Saran
198 | USS-177-2 | Saran | Dariyapur | Middle School, Bhongha 9006298659 | Inaugurated | Saran
199 | USS-177-3 | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | Inaugurated | Saran
200 | USS-178-1 | Saran | Sonpur | Middle School, Shikharpur 9631221348 | Inaugurated | Saran
201 | USS-179-1 | Saran | Lahaladpur | Middle School, Basahi Urdu | Inaugurated | Saran
202 | USS-179-2 | Saran | Ekma | Middle School, Bhodasa | Inaugurated | Saran
203 | USS-179-3 | Saran | Ekma | Middle School, Betbaniya 8294839353 | Inaugurated | Saran
204 | USS-179-4 | Saran | Ekma | Middle School, Eksar 9572740280 | Inaugurated | Saran
205 | USS-179-5 | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | Inaugurated | Saran
206 | USS-181-1 | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | Inaugurated | Saran
207 | USS-182-1 | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | Inaugurated | Saran
208 | USS-182-2 | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | Inaugurated | Saran
209 | USS-182-3 | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | Inaugurated | Saran
210 | USS-183-1 | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | Inaugurated | Saran
211 | USS-183-2 | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | Inaugurated | Saran
212 | USS-183-4 | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | Inaugurated | Saran
213 | USS-184-1 | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | Inaugurated | Saran
214 | USS-184-2 | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | Inaugurated | Saran
215 | USS-184-3 | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | Inaugurated | Saran
216 | USS-185-1 | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | Inaugurated | Saran
217 | USS-185-3 | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | Inaugurated | Saran
218 | USS-186-1 | Gopalganj | Hathua | U. M. S, Satai 8757888461 | Inaugurated | Saran
219 | USS-186-2 | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | Inaugurated | Saran
220 | USS-186-4 | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 |  | Saran
Note on B21: ACCORD. TO 475 USS-108-1
Note on B216: List from 161 & 250 ing list

## Not Start USS 2010-11
8 | USS-102-3 | Nalanda | Chandi | M.S. Dariya Bigha 9931236900 | Land not available, work not possible | Patna East | 2010-11
9 | USS-102-4 | Nalanda | Chandi | Urdu.M.S. Baisa 9939043903 | Land not available, work not possible | Patna East | 2010-11
13 | USS-103-2 | Nalanda | Hilsa | M.S. Rasai Bigha 9934593683 | Retender | Patna East | 2010-11
16 | USS-104-1 | Patna | Khushrupur | M.S. Jagmal Bigha 9771442400 | Insufficient land | Patna East | 2010-11
17 | USS-104-2 | Patna | Khushrupur | U.M.S. Arrai Benipur 9135748584 | Insufficient land | Patna East | 2010-11
24 | USS-106-1 | Patna | Bihta | M.S. Kateshar 7250695245 | Low Land about 12'-0", work not possible | Patna East | 2010-11
25 | USS-106-2 | Patna | Bikram | M.S. Barah 8084301353 | Land not regitered to school, work not possible | Patna East | 2010-11
26 | USS-106-3 | Patna | Bihta | M.S. Kanhauli 9386873458 | Land dispute between School & college, work not possible | Patna East | 2010-11
32 | USS-108-6 | Bhojpur | Agioan | M.S. Lasarhi 9661399087 | Land not available, work not possible | Patna East | 2010-11
56 | USS-114-1 | Bhojpur | Sandesh | U.M.S.Nasratpur 9334673203 | Land Dispute | Patna East | 2010-11
61 | USS-115-2 | Buxar | Buxar | M.S.Manjharia 9472951603 | No Way | Patna West | 2010-11
63 | USS-115-4 | Buxar | Rajpur | Urdu M.S. Banni 9973105344 | Land not available | Patna West | 2010-11
73 | USS-118-1 | Buxar | Simiri | M.S.Dhanpura 9199795834 |  | Patna West | 2010-11
74 | USS-118-2 | Buxar | Simiri | M.S. Barka Singhnpura 9934740004 |  | Patna West | 2010-11
75 | USS-118-3 | Buxar | Simiri | M.S. Kharha Tarnh 9199359782 |  | Patna West | 2010-11
82 | USS-120 (C) | Kaimur | Nuaon | Govt. Basic School Kari Ram Akhili | Tender Process | Patna West | 2010-11
94 | USS-122-5 | Rohtas | Bikramganj | M.S. Jamorhi, 9955952582 |  | Patna West | 2010-11
110 | USS-143-3 | Jehanabad | Kako | M.S.Pinzour 9931803275 | Insufficient Land | Magadh | 2010-11
113 | USS-144 (B) | Jehanabad | Makhdumpur | M.S.Akbarpur, 9934858600 | Tender Process | Magadh | 2010-11
119 | USS-145-5 | Nawada | Nawada | M.S. Wermi, 9708857028 | Land not available | Magadh | 2010-11
124 | USS-146 (E) | Nawada | Kashichak | U.M.S. Vishbnathpur , 9386540972 | Retender | Magadh | 2010-11
128 | USS-148-2 | Gaya | Bodh Gaya | M.S. Titoiya, 9934672899 | Land Problem | Magadh | 2010-11
130 | USS-148-4 | Gaya | Bodh Gaya | M.S. Gapha Kala, 9934972678 | Not start | Magadh | 2010-11
152 | USS-153 (D) | Gaya | Sherghatty | M.S. Naknuppa, 9431289085 | Land not available | Magadh | 2010-11
155 | USS-154-3 | Aurangabad | Kutumba | M.S. Darmi, 9955519885, 9931921788 | Land not available | Magadh | 2010-11
160 | USS-155-3 | Aurangabad | Obra | M.S. Tejpur, 9973299799 | Land not available | Magadh | 2010-11
162 | USS-156-1 | Aurangabad | Haspura | M.S. Piru, 9135064392 | Land Encrochment | Magadh | 2010-11
163 | USS-156-2 | Aurangabad | Haspura | M.S. Sriwanbhatt, 9939023445 | Land not available | Magadh | 2010-11
176 | USS-133(B) | Lakhisarai | Barahiya | M.S.Lal Diyara 9097688412 | Not start | Munger | 2010-11
177 | USS-133(C) | Lakhisarai | Halsi | M.S. Geruapursanda 8084044144 | Not start | Munger | 2010-11
186 | USS-136-2 | Munger | Sangrampur | M.S.Khapra 9934832035 | Land not available | Munger | 2010-11
193 | USS-138-1 | Begusarai | Mansurchak | M.S.Chhabilapur 9771848155 | Land not available | Munger | 2010-11
197 | USS-138-5 | Begusarai | Sahebpur Kamal | M.S.Rajoura 9709067460 | Land not available | Munger | 2010-11
217 | USS-127 (A) | Bhagalpur | Pirpainti | M.S.Mahuadhih 9955027709, 7549131650 | LAND PROBLEM | Bhagalpur | 2010-11
218 | USS-127 (B) | Bhagalpur | Pirpainti | M.S. Maultola, 9534766339 | LAND PROBLEM | Bhagalpur | 2010-11
226 | USS-129 (A) | Bhagalpur | Rangrachauk | M.S.Murli 9534523062 | Land Dispute | Bhagalpur | 2010-11
239 | USS-199D-3 | Madhepura | Kumarkhand | Middle School Rahta 9631460084 | Land not available | Kosi | 2010-11
245 | USS-195-2 | Katihar | Manihari | Middle School Mirjapur 8084519254 941640318 |  | Purnea | 2010-11
252 | USS-197(B) | Katihar | Dhankhora | Middle School Durgasthan Dhankhora9431869787 | Land not available | Purnea | 2010-11
255 | USS-198-1 | Katihar | Brari | Middle School Laxmipur | Tender Process | Purnea | 2010-11
256 | USS-198-2 | Katihar | Brari | Middle School Anarkali | Tender Process | Purnea | 2010-11
257 | USS-198-3 | Katihar | Hasanganj | Middle School Hasanganj | Tender Process | Purnea | 2010-11
270 | USS-162 (D) | Sitamarhi | Riga | M. S. Ramnagara 9570781314 |  | Tirhut East | 2010-11
280 | USS-164-4 | Vaishali | Bhagwanpur | M. S. Kutubpur 9534509369 | No Land | Tirhut East | 2010-11
281 | USS-164-5 | Vaishali | Lalganj | U.M.S. Basanta 9934417163 | No Land | Tirhut East | 2010-11
285 | USS-165-4 | Vaishali | Sahadei Bujurg | M.S, Nayaganj 9934912623 |  | Tirhut East | 2010-11
289 | USS-166 (C) | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 |  | Tirhut East | 2010-11
325 | USS-159-2 | East Champaran | chaaiya | M.S. Madhubani 9430565177 |  | Tirhut West | 2010-11
333 | USS-160-5 | West Champaran | Nautan | M.S.Sansariya 8757124792 |  | Tirhut West | 2010-11
337 | USS-187-2 | Madhubani | Lakhanpur | M. S. Belaucha | Land Not Avilable | Darbhanga | 2010-11
338 | USS-187-3 | Madhubani | Jaynagar | Middle School, Dhaniyapatti 9931037199 9661794550 | Land Not Avilable | Darbhanga | 2010-11
341 | USS-188-1 | Madhubani | Banipatti | M. S.Ganguli 9431629001 | AGREEMENT NOT DONE (CONTRACTOR REFUSED) | Darbhanga | 2010-11
342 | USS-188-2 | Madhubani | Kaluahi | M. S.Kalikapur 9973900631 |  | Darbhanga | 2010-11
343 | USS-188-3 | Madhubani | Bisfi | M. S.Singhaso 9162249674 8051935537 |  | Darbhanga | 2010-11
345 | USS-189-2 | Samastipur | Vibhutipur | U. M. S, Mustafapur | LOW LAND | Darbhanga | 2010-11
348 | USS-191-1 | Darbhanga | Manigachhi | U. M. S, Dahaura 9431405480 | required land 68'x67' avlaible land27'x25' | Darbhanga | 2010-11
349 | USS-191-2 | Darbhanga | Kewati | M. S, Koila Majhigama 9304020023 | LAND DISPUTE | Darbhanga | 2010-11
359 | USS-193-3 | Darbhanga | Alinagar | U. M. S, Rampur Uday 9546520079 | required land 68'x67' avlaible land16'x14' | Darbhanga | 2010-11
390 | USS-183-3 | Gopalganj | Kuchaikot | Middle School, Balthari 9973181137 | Low Land | Saran | 2010-11
395 | USS-184-4 | Gopalganj | Singhwaliya | Middle School, Amarpura Jagiraha 9801115115 | Land Not Available | Saran | 2010-11
397 | USS-185-2 | Gopalganj | Gopalganj | Middle School, Karariya 9934499260 | Land Problem | Saran | 2010-11
399 | USS-185-4 | Gopalganj | Gopalganj | Middle School, Baraipatti 9955771721 | Land Problem | Saran | 2010-11
402 | USS-186-3 | Gopalganj | Hathua | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 | Land Problem | Saran | 2010-11
Note on F9: Group will closed due dely in land availability.
Note on E40: Gurudev Const.

## Sheet1
Group No. | 10
USS -77-2 |  | USS-199B-2
USS -77-3 |  | USS-199B-3
USS -77-4 |  | USS-154-1
USS-78-1 |  | USS-154-2
USS-78-2 |  | USS-154-4
USS-78-3 |  | USS-154-5
USS-78-4 |  | USS-155-1
USS-79-2 |  | USS-155-2
USS-79-4 |  | USS-155-4
USS 199B-1 | 1 | USS 199B-1
USS-199B-2 | 1 | USS-199B-2
USS-199B-3 | 1 | USS-199B-3
USS-29-1 |  | USS-154-1
USS-29-4 |  | USS-154-2
USS-30-1 |  | USS-154-4
USS-30-3 |  | USS-154-5
USS-30-4 |  | USS-155-1
USS-31-3 |  | USS-155-2
USS-154-1 | 1 | USS-155-4
USS-154-2 | 1 | USS-156-3
USS-154-4 | 1 | USS-201-4
USS-154-5 | 1 | USS-202-1
USS-155-1 | 1 | USS-202-2
USS-155-2 | 1 | USS-202-4
USS-155-4 | 1 | USS-202-5
USS-156-3 | 1 | USS-203-1
USS-84-2 |  | USS-203-2
USS-84-3 |  | USS-203-3
USS-84-4 |  | USS-203-4
USS-85-2 |  | USS-207-1
USS-86-2 |  | USS-207-2
USS-201-4 | 1 | USS-207-3
USS-202-1 | 1 | USS-207-4
USS-202-2 | 1 | USS-142-2
USS-202-4 | 1 | USS-142-3
USS-202-5 | 1 | USS-151-1
USS-203-1 | 1 | USS-151-2
USS-203-2 | 1 | USS-151-3
USS-203-3 | 1 | USS-152-1
USS-203-4 | 1 | USS-152-2
USS-207-1 | 1 | USS-152-5
USS-207-2 | 1 | USS-152-6
USS-207-3 | 1 | USS-183-1
USS-207-4 | 1 | USS-183-2
USS-27-5 |  | USS-183-4
USS-142-2 | 1 | USS-184-1
USS-142-3 | 1 | USS-184-2
USS-32-3 |  | USS-184-3
USS-32-4 |  | USS-185-1
USS-33-1 |  | USS-185-3
USS-33-2 |  | USS-186-1
USS-33-3 |  | USS-186-2
USS-33-4 |  | USS-143-2
USS-34A-2 |  | USS-143-4
USS-34-3 |  | USS-191-3
USS-34-4 |  | USS-191-4
USS-34-5 |  | USS-191-5
USS-151-1 | 1 | USS-193-1
USS-151-2 | 1 | USS-193-2
USS-151-3 | 1 | USS-193-4
USS-152-1 | 1 | USS-146C-1
USS-152-2 | 1 | USS-102A-1
USS-152-5 | 1 | USS-104-3
USS-152-6 | 1 | USS-104-4
USS-183-1 | 1 | USS-105-1
USS-183-2 | 1 | USS-105-2
USS-183-4 | 1 | USS-105-3
USS-184-1 | 1 | USS-105-4
USS-184-2 | 1 | USS-107-1
USS-184-3 | 1 | USS-160-3
USS-185-1 | 1 | USS-194-1
USS-185-3 | 1 | USS-159-4
USS-186-1 | 1 | USS-139-2
USS-186-2 | 1 | USS-139-3
USS-23-2 |  | USS-139-4
USS-143-2 | 1 | USS-139-5
USS-143-4 | 1 | USS-140-3
USS-63-2 |  | USS-130-1
USS-64-1 |  | USS-130-2
USS-64-2 |  | USS-130-3
USS-64-3 |  | USS-130-4
USS-65-1 |  | USS-130-5
USS-65-2 |  | USS-127(C)
USS-65-3 |  | USS-108-1
USS-66-2 |  | USS-108-2
USS-191-3 | 1 | USS-108-3
USS-191-4 | 1 | USS-109-1
USS-191-5 | 1 | USS-109-3
USS-193-1 | 1 | USS-109-4
USS-193-2 | 1 | USS-109-5
USS-193-4 | 1 | USS-111-1
USS-146C-1 | 1 | USS-111-2
USS-102A-1 | 1 | USS-111-3
USS-3-4 |  | USS-111-4
USS-5-2 |  | USS-112-2
USS-104-3 | 1 | USS-113-4
USS-104-4 | 1 | USS-114-2
USS-105-1 | 1 | USS-114-4
USS-105-2 | 1 | USS-219 -1
USS-105-3 | 1 | USS-199D-2
USS-105-4 | 1 | USS-135-1
USS-107-1 | 1 | USS-135-2
USS-39-1 |  | USS-136-1
USS-39-3 |  | USS-136-3
USS-160-3 | 1 | USS-137-1
USS-81-1 |  | USS-137-2
USS-81-2 |  | USS-137-3
USS-82-1 |  | USS-137-4
USS-82-2 |  | USS-137-5
USS-82-4 |  | USS-167-1
USS-194-1 | 1 | USS-167-2
USS-42-4 |  | USS-167-3
USS-44-1 |  | USS-167-4
USS-44-4 |  | USS-167-5
USS-159-4 | 1 | USS-168-1
USS-9-4 |  | USS-168-2
USS-10-1 |  | USS-168-3
USS-10-2 |  | USS-168-4
USS-10-4 |  | USS-169-1
USS-18-1 |  | USS-169-2
USS-25-2 |  | USS-169-3
USS-139-2 | 1 | USS-169-4
USS-139-3 | 1 | USS-169-5
USS-139-4 | 1 | USS-170-1
USS-139-5 | 1 | USS-170-5
USS-140-3 | 1 | USS-171-1
USS-16-1 |  | USS-172-1
USS-16-2 |  | USS-172-2
USS-16-3 |  | USS-172-3
USS-130-1 | 1 | USS-172-4
USS-130-2 | 1 | USS-172-5
USS-130-3 | 1 | USS-125-1
USS-130-4 | 1 | USS-164-1
USS-130-5 | 1 | USS-164-2
USS-127(C) | 1 | USS-132-1
USS-108-1 | 1 | USS-132-2
USS-108-2 | 1 | USS-132-3
USS-108-3 | 1 | USS-132-4
USS-109-1 | 1 | USS-132-5
USS-109-3 | 1 | USS-177-1
USS-109-4 | 1 | USS-177-2
USS-109-5 | 1 | USS-177-3
USS-111-1 | 1 | USS-178-1
USS-111-2 | 1 | USS-179-1
USS-111-3 | 1 | USS-179-2
USS-111-4 | 1 | USS-179-3
USS-112-2 | 1 | USS-179-4
USS-113-4 | 1 | USS-179-5
USS-114-2 | 1 | USS-181-1
USS-114-3 |  | USS-182-1
USS-114-4 | 1 | USS-182-3
USS-219 -1 | 1 | USS-182-5
USS-71-2 |  | USS-174-1
USS-71-3 |  | USS-174-3
USS-71-4 |  | USS-174-4
USS-199D-2 | 1 | USS-175-2
USS-135-1 | 1 | USS-175-3
USS-135-2 | 1 | USS-175-4
USS-136-1 | 1 | USS-176-1
USS-136-3 | 1 | USS-176-2
USS-137-1 | 1 | USS-176-3
USS-137-2 | 1 | USS-212-1
USS-137-3 | 1 | USS-173 (B)-1/ USS-173-3
USS-137-4 | 1 | USS-162 (B)-1 / USS-162-2
USS-137-5 | 1 | USS-162 (C)-1 / USS-162-3
USS-51-3 |  | USS-163 (B)-1 / USS-163-2
USS-167-1 | 1 | USS-163 (C)-1 / USS-163-3
USS-167-2 | 1
USS-167-3 | 1
USS-167-4 | 1
USS-167-5 | 1
USS-168-1 | 1
USS-168-2 | 1
USS-168-3 | 1
USS-168-4 | 1
USS-169-1 | 1
USS-169-2 | 1
USS-169-3 | 1
USS-169-4 | 1
USS-169-5 | 1
USS-170-1 | 1
USS-170-5 | 1
USS-171-1 | 1
USS-172-1 | 1
USS-172-2 | 1
USS-172-3 | 1
USS-172-4 | 1
USS-172-5 | 1
USS-13-1
USS-14-1
USS-125-1 | 1
USS-52-1
USS-53-1
USS-53-2
USS-53-3
USS-164-1 | 1
USS-164-2 | 1
USS-132-1 | 1
USS-132-2 | 1
USS-132-3 | 1
USS-132-4 | 1
USS-132-5 | 1
USS-73-1
USS-73-2
USS-73-3
USS-72-3
USS-60-1
USS-60-2
USS-60-3
USS-60-4
USS-60-5
USS-177-1 | 1
USS-177-2 | 1
USS-177-3 | 1
USS-178-1 | 1
USS-179-1 | 1
USS-179-2 | 1
USS-179-3 | 1
USS-179-4 | 1
USS-179-5 | 1
USS-181-1 | 1
USS-182-1 | 1
USS-182-3 | 1
USS-182-5 | 1
USS-174-1 | 1
USS-174-3 | 1
USS-174-4 | 1
USS-175-2 | 1
USS-175-3 | 1
USS-175-4 | 1
USS-176-1 | 1
USS-176-2 | 1
USS-176-3 | 1
USS-212-1 | 1
USS-173 (B)-1/ USS-173-3 | 1
USS-46-3
USS-46-4
USS-47-1
USS-47-3
USS-47-4
USS-47-5
USS-162 (B)-1 / USS-162-2 | 1
USS-162 (C)-1 / USS-162-3 | 1
USS-163 (B)-1 / USS-163-2 | 1
USS-163 (C)-1 / USS-163-3 | 1
USS-75-1
USS-75-2
USS-75-3
USS-76-3
USS-76-4
Note on G86: according to div.(EE) USS-108-2
Note on G87: accord. To div USS-108-3
Note on G88: accord. To div USS-108-3
Note on A138: according to div.(EE) USS-108-2
Note on A139: accord. To div USS-108-3
Note on A140: accord. To div USS-108-3
Note on G153: ACCORDING TO DIV. USS-182-2
Note on G154: ACCORD. TO DIV. USS-182-3
Note on A225: ACCORDING TO DIV. USS-182-2
Note on A226: ACCORD. TO DIV. USS-182-3

## USS-9-10(250)
BSEIDC , Patna
Physical Status of USS (Central Fund) - 2009-10
S.N. | Group No. | Name of District | Name of Block | Name of School | Physical Status | [9 empty] | Remarks | Division | Session
[5 empty] | Not Start | Layout | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[9 empty] | LL | RL | LL | RL
1 | USS-1-1 | Nalanda | p.Mh | eŒfoŒlwedk 9931607862 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
2 | USS-1-2 | Nalanda | bLykeiqj | eŒfoŒenkjxat 9631262679 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
3 | USS-1-3 | Nalanda | fgylk | eŒfoŒvdcjiqj 9470085363 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
4 | USS-1-4 | Nalanda | fcgkj 'kjhQ | eŒfoŒflaxFkq 9204881769 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
5 | USS-2-2 | Nalanda | drjhljk; | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
6 | USS-2-3 | Nalanda | jktxhj | eŒfoŒygqvkj 9798642205@9504394778 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
7 | USS-2-4 | Nalanda | flyko | eŒfoŒujgj fcxgk 8002186727 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
8 | USS-3-2 | Patna | ck<+ | eŒfoŒeqckjdiqj 9631978359 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
9 | USS-3-3 | Patna | Qrqgk¡ | eŒfoŒMqejh 8521893444 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
10 | USS-3-4 | Patna | Qrqgk¡ | mRØŒeŒfoŒip:f[k;k 9801459905 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
11 | USS-4-1 | Patna | nkukiqj | eŒfoŒvdhyiqj 9835490244 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
12 | USS-4-2 | Patna | ukScriqj | eŒfoŒvgqvkjk 9939680617 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
13 | USS-5-1 | Patna | /ku:vk | eŒfoŒdkslqr 9973270948@9974270948 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
14 | USS-5-2 | Patna | elkS<+h | eŒfoŒNkrk 8084994281 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
15 | USS-5-3 | Patna | lairpd | eŒfoŒyadk dNqvkjk 9162137790 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
16 | USS-5-4 | Patna | iquiqu | eŒfoŒdY;k.kiqj 9507549063 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2009-10
17 | USS-9-1 | Buxar | cDlj | eŒfoŒd`riqjk 9576622685 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
18 | USS-9-2 | Buxar | pkSlk | eŒfoŒcukjiqj 8873946373 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
19 | USS-9-3 | Buxar | jktiqj | eŒfoŒjlsu 9006272320 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
20 | USS-9-4 | Buxar | bVkM+h | eŒfoŒcSdqUBiqj 9931755863 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
21 | USS-10-1 | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
22 | USS-10-2 | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
23 | USS-10-4 | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
24 | USS-11-1 | Kaimur | dqnjk | eŒfoŒvojS;k 9973613935 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
25 | USS-11-2 | Kaimur | eksgfu;k¡ | eŒfoŒdVjkdyk 9006263731 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
26 | USS-11-3 | Kaimur | jkex<+ | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
27 | USS-11-4 | Kaimur | nqxkZorh | eŒfoŒnqxkZorh 9430340748@9955221828 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
28 | USS-12-1 | Kaimur | HkHkqvk | eŒfoŒdqM+klu 9031437647 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
29 | USS-12-2 | Kaimur | pSuiqj | eŒfoŒdasok 9430026932 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
30 | USS-13-1 | Rohtas | djxgj | eŒfoŒrksjuh 9631253327 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
31 | USS-13-3 | Rohtas | lklkjke | eŒfoŒfldfj;k 9431464894 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
32 | USS-13-4 | Rohtas | dkspl | eŒfoŒegqvkjh 9661222301 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
33 | USS-14-1 | Rohtas | fMgjh | eŒfoŒxaxkSyh 7352200057 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
34 | USS-14-2 | Rohtas | fnukjk | eŒfoŒljuk 9771634397 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
35 | USS-14-3 | Rohtas | dkjkdkV | eŒfoŒeksguiqj 9801296392 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
36 | USS-14-4 | Rohtas | uks[kk | eŒfoŒ?kksjfMgk 9801894133 | [9 empty] | 1 | Inaugurated | Patna West | 2009-10
37 | USS-28-1 | Jehanabad | tgkukckn | eŒfoŒveSu 9473327625 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
38 | USS-28-2 | Jehanabad | dkdks | eŒfoŒHknljk 9006927848 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
39 | USS-28-3 | Jehanabad | e[knqeiqj | eŒfoŒdksgjk 9162155024 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
40 | USS-29-1 | Aurangabad | nso | eŒfoŒcs<+uh 9631266207 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
41 | USS-29-2 | Aurangabad | enuiqj | eŒfoŒfijok¡ 9934340488 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
42 | USS-29-4 | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
43 | USS-30-1 | Aurangabad | vkscjk | eŒfoŒ'kadjiqj 7739690373 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
44 | USS-30-2 | Aurangabad | nkmnuxj | eŒfoŒteqvkok¡ 9801563600 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
45 | USS-30-3 | Aurangabad | nkmnuxj | eŒfoŒpkSjh 9934434990 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
46 | USS-30-4 | Aurangabad | gliqjk | eŒfoŒdksbyok¡ 9135312996 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
47 | USS-31-1 | Aurangabad | dqVqEck | eŒfoŒfjfl;i 9955874942 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
48 | USS-31-2 | Aurangabad | uohuxj | eŒfoŒiM+fj;k 9931622753 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
49 | USS-31-3 | Aurangabad | ok:.k | eŒfoŒikSFkq 9471060433 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
50 | USS-32-1 | Gaya | cks/k x;k | eŒfoŒchjgqr 9934480418 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2009-10
51 | USS-32-2 | Gaya | uxj fuxe | eŒfoŒpwjh 9199466924 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
52 | USS-32-3 | Gaya | osykxat | mRØŒeŒfoŒve>j 9931835374 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
53 | USS-32-4 | Gaya | fVdkjh | eŒfoŒrkik Qrsgiqj 9430070517 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
54 | USS-33-1 | Gaya | MksHkh | eŒfoŒihjklhu 9473140628 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
55 | USS-33-2 | Gaya | dksp | eŒfoŒfnX?kh 9576852929 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
56 | USS-33-3 | Gaya | f[ktjljk; | eŒfoŒvkneiqj 9771084118 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
57 | USS-33-4 | Gaya | cthjxat | eŒfoŒikys 9955418354 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
58 | USS-34 A-2 | Gaya | Qrsgiqj | eŒfoŒckiwxzke 9934840966 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
59 | USS-34 A-3 | Gaya | eksguiqj | eŒfoŒvedksyk 9955837262 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
60 | USS-34 B-1 | Gaya | xq:vk | eŒfoŒpk¡lh 9006129640 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
61 | USS-34 B-2 | Gaya | bekexat | mRØŒeŒfoŒ]dksBh 9931625800 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
62 | USS-35-2 | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 | [9 empty] | 1 |  | Magadh | 2009-10
63 | USS-35-4 | Nawada | okfjlyhxat | mRØŒeŒfoŒelwnk 9708007113 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2009-10
64 | USS-36-2 | Nawada | jtkSyh | mRØŒeŒfoŒ]ckjkVk¡M loS;k | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
65 | USS-36-3 | Nawada | fljnyk | eŒfoŒlka< 9771960601 | [9 empty] | 1 | Inaugurated | Magadh | 2009-10
66 | USS-21-1 | Sheikhpura | 'ks[kiqjk | eŒfoŒckn'kkgiqj 9709066149 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
67 | USS-22-1 | Jamui | pdkbZ | eŒfoŒnqyeiqj 9973390953@9661984491 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
68 | USS-22-2 | Jamui | >k>k | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
69 | USS-22-3 | Jamui | lksuks | eŒfoŒiSjk efVgkuk 9801576608 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
70 | USS-23-1 | Jamui | teqbZ | mRØŒeŒfoŒ HkkVpd 9430818763 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
71 | USS-23-2 | Jamui | y{ehiqj | eŒfoŒgjyk 9162733763@9006655639 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
72 | USS-23-3 | Jamui | [kSjk | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
73 | USS-23-4 | Jamui | bZŒ vyhxat | eŒfoŒfetkZxat 8292659272 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
74 | USS-24-1 | Begusarai | cNokM+k | eŒfoŒQrsg 9570919206 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
75 | USS-24-2 | Begusarai | Hkxokuiqj | eŒfoŒeksf[r;kjiqj 9934441250 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
76 | USS-24-3 | Begusarai | psfj;k cfj;kjiqj | eŒfoŒldjoklk 9939576953 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
77 | USS-25-2 | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
78 | USS-26-1 | Begusarai | cjkSuh | eŒfoŒcFkkSyh 9801572247@9534334080 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
79 | USS-26-2 | Begusarai | efVgkuh | eŒfoŒtxriqjk 9939465778 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
80 | USS-27-1 | Khagaria | ijoÙkk | eŒfoŒdjuk 9939629342@9006237936 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
81 | USS-27-2 | Khagaria | vykSyh | eŒfoŒes?kkSuk 9534870633 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
82 | USS-27-3 | Khagaria | pkSFke | eŒfoŒigkM+pd 9431651745 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
83 | USS-27-4 | Khagaria | xksxjh | eŒfoŒidjSy 9955068112 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
84 | USS-27-5 | Khagaria | [kxfM+;k | eŒfoŒeksjdkgh Fkkuk 9534404397 | [9 empty] | 1 | Inaugurated | Munger | 2009-10
85 | USS-15-1 | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
86 | USS-15-2 | Bhagalpur | Sultanganj | MS Udadih 9801583582 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
87 | USS-15-4 | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
88 | USS-16-1 | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
89 | USS-16-2 | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
90 | USS-16-3 | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
91 | USS-16-4 | Bhagalpur | Goradih | MS Garhotiya 9931865594 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
92 | USS-17-1 | Bhagalpur | Sabaur | MS Shivaydih 9973394344 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
93 | USS-17-2 | Bhagalpur | Kharik | MS Dadpur 8051625862/ 2 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
94 | USS-17-4 | Bhagalpur | Ismailpur | MS Laxmipur 9546492998 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
95 | USS-18-1 | Banka | Barahat | MS Saharna 9431689507/ | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
96 | USS-18-2 | Banka | Bounsi | MS Bishanpur 9006554728 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
97 | USS-18-3 | Banka | Dhouriya | MS Bhatuachak 9955916141 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
98 | USS-18-4 | Banka | Rajoun | MS Majhgay 9771243197 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
99 | USS-19-1 | Banka | Amarpur | MS Bhadariya 9939749402 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2009-10
100 | USS-71-2 | Madhepura | Murliganj | M/S Parsha Navtol 9973625392 | [9 empty] | 1 | Inaugurated. | Kosi | 2009-10
101 | USS-71-3 | Madhepura | Kumarkhand | M/S Karuvaili 9771194253 | [9 empty] | 1 | Inaugurated. | Kosi | 2009-10
102 | USS-71-4 | Madhepura | Sigheshwar | M/S Singyon 9430633497 | [9 empty] | 1 | Inaugurated. | Kosi | 2009-10
103 | USS-72-1 | Madhepura | Uda kishunganj | M/S Barataini 9631850096 | [9 empty] | 1 | Inaugurated 2016 | Kosi | 2009-10
104 | USS-72-2 | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | [9 empty] | 1 | Inaugurated 2016 | Kosi | 2009-10
105 | USS-72-3 | Madhepura | Alamnagar | M/S Bargaon 9939489984 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
106 | USS-73-1 | Saharsa | Saur Bazar | M/S Khajuri 9472653157 9430632563 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
107 | USS-73-2 | Saharsa | Navhatta | M/S Kedalpatti 9939942137 8987203752 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
108 | USS-73-3 | Saharsa | Sonbarsa | M/S Pachlakh 7549317375 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
109 | USS-74-1 | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | [9 empty] | 1 | Inaugurated 2016 | Kosi | 2009-10
110 | USS-74-3 | Saharsa | Mahishi | M/S Jhara 9430696742 | [9 empty] | 1 | Inaugurated 2016 | Kosi | 2009-10
111 | USS-75-1 | Supaul | Basantpur | M/S Balbhadrapur 9472034607 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
112 | USS-75-2 | Supaul | Chatapur | M/S Madhubani 9631295927 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
113 | USS-75-3 | Supaul | Marauna | M/S Parikoch 9931662963 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
114 | USS-75-4 | Supaul | Raghopur | Lakhi Chand Sahu M/S Hariraha 9470047275 | [9 empty] | 1 | HANDOVER | Kosi | 2009-10
115 | USS-76-1 | Supaul | Kishanpur | M/S Phulwaria 8298274284 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
116 | USS-76-2 | Supaul | Pipra | M/S Ramnagar 9472335572 9570603091 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
117 | USS-76-3 | Supaul | Supaul | M/S Kariho 9430029088 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
118 | USS-76-4 | Supaul | Triveniganj | M/S Kumiyahi 8986062906 | [9 empty] | 1 | Inaugurated | Kosi | 2009-10
119 | USS-77-1 | Araria | Hkjxkek | mRØŒeŒfoŒjgfM+;k 9534388120 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
120 | USS-77-2 | Araria | jkuhxat | ckfydk eŒfoŒxq.korh 9771105449 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
121 | USS-77-3 | Araria | jkuhxat | eŒfoŒijekuaniqj 9631149958 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
122 | USS-77-4 | Araria | ujirxat | eŒfoŒuksfu;k Vksyk pdyk 9973417759 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
123 | USS-78-1 | Araria | Qkjfclxat | eŒfoŒe/kqcuh 9661601762 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
124 | USS-78-2 | Araria | Qkjfclxat | eŒfoŒVs<+h eqlgjh 9801199615 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
125 | USS-78-3 | Araria | vjfj;k | eŒfoŒiSdVksyk 9431087519@9431471118 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
126 | USS-78-4 | Araria | vjfj;k | eŒfoŒck¡lckM+h 9430264342 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
127 | USS-79-1 | Araria | dqlkZdk¡Vk | eŒfoŒdikjQksM+k 9931414194 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
128 | USS-79-2 | Araria | fldVh | eŒfoŒlksgkxekM+ksa 9661752676@9006316855 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
129 | USS-79-4 | Araria | iyklh | eŒfoŒ:iSy e/kSy 9771866133 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
130 | USS-80-1 | Kishanganj | fnX?kycSad | eŒfoŒgjokMaxk 8987208103 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
131 | USS-80-2 | Kishanganj | Bkdqjxat | eŒfoŒtaxyHkhVk 8987254242 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
132 | USS-80-3 | Kishanganj | dksapk/kkeu | eŒfoŒ/kuiqjk 9470868499 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
133 | USS-80-4 | Kishanganj | iksfB;k | eŒfoŒgfjiks[kj ØkafrxkN 9430677962 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
134 | USS-80-5 | Kishanganj | cgknqjxat | eŒfoŒgfjHkk"kk 9471834254 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
135 | USS-81-1 | Purnea | dsŒ uxj | vkn'kZ eŒfoŒijksjk 9631003614 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
136 | USS-81-2 | Purnea | dlok | mRØŒ eŒ foŒ dnok 9006717685@9162698638 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
137 | USS-81-3 | Purnea | Mx:vk | eŒfoŒeksgEeniqj 8877902279@9852305617 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
138 | USS-82-1 | Purnea | /kenkgk | vkn'kZ eŒfoŒfo'kuiqj 8002692294 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
139 | USS-82-2 | Purnea | Hkokuhiqj | eŒfoŒczãKkuh 9931249419 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
140 | USS-82-3 | Purnea | :ikSyh | eŒfoŒykyxat 9934565697 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2009-10
141 | USS-82-4 | Purnea | cueu[kh | eŒfoŒtkudh uxj gkV 9430675018 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
142 | USS-84-2 | Katihar | ckjlksbZ | eŒ foŒ clyxkao 9126846409 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
143 | USS-84-3 | Katihar | ckjlksbZ | eŒ foŒ <ëk 9471674809 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
144 | USS-84-4 | Katihar | vkteuxj | eŒ foŒ tydh 9470423557@ 8877799621 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
145 | USS-85-2 | Katihar | efugkjh | eŒfoŒiVuh ukjk;.kiqj 9430970158 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
146 | USS-85-3 | Katihar | Qydk | eŒfoŒ>x:pd 0431668067 | [9 empty] | 1 |  | Purnea | 2009-10
147 | USS-85-4 | Katihar | dks<+k | eŒfoŒf'kf'k;k 9431625914@ 0430582029 | [9 empty] | 1 |  | Purnea | 2009-10
148 | USS-86-2 | Katihar | dnok | eŒfoŒvk'k;kuh 8986509086 | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
149 | USS-46-1 | Sheohar | rfj;kuh | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2009-10
150 | USS-46-2 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] cyqvk 9771099254 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2009-10
151 | USS-46-3 | Sitamarhi | :Uuh lSniqj | eŒ foŒ] FkqEek 9472379528 | [9 empty] | 1 |  | Tirhut East | 2009-10
152 | USS-46-4 | Sitamarhi | csylaM | eŒ foŒ] ipukSj | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
153 | USS-47-1 | Sitamarhi | jhxk | eŒ foŒ] ;ksxokuk 9534893264 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
154 | USS-47-2 | Sitamarhi | cFkukgk | eŒ foŒ] fMgBh 9973981418 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
155 | USS-47-3 | Sitamarhi | ukuiqj | eŒ foŒ] cÙkjk 9931668054 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
156 | USS-47-4 | Sitamarhi | ukuiqj | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
157 | USS-47-5 | Sitamarhi | lksucjlk | eŒ foŒ] bVgjok 9546578977 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
158 | USS-48-1 | Muzaffarpur | vkSjkbZ | eŒ foŒ] cSaxuk 7209905677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
159 | USS-48-2 | Muzaffarpur | ckspgk¡ | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
160 | USS-48-3 | Muzaffarpur | xk; ?kkV | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
161 | USS-48-4 | Muzaffarpur | dVjk | eŒ foŒ] cq/kdkjk 9934016332 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
162 | USS-49-2 | Muzaffarpur | eM+ou | eŒ foŒ] jsiqjk 8252129824 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
163 | USS-49-3 | Muzaffarpur | ehukiqj | eŒ foŒ] tkfeu efB;k 9934619525 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
164 | USS-51-1 | Muzaffarpur | ldjk | eŒ foŒ] ckth cqtqxZ 9572907300 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
165 | USS-51-2 | Muzaffarpur | eq'kgjh | eŒ foŒ] fn?kM+k 9430051489@9304110351 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
166 | USS-51-3 | Muzaffarpur | eksrhiqj | eŒ foŒ] ckjthMhg 9934895236 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
167 | USS-52-1 | Vaishali | lgnsbZ cqtqxZ | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
168 | USS-52-2 | Vaishali | egukj | eŒ foŒ deyk dU;k] djukSrh 8002747546 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
169 | USS-52-3 | Vaishali | tUnkgk | eŒ foŒ] jlqyiqj 8651291731 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
170 | USS-52-4 | Vaishali | fonqiqj | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
171 | USS-53-1 | Vaishali | gkthiqj | eŒ foŒ] yksek 9470638549 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
172 | USS-53-2 | Vaishali | gkthiqj | eŒ foŒ] dqrqciqj 9905099533 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
173 | USS-53-3 | Vaishali | ykyxat | eŒ foŒ] xqjfe;k 8651626851 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
174 | USS-53-4 | Vaishali | xksjkSy | eŒ foŒ] Bhdgk¡ 9431254109 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
175 | USS-54-2 | Vaishali | ikrsiqj | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
176 | USS-54-3 | Vaishali | jk?kksiqj | eŒ foŒ] ohjiqj 9931458401 | [9 empty] | 1 |  | Tirhut East | 2009-10
177 | USS-37-1 | West Champaran | Manjhauliya | M.S.Aharwar Shekh 9470655463 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
178 | USS-37-2 | West Champaran | Manjhauliya | M.S. Parsa Bahuarwa 9470859628 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
179 | USS-37-3 | West Champaran | Bairiya | M.S. Bathna 9431466192 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
180 | USS-37-4 | West Champaran | Nautan | M.S. Mangalpur 9430691686 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
181 | USS-38-1 | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
182 | USS-38-2 | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
183 | USS-38-3 | West Champaran | Lauriya | M.S.Dhobani 9430571439 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
184 | USS-38-4 | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
185 | USS-39-1 | West Champaran | Mainatand | M.S. Tajpur 8986956152 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
186 | USS-39-3 | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
187 | USS-42-1 | East Champaran | Areraj | M.S. Radhiya 9576399366 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
188 | USS-42-2 | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
189 | USS-42-3 | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
190 | USS-42-4 | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
191 | USS-44-1 | East Champaran | Chakiya | M.S. Chintamanpur 9546123872 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
192 | USS-44-3 | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
193 | USS-44-4 | East Champaran | Mehshi | M.S. Jhitkahiya 9162250321 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
194 | USS-44-5 | East Champaran | Paharpur | M.S. Siswa Bazar 8809296371 | [9 empty] | 1 | Inaugurated | Tirhut West | 2009-10
195 | USS-61-1 | Madhubani | ?kks?kjMhgk | eŒ foŒ] xax}kj 9934407620 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
196 | USS-61-2 | Madhubani | >a>kjiqj | eŒ foŒ]ykSguk 9430835195 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
197 | USS-61-3 | Madhubani | ykSdgh | eŒ foŒ] dyqvkgh 9572025500 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
198 | USS-62-1 | Madhubani | t;uxj | eŒ foŒflyukFk cjgh 9572618953 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
199 | USS-62-2 | Madhubani | i.MkSy | eŒ foŒ] 'kkgiqj 9973048002 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
200 | USS-62-3 | Madhubani | jktuxj | eŒ foŒ] eaxjkSuh 9931643145 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
201 | USS-63-1 | Darbhanga | guqeku uxj | eŒfoŒ]Fkyokjk 9771791978 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
202 | USS-63-2 | Darbhanga | cgsM+h | eŒfoŒ fctqfy;k 9939521323 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
203 | USS-63-3 | Darbhanga | cgknqjiqj | mRØŒeŒfoŒ dejkSyh 9801391631 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
204 | USS-64-1 | Darbhanga | ?ku';keiqj | eŒfoŒ]rqekSy 9939754496 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
205 | USS-64-2 | Darbhanga | csuhiqj | mRØŒeŒfoŒ jf<+;ke 9770623526 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
206 | USS-64-3 | Darbhanga | euhxkNh | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
207 | USS-65-1 | Darbhanga | dq'ks'oj LFkku iwŒ | mRØŒeŒfoŒ egknso eB 9973391579 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
208 | USS-65-2 | Darbhanga | dq'ks'oj LFkku iŒ | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
209 | USS-65-3 | Darbhanga | fojkSy | eŒfoŒ]iVfu;k¡ 9771113614 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
210 | USS-66-1 | Darbhanga | fal?kokM+k | mRØŒeŒfoŒ e/kqiqj 9934911481 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
211 | USS-66-2 | Darbhanga | dsoVh | eŒfoŒ]dks;yk LFkku 9905459110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
212 | USS-66-3 | Darbhanga | njHkaxk xzkeh.k | mRØŒeŒfoŒ cygk 9570479967 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
213 | USS-67-2 | Samastipur | nyflag ljk; | eŒfoŒ]ekyiqj 9934140121 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
214 | USS-67-3 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]fcUn ckspgk 9939988449 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
215 | USS-67-4 | Samastipur | fo¦kifr uxj | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
216 | USS-67-5 | Samastipur | eksfgmÌhu uxj | eŒfoŒ]efu;kj 7549600801 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
217 | USS-68-1 | Samastipur | foHkwfriqj | eŒfoŒ]nsljh 9939816100 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
218 | USS-68-2 | Samastipur | fcFkku | eŒfoŒ]NsNuh 9934979521 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
219 | USS-68-3 | Samastipur | gluiqj | mRØŒeŒfoŒ egqyh 9801690551 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
220 | USS-68-4 | Samastipur | f'kokth uxj | eŒfoŒ]Jhiqjetjfg;k 9955507715 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
221 | USS-68-5 | Samastipur | foHkwfriqj | eŒfoŒ]irSfy;k 9973163333 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
222 | USS-68-6 | Samastipur | f'kokth uxj | eŒfoŒ]jkuhiêh 9955989162 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
223 | USS-69-1 | Samastipur | dY;k.kiqj | eŒfoŒ]eksjokjk 9162249115 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
224 | USS-69-2 | Samastipur | leLrhiqj | eŒfoŒ][kksM+h 9263781760 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
225 | USS-69-3 | Samastipur | mft;kiqj | eŒfoŒ]vaxkj ?kkV 9204971619 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
226 | USS-69-4 | Samastipur | mft;kiqj | eŒfoŒdksjc)k] irSyh 9263731315 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
227 | USS-70-1 | Samastipur | eksjok | eŒfoŒ iq:"kksreiqj 9973123260 | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
228 | USS-70-2 | Samastipur | iwlk | eŒfoŒ]efYydkSj | [9 empty] | 1 | Inaugurated | Darbhanga | 2009-10
229 | USS-55-1 | Gopalganj | Baikunthapur | M. School, Deokulli, Mob.: 9708861129 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
230 | USS-55-2 | Gopalganj | Baikunthapur | M. School, Maharani, Mob.:9199443900 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
231 | USS-55-3 | Gopalganj | Kuchayakot | M. School, Mahuaba, Hindi, Mob.: 9430055420/9162622220 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
232 | USS-55-4 | Gopalganj | Singhawalia | U. M. School, Dumaria East, Mob.: 9955648224 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
233 | USS-56-1 | Gopalganj | Bhore | M. School, Shivarajpur, Mob.: 9973200939 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
234 | USS-56-2 | Gopalganj | Kattaya | M. School, Rudrapur, Mob.: 9628550100 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
235 | USS-56-3 | Gopalganj | Kuchayakot | M. School, Purkhaus, Mob.: 9955647418 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
236 | USS-56-4 | Gopalganj | Vijayipur | M. School, Mathaulli, Mob.: 9838674751 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
237 | USS-57-1 | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
238 | USS-57-2 | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
239 | USS-57-3 | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
240 | USS-57-4 | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
241 | USS-58-1 | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
242 | USS-58-2 | Siwan | Guddhani | U. M. School, Bangardha, Mob.: 9801180809 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
243 | USS-58-3 | Siwan | Daraulli | M. School, Dumarhar Bujurga, Mob.: 9199854822 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
244 | USS-58-4 | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
245 | USS-58-5 | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
246 | USS-60-1 | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
247 | USS-60-2 | Saran | Manjhi | M. School, Dumari, Mob.: 8083701946/8757054210 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
248 | USS-60-3 | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
249 | USS-60-4 | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | [9 empty] | 1 | Inaugurated | Saran | 2009-10
250 | USS-60-5 | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | [9 empty] | 1 | Inaugurated | Saran | 2009-10

## Sheet4
BSEIDC , Patna
Physical Status of USS (Central Fund) - 2010-11
S.N. | Group No. | Name of District | Name of Block | Name of School | Physical Status | [9 empty] | Remarks | Division | Session
[5 empty] | Not Start | Layout | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[9 empty] | LL | RL | LL | RL
1 | USS-101-1 | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
2 | USS-101-2 | Nalanda | Ben | M.S. Akouna 9570951336 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
3 | USS-101-3 | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
4 | USS-101-5 | Nalanda | Ben | M.S. Ramganj 9135849205 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
5 | USS-102-1 | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
6 | USS-102-5 | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2010-11
7 | USS-102-6 | Nalanda | Sarmera | M.S.Singhaul 9934212058 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2010-11
8 | USS-103-1 | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
9 | USS-103-3 | Nalanda | Islampur | M.S. Bargounw 9279149331 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
10 | USS-103-4 | Nalanda | Islampur | M.S. Banbag 9934487509 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
11 | USS-104-3 | Patna | Barh | U.M.S. Malahi 7250940590 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
12 | USS-104-4 | Patna | Fatuha | M.S. Gabaspur 9955241716 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
13 | USS-105-1 | Patna | Patna Sadar | M.S. Khokhna 9135334773 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
14 | USS-105-2 | Patna | Patna Sadar | M.S. Marchi 9430934711 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
15 | USS-105-3 | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
16 | USS-105-4 | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
17 | USS-107-1 | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
18 | USS-108-2 | Bhojpur | Agioan | M.S. Berath 09955434210 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
19 | USS-108-3 | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
20 | USS-108-4 | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
21 | USS-108-5 | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 | [9 empty] | 1 |  | Patna East | 2010-11
22 | USS-109-1 | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
23 | USS-109-3 | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
24 | USS-109-4 | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
25 | USS-109-5 | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
26 | USS-110-1 | Bhojpur | Barhara | U.M.S. Shaligram Singh Ka Tola 8409626973 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2010-11
27 | USS-110-3 | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2010-11
28 | USS-110-5 | Bhojpur | Koilwar | M.S. Khangaown 9631265664 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2010-11
29 | USS-111-1 | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
30 | USS-111-2 | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
31 | USS-111-3 | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
32 | USS-111-4 | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
33 | USS-112-1 | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 | [9 empty] | 1 |  | Patna East | 2010-11
34 | USS-113-3 | Bhojpur | Tarari | M.S. Tarari 9631136009 | [9 empty] | 1 | Inaugurated 2016 | Patna East | 2010-11
35 | USS-113-4 | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
36 | USS-114-2 | Bhojpur | Sahar | M.S. Baruhi 9199571702 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
37 | USS-114-3 | Bhojpur | Ara | M.S. Basantpur 09308735308 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
38 | USS-114-4 | Bhojpur | Sahar | M.S. Nawada 9934483628 | [9 empty] | 1 | Inaugurated | Patna East | 2010-11
39 | USS-116 (B) | Buxar | Dumraon | M.S. Kanjharua 9955867071 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
40 | USS-116 (D) | Buxar | Dumraon | M.S. Karuaj 9931281346 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
41 | USS-116 (E) | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
42 | USS-117 (B) | Buxar | Ithari | M.S. Barkagaon 8651239720 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
43 | USS-117 (D) | Buxar | Ithari | M.S. Basawan Kala 7739120173 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
44 | USS-119 (A) | Kaimur | Bhabhua | M.S.Miun | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
45 | USS-119 (B) | Kaimur | Bhabhua | M.S.Piliyan | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
46 | USS-119 (D) | Kaimur | Bhabhua | M.S. Mohan Darwan | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
47 | USS-120 (A) | Kaimur | Ramgarh | M.S.Sijhua | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
48 | USS-120 (B) | Kaimur | Ramgarh | M.S.Upari 9939613033 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
49 | USS-121 (B) | Rohtas | Karakat | Girl's M.S.Motha 9162106111 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
50 | USS-121 (C) | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
51 | USS-121 (D) | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
52 | USS-121 (E) | Rohtas | Akorhigola | M.S.Chhapra 9934757484 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
53 | USS-122-1 | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
54 | USS-122-2 | Rohtas | Dinara | M.S.Sarwan ,8084920823 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
55 | USS-122-3 | Rohtas | Dinara | M.S. Baliyan, 9931111475 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
56 | USS-122-4 | Rohtas | Dinara | M.S. Bararhi, 9955083783 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
57 | USS-122-6 | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
58 | USS-123-1 | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
59 | USS-123-2 | Rohtas | Kochas | M.S. Ubadhi, 8002578689 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
60 | USS-123-3 | Rohtas | Kochas | M.S. Kuchila, 8002537247 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
61 | USS-123-4 | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
62 | USS-123-5 | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
63 | USS-123-6 | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
64 | USS-124-1 | Rohtas | Chenari | M.S. Ramgarh 9771746971 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
65 | USS-124-2 | Rohtas | Chenari | M.S. Chandrakaithi, 9934281842 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
66 | USS-124-3 | Rohtas | Sheosagar | M.S. Alampur, 9572407040 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
67 | USS-124-4 | Rohtas | Sheosagar | M.S. Sonhar 9006103550 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
68 | USS-124-5 | Rohtas | Sasaram | M.S. Akasi , 9204460486 | [9 empty] | 1 | Inaugurated 2016 | Patna West | 2010-11
69 | USS-125-1 | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | [9 empty] | 1 | Inaugurated | Patna West | 2010-11
70 | USS-143-1 | Jehanabad | Kako | M.S.Kajisarai 9934814478 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
71 | USS-143-2 | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
72 | USS-143-4 | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
73 | USS-146 (B) | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
74 | USS-146 (C) | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
75 | USS-146 (D) | Nawada | Pakribarawan | M.S. Ukaorah | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
76 | USS-147-1 | Nawada | Narhat | M.S. Khanwa, 9905846666 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
77 | USS-147-2 | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
78 | USS-149 (B) | Gaya | Imamganj | M.S. Karsan Kala, 9199768865, 9199061230 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
79 | USS-149 (C) | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
80 | USS-149 (E) | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
81 | USS-150 (A) | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
82 | USS-151-1 | Gaya | Bathani | Basic M.S. Radui, 7654409634 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
83 | USS-151-2 | Gaya | Bathani | M.S. Karubigha, 9934427661 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
84 | USS-151-3 | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
85 | USS-152-1 | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
86 | USS-152-2 | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
87 | USS-152-5 | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
88 | USS-152-6 | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
89 | USS-153 (A) | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
90 | USS-154-1 | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
91 | USS-154-2 | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
92 | USS-154-4 | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
93 | USS-154-5 | Aurangabad | Deo | M.S. Vijouli, 9801123435 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
94 | USS-155-1 | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
95 | USS-155-2 | Aurangabad | Obra | M.S. Ratwar, 9931418907 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
96 | USS-155-4 | Aurangabad | Obra | M.S. Karsawan, 9470488343 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
97 | USS-156-3 | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | [9 empty] | 1 | Inaugurated | Magadh | 2010-11
98 | USS-157 (A) | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
99 | USS-157 (C) | Aurangabad | Madanpur | M.S. Judahi, 9931892284 | [9 empty] | 1 | Inaugurated 2016 | Magadh | 2010-11
100 | USS-132-1 | Sheikhpura | Barbigha | M.S.Keuti | [9 empty] | 1 | Inaugurated | Munger | 2010-11
101 | USS-132-2 | Sheikhpura | SheKhpura | M.S.Lodipur | [9 empty] | 1 | Inaugurated | Munger | 2010-11
102 | USS-132-3 | Sheikhpura | Chewara | M.S.Lahana | [9 empty] | 1 | Inaugurated | Munger | 2010-11
103 | USS-132-4 | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | [9 empty] | 1 | Inaugurated | Munger | 2010-11
104 | USS-132-5 | Sheikhpura | Ariari | M.S.Husainawad | [9 empty] | 1 | Inaugurated | Munger | 2010-11
105 | USS-133(A) | Lakhisarai | Barahiya | M.S.Pali 9546977875 | [9 empty] | 1 | Inaugurated 2016 | Munger | 2010-11
106 | USS-133(D) | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 | [9 empty] | 1 | Inaugurated 2016 | Munger | 2010-11
107 | USS-133(F) | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | [9 empty] | 1 | Inaugurated 2016 | Munger | 2010-11
108 | USS-135-1 | Munger | Asarganj | M.S.Chakhand 9135065232 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
109 | USS-135-2 | Munger | Asarganj | M.S. Beran 9204931976 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
110 | USS-136-1 | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
111 | USS-136-3 | Munger | Sangrampur | M.S.Katiyari 9199782900 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
112 | USS-137-1 | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
113 | USS-137-2 | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
114 | USS-137-3 | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
115 | USS-137-4 | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
116 | USS-137-5 | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
117 | USS-139-2 | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
118 | USS-139-3 | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
119 | USS-139-4 | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
120 | USS-139-5 | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
121 | USS-140-1 | Begusarai | Garhpura | M.S.Kuddhar 9955509070 | [9 empty] | 1 |  | Munger | 2010-11
122 | USS-140-2 | Begusarai | Dandari | M.S.Katarmala 9709640304 | [9 empty] | 1 |  | Munger | 2010-11
123 | USS-140-3 | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
124 | USS-141 (D) | Khagaria | Khagaria | M.S.Mathar 9771388437 | [9 empty] | 1 | Inaugurated 2016 | Munger | 2010-11
125 | USS-142-2 | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
126 | USS-142-3 | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | [9 empty] | 1 | Inaugurated | Munger | 2010-11
127 | USS-127 (C) | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
128 | USS-127 (E) | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | [9 empty] | 1 | Inaugurated 2016 | Bhagalpur | 2010-11
129 | USS-128 (B) | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | [9 empty] | 1 | Inaugurated 2016 | Bhagalpur | 2010-11
130 | USS-128 (C) | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | [9 empty] | 1 | Inaugurated 2016 | Bhagalpur | 2010-11
131 | USS-129 (B) | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | [9 empty] | 1 | Inaugurated 2016 | Bhagalpur | 2010-11
132 | USS-130-1 | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
133 | USS-130-2 | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
134 | USS-130-3 | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
135 | USS-130-4 | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
136 | USS-130-5 | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | [9 empty] | 1 | Inaugurated | Bhagalpur | 2010-11
137 | USS-199C | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | [9 empty] | 1 | Inaugurated 2016 | Kosi | 2010-11
138 | USS-199D-1 | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | [9 empty] | 1 | Inaugurated 2016 | Kosi | 2010-11
139 | USS-199 D-2 | Madhepura | Singheshwar | Middle School Barhari 9661376885 | [9 empty] | 1 | Inaugurated | Kosi | 2010-11
140 | USS-194-1 | Purnea | Amaur | U. M. S. Bagdar 9939096309 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
141 | USS-194-2 | Purnea | K. Nagar | M S Gauasi 9473124829 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
142 | USS-194-3 | Purnea | Purnia East | M S Maranga 9939732346 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
143 | USS-194-4 | Purnea | Rupauli | M. S. Bairiya 9434821065 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
144 | USS-196(B) | Katihar | Ajamnagar | Middle School Arihana 8809322797 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
145 | USS-197(D) | Katihar | Kadwa | Dukhi Ram Middle School Chandpur9709755452 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
146 | USS-199A (A) | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
147 | USS-199A (B) | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
148 | USS-199A (C) | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
149 | USS-199A (D) | Araria | Narpatganj | Middle School Achra 9801296055 | [9 empty] | 1 | Inaugurated 2016 | Purnea | 2010-11
150 | USS-199 B-1 | Araria | Jokihat | Middle School Jhanpur 9471219710 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
151 | USS-199 B-2 | Araria | Raniganj | Middle School Kosikapur 9199673607 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
152 | USS-199 B-3 | Araria | Araria | Middle School Araria Basti 9661185784 | [9 empty] | 1 | Inaugurated | Purnea | 2010-11
153 | USS-162 (A) | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | [9 empty] | 1 | handover | Tirhut East | 2010-11
154 | USS-162 (B) | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
155 | USS-162 (C) | Sitamarhi | Suppi | M. S. Aktha 9470821881 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
156 | USS-162 (E) | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
157 | USS-162 (F) | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
158 | USS-163 (A) | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
159 | USS-163 (B) | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
160 | USS-163 (C) | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
161 | USS-163 (D) | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
162 | USS-164-1 | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
163 | USS-164-2 | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
164 | USS-164-3 | Vaishali | Bhagwanpur | M. S. Askaranpur | [9 empty] | 1 |  | Tirhut East | 2010-11
165 | USS-166 (B) | Vaishali | Raghopur | M.S,Paharpur 7654539556 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
166 | USS-166 (C) | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 | [9 empty] | 1 |  | Tirhut East | 2010-11
167 | USS-167-1 | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
168 | USS-167-2 | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
169 | USS-167-3 | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
170 | USS-167-4 | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
171 | USS-167-5 | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
172 | USS-168-1 | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
173 | USS-168-2 | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
174 | USS-168-3 | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
175 | USS-168-4 | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
176 | USS-169-1 | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
177 | USS-169-2 | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
178 | USS-169-3 | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
179 | USS-169-4 | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
180 | USS-169-5 | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
181 | USS-170-1 | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
182 | USS-170-2 | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
183 | USS-170-3 | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
184 | USS-170-4 | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
185 | USS-170-5 | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
186 | USS-171-1 | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
187 | USS-171-2 | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
188 | USS-171-3 | Muzaffarpur | Gaighat | M. S,Dahila 9973658759 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
189 | USS-171-4 | Muzaffarpur | Katra | M. S, Bakhari 9631173639 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
190 | USS-171-5 | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | [9 empty] | 1 | Inaugurated 2016 | Tirhut East | 2010-11
191 | USS-172-1 | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
192 | USS-172-2 | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
193 | USS-172-3 | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
194 | USS-172-4 | Muzaffarpur | Mushhari | M. S, Dronpur | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
195 | USS-172-5 | Muzaffarpur | Muraul | M. S, Pilkhi | [9 empty] | 1 | Inaugurated | Tirhut East | 2010-11
196 | USS-159-4 | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
197 | USS-160-3 | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | [9 empty] | 1 | Inaugurated | Tirhut West | 2010-11
198 | USS-191-3 | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
199 | USS-191-4 | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
200 | USS-191-5 | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
201 | USS-192 C | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 | [9 empty] | 1 | Inaugurated 2016 | Darbhanga | 2010-11
202 | USS-192 D | Darbhanga | Biraul | U. M. S, Balha 7631905606 | [9 empty] | 1 | Inaugurated 2016 | Darbhanga | 2010-11
203 | USS-193-1 | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
204 | USS-193-2 | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
205 | USS-193-4 | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | [9 empty] | 1 | Inaugurated | Darbhanga | 2010-11
206 | USS-173 (B) | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
207 | USS-174-1 | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
208 | USS-174-2 | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 | [9 empty] | 1 |  | Saran | 2010-11
209 | USS-174-3 | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
210 | USS-174-4 | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
211 | USS-175-1 | Siwan | Siswan | M. S, Gyaspur 8809341191 | [9 empty] | 1 | Hand Over | Saran | 2010-11
212 | USS-175-2 | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
213 | USS-175-3 | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
214 | USS-175-4 | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
215 | USS-176-1 | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
216 | USS-176-2 | Siwan | Gudhani | M. S, Belauri 8809165382 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
217 | USS-176-3 | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
218 | USS-177-1 | Saran | Dariyapur | Middle School, Saraiya 9431647901 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
219 | USS-177-2 | Saran | Dariyapur | Middle School, Bhongha 9006298659 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
220 | USS-177-3 | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
221 | USS-178-1 | Saran | Sonpur | Middle School, Shikharpur 9631221348 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
222 | USS-179-1 | Saran | Lahaladpur | Middle School, Basahi Urdu | [9 empty] | 1 | Inaugurated | Saran | 2010-11
223 | USS-179-2 | Saran | Ekma | Middle School, Bhodasa | [9 empty] | 1 | Inaugurated | Saran | 2010-11
224 | USS-179-3 | Saran | Ekma | Middle School, Betbaniya 8294839353 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
225 | USS-179-4 | Saran | Ekma | Middle School, Eksar 9572740280 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
226 | USS-179-5 | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
227 | USS-181-1 | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
228 | USS-182-1 | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
229 | USS-182-2 | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
230 | USS-182-3 | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
231 | USS-183-1 | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
232 | USS-183-2 | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
233 | USS-183-4 | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
234 | USS-184-1 | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
235 | USS-184-2 | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
236 | USS-184-3 | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
237 | USS-185-1 | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
238 | USS-185-3 | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
239 | USS-186-1 | Gopalganj | Hathua | U. M. S, Satai 8757888461 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
240 | USS-186-2 | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | [9 empty] | 1 | Inaugurated | Saran | 2010-11
241 | USS-186-4 | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 | [9 empty] | 1 |  | Saran | 2010-11
Note on B23: ACCORD. TO 475 USS-108-1
Note on B239: List from 161 & 250 ing list