## CT
Bihar State Educational Infrastruture Development Corporation, Patna
Name of Division :-
Name & contact no. of EE :-
Progress Report for the construction of College Toilets As on 31.05.2016
S.N. | Group No. | Name of District | S.N. | Name Of College | Name Of Agency | TIME OF COMPLETION | A/A | Eistmated Amount(in lac) | T/S | L.O.A &Issued Date | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Aggrement | Agreement Amount | Fin. Exp. (in lac) | Financial Achievement (%) | Land Dipute | Physical Status | [7 empty] | Remarks
[19 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | Finishing | Complete
[23 empty] | LL | RL
1 | CT-1 | Muzafferpur | 1 | L.S COLLEGE MUZAFFARPUR | M/S CHANDAN CONSTRUCTION | 6 MONTHS FOR ALL |  | 400000.00 For Each College Toilet |  | 39.16 |  | 2012-05-05 | 2012-05-30 | 2012-06-06 | [11 empty] | 1
|  |  | 2 | mddm college muzaffarpur | [21 empty] | 1
|  |  | 3 | RDS college muzaffarpur | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 4 | Rameshwar college muzaffarpur | [21 empty] | 1
|  |  | 5 | MSKB college muzaffarpur | [21 empty] | 1
|  |  | 6 | MP Sinha Since college muzaffarpur | [21 empty] | 1
|  |  | 7 | Dr. RLMS college muzaffarpur | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 8 | LNT college muzaffarpur | [21 empty] | 1
|  |  | 9 | Nitishwar college muzaffarpur | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 10 | RBBM college muzaffarpur | [13 empty] | 1 | 1 | [7 empty] | Land not available
2 | CT-2 | Muzaffarpur | 1 | SRPS College Jaintpur | Braj Bihari Singh |  |  | 1424125 | 15.67 | 2013-01-11 | 2012-09-30 |  |  | 83 F2 of 2012-13 11.01.2013 | 1415512.92 | [10 empty] | 1
|  |  | 2 | Jiwachh college Motipur | [21 empty] | 1 | Handover
|  |  | 3 | jbsd college Bakuchi | [21 empty] | 1 | Handover
|  |  | 4 | cn college Sahebganj | [21 empty] | 1 | Handover
3 | CT-3 | Vaishali | 1 | RN college Hajipur | Anup kumar Singh |  |  | 3137113 | 34.51 | ISSUED 14.06.2012 | 05.05.2012 | 30.05.2012 | 06.06.2012 | 70 F2 of 2012-13 22.11.2012 | 3117735.45 | [10 empty] | 1 | Handover
|  |  | 2 | jamuni lal college hajipur | [21 empty] | 1 | Handover
|  |  | 3 | DC College, Hajipur | [21 empty] | 1 | Handover
|  |  | 4 | LN College, Bhagwanpur | [21 empty] | 1 | Handover
|  |  | 5 | BMD College, Dayalpur | [21 empty] | 1 | Handover
|  |  | 6 | RPS College, Chakiyaj | [21 empty] | 1 | Handover
|  |  | 7 | Vaishali Mahila College | [21 empty] | 1 | Handover
|  |  | 8 | YN College,Dighwara | [21 empty] | 1 | Handover
|  |  | 9 | Samta College Jandaha, Vaishali | [21 empty] | 1 | Handover
4 | CT-4 | chapra | 1 | Ganga Singh College ,Chapra | M/S Shiv Shakti construction |  |  | 3052726 | 33.58 |  |  |  |  | 64 F2 of 2012-13 08.11.2012 | 3033348.57 | [10 empty] | 1 | Handover
|  |  | 2 | J.P Mahila College, Chapra | [21 empty] | 1 | Handover
|  |  | 3 | Jagdam College ,Chapra | [21 empty] | 1 | Handover
|  |  | 4 | P.C vigyan college, Chapra | [13 empty] | 1 | 1 | [7 empty] | Land not available (Dropped)
|  |  | 5 | Rajendra College, chapra | [21 empty] | 1 | Handover
|  |  | 6 | Ram Jaipal College,chapra | [21 empty] | 1 | Handover
|  |  | 7 | H.R. College, Amnaur | [21 empty] | 1 | Handover
|  |  | 8 | R.B.G.R.College,Maharajganj | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 9 | Jaglal Chaudhary college,chapra | [21 empty] | 1 | Handover
5 | CT-5 | siwan | 1 | BPS College, Bhore |  |  |  | 4748685 | 52.24 |  |  |  |  | 61 F2 of 2012-13 18.10.2012 | 4718542.22 | [10 empty] | 1 | Handover
|  |  | 2 | DAV Collage, siwan | [21 empty] | 1 | Handover
|  |  | 3 | Gopalgang college,Gopalganj | [21 empty] | 1 | Handover
|  |  | 4 | Gopeshwar College , Hathwa | [21 empty] | 1 | Handover
|  |  | 5 | H.R. College, Mairwa | [21 empty] | 1 | Handover
|  |  | 6 | Mahendra Mahila College,Gopalganj | [21 empty] | 1 | Handover
|  |  | 7 | NlsCollege,Jaitpur,Daudpur | [21 empty] | 1 | Handover
|  |  | 8 | P.N. College,Parsa | Ashiana Contract Pvt. Ltd | [20 empty] | 1 | Handover
|  |  | 9 | Raja singh college siwan | [21 empty] | 1 | Handover
|  |  | 10 | Vidya Bhawan Mahila college, Siwan | [21 empty] | 1
|  |  | 11 | Bharat Mishra Sans, college, chapra | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 12 | Baijnath Pandey Arya Sans college Siwan | [21 empty] | 1 | Handover
|  |  | 13 | Sri Ram College Vijayapur, Gopalgang | [21 empty] | 1 | Handover
|  |  | 14 | Narayan college, Goriyakothi | [21 empty] | 1 | Handover
6 | CT-6 | Ara | 1 | H.D.Jain College Ara |  |  |  | 3462153 | 38.08 |  |  |  |  | 65 F2 of 2012-13 08.11.2012 | 3440621.7 | [10 empty] | 1 | Handover
|  |  | 2 | Maharaja college,Ara | [21 empty] | 1 | Handover
|  |  | 3 | J.J College ,Ara | [21 empty] | 1 | Handover
|  |  | 4 | M.M.Mahila college, Ara | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 5 | S.B.College,Ara | M/S Shiv Shakti construction | [20 empty] | 1 | Handover
|  |  | 6 | D.K.College, Dumraon | [21 empty] | 1 | Handover
|  |  | 7 | M.V.College, Buxar | [21 empty] | 1 | Handover
|  |  | 8 | Sidheswari sans.College,Pachrukhiya,Bhojpur | [21 empty] | 1 | Handover
|  |  | 9 | Shiv Prasad Sans.DegreeCollege,Rampur,Buxer | [21 empty] | 1 | Handover
|  |  | 10 | Ramadhin Mishra Bhaskroday Sanskrit College, Deorahia, Buxer | [21 empty] | 1 | Handover
7 | CT- 7 | Sasaram | 1 | S.P. Jain College,Sasaram |  |  |  | 3379262 | 37.17 |  |  |  |  | 59 F2 of 2012-13 18.10.2012 | 3357730.4 | [10 empty] | 1 | Handover
|  |  | 2 | A.S.College,Bikramganj | [21 empty] | 1 | Handover
|  |  | 3 | J.L.N. College,Dehari-on-sone,Rohtas | [21 empty] | 1 | Handover
|  |  | 4 | S.N.College,shahmal khaira_Deo,Rohtas | [21 empty] | 1 | Handover
|  |  | 5 | Sri Shankar college, sasaram | Amrendar Kumar Singh | [20 empty] | 1 | Handover
|  |  | 6 | Rohtas Mahila college, sasaram | [21 empty] | 1 | Handover
|  |  | 7 | Mahila college,Dalmianagar | [21 empty] | 1 | Handover
|  |  | 8 | sher shah college, sasaram | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 9 | s.v.p. College, Bhabhua | [21 empty] | 1 | Handover
|  |  | 10 | G.B. College,RamGarh,Kaimur | [21 empty] | 1 | Handover
8 | CT-8 | patna | 1 | Science college,patna |  |  |  | 4676403 | 51.44 | ISSUED 27.02.2013 |  |  |  | 102 F2 of 2012-13 27.02.2013 | 4648412.08 | [10 empty] | 1 | Handover
|  |  | 2 | Patna college,patna | [21 empty] | 1 | Handover
|  |  | 3 | B.N.college, Patna | [21 empty] | 1 | Handover
|  |  | 4 | MagadhMahila College,Patna | [21 empty] | 1 | Handover
|  |  | 5 | Patna Women'sTraningCollege,Patna | [21 empty] | 1 | Handover
|  |  | 6 | Patna Training college,patna | M/s Pramod Construction | [20 empty] | 1 | Handover
|  |  | 7 | Patna Law College,Patna | [21 empty] | 1 | Handover
|  |  | 8 | College Of Arts&Crafts,patna | [21 empty] | 1 | Handover
|  |  | 9 | Vanijya Mahavidyalaya,patna | [21 empty] | 1 | Handover
|  |  | 10 | College of Commerce,patna | [13 empty] | 1 | 1 | [7 empty] | Landless
|  |  | 11 | Govt.Sanskrit College,Kajipur,patna | [21 empty] | 1 | Handover
|  |  | 12 | Sir Arvind Mahila College, Patna | [21 empty] | 1 | Handover
|  |  | 13 | T.P.S. College,Patna | [21 empty] | 1 | Handover
9 | CT- 9 | Patna | 1 | B.S.College,Danapur,patna |  |  |  | 2158340 | 23.74 | ISSUED 21.02.2013 | 30.07.2012 | 21.08.2012 | 27.08.2012 | 102 F2 of 2012-13 21.02.2013 | 2145420.96 | [10 empty] | 1 | Handover
|  |  | 2 | J.D.Women's college,patna | [13 empty] | 1 | 1 | [7 empty] | No Need
|  |  | 3 | J.N.L.college,Khagual | Om Prakash | [12 empty] | 1 | 1 | [7 empty] | Landless
|  |  | 4 | R.K.D.College,Patna | [14 empty] | 1 | [7 empty] | Intenal Dispute
|  |  | 5 | Ganga Devi Mahila College,Patna | [14 empty] | 1 | [7 empty] | not started by contractor
|  |  | 6 | AG.College,Rambagh,Bihta | [21 empty] | 1 | Handover
10 | CT- 10 | East Champran | 1 | M.S college,Motihari |  |  |  | 4063384 | 44.7 | ISSUED 14.06.2012 | 05.05.2012 | 30.05.2012 | 06.06.2012 | 60 F2 of 2012-13 18.10.2012 | 4039700.17 | [10 empty] | 1 | Handover
|  |  | 2 | L.N.D.College,Mothari | [21 empty] | 1 | Handover
|  |  | 3 | S.N.S. College,Mothari | [21 empty] | 1 | Handover
|  |  | 4 | SRAP College,Barachaika | [21 empty] | 1 | Handover
|  |  | 5 | JlLNM College,Ghorasahan | Braj Bihari Singh | [20 empty] | 1 | Handover
|  |  | 6 | MJK College,Bettiah | [21 empty] | 1 | Handover
|  |  | 7 | KCTC College | [21 empty] | 1 | Handover
|  |  | 8 | RLSY College,Bettiah | [21 empty] | 1 | Handover
|  |  | 9 | TP Varma College | [13 empty] | 1 | 1 | [7 empty] | Land not available
|  |  | 10 | Dr.S.K.Sinha College | [21 empty] | 1 | Handover
|  |  | 11 | Mssg College,Areraj | [21 empty] | 1 | Handover
11 | CT-11 | Gaya+ Aurangabad | 1 | A.M. College,Gaya |  |  |  | 4789000 | 36.68 | ISSUED 7.2.2014 | 06.12.2013 | 03.01.2014 | 2014-01-16 | 156 F2 of 2014-15 03.07.2014 | [11 empty] | 1 | Handover
|  |  | 2 | G.B.M College,Gaya | [13 empty] | 1 | 1 | [7 empty] | Project to be drop since college is running in private building according to principle
|  |  | 3 | Jagivan College,Gaya | [21 empty] | 1 | Handover
|  |  | 4 | S.M.S.G,College,Sherghati (Gaya) | [15 empty] | 1
|  |  | 5 | S.N.S College,Tekari,Gaya | [21 empty] | 1 | Handover
|  |  | 6 | Gaya College,Gaya | Sanjeev Kumar | [20 empty] | 1 | Handover
|  |  | 7 | R.L.S.Y,College,Aurangabad | [21 empty] | 1 | Handover
|  |  | 8 | K.s.m. College,Aurangabad | [21 empty] | 1 | Handover
|  |  | 9 | A.N.S.College,Nabinagar,Aurangabad | [17 empty] | 1 |  |  |  |  | Works Stop due to local problem
|  |  | 10 | S. N. Sinha College,Aurangabad | [13 empty] | 1 | 1 | [7 empty] | Not Start due to tree
12 | CT-12 | Patna | 1 | R.P.M.College,Patna city |  |  |  | 2874857 | 31.62 | ISSUED 7.2.2014 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 69 F2 of 2012-13 12.11.2012 | 2857631.76 |  |  | 1 | 1 | [7 empty] | Land not available
|  |  | 2 | A.N.S.College,Barh | [21 empty] | 1 | Handover
|  |  | 3 | R.R.S.College,Mokama,patna | [21 empty] | 1 | Handover
|  |  | 4 | R.L.S.Ycollege,Bakhtayarpur | [21 empty] | 1 | Handover
|  |  | 5 | S.G.G.S.College, Patna,City | Nawal Kishore Shingh | [20 empty] | 1 | Handover
|  |  | 6 | Mahanth keshav sans. College fatuha , patna | [21 empty] | 1 | Handover
|  |  | 7 | Nimbark krishna Madhwanand sans. College' Dhanamath, patna | [20 empty] | 1
|  |  | 8 | Raghwendra sans. College , Taretpali, patna | [20 empty] | 1
13 | CT-13 | Biharsarif+ Nalanda+ Nawada | 1 | K.L.S College, Nawada |  |  |  | 2744922 | 30.19 | ISSUED18.07.2013 | 25.04.2013 |  | 28.06.2013 | 133 F2 of 2013-14 10.10.2013 | 2878634.56 | [10 empty] | 1 | Handover
|  |  | 2 | Kisan college sohsarai, Nalanda | [21 empty] | 1 | Handover
|  |  | 3 | Nalanda Mahila College , Biharsarif | [21 empty] | 1 | Handover
|  |  | 4 | R.M.W. College , Nawada | Raja Ram Prasad Sharma | [20 empty] | 1 | Handover
|  |  | 5 | S.N Sinha college, Warisaliganj | [21 empty] | 1 | Handover
|  |  | 6 | S.P.M. College, Udantpuri, Biharsharif | [21 empty] | 1 | Handover
|  |  | 7 | S.U. College, Hilsa | [21 empty] | 1 | Handover
|  |  | 8 | T.S. College Hisua | [21 empty] | 1 | Handover
14 | CT-14 | Arwal+ Jehanabad | 1 | S.D.College, kelar (Arwal) |  |  |  | 2717548 | 29.89 | ISSUED 08.10.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 104 F2 of 2012-13 26.02.2013 | 2700323.04 | [10 empty] | 1 | Handover
|  |  | 2 | S.N Sinha college Jehanabad | [21 empty] | 1 | Handover
|  |  | 3 | S.S college Jehanabad | [21 empty] | 1 | Handover
|  |  | 4 | S.B.A.N. College, Derheta Lari Arwal | Er. Ashok kumar singh | [20 empty] | 1
|  |  | 5 | S.M.D.College Punpun, Patna | [21 empty] | 1 | Handover
|  |  | 6 | M.D. College Naubatpur | [21 empty] | 1 | Handover
|  |  | 7 | M.M.College, Bikram | [21 empty] | 1
|  |  | 8 | Daudnagar College , Daudnagar | [21 empty] | 1 | Handover
15 | CT-15 | Darbhanga | 1 | C.M.Science college, Darbhanga | M/S SRI JAN ENGICON PVT LTD |  |  |  | 25.54 | 28.09 | ISSUED 08.10.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | [11 empty] | 1
|  |  | 2 | Marwari college Darbhanga | [21 empty] | 1
|  |  | 3 | Millat college Laheriasarai | [21 empty] | 1
|  |  | 4 | M.R.M college Darbhanga | [21 empty] | 1
|  |  | 5 | k.s college Laheriasarai,Darbhanga | [21 empty] | 1
|  |  | 6 | m.k.College laheriasarai | [21 empty] | 1
|  |  | 7 | M.A.R. L.Sans. College, Darbhanga | [21 empty] | 1
16 | CT-16 | Darbhanga | 1 | J.K.College Biroul | M/S SRI JAN ENGICON PVT LTD |  |  |  |  | 40.58 |  |  |  | 2014-07-10 | [11 empty] | 1
|  |  | 2 | J.N College, Nehra | [21 empty] | 1
|  |  | 3 | M.K.S College, Trimuhan, Chandauna | [21 empty] | 1
|  |  | 4 | jagdamba Sans. College, Batho, Darbhanga | [21 empty] | 1
|  |  | 5 | Umesh Sans. College, Tarauni Darbhanga | [21 empty] | 1
|  |  | 6 | M.L.S..M..College Darbhanga | [21 empty] | 1
|  |  | 7 | Baba saheb Ram Sans. College, Pacharhi, Darbhanga | [21 empty] | 1
|  |  | 8 | Purnima Ram Pratap Sans. College, Pacharhi, Darbhanga | [21 empty] | 1
|  |  | 9 | Ramawatar Gautamm Sans. College, Ahilyasthan, Darbhanga | [21 empty] | 1
|  |  | 10 | Laxmi Narayan Rameshwar Sans College, jaideo patti, Darbhanga | [21 empty] | 1
17 | CT-17 | Madhubani | 1 | H.P.S. College, Madhepur |  |  |  | 4860662 | 53.47 | ISSUED 08.10.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 44 F2 of 2013-14 04.07.2013 | 4832671.61 | [10 empty] | 1 | Handover
|  |  | 2 | V.SJ.College Raj Nagar | [21 empty] | 1 | Handover
|  |  | 3 | B.M College, Rahika | [21 empty] | 1 | Handover
|  |  | 4 | C.M.J. College, Donwarihat | [21 empty] | 1 | Handover
|  |  | 5 | C. M. B College, Deorh, Ghoghardiha | [21 empty] | 1 | Handover
|  |  | 6 | K.V.Science College , Bennipatti | M/S R. Construction& Co. | [20 empty] | 1 | Handover
|  |  | 7 | L. N. J. College, Jhanjharpur | [21 empty] | 1 | Handover
|  |  | 8 | R. N. College, Panadaul, Madhubani | [21 empty] | 1 | Handover
|  |  | 9 | M. L. S. College, Sarisabpahi | [21 empty] | 1 | Handover
|  |  | 10 | D. B. College, Jainagar | [21 empty] | 1 | Handover
|  |  | 11 | M. M. L.Sans.Vidyapeeth, Lohana, Madhubani | [13 empty] | 1 | 1 | [7 empty] | No location
|  |  | 12 | Aditya Nath Paras Mani Sans College, Rahua Sangram, Madhubani | [21 empty] | 1 | Handover
|  |  | 13 | Rishikul Br.Sans.College, Vedivan, Madhubani | [13 empty] | 1 | 1 | [7 empty] | college not located
18 | CT-18 | Madhubani | 1 | J. N. College, Madhubani |  |  |  |  | 28.7 | ISSUED 08.10.2012 | 2014-02-18 | 2014-04-17 | 2014-01-09 | 332 F2 OF 13-14 / 13-9-14 | [11 empty] | 1 | Handover
|  |  | 2 | R. K. College, Madhubani | [21 empty] | 1 | Handover
|  |  | 3 | J. M. D. P. L. M. College, Madhubani | [13 empty] | 1 | 1 | [7 empty] | land problem
|  |  | 4 | Nandan Sans. College, Isahpur, Madhubani | Kumari Sindhu | [20 empty] | 1 | Handover
|  |  | 5 | Kalyani Mithila College, Dip, Madhubani | [21 empty] | 1 | Handover
|  |  | 6 | Madaneshwar Sans.College, Madaneshwar Sthan | [21 empty] | 1 | Handover
|  |  | 7 | Nirmali College, Nirmali | [21 empty] | 1 | Handover
19 | CT-19 | Samastipur | 1 | Samastipur College, Samastipur |  |  |  | 4642997 | 51.07 | ISSUED19.09.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 79 F2 of 2012-13 04.01.2013 | 4615007.02 | [10 empty] | 1 | Handover
|  |  | 2 | A. N. D. College, Shahpur Patori | [21 empty] | 1 | Handover
|  |  | 3 | U. R. College, Rosrha | [21 empty] | 1 | Handover
|  |  | 4 | R. B. College, Dalsinghsarai | [21 empty] | 1 | Handover
|  |  | 5 | U. P. College, Pusa | [21 empty] | 1 | Handover
|  |  | 6 | G. M. R. D. College, Mohanpur | Amrender Kumar | [20 empty] | 1 | Handover
|  |  | 7 | Dr. L. K. D. V. College, Tajpur | [21 empty] | 1 | Handover
|  |  | 8 | D. B. K. N. College, Narhan | [21 empty] | 1 | Handover
|  |  | 9 | B. R. B. College, Samastipur | [21 empty] | 1 | Handover
|  |  | 10 | Women's"College, Samastipur | [21 empty] | 1 | Handover
|  |  | 11 | R. N. A. R. College, Samastipur | [21 empty] | 1 | Handover
|  |  | 12 | R. B. S. College, Andour | [21 empty] | 1 | Handover
|  |  | 13 | R. C. College, Sakra | [21 empty] | 1 | Handover
20 | CT-20 | Begusarai+ Khagaria+ Lakhisarai | 1 | Akhil Bhartiya Sans. Vidyapeeth, Khamhar , Begusarai |  |  |  | 3462786 | 3809% | ISSUED08.10.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 92 F2 of 2012-13 23.01.2013 | 3441254.8 | [10 empty] | 1
|  |  | 2 | awadh Buihari Sans. College, Rahimpur, Khagaria | [21 empty] | 1
|  |  | 3 | G. D. College, Begusarai | [21 empty] | 1
|  |  | 4 | A. P. S. M. College, Barauni | [21 empty] | 1
|  |  | 5 | S. K. Mahila College, Begusarai | Agni kumar Singh | [20 empty] | 1
|  |  | 6 | Co-Operative College, Begusarai | [21 empty] | 1
|  |  | 7 | R. C. S. College, Manjhaul | [21 empty] | 1
|  |  | 8 | B. N. M. College, Barhiya | [21 empty] | 1
|  |  | 9 | K. S. S. College, Lakhisarai | [21 empty] | 1
|  |  | 10 | Koshi College, Khagarhiya | [21 empty] | 1
21 | CT-21 | Bhagalpur+ Banka+ Khagaria | 1 | Bhagalpur national college, Bhagalpur |  |  |  | 4826791 | 53.09 | ISSUED 02.05.2014 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 32 F2 of 2014-15 28.05.2014 | [10 empty] | 1
|  |  | 2 | G. B. College, Naugachhia | [21 empty] | 1 | Handover
|  |  | 3 | J. P. College, Narayanpur | [20 empty] | 1
|  |  | 4 | Marwani College, Bhagalpur | [20 empty] | 1
|  |  | 5 | Muraka College, Sultanganj | [20 empty] | 1
|  |  | 6 | P. B. S. College, Banka | [20 empty] | 1
|  |  | 7 | S. M. College, Bhagalpur | D.P. Maheswari pvt Ltd | [19 empty] | 1
|  |  | 8 | S. S. V. College, Kahalgaon | [13 empty] | 1 | 1 | [7 empty] | land not avilable
|  |  | 9 | T. N. B. College, Bhagalpur | [20 empty] | 1
|  |  | 10 | Sabour College, Sabour | [13 empty] | 1 | 1 | [7 empty] | Sufficient land not avilable
|  |  | 11 | T. N. B. Law College, Bhagalpur | [17 empty] | 1
|  |  | 12 | Mahila college, Khagaria | [14 empty] | 1
|  |  | 13 | M. A. M. College, Naugachhia | [21 empty] | 1
|  |  | 14 | L. P. N. S. College, Banka | [13 empty] | 1 | 1 | [7 empty] | college not located
22 | CT-22 | Purnia+ Araria+ Katihar+ Kishanganj | 1 | Purnia College, Purnia, |  |  |  | 4333385 | 47.67 | ISSUED 19.09.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 55 F2 of 2013-14 19.07.2013 | 4307547.36 | [10 empty] | 1 | Handover
|  |  | 2 | D. S. College, Katihar | [21 empty] | 1
|  |  | 3 | Forbisganj College, Forbisganj | [21 empty] | 1 | Handover
|  |  | 4 | Purnia Mahila College, | [13 empty] | 1 | 1 | [7 empty] | Land problem
|  |  | 5 | M. L. Arya College, Kasba | [21 empty] | 1 | Handover
|  |  | 6 | Araria College, Araria | Bansidhar Tirupati Agency | [20 empty] | 1 | Handover
|  |  | 7 | R. L. College, Madhopur, Purnia | [21 empty] | 1 | Handover
|  |  | 8 | K. B. Jha College, Katihar | [21 empty] | 1 | Handover
|  |  | 9 | Marwari College, Kishanganj | [13 empty] | 1 | 1 | [7 empty] | land problem
|  |  | 10 | M. J. M. Mahila College | [13 empty] | 1 | 1 | [7 empty] | land problem
|  |  | 11 | R. D. S. College, Salmari | [21 empty] | 1
|  |  | 12 | Radha Umakant Sans.College,Sukhsena, Purnia | [13 empty] | 1 | 1 | [7 empty] | land problem
23 | CT-23 | Madhepura | 1 | G. L. M. College, Banmankhi |  |  |  | 2895860 | 31.85 | ISSUED24.07.2013 | 25.04.2013 | 22.05.2013 | 28.06.2014 | 162 F2 of 2013-14 26.11.2013 | 2878634.56 | [10 empty] | 1 | Handover
|  |  | 2 | T. P. College, Madhepura | [21 empty] | 1 | Handover
|  |  | 3 | H. S. College, Udakishanganj | [21 empty] | 1 | Handover
|  |  | 4 | K. P. College, Murliganj | SanjeevRanjan Sinha | [20 empty] | 1 | Handover
|  |  | 5 | Nehru College, Bahadurganj | [13 empty] | 1 | 1 | [7 empty] | land problem
|  |  | 6 | L. K. M. College, Birpur | [13 empty] | 1 | 1 | [7 empty] | land problem
|  |  | 7 | B. N. M. V. College, Madhepura | [21 empty] | 1 | Handover
|  |  | 8 | P. Sc. College, Madhepura | [21 empty] | 1 | Handover
24 | CT-24 | Munger+ jamui+ seikhpura+ khagaria | 1 | B. R. M. College, Monger |  |  |  | 4560623 | 50.16 | ISSUED08.10.2012 | 30.07.2012 | 22.08.2012 | 29.08.2012 | 163 F2 of 2013-14 27.11.2013 | 4532632 | [9 empty] | 1
|  |  | 2 | D. S. M. College, Jhajha | [20 empty] | 1
|  |  | 3 | H. S. College, Havelikharhagpur | [19 empty] | 1
|  |  | 4 | J. M. S. College, Monger | [20 empty] | 1
|  |  | 5 | J. R. S. College, Jamalpur | [20 empty] | 1
|  |  | 6 | K. D. S. College, Gogari | [17 empty] | 1
|  |  | 7 | K. K. M. College, Jamui | D.P. M aheswari Const. | [19 empty] | 1
|  |  | 8 | K. M. D. College, Parbatta | [19 empty] | 1
|  |  | 9 | R. D. College, Sheishpur | [19 empty] | 1
|  |  | 10 | R. S. College, tarapur | [20 empty] | 1
|  |  | 11 | R. D. & D. J. College, Monger | [19 empty] | 1
|  |  | 12 | S. K. R. College, Barbigha | [19 empty] | 1
|  |  | 13 | Jamalpur College, Jamalpur | [19 empty] | 1
25 | CT-25 | Saharsa+ Supaul | 1 | M. L. T. College, Saharsa |  |  |  | 2912408 | 32.03 |  | 25.04.2013 | 22.05.2013 | 28.06.2014 | 161 F2 of 2013-14 26.11.2013 | 2895183.04 | [10 empty] | 1 | Handover
|  |  | 2 | M. H. M. College, Saharsa | [21 empty] | 1 | Handover
|  |  | 3 | R. M. M. Law College, Saharsa | [13 empty] | 1 | 1 | [7 empty] | Land Problem
|  |  | 4 | R. Jha. Mahila College, Saharsa | [13 empty] | 1 | 1 | [7 empty] | Land Problem
|  |  | 5 | R. M. College, Saharsa | Sanjeev Rsanjan Sinha. | [20 empty] | 1 | Handover
|  |  | 6 | B. S. S. College, Supaul | [21 empty] | 1 | Handover
|  |  | 7 | S. N. S. R. K. S. College, Saharsa | [21 empty] | 1 | Handover
|  |  | 8 | Ugratara Bharati Mandan Sans. College, Maheshi, Saharsa | [21 empty] | 1 | Handover
26 | CT-26 | Sitamarhi | 1 | S. R. K. G. College, Sitamarhi |  |  |  | 1826295 | 20.09 | ISSUED 08.01.2014 | 25.04.2013 | 22.05.2013 | 28.06.2013 | 200 F2 of 2013-14 08.01.2014 | [11 empty] | 1 | Handover
|  |  | 2 | J. S. College, Chandauli | [21 empty] | 1 | Handover
|  |  | 3 | R. S. S. M. College, Sitamarhi | Amit Kumar | [20 empty] | 1 | Handover
|  |  | 4 | S. L. K. College, Sitamarhi | [21 empty] | 1 | Handover
|  |  | 5 | R. S. S. Sc. College, Sitamarhi | [21 empty] | 1 | Handover
|  |  | 250 | [14 empty] | 26 | 33 | 1 | 0 | 3 | 0 | 6 | 15 | 192