## DEGREE COLLEGE
BSEIDC, PATNA
Progress Report for the construction of DEGREE COLLEGE | [38 empty] | 30.09.2016
S.N. | Name of District | Name of Block | S.N. | Name of College | Name of Agency | [17 empty] | Retender | Tender Process | Physical Status | [11 empty] | Agreement Amount (in Lakh) | Remarks | Division
[6 empty] | A/A | T/S | BOQ Amount ( in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting | L.O.A &Issued Date | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date | Date of Aggrement | TIME OF COMPLITION |  |  | Not Start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd Floor |  | Finishing | Complete
[29 empty] | LL | RL | LL | RL | LL | RL
1 | lgjlk |  |  | vaxhHkwr fMxzh egkfo¦ky;] flejh of[r;kjiqj] lgjlkA | INDRA NARAYAN SINGH |  |  | 544.46 | NIT-25, 07-10-201408 |  |  |  |  | 1879/4.03.15 | [7 empty] | 17 Months |  |  | 1 | [12 empty] | Land not available | Koshi
2 | dfVgkj |  |  | vaxhHkwr fMxzh egkfo¦ky;] efugkjh] dfVgkjA | SAI HIGHWAY & BUILDERS PVT LTD |  |  | 539.33 | NIT-25, 07-10-201408 |  |  |  |  | 3995/21.05.15 | [6 empty] | 293 SBD OF 2014-15 (04.09.2015) | 17 Months |  |  | 1 | [11 empty] | 500.8213 | LAND NOT AVAILABLE | Purnea
3 | osxwljk; |  |  | vaxhHkwr fMxzh egkfo¦ky;] rs?kM+k] osxwljk;A | SAI HIGHWAY & BUILDERS PVT LTD | 546.58 | 574.03 | 516.03 | NIT-25, 07-10-201408 |  |  |  |  | 1883/4-3-15 | [6 empty] | 92 SBD OF 2014-15 (06.06.2015) | 17 Months |  |  | 1 | [11 empty] | 484.1894 | Land not available | Munger
4 | osxwljk; |  |  | vaxhHkwr fMxzh egkfo¦ky;] c[kjh] osxwljk;A | M/S BALRAM KUMAR | 546.58 | 586.36 | 531.67 | NIT-25, 07-10-201408 |  |  |  |  | 1882/4-3-15 | [6 empty] | 47 SBD OF 2015-16 (6.05.15) | 17 Months |  |  | 1 | [11 empty] | 504.9845 | Land not available | Munger
5 | osxwljk; |  |  | vaxhHkwr fMxzh egkfo¦ky;] cfy;k] osxwljk;A | SAI HIGHWAY & BUILDERS PVT LTD | 546.58 | 591.42 | 527.12 | NIT-25, 07-10-201408 |  |  |  |  | 1885/4-3-15 | [6 empty] | 91 SBD OF 2014-15 (06.06.2015) | 17 Months |  |  | 1 | [11 empty] | 494.6014 | Land not available | Munger
6 | iwf.kZ;k¡ |  |  | vaxhHkwr fMxzh egkfo¦ky;] ok;lh] iwf.kZ;k¡A | SUNIL KUMAR SUMAN | 546.58 | 602.69 | 541.82 | NIT-25, 07-10-201408 |  |  |  |  | 1884/4-3-15 | [6 empty] | 238 SBD OF 2014-15 (29.08.2015) | 17 Months | [10 empty] | 1 |  |  |  | 503.7832 |  | Purnea
7 | njHkaxk |  |  | vaxhHkwr fMxzh egkfo¦ky;] csuhiqj] njHkaxkA | MOTHER INDIA CONSTRUCTION PVT LTD | 546.58 |  | 544.88 | NIT-25, 07-10-201408 |  |  |  |  | 4050/25.05.15 | [6 empty] | 253 SBD OF 2014-15 (31.08.2015) | 17 Months | [7 empty] | 1 | [6 empty] | 520.1909 |  | Darbhanga
8 | if'pe pEikj.k |  |  | vaxhHkwr fMxzh egkfo¦ky;] cxgk cjxkWao if'pe pEikj.kA | SANJAY CONSTRUCTION | 546.58 | 621.52 | 558.76 | NIT-25, 07-10-201408 |  |  |  |  | 1881/4-3-15 | [6 empty] | 209 SBD OF 2014-15 (14.08.2015) | 17 Months | [8 empty] | 1 | [5 empty] | 529.6528 |  | Tirhut West
9 | ukyUnk |  |  | vaxhHkwr fMxzh egkfo¦ky;] jktxhj] ukyUnkA | SAI HIGHWAY & BUILDERS PVT LTD | 546.58 | 571.21 | 513.5 | NIT-25, 07-10-201416 |  |  |  |  | 1880/4-3-15 | [6 empty] | 90 SBD OF 2014-15 (06.06.2015) | 17 Months |  |  |  | 1 | [10 empty] | 472.9825 | Foundation RCC | Patna East
10 | iwf.kZ;k¡ |  |  | vaxhHkwr fMxzh egkfo¦ky;] ?kenkgk] iwf.kZ;k | BIHAR SHARIF CONS. |  |  | 541.82 | NIT-38 20.12.14 |  |  |  |  | 6715/27.07.15 | [6 empty] | 224 SBD OF 2014-15 (025.08.2015) | 17 Months | [12 empty] | 1 |  | 498.8675 |  | Purnea
Total Number of Degree College |  |  |  |  | 10 | [16 empty] | TOTAL | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | #REF!